## MilCon Contracts Data
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Contract Office Code | Prime Contract Number | Contract Number (Clean) | Match Index | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date | Amount Delta (Positive=Overrun) | Completion Delta | Current Contract Completion Year | Current Contract Completion Month | Current Contract Completion Day | CCC YYYMMDD | Contract Award Fiscal Year | Contract Completion Fiscal Year | Award TY to CY23 Index | Median FY Index | Median FY to CY23 Index | Original Contract Amount (CY23$) | Final Contract Obligations (CY23$) | Delta (CY23$) | Overrun (Underrun) Days | Original Duration | Schedule % Overrun
2022-01-06 | 2009 | Special Operations Command | 67428 |  | 2008-07-21 | 2009-01-23 | Hensel Phelps Construction Company | W91278 | W91278-09-C-0017 | W9127809C0017 |  | 0 | 39068176 | 2011-07-29 | 2011-07-29 | 39068176 | 0 | 2011 | 07 | 29 | 20110729 | 2009 | 2011 | 1.0006 | 2010 | 0.97698 | 0 | 38168737.3761 | 38168737.3761 | 0 | 917 | 0%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR | W912DR-09-C-0026 | W912DR09C0026 |  | 0 | 3949000 | 2014-05-31 | 2023-05-25 | 3949000 | 3281 | 2023 | 05 | 25 | 20230525 | 2009 | 2023 | 0.97698 | 2016 | 0.95701 | 0 | 3779240.4906 | 3779240.4906 | 3281 | 1891 | 173.5%
2022-01-06 | 2009 | Special Operations Command | 60636 |  | 2009-06-15 | 2009-08-31 | Team Construction LLC A JV of Mil Fed/WT Humphrey | W912HN | W912HN-09-C-0054 | W912HN09C0054 | 60636,W912HN-09-C-0054 | 0 | 0 | 2010-06-12 | 2010-11-15 | 0 | 156 | 2010 | 11 | 15 | 20101115 | 2009 | 2011 | 0.97698 | 2010 | 0.95701 | 0 | 0 | 0 | 156 | 285 | 54.74%
2022-01-06 | 2011 | Special Operations Command | 063054x |  | 2011-02-23 | 2011-04-09 | Hensel Phelps Construction Co. | W912PP | W912PP-10-C-0015 | W912PP10C0015 | 063054x,W912PP-10-C-0015 | 0 | 4616078 | 2012-02-26 | 2013-03-15 | 4616078 | 383 | 2013 | 03 | 15 | 20130315 | 2011 | 2013 | 1.0006 | 2012 | 0.97698 | 0 | 4509805.3436 | 4509805.3436 | 383 | 323 | 118.6%
2022-01-13 | 2013 | Defense Health Agency | 58395 | 78210-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR | W912DR-15-C-0025 | W912DR15C0025 | 58395,W912DR-15-C-0025 | 0 | 141000 | 2017-03-31 | 2017-05-04 | 141000 | 34 | 2017 | 05 | 04 | 20170504 | 2015 | 2017 | 1.0276 | 2016 | 1.0006 | 0 | 141086.0582 | 141086.0582 | 34 | 560 | 6.071%
2022-02-02 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB | W912GB-12-C-0006/50005397 | W912GB12C0006 | EU00034,W912GB-12-C-0006/50005397 | 0 | 388829 | 2018-12-24 | 2019-06-13 | 388829 | 171 | 2019 | 06 | 13 | 20190613 | 2016 | 2019 | 1.0276 | 2018 | 1.0006 | 0 | 389066.3186 | 389066.3186 | 171 | 885 | 19.32%
2022-02-02 | 2012 | DoD Education Activity | EU00031 | 89 | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB | W912GB-11-C-0029/59013541 | W912GB11C0029 | EU00031,W912GB-11-C-0029/59013541 | 0 | 204671 | 2019-05-08 | 2019-10-31 | 204671 | 176 | 2019 | 10 | 31 | 20191031 | 2017 | 2020 | 1.0006 | 2019 | 0.97698 | 0 | 199959.0062 | 199959.0062 | 176 | 901 | 19.53%
2021-12-31 | 2016 | Air Force Active | AGGN123003 |  | 2018-06-14 | 2019-09-27 | Sheffield-Korte Team | W912BV | W912BV19C0024 | W912BV19C0024 | AGGN123003,W912BV19C0024 | 0 | 0 | 2021-10-26 | 2022-11-09 | 0 | 379 | 2022 | 11 | 09 | 20221109 | 2019 | 2023 | 1.0751 | 2021 | 1.0276 | 0 | 0 | 0 | 379 | 760 | 49.87%
2021-12-31 | 2018 | Air Force Active | PRQE055155 |  | 2019-06-28 | 2019-09-28 | McConnell COMBAT ARMS FACILITY | W912DQ | W912DQ18C4051 | W912DQ18C4051 | PRQE055155,W912DQ18C4051 | 0 | 0 | 2020-07-05 | 2021-06-30 | 0 | 360 | 2021 | 06 | 30 | 20210630 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 0 | 0 | 0 | 360 | 281 | 128.1%
2021-12-31 | 2019 | Air Force Active | FBNV033002 |  | 2019-07-30 | 2019-09-28 | BFL Construction CO | W912PL | W912PL19C0035 | W912PL19C0035 | FBNV033002,W912PL19C0035 | 0 | 0 | 2021-04-20 | 2022-06-10 | 0 | 416 | 2022 | 06 | 10 | 20220610 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 0 | 0 | 0 | 416 | 570 | 72.98%
2021-12-31 | 2020 | Air Force Active | XDAT1026962 |  | 2020-06-20 | 2020-07-16 | J.I. Garcia Construction Inc. Travis AFB KC-46A Alter B881, B885 & B887 Squadron Ops/AMU | N62473 | N6247318D5817 | N6247318D5817 | XDAT1026962,N6247318D5817 | 0 | 0 | 2021-09-09 | 2023-08-31 | 0 | 721 | 2023 | 08 | 31 | 20230831 | 2020 | 2023 | 1.0993 | 2022 | 1.0751 | 0 | 0 | 0 | 721 | 420 | 171.7%
2022-01-12 | 2020 | Special Operations Command | Q463 |  | 2019-08-29 | 2020-04-15 | HENSEL PHELPS CONSTRUCTION CO. | N62478 | N6247819D5029 | N6247819D5029 | Q463,N6247819D5029 | 0 | 64930 | 2022-04-15 | 2022-04-15 | 64930 | 0 | 2022 | 04 | 15 | 20220415 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 0 | 63435.1631 | 63435.1631 | 0 | 730 | 0%
2022-01-12 | 2020 | Marine Corps Reserve | N83447181 |  | 2020-06-25 | 2020-09-25 | ENCANTO FACILITY SERVICES 2, LLC | N69450 | N6945020D0036 N6945020F1278 | N6945020D0036 | N83447181,N6945020D0036 N6945020F1278 | 0 | 1101000 | 2021-09-26 | 2021-09-26 | 1101000 | 0 | 2021 | 09 | 26 | 20210926 | 2020 | 2021 | 1.0276 | 2021 | 1.0006 | 0 | 1101671.9863 | 1101671.9863 | 0 | 366 | 0%
2021-12-31 | 2020 | Air Force Active | FTFA163007 |  | 2020-07-07 | 2020-09-29 | Cyberspace Test Facility | W91278 | W9127820C0033 | W9127820C0033 | FTFA163007,W9127820C0033 | 0 | 0 | 2022-04-30 | 2022-10-31 | 0 | 184 | 2022 | 10 | 31 | 20221031 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 0 | 0 | 0 | 184 | 578 | 31.83%
2021-12-31 | 2019 | Air Force Active | FBNV163001 |  | 2019-04-12 | 2020-01-17 | Chase, Carson and White, LLC | W912PL | W912PL20C0008 | W912PL20C0008 | FBNV163001,W912PL20C0008 | 0 | 0 | 2021-02-11 | 2021-06-25 | 0 | 134 | 2021 | 06 | 25 | 20210625 | 2020 | 2021 | 1.0006 | 2021 | 0.97698 | 0 | 0 | 0 | 134 | 391 | 34.27%
2021-12-31 | 2018 | Air Force Active | KWRD143000 |  | 2018-08-22 | 2019-10-31 | RPA Fixed Ground Control Station | W912PP | W912PP19C0019 | W912PP19C0019 | KWRD143000,W912PP19C0019 | 0 | 0 | 2020-12-30 | 2021-10-25 | 0 | 299 | 2021 | 10 | 25 | 20211025 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 0 | 0 | 0 | 299 | 426 | 70.19%
2022-01-12 | 2021 | Marine Corps Active | M626131010U |  | 2021-06-01 | 2021-09-09 | MECCS MITOMO JV | N40084 | N4008420D0071 N4008421F4605 | N4008420D0071 | M626131010U,N4008420D0071 N4008421F4605 | 0 | 986000 | 2022-07-06 | 2022-07-06 | 986000 | 0 | 2022 | 07 | 06 | 20220706 | 2021 | 2022 | 0.95701 | 2022 | 0.9382 | 0 | 925063.2918 | 925063.2918 | 0 | 300 | 0%
2022-01-12 | 2021 | Navy Active | N62688404 |  | 2021-03-29 | 2021-09-30 | BAMFORTH ENGINEERS + SURVEYORS,INC. | N40085 | N4008519D9164 N4008520F4014-New Mod | N4008519D9164 | N62688404,N4008519D9164 N4008520F4014-New Mod | 0 | 1458000 | 2019-11-30 | 2023-06-20 | 1458000 | 1298 | 2023 | 06 | 20 | 20230620 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 0 | 1424433.5106 | 1424433.5106 | 1298 | -670 | -193.7%
2022-01-12 | 2021 | Special Operations Command | Q997 |  | 2020-10-14 | 2021-05-07 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008521F5236 | N4008520D0034 | Q997,N4008520D0034 N4008521F5236 | 0 | 0 | 2024-03-16 | 2024-03-16 | 0 | 0 | 2024 | 03 | 16 | 20240316 | 2021 | 2024 | 0.97698 | 2023 | 0.9382 | 0 | 0 | 0 | 0 | 1044 | 0%
2022-01-12 | 2021 | Navy Active | N32446381 |  | 2020-11-13 | 2021-08-13 | CAISSON PROCUREMENT | N40085 | N4008521C0077 AWD | N4008521C0077 | N32446381,N4008521C0077 AWD | 0 | 68582000 | 2028-06-01 | 2028-06-01 | 68582000 | 0 | 2028 | 06 | 01 | 20280601 | 2021 | 2028 | 0.97698 | 2025 | 0.95701 | 0 | 65633798.7654 | 65633798.7654 | 0 | 2484 | 0%
2022-01-12 | 2020 | Navy Active | N626881035 |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N40085 | N4008521D0083 N4008521F6191 | N4008521D0083 | N626881035,N4008521D0083 N4008521F6191 | 0 | 2907000 | 2024-03-22 | 2024-03-22 | 2907000 | 0 | 2024 | 03 | 22 | 20240322 | 2021 | 2024 | 1.0507 | 2023 | 1.0006 | 0 | 2908774.2635 | 2908774.2635 | 0 | 945 | 0%
2022-01-12 | 2021 | Navy Active | N626881035A |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N40085 | N4008521D0083 N4008521F6191 | N4008521D0083 | N626881035A,N4008521D0083 N4008521F6191 | 0 | 2907000 | 2024-03-22 | 2024-03-22 | 2907000 | 0 | 2024 | 03 | 22 | 20240322 | 2021 | 2024 | 0.97698 | 2023 | 0.95701 | 0 | 2782033.9595 | 2782033.9595 | 0 | 945 | 0%
2022-01-12 | 2021 | Marine Corps Active | M006811090A |  | 2020-05-15 | 2021-03-23 | DPR-RQ CONSTRUCTION, LLC | N62473 | N6247320C0055 PC000009 | N6247320C0055 | M006811090A,N6247320C0055 PC000009 | 0 | 248000 | 2024-01-07 | 2024-01-07 | 248000 | 0 | 2024 | 01 | 07 | 20240107 | 2021 | 2024 | 1.1743 | 2023 | 1.0751 | 0 | 266619.269 | 266619.269 | 0 | 1020 | 0%
2022-01-12 | 2021 | Marine Corps Active | M67865280 |  | 2021-04-26 | 2021-06-30 | DE LA FUENTE CONSTRUCTION, INC. | N62473 | N6247321D1220 N6247321F4960 | N6247321D1220 | M67865280,N6247321D1220 N6247321F4960 | 0 | 5325000 | 2023-03-07 | 2023-03-07 | 5325000 | 0 | 2023 | 03 | 07 | 20230307 | 2021 | 2023 | 1.0276 | 2022 | 1.0006 | 0 | 5328250.0699 | 5328250.0699 | 0 | 615 | 0%
2022-01-12 | 2021 | Marine Corps Active | N61159803 |  | 2021-04-08 | 2021-08-13 | CHUGACH CONSOLIDATED SOLUTIONS, LLC | N62742 | N6274221C1315 AWD | N6274221C1315 | N61159803,N6274221C1315 AWD | 0 | 9380000 | 2022-08-27 | 2022-09-04 | 9380000 | 8 | 2022 | 09 | 04 | 20220904 | 2021 | 2022 | 1.0276 | 2022 | 0.97698 | 0 | 9164050.9807 | 9164050.9807 | 8 | 379 | 2.111%
2022-01-12 | 2019 | Marine Corps Active | N41557735 |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N62742 | N6274221C1346 AWD | N6274221C1346 | N41557735,N6274221C1346 AWD | 0 | 6003000 | 2024-10-25 | 2024-10-25 | 6003000 | 0 | 2024 | 10 | 25 | 20241025 | 2021 | 2025 | 1.0993 | 2023 | 1.0276 | 0 | 6168629.5975 | 6168629.5975 | 0 | 1123 | 0%
2021-10-20 | 2020 | Special Operations Command | Q246U |  | 2021-06-24 | 2021-09-28 | DRACE ANDERSON JOINT VENTURE | N69450 | N6945018D1323 N6945021F0743 | N6945018D1323 | Q246U,N6945018D1323 N6945021F0743 | 0 | 3141 | 2022-10-03 | 2022-10-03 | 3141 | 0 | 2022 | 10 | 03 | 20221003 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 0 | 2946.8801 | 2946.8801 | 0 | 370 | 0%
2022-01-12 | 2021 | Special Operations Command | Q246U |  | 2021-06-24 | 2021-09-28 | DRACE ANDERSON JOINT VENTURE | N69450 | N6945018D1323 N6945021F0743 | N6945018D1323 | Q246U,N6945018D1323 N6945021F0743 | 0 | 3187 | 2022-10-03 | 2022-10-03 | 3187 | 0 | 2022 | 10 | 03 | 20221003 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 0 | 3113.628 | 3113.628 | 0 | 370 | 0%
2022-01-12 | 2020 | Navy Active | N62863785 |  | 2021-10-07 | 2021-12-21 | FERROVIAL AGROMAN SA | N62470 | N6247021D0016 N6247022F9002 | N6247021D0016 | N62863785,N6247021D0016 N6247022F9002 | 0 | 0 | 2023-12-31 | 2023-12-31 | 0 | 0 | 2023 | 12 | 31 | 20231231 | 2022 | 2024 | 1.0276 | 2023 | 0.97698 | 0 | 0 | 0 | 0 | 740 | 0%
2021-12-31 | 2021 | Army Active | 81352 |  | 2021-08-26 | 2021-11-04 | KLK Electric, Inc | W912DS | W912DS22C0002 | W912DS22C0002 | 81352,W912DS22C0002 | 0 | 0 | 2023-02-02 | 2023-01-25 | 0 | -8 | 2023 | 01 | 25 | 20230125 | 2022 | 2023 | 1.0006 | 2023 | #N/A | 0 | #N/A | #N/A | -8 | 455 | -1.758%
2021-11-30 | 2018 | Army Active | 78713 |  | 2021-07-21 | 2021-12-09 | Staatliches Hochbauamt Amberg | W912GB | W912GB18C0002 | W912GB18C0002 | 78713,W912GB18C0002 | 0 | 0 | 2023-09-18 | 2023-09-18 | 0 | 0 | 2023 | 09 | 18 | 20230918 | 2022 | 2023 | 1.0006 | 2023 | #N/A | 0 | #N/A | #N/A | 0 | 648 | 0%
2021-12-31 | 2019 | Army Active | 93209 |  | 2020-11-16 | 2021-11-02 | Staatliches Hochbauamt Amberg | W912GB | W912GB18C0024 | W912GB18C0024 | 93209,W912GB18C0024 | 0 | 0 | 2023-05-04 | 2023-08-02 | 0 | 90 | 2023 | 08 | 02 | 20230802 | 2022 | 2023 | 1.0993 | 2023 | 1.0276 | 0 | 0 | 0 | 90 | 548 | 16.42%
2021-09-13 | 2014 | Special Operations Command | P771 |  | 2018-07-13 | 2018-09-19 | SOLPAC CONSTRUCTION INC | N62473 | N6247317D0821 | N6247317D0821 | P771,N6247317D0821 | 32 | 34250 | 2020-02-02 | 2021-08-13 | 34218 | 558 | 2021 | 08 | 13 | 20210813 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 31.2633 | 32778.3008 | 32747.0375 | 558 | 501 | 111.4%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB | W912GB-10-C-0031, ABG4 P00037 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31 | 0 | 0 | 2014 | 12 | 31 | 20141231 | 2012 | 2015 | 0.97698 | 2014 | 0.95701 | 976.9777 | 976.9777 | 0 | 0 | 1021 | 0%
2021-09-13 | 2013 | Special Operations Command | P1410 |  | 2013-09-04 | 2013-09-26 | QUADRANT CONSTRUCTION, INC | N40085 | N4008510D0261 | N4008510D0261 | P1410,N4008510D0261 | 1826 | 1809 | 2014-09-22 | 2015-06-30 | -17 | 281 | 2015 | 06 | 30 | 20150630 | 2013 | 2015 | 1.0507 | 2014 | 1.0006 | 1918.5799 | 1901.5695 | -17.0104 | 281 | 361 | 77.84%
2021-10-20 | 2013 | Special Operations Command | Q1410 |  | 2013-09-04 | 2013-09-26 | QUADRANT CONSTRUCTION, INC | N40085 | N4008510D0261 | N4008510D0261 | Q1410,N4008510D0261 | 1826 | 1809 | 2014-09-22 | 2015-06-30 | -17 | 281 | 2015 | 06 | 30 | 20150630 | 2013 | 2015 | 0.97698 | 2014 | 0.95701 | 1783.9613 | 1767.6921 | -16.2692 | 281 | 361 | 77.84%
2021-09-13 | 2020 | Special Operations Command | P224 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519D9070 N4008521F4540 | N4008519D9070 | P224,N4008519D9070 N4008521F4540 | 1828 | 26134 | 2023-08-05 | 2023-08-05 | 24306 | 0 | 2023 | 08 | 05 | 20230805 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 1829.1157 | 25090.25 | 23261.1343 | 0 | 918 | 0%
2021-09-13 | 2020 | Special Operations Command | P999 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519D9070 N4008521F4540 | N4008519D9070 | P999,N4008519D9070 N4008521F4540 | 1828 | 11501 | 2023-08-05 | 2023-08-05 | 9673 | 0 | 2023 | 08 | 05 | 20230805 | 2021 | 2023 | 1.2826 | 2022 | 1.1227 | 2344.5269 | 13204.1308 | 10859.6039 | 0 | 918 | 0%
2021-09-13 | 2014 | Special Operations Command | P1469 |  | 2014-08-20 | 2014-09-30 | Awarded by Other Agency | N40085 | N4008510D0261 | N4008510D0261 | P1469,N4008510D0261 | 1944 | 1938 | 2015-11-24 | 2016-08-25 | -6 | 275 | 2016 | 08 | 25 | 20160825 | 2014 | 2016 | 1.0006 | 2015 | 0.97698 | 1945.1865 | 1939.3246 | -5.8619 | 275 | 420 | 65.48%
2022-01-12 | 2014 | Special Operations Command | Q1469 |  | 2014-08-20 | 2014-09-30 | Awarded by Other Agency | N40085 | N4008510D0261 | N4008510D0261 | Q1469,N4008510D0261 | 1944 | 1938 | 2015-11-24 | 2016-08-25 | -6 | 275 | 2016 | 08 | 25 | 20160825 | 2014 | 2016 | 1.0006 | 2015 | 0.97698 | 1945.1865 | 1939.3246 | -5.8619 | 275 | 420 | 65.48%
2022-01-12 | 2018 | Special Operations Command | Q698 |  | 2020-12-21 | 2021-03-24 | SYNCON, LLC | N40085 | N4008518D1143 N4008521F4963 | N4008518D1143 | Q698,N4008518D1143 N4008521F4963 | 2846 | 4299 | 2022-08-08 | 2022-09-05 | 1453 | 28 | 2022 | 09 | 05 | 20220905 | 2021 | 2022 | 1.0276 | 2022 | 0.97698 | 2924.5244 | 4344.073 | 1419.5486 | 28 | 502 | 5.578%
2021-09-13 | 2018 | Special Operations Command | P698 |  | 2020-12-21 | 2021-03-24 | SYNCON, LLC | N40085 | N4008518D1143 N4008521F4963 | N4008518D1143 | P698,N4008518D1143 N4008521F4963 | 2846 | 4445 | 2022-08-08 | 2022-08-08 | 1599 | 0 | 2022 | 08 | 08 | 20220808 | 2021 | 2022 | 1.0751 | 2022 | 1.0276 | 3059.6711 | 4702.7894 | 1643.1182 | 0 | 502 | 0%
2021-09-13 | 2015 | Special Operations Command | P1475 |  | 2018-02-07 | 2018-06-19 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N40085 | N4008518C6101 | N4008518C6101 | P1475,N4008518C6101 | 3136 | 3130 | 2019-09-13 | 2021-01-14 | -6 | 489 | 2021 | 01 | 14 | 20210114 | 2018 | 2021 | 1.0507 | 2020 | 1.0006 | 3294.9981 | 3288.9945 | -6.0037 | 489 | 451 | 108.4%
2022-01-12 | 2015 | Special Operations Command | Q1475 |  | 2018-02-07 | 2018-06-19 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N40085 | N4008518C6101 | N4008518C6101 | Q1475,N4008518C6101 | 3136 | 3130 | 2019-09-13 | 2021-01-14 | -6 | 489 | 2021 | 01 | 14 | 20210114 | 2018 | 2021 | 1.0006 | 2020 | 0.97698 | 3137.914 | 3132.0522 | -5.8619 | 489 | 451 | 108.4%
2021-09-13 | 2017 | Special Operations Command | P900 |  | 2018-06-28 | 2019-02-22 | SYNCON, LLC | N40085 | N4008518D1143 | N4008518D1143 | P900,N4008518D1143 | 3422 | 0 | 2020-02-10 | 2023-07-26 | -3422 | 1262 | 2023 | 07 | 26 | 20230726 | 2019 | 2023 | 1.0751 | 2021 | 1.0507 | 3678.9159 | 83.4173 | -3595.4986 | 1262 | 353 | 357.5%
2022-01-12 | 2017 | Special Operations Command | Q900 |  | 2018-06-28 | 2019-02-22 | SYNCON, LLC | N40085 | N4008518D1143 | N4008518D1143 | Q900,N4008518D1143 | 3422 | 0 | 2020-02-10 | 2023-07-26 | -3422 | 1262 | 2023 | 07 | 26 | 20230726 | 2019 | 2023 | 1.0006 | 2021 | 0.97698 | 3424.0886 | 80.8708 | -3343.2177 | 1262 | 353 | 357.5%
2021-09-13 | 2016 | Special Operations Command | P225 |  | 2017-09-05 | 2018-08-03 | TIKIGAQ CONSTRUCTION, LLC | N40085 | N4008517D0362 | N4008517D0362 | P225,N4008517D0362 | 3455 | 3445 | 2019-08-30 | 2020-01-07 | -10 | 130 | 2020 | 01 | 07 | 20200107 | 2018 | 2020 | 1.0276 | 2019 | 0.97698 | 3550.3274 | 3540.5576 | -9.7698 | 130 | 392 | 33.16%
2022-01-12 | 2016 | Special Operations Command | Q225 |  | 2017-09-05 | 2018-08-03 | TIKIGAQ CONSTRUCTION, LLC | N40085 | N4008517D0362 | N4008517D0362 | Q225,N4008517D0362 | 3455 | 3450 | 2019-10-22 | 2020-01-07 | -5 | 77 | 2020 | 01 | 07 | 20200107 | 2018 | 2020 | 1.0276 | 2019 | 0.95701 | 3550.3274 | 3545.5423 | -4.7851 | 77 | 445 | 17.3%
2021-09-13 | 2016 | Special Operations Command | P1481 |  | 2018-03-05 | 2018-08-31 | LARION HUMPHREY CONSTRUCTION LLC | N40085 | N4008518C6118 | N4008518C6118 | P1481,N4008518C6118 | 3716 | 3594 | 2019-11-11 | 2020-07-06 | -122 | 238 | 2020 | 07 | 06 | 20200706 | 2018 | 2020 | 1.1914 | 2019 | 1.1743 | 4427.0961 | 4283.8292 | -143.2669 | 238 | 437 | 54.46%
2022-01-12 | 2016 | Special Operations Command | Q1481 |  | 2018-03-05 | 2018-08-31 | LARION HUMPHREY CONSTRUCTION LLC | N40085 | N4008518C6118 | N4008518C6118 | Q1481,N4008518C6118 | 3716 | 3594 | 2019-11-11 | 2020-07-06 | -122 | 238 | 2020 | 07 | 06 | 20200706 | 2018 | 2020 | 1.0751 | 2019 | 1.0507 | 3994.9887 | 3866.8032 | -128.1855 | 238 | 437 | 54.46%
2022-01-12 | 2014 | Special Operations Command | Q9440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N69450 | N6945014D1271 0003 | N6945014D1271 | Q9440,N6945014D1271 0003 | 4140 | 4085 | 2016-08-22 | 2019-07-17 | -55 | 1059 | 2019 | 07 | 17 | 20190717 | 2015 | 2019 | 0.97698 | 2017 | 0.95701 | 4044.6877 | 3992.0521 | -52.6357 | 1059 | 480 | 220.6%
2021-09-13 | 2020 | Special Operations Command | P1482 |  | 2020-06-30 | 2020-09-22 | QUADRANT CONSTRUCTION, INC | N40085 | N4008515D0851 N4008520F6725 | N4008515D0851 | P1482,N4008515D0851 N4008520F6725 | 4524 | 5128 | 2021-09-18 | 2022-07-15 | 604 | 300 | 2022 | 07 | 15 | 20220715 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 4648.8223 | 5253.191 | 604.3686 | 300 | 361 | 83.1%
2021-09-13 | 2020 | Special Operations Command | P914U |  | 2020-07-09 | 2020-10-07 | ASTURIAN-CONSIGLI JV, LLC | N40085 | N4008518D1124 N4008521F4027 | N4008518D1124 | P914U,N4008518D1124 N4008521F4027 | 4626 | 5081 | 2022-04-23 | 2022-04-23 | 455 | 0 | 2022 | 04 | 23 | 20220423 | 2021 | 2022 | 0.97698 | 2022 | 0.9382 | 4519.4989 | 4946.379 | 426.8801 | 0 | 563 | 0%
2021-09-13 | 2018 | Special Operations Command | P241 |  | 2019-08-08 | 2019-09-26 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N40085 | N4008514D1322 | N4008514D1322 | P241,N4008514D1322 | 4921 | 5145 | 2020-11-13 | 2021-04-16 | 224 | 154 | 2021 | 04 | 16 | 20210416 | 2019 | 2021 | 1.2319 | 2020 | 1.2082 | 6062.3627 | 6333.0054 | 270.6427 | 154 | 414 | 37.2%
2022-01-12 | 2018 | Special Operations Command | Q241 |  | 2019-08-08 | 2019-09-26 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N40085 | N4008514D1322 | N4008514D1322 | Q241,N4008514D1322 | 4921 | 5129 | 2020-11-13 | 2021-04-16 | 208 | 154 | 2021 | 04 | 16 | 20210416 | 2019 | 2021 | 1.2319 | 2020 | 1.1914 | 6062.3627 | 6310.1658 | 247.803 | 154 | 414 | 37.2%
2022-01-12 | 2020 | Special Operations Command | Q914U |  | 2020-07-09 | 2020-10-07 | ASTURIAN-CONSIGLI JV, LLC | N40085 | N4008518D1124 N4008521F4027 | N4008518D1124 | Q914U,N4008518D1124 N4008521F4027 | 5098 | 5083 | 2022-04-23 | 2022-04-23 | -15 | 0 | 2022 | 04 | 23 | 20220423 | 2021 | 2022 | 1.0276 | 2022 | 1.0006 | 5238.6596 | 5223.6505 | -15.0092 | 0 | 563 | 0%
2022-01-12 | 2020 | Special Operations Command | Q1482 |  | 2020-06-30 | 2020-09-22 | QUADRANT CONSTRUCTION, INC | N40085 | N4008515D0851 N4008520F6725 | N4008515D0851 | Q1482,N4008515D0851 N4008520F6725 | 5152 | 5128 | 2021-09-18 | 2022-07-15 | -24 | 300 | 2022 | 07 | 15 | 20220715 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 5155.1445 | 5132.1762 | -22.9683 | 300 | 361 | 83.1%
2022-01-12 | 2018 | Special Operations Command | 1362 |  | 2020-01-27 | 2020-07-22 | PATRIOT CONSTRUCTION, LLC | N40085 | N4008520C0142 AWD | N4008520C0142 | 1362,N4008520C0142 AWD | 7962 | 7820 | 2022-02-07 | 2022-02-07 | -142 | 0 | 2022 | 02 | 07 | 20220207 | 2020 | 2022 | 1.0751 | 2021 | 1.0276 | 8559.7686 | 8413.8507 | -145.9179 | 0 | 565 | 0%
2021-09-13 | 2018 | Special Operations Command | P1362 |  | 2020-01-27 | 2020-07-22 | PATRIOT CONSTRUCTION, LLC | N40085 | N4008520C0142 AWD | N4008520C0142 | P1362,N4008520C0142 AWD | 7962 | 8206 | 2022-02-07 | 2022-02-07 | 244 | 0 | 2022 | 02 | 07 | 20220207 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 8181.6806 | 8420.0632 | 238.3826 | 0 | 565 | 0%
2021-08-31 | 2018 | Army Active | 86711 |  | 2018-11-08 | 2019-05-24 | Canoochee EMC | DACA87 | DACA87-01-D-0014 | DACA8701D0014 | 86711,DACA87-01-D-0014 | 8000 | 8000 | 2020-07-21 | 2021-02-19 | 0 | 213 | 2021 | 02 | 19 | 20210219 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 8220.7291 | 8220.7291 | 0 | 213 | 424 | 50.24%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AF | S | XLWU203006,S/CLIN 1019AF | 8437 | 8437 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0276 | 2022 | 1.0006 | 8669.7864 | 8669.7864 | 0 | 0 | 745 | 0%
2022-01-12 | 2015 | Special Operations Command | Q1396 |  | 2015-05-29 | 2015-08-17 | WHITING-TURNER CONTRACTING CO | N40085 | N4008510D5330 0012 | N4008510D5330 | Q1396,N4008510D5330 0012 | 10331 | 12848 | 2017-03-09 | 2017-10-27 | 2517 | 232 | 2017 | 10 | 27 | 20171027 | 2015 | 2018 | 1.0006 | 2017 | 0.97698 | 10337.3054 | 12796.3584 | 2459.0529 | 232 | 570 | 40.7%
2021-09-13 | 2019 | Special Operations Command | P834 |  | 2019-03-22 | 2019-11-12 | Awarded by Other Agency | N40085 | N4008518D1125 N4008520F4066 | N4008518D1125 | P834,N4008518D1125 N4008520F4066 | 10586 | 10666 | 2021-05-20 | 2021-08-18 | 80 | 90 | 2021 | 08 | 18 | 20210818 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 10878.0798 | 10956.238 | 78.1582 | 90 | 555 | 16.22%
2022-01-12 | 2019 | Special Operations Command | Q834 |  | 2019-03-22 | 2019-11-12 | Awarded by Other Agency | N40085 | N4008518D1125 N4008520F4066 | N4008518D1125 | Q834,N4008518D1125 N4008520F4066 | 10586 | 10233 | 2021-05-20 | 2021-05-20 | -353 | 0 | 2021 | 05 | 20 | 20210520 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 10878.0798 | 10533.2066 | -344.8731 | 0 | 555 | 0%
2022-01-12 | 2015 | Special Operations Command | Q170 |  | 2015-03-10 | 2016-01-26 | PENTACON, LLC | N69450 | N6945014D0757 0002 | N6945014D0757 | Q170,N6945014D0757 0002 | 10593 | 10431 | 2017-10-17 | 2018-06-16 | -162 | 242 | 2018 | 06 | 16 | 20180616 | 2016 | 2018 | 1.0276 | 2017 | 1.0006 | 10885.2729 | 10723.174 | -162.0989 | 242 | 630 | 38.41%
2022-01-12 | 2020 | Special Operations Command | Q999 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519D9070 N4008521F4540 | N4008519D9070 | Q999,N4008519D9070 N4008521F4540 | 10850 | 11501 | 2023-08-05 | 2023-09-06 | 651 | 32 | 2023 | 09 | 06 | 20230906 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 10856.6222 | 11479.637 | 623.0148 | 32 | 918 | 3.486%
2022-01-12 | 2016 | Special Operations Command | Q1126 |  | 2016-05-10 | 2016-08-08 | A&D GC INC | N62473 | N6247315D2403 0005 | N6247315D2403 | Q1126,N6247315D2403 0005 | 10911 | 11647 | 2018-02-14 | 2019-02-28 | 736 | 379 | 2019 | 02 | 28 | 20190228 | 2016 | 2019 | 1.2319 | 2018 | 1.2082 | 13441.6663 | 14330.9209 | 889.2546 | 379 | 555 | 68.29%
2021-09-13 | 2020 | Special Operations Command | P824 |  | 2020-08-05 | 2020-09-30 | ASTURIAN-CONSIGLI JV, LLC | N40085 | N4008518D1124 N4008520F6689 | N4008518D1124 | P824,N4008518D1124 N4008520F6689 | 11130 | 12399 | 2022-08-16 | 2022-08-16 | 1269 | 0 | 2022 | 08 | 16 | 20220816 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 11437.0894 | 12676.8741 | 1239.7847 | 0 | 685 | 0%
2022-01-12 | 2018 | Special Operations Command | Q1394 |  | 2019-09-17 | 2020-03-27 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520D0036 | N4008520D0036 | Q1394,N4008520D0036 | 11658 | 11912 | 2021-10-04 | 2022-03-28 | 254 | 175 | 2022 | 03 | 28 | 20220328 | 2020 | 2022 | 1.0751 | 2021 | 1.0006 | 12533.2558 | 12787.4108 | 254.155 | 175 | 556 | 31.47%
2021-09-13 | 2018 | Special Operations Command | P1394 |  | 2019-09-17 | 2020-03-27 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520D0036 | N4008520D0036 | P1394,N4008520D0036 | 11658 | 11915 | 2021-10-04 | 2021-10-23 | 257 | 19 | 2021 | 10 | 23 | 20211023 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 11665.1154 | 11911.0675 | 245.9521 | 19 | 556 | 3.417%
2022-01-12 | 2015 | Special Operations Command | Q1119 |  | 2015-08-05 | 2015-09-29 | COX CONSTRUCTION CO | N62473 | N6247315D2405 0003 | N6247315D2405 | Q1119,N6247315D2405 0003 | 12428 | 12167 | 2016-04-06 | 2016-04-06 | -261 | 0 | 2016 | 04 | 06 | 20160406 | 2015 | 2016 | 1.1743 | 2016 | 1.1519 | 14594.4303 | 14293.7928 | -300.6374 | 0 | 190 | 0%
2022-01-12 | 2020 | Special Operations Command | Q824 |  | 2020-08-05 | 2020-09-30 | ASTURIAN-CONSIGLI JV, LLC | N40085 | N4008518D1124 N4008520F6689 | N4008518D1124 | Q824,N4008518D1124 N4008520F6689 | 12500 | 12399 | 2022-08-16 | 2022-08-16 | -101 | 0 | 2022 | 08 | 16 | 20220816 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 12844.8892 | 12746.2145 | -98.6747 | 0 | 685 | 0%
2021-12-31 | 2017 | Air Force Active | FTFA033003 |  | 2017-11-21 | 2017-12-21 | Yerkes South, Inc (Abatement) | FA2823 | FA282318F4654 | FA282318F4654 | FTFA033003,FA282318F4654 | 13216 | 13216 | 2018-03-16 | 2018-03-16 | 0 | 0 | 2018 | 03 | 16 | 20180316 | 2018 | 2018 | 1.0507 | 2018 | 1.0276 | 13886.0636 | 13886.0636 | 0 | 0 | 85 | 0%
2021-09-13 | 2020 | Special Operations Command | P1395 |  | 2020-07-14 | 2020-12-18 | WHITING-TURNER CONTRACTING CO | N40085 | N4008521C0018 AWD | N4008521C0018 | P1395,N4008521C0018 AWD | 13438 | 15727 | 2022-12-17 | 2023-02-17 | 2289 | 62 | 2023 | 02 | 17 | 20230217 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 14446.8941 | 16737.2912 | 2290.3971 | 62 | 729 | 8.505%
2022-01-12 | 2015 | Special Operations Command | Q166 |  | 2015-05-05 | 2015-09-21 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N40085 | N4008510D5333 0011 | N4008510D5333 | Q166,N4008510D5333 0011 | 13588 | 13362 | 2017-07-17 | 2019-03-04 | -226 | 595 | 2019 | 03 | 04 | 20190304 | 2015 | 2019 | 1.0006 | 2017 | 0.97698 | 13596.2933 | 13375.4964 | -220.797 | 595 | 665 | 89.47%
2022-01-12 | 2016 | Special Operations Command | Q1288 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N40085 | N4008518C0614 | N4008518C0614 | Q1288,N4008518C0614 | 14741 | 15200 | 2020-01-12 | 2021-12-17 | 459 | 705 | 2021 | 12 | 17 | 20211217 | 2018 | 2022 | 0.95701 | 2020 | 0.9382 | 14107.3143 | 14537.9472 | 430.6329 | 705 | 745 | 94.63%
2021-09-13 | 2013 | Special Operations Command | P888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N62473 | N6247309D1655 0005 | N6247309D1655 | P888,N6247309D1655 0005 | 14869 | 14339 | 2016-09-29 | 2017-11-08 | -530 | 405 | 2017 | 11 | 08 | 20171108 | 2014 | 2018 | 1.0507 | 2016 | 1.0507 | 15622.8722 | 15066.0007 | -556.8715 | 405 | 730 | 55.48%
2021-10-20 | 2013 | Special Operations Command | Q888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N62473 | N6247309D1655 0005 | N6247309D1655 | Q888,N6247309D1655 0005 | 14869 | 14256 | 2016-09-29 | 2017-11-08 | -613 | 405 | 2017 | 11 | 08 | 20171108 | 2014 | 2018 | 1.2082 | 2016 | 1.1914 | 17965.1175 | 17234.8135 | -730.3041 | 405 | 730 | 55.48%
2022-01-12 | 2015 | Special Operations Command | Q183 |  | 2015-08-12 | 2016-04-17 | CLARK NEXSEN - CH2M HILL - NORFOLK | N62470 | N6247011D1010 WE11 | N6247011D1010 | Q183,N6247011D1010 WE11 | 15050 | 16162 | 2017-10-01 | 2018-05-18 | 1112 | 229 | 2018 | 05 | 18 | 20180518 | 2016 | 2018 | 1.0276 | 2017 | 1.0006 | 15465.2466 | 16577.9253 | 1112.6787 | 229 | 532 | 43.05%
2022-01-12 | 2019 | Special Operations Command | Q918 |  | 2019-05-01 | 2019-09-26 | THE HASKELL COMPANY | N62473 | N6247317D0818 | N6247317D0818 | Q918,N6247317D0818 | 15182 | 14821 | 2021-10-09 | 2022-02-24 | -361 | 138 | 2022 | 02 | 24 | 20220224 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 15191.2662 | 14838.5773 | -352.689 | 138 | 744 | 18.55%
2021-09-13 | 2019 | Special Operations Command | P918 |  | 2019-05-01 | 2019-09-26 | THE HASKELL COMPANY | N62473 | N6247317D0818 | N6247317D0818 | P918,N6247317D0818 | 15182 | 15119 | 2021-10-09 | 2021-11-11 | -63 | 33 | 2021 | 11 | 11 | 20211111 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 15191.2662 | 15129.7166 | -61.5496 | 33 | 744 | 4.435%
2022-01-12 | 2020 | Special Operations Command | Q1395 |  | 2020-07-14 | 2020-12-18 | WHITING-TURNER CONTRACTING CO | N40085 | N4008521C0018 AWD | N4008521C0018 | Q1395,N4008521C0018 AWD | 15417 | 15683 | 2022-12-17 | 2023-02-17 | 266 | 62 | 2023 | 02 | 17 | 20230217 | 2021 | 2023 | 1.0993 | 2022 | 1.0276 | 16947.2176 | 17220.5568 | 273.3392 | 62 | 729 | 8.505%
2021-09-13 | 2019 | Special Operations Command | P949 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N62473 | N6247317D0822 N6247320F4023 | N6247317D0822 | P949,N6247317D0822 N6247320F4023 | 15467 | 16676 | 2022-05-19 | 2022-09-12 | 1209 | 116 | 2022 | 09 | 12 | 20220912 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 15476.4402 | 16657.6062 | 1181.1661 | 116 | 934 | 12.42%
2022-01-12 | 2019 | Special Operations Command | Q949 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N62473 | N6247317D0822 N6247320F4023 | N6247317D0822 | Q949,N6247317D0822 N6247320F4023 | 15467 | 16189 | 2022-05-19 | 2022-09-12 | 722 | 116 | 2022 | 09 | 12 | 20220912 | 2020 | 2022 | 1.1743 | 2021 | 1.1227 | 18163.1842 | 18973.7532 | 810.569 | 116 | 934 | 12.42%
2021-12-31 | 2017 | Air Force Active | FTQW170100 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB | W911KB21F0085 | W911KB21F0085 | FTQW170100,W911KB21F0085 | 15588 | 15588 | 2021-08-14 | 2021-08-14 | 0 | 0 | 2021 | 08 | 14 | 20210814 | 2021 | 2021 | 1.0006 | 2021 | 0.9382 | 15597.514 | 15597.514 | 0 | 0 | 45 | 0%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AE | S | XLWU203006,S/CLIN 1019AE | 16114 | 16114 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 16930.9949 | 16930.9949 | 0 | 0 | 745 | 0%
2022-01-12 | 2017 | Special Operations Command | Q952 |  | 2017-04-28 | 2017-08-10 | SOLTEK PACIFIC CONSTRUCTION CO | N62473 | N6247317D0821 | N6247317D0821 | Q952,N6247317D0821 | 16668 | 16762 | 2019-11-22 | 2020-03-02 | 94 | 101 | 2020 | 03 | 02 | 20200302 | 2017 | 2020 | 1.1914 | 2019 | 1.1743 | 19857.5988 | 19967.9847 | 110.3859 | 101 | 834 | 12.11%
2022-02-02 | 2014 | DoD Education Activity | EU00072 | 7 | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB | W912GB-12-C-0022 | W912GB12C0022 | EU00072,W912GB-12-C-0022 | 16940 | 234472 | 2019-04-19 | 2018-07-26 | 217532 | -267 | 2018 | 07 | 26 | 20180726 | 2016 | 2018 | 1.0006 | 2017 | 0.97698 | 16950.3392 | 229474.2558 | 212523.9166 | -267 | 1093 | -24.43%
2021-09-13 | 2020 | Special Operations Command | P945 |  | 2020-01-23 | 2021-01-15 | EG DESIGNBUILD, L.L.C | N69450 | N6945019D0919 N6945021F0872 | N6945019D0919 | P945,N6945019D0919 N6945021F0872 | 17165 | 18219 | 2022-10-31 | 2022-10-31 | 1054 | 0 | 2022 | 10 | 31 | 20221031 | 2021 | 2023 | 1.0006 | 2022 | 0.9382 | 17175.4765 | 18164.3373 | 988.8608 | 0 | 654 | 0%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB | W912GB-10-C-0031, ABG4 P00031 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31 | 0 | 0 | 2014 | 12 | 31 | 20141231 | 2012 | 2015 | 1.1914 | 2014 | 1.1519 | 21102.5706 | 21102.5706 | 0 | 0 | 1021 | 0%
2022-01-12 | 2017 | Special Operations Command | Q919 |  | 2016-09-20 | 2017-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N62473 | N6247317D0821 | N6247317D0821 | Q919,N6247317D0821 | 18210 | 18051 | 2018-10-22 | 2020-03-06 | -159 | 501 | 2020 | 03 | 06 | 20200306 | 2017 | 2020 | 1.0276 | 2019 | 1.0006 | 18712.4346 | 18553.3376 | -159.097 | 501 | 571 | 87.74%
2021-12-31 | 2018 | Air Force Active | FTQW180107 |  | 2020-05-25 | 2020-06-24 | AECOM Technical Services, Inc | W911KB | W911KB19F0159 | W911KB19F0159 | FTQW180107,W911KB19F0159 | 18242 | 18242 | 2020-08-08 | 2020-08-08 | 0 | 0 | 2020 | 08 | 08 | 20200808 | 2020 | 2020 | 1.0276 | 2020 | 0.97698 | 18745.3175 | 18745.3175 | 0 | 0 | 45 | 0%
2022-01-12 | 2020 | Special Operations Command | Q945 |  | 2020-01-23 | 2021-01-15 | EG DESIGNBUILD, L.L.C | N69450 | N6945019D0919 N6945021F0872 | N6945019D0919 | Q945,N6945019D0919 N6945021F0872 | 18408 | 18219 | 2022-10-31 | 2022-10-31 | -189 | 0 | 2022 | 10 | 31 | 20221031 | 2021 | 2023 | 1.1743 | 2022 | 1.1227 | 21616.8549 | 21404.6699 | -212.185 | 0 | 654 | 0%
2021-09-13 | 2019 | Special Operations Command | P950 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N62473 | N6247317D0822 N6247320F4023 | N6247317D0822 | P950,N6247317D0822 N6247320F4023 | 18434 | 21058 | 2022-05-19 | 2022-09-12 | 2624 | 116 | 2022 | 09 | 12 | 20220912 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 18942.615 | 21568.2166 | 2625.6015 | 116 | 934 | 12.42%
2022-01-12 | 2019 | Special Operations Command | Q950 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N62473 | N6247317D0822 N6247320F4023 | N6247317D0822 | Q950,N6247317D0822 N6247320F4023 | 18434 | 20159 | 2022-05-19 | 2022-09-12 | 1725 | 116 | 2022 | 09 | 12 | 20220912 | 2020 | 2022 | 1.0006 | 2021 | 0.9382 | 18445.251 | 20063.6427 | 1618.3917 | 116 | 934 | 12.42%
2022-01-12 | 2015 | Special Operations Command | Q240 |  | 2019-04-22 | 2019-07-29 | TIKIGAQ CONSTRUCTION, LLC | N69450 | N6945019C5214 | N6945019C5214 | Q240,N6945019C5214 | 18436 | 16982 | 2020-01-25 | 2020-01-25 | -1454 | 0 | 2020 | 01 | 25 | 20200125 | 2019 | 2020 | 1.0751 | 2020 | 1.0276 | 19820.1324 | 18326.0149 | -1494.1175 | 0 | 180 | 0%
2022-01-12 | 2014 | Special Operations Command | Q157 |  | 2014-11-13 | 2016-02-26 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N40085 | N4008510D5333 0008 | N4008510D5333 | Q157,N4008510D5333 0008 | 19230 | 19583 | 2017-09-03 | 2020-09-16 | 353 | 1109 | 2020 | 09 | 16 | 20200916 | 2016 | 2020 | 1.0006 | 2018 | 0.97698 | 19241.7369 | 19586.61 | 344.8731 | 1109 | 555 | 199.8%
2022-01-12 | 2015 | Special Operations Command | Q418 |  | 2015-06-12 | 2015-08-18 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247310D5406 0006 | N6247310D5406 | Q418,N6247310D5406 0006 | 20585 | 21213 | 2017-02-23 | 2018-02-12 | 628 | 354 | 2018 | 02 | 12 | 20180212 | 2015 | 2018 | 1.0006 | 2017 | 0.95701 | 20597.5639 | 21198.5674 | 601.0036 | 354 | 555 | 63.78%
2021-12-31 | 2018 | Air Force Active | FTQW180107 |  | 2020-05-31 | 2020-06-30 | Sundance - EA II, LLC | W911KB | W911KB17F0055 | W911KB17F0055 | FTQW180107,W911KB17F0055 | 22546 | 22546 | 2020-08-14 | 2020-08-14 | 0 | 0 | 2020 | 08 | 14 | 20200814 | 2020 | 2020 | 1.0507 | 2020 | 1.0006 | 23689.1033 | 23689.1033 | 0 | 0 | 45 | 0%
2021-09-13 | 2018 | Special Operations Command | P791 |  | 2018-01-19 | 2018-09-13 | HOURIGAN CONSTRUCTION CORPORATION | N40085 | N4008518C1103 | N4008518C1103 | P791,N4008518C1103 | 24701 | 24983 | 2021-03-17 | 2022-04-05 | 282 | 384 | 2022 | 04 | 05 | 20220405 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 24716.0761 | 24991.5838 | 275.5077 | 384 | 916 | 41.92%
2022-01-12 | 2018 | Special Operations Command | Q791 |  | 2018-01-19 | 2018-09-13 | HOURIGAN CONSTRUCTION CORPORATION | N40085 | N4008518C1103 | N4008518C1103 | Q791,N4008518C1103 | 24701 | 24983 | 2021-03-17 | 2022-04-05 | 282 | 384 | 2022 | 04 | 05 | 20220405 | 2018 | 2022 | 1.2581 | 2020 | 1.2082 | 31075.3583 | 31416.0781 | 340.7198 | 384 | 916 | 41.92%
2021-09-13 | 2016 | Special Operations Command | P777 |  | 2016-10-31 | 2018-07-16 | WHITING-TURNER CONTRACTING CO | N40085 | N4008518C1137 | N4008518C1137 | P777,N4008518C1137 | 24780 | 24173 | 2020-10-09 | 2021-04-12 | -607 | 185 | 2021 | 04 | 12 | 20210412 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 25463.7084 | 24870.6829 | -593.0255 | 185 | 816 | 22.67%
2022-01-12 | 2016 | Special Operations Command | Q777 |  | 2016-10-31 | 2018-07-16 | WHITING-TURNER CONTRACTING CO | N40085 | N4008518C1137 | N4008518C1137 | Q777,N4008518C1137 | 24780 | 24173 | 2020-10-09 | 2021-04-12 | -607 | 185 | 2021 | 04 | 12 | 20210412 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 25463.7084 | 24870.6829 | -593.0255 | 185 | 816 | 22.67%
2021-09-13 | 2015 | Special Operations Command | P893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N62473 | N6247315C1609 AWD | N6247315C1609 | P893,N6247315C1609 AWD | 24873 | 24379 | 2018-04-02 | 2019-03-11 | -494 | 343 | 2019 | 03 | 11 | 20190311 | 2015 | 2019 | 1.0006 | 2017 | 0.97698 | 24888.181 | 24405.554 | -482.627 | 343 | 915 | 37.49%
2022-01-12 | 2015 | Special Operations Command | Q893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N62473 | N6247315C1609 AWD | N6247315C1609 | Q893,N6247315C1609 AWD | 24873 | 24376 | 2018-04-02 | 2019-03-11 | -497 | 343 | 2019 | 03 | 11 | 20190311 | 2015 | 2019 | 1.0507 | 2017 | 1.0276 | 26134.0844 | 25623.3716 | -510.7128 | 343 | 915 | 37.49%
2021-12-31 | 2018 | Air Force Active | FTQW180107 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB | W911KB21F0085 | W911KB21F0085 | FTQW180107,W911KB21F0085 | 26041 | 26041 | 2021-08-14 | 2021-08-14 | 0 | 0 | 2021 | 08 | 14 | 20210814 | 2021 | 2021 | 1.1227 | 2021 | 1.0993 | 29235.4952 | 29235.4952 | 0 | 0 | 45 | 0%
2022-01-12 | 2020 | Special Operations Command | Q1534 |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | Q1534,N4008520D0034 N4008520F6501 | 26080 | 26796 | 2024-05-27 | 2025-01-07 | 716 | 225 | 2025 | 01 | 07 | 20250107 | 2020 | 2025 | 1.0751 | 2023 | 1.0006 | 28038.0264 | 28754.4634 | 716.437 | 225 | 1350 | 16.67%
2021-09-13 | 2019 | Special Operations Command | P200 |  | 2019-01-30 | 2020-06-30 | RQ CONSTRUCTION, LLC | N62473 | N6247317D0820 N6247320F4839 | N6247317D0820 | P200,N6247317D0820 N6247320F4839 | 26431 | 30463 | 2023-01-20 | 2023-01-20 | 4032 | 0 | 2023 | 01 | 20 | 20230120 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 27771.0764 | 31805.5373 | 4034.4609 | 0 | 934 | 0%
2022-01-12 | 2019 | Special Operations Command | Q200 |  | 2019-01-30 | 2020-06-30 | RQ CONSTRUCTION, LLC | N62473 | N6247317D0820 N6247320F4839 | N6247317D0820 | Q200,N6247317D0820 N6247320F4839 | 26431 | 30670 | 2023-01-20 | 2023-01-20 | 4239 | 0 | 2023 | 01 | 20 | 20230120 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 27160.2614 | 31301.6699 | 4141.4085 | 0 | 934 | 0%
2022-01-12 | 2020 | Special Operations Command | Q224 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519D9070 N4008521F4540 | N4008519D9070 | Q224,N4008519D9070 N4008521F4540 | 26797 | 26134 | 2023-08-05 | 2023-09-06 | -663 | 32 | 2023 | 09 | 06 | 20230906 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 28155.633 | 27492.2283 | -663.4047 | 32 | 918 | 3.486%
2021-09-13 | 2014 | Special Operations Command | P334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N40085 | N4008510D5333 0007 | N4008510D5333 | P334,N4008510D5333 0007 | 29668 | 31020 | 2018-07-29 | 2020-05-01 | 1352 | 642 | 2020 | 05 | 01 | 20200501 | 2016 | 2020 | 1.0751 | 2018 | 1.0276 | 31895.4051 | 33284.7083 | 1389.3032 | 642 | 900 | 71.33%
2022-01-12 | 2014 | Special Operations Command | Q334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N40085 | N4008510D5333 0007 | N4008510D5333 | Q334,N4008510D5333 0007 | 29668 | 31020 | 2018-07-29 | 2020-05-01 | 1352 | 642 | 2020 | 05 | 01 | 20200501 | 2016 | 2020 | 1.2826 | 2018 | 1.2581 | 38051.1069 | 39752.005 | 1700.8981 | 642 | 900 | 71.33%
2021-12-31 | 2017 | Air Force Active | FTQW170100 |  | 2020-05-25 | 2020-06-24 | AECOM Technical Services, Inc | W911KB | W911KB19F0159 | W911KB19F0159 | FTQW170100,W911KB19F0159 | 30099 | 30099 | 2020-08-08 | 2020-08-08 | 0 | 0 | 2020 | 08 | 08 | 20200808 | 2020 | 2020 | 1.0276 | 2020 | 0.97698 | 30929.4656 | 30929.4656 | 0 | 0 | 45 | 0%
2022-01-12 | 2015 | Special Operations Command | Q776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N62473 | N6247315D2426 0002 | N6247315D2426 | Q776,N6247315D2426 0002 | 30528 | 37009 | 2017-10-23 | 2019-07-23 | 6481 | 638 | 2019 | 07 | 23 | 20190723 | 2015 | 2019 | 1.0751 | 2017 | 1.0507 | 32819.9719 | 39629.5647 | 6809.5928 | 638 | 754 | 84.62%
2022-01-12 | 2014 | Special Operations Command | 1391 |  | 2014-05-29 | 2014-08-28 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N40085 | N4008510D5333 0004 | N4008510D5333 | 1391,N4008510D5333 0004 | 30963 | 30840 | 2016-09-02 | 2019-01-31 | -123 | 881 | 2019 | 01 | 31 | 20190131 | 2014 | 2019 | 1.1914 | 2017 | 1.1743 | 36888.0988 | 36743.6576 | -144.4412 | 881 | 736 | 119.7%
2021-12-31 | 2017 | Air Force Active | FTQW183001 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB | W911KB21F0085 | W911KB21F0085 | FTQW183001,W911KB21F0085 | 31412 | 31412 | 2021-08-14 | 2021-08-14 | 0 | 0 | 2021 | 08 | 14 | 20210814 | 2021 | 2021 | 1.0507 | 2021 | 1.0006 | 33004.6178 | 33004.6178 | 0 | 0 | 45 | 0%
2022-01-12 | 2014 | Special Operations Command | Q771 |  | 2018-07-13 | 2018-09-19 | SOLPAC CONSTRUCTION INC | N62473 | N6247317D0821 | N6247317D0821 | Q771,N6247317D0821 | 32018 | 34171 | 2020-02-02 | 2021-12-02 | 2153 | 669 | 2021 | 12 | 02 | 20211202 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 32901.413 | 35055.7271 | 2154.3141 | 669 | 501 | 133.5%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AC | S | XLWU203006,S/CLIN 1019AC | 35974 | 35974 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 37797.9155 | 37797.9155 | 0 | 0 | 745 | 0%
2022-01-12 | 2017 | Special Operations Command | Q889 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N62473 | N6247314D0061 | N6247314D0061 | Q889,N6247314D0061 | 36321 | 34701 | 2020-03-31 | 2021-01-31 | -1620 | 306 | 2021 | 01 | 31 | 20210131 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 36343.1682 | 34760.4643 | -1582.7039 | 306 | 915 | 33.44%
2022-01-12 | 2017 | Special Operations Command | Q890 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N62473 | N6247317C0830 | N6247317C0830 | Q890,N6247317C0830 | 37097 | 35530 | 2020-03-31 | 2021-01-31 | -1567 | 306 | 2021 | 01 | 31 | 20210131 | 2017 | 2021 | 1.0507 | 2019 | 1.0507 | 38977.8526 | 37331.4043 | -1646.4484 | 306 | 915 | 33.44%
2021-12-31 | 2017 | Air Force Active | FTQW170100 |  | 2020-05-31 | 2020-06-30 | Sundance - EA II, LLC | W911KB | W911KB17F0055 | W911KB17F0055 | FTQW170100,W911KB17F0055 | 37199 | 37199 | 2020-08-14 | 2020-08-14 | 0 | 0 | 2020 | 08 | 14 | 20200814 | 2020 | 2020 | 1.2319 | 2020 | 1.1914 | 45826.8302 | 45826.8302 | 0 | 0 | 45 | 0%
2021-09-13 | 2020 | Special Operations Command | P1534 |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | P1534,N4008520D0034 N4008520F6501 | 38218 | 26796 | 2024-05-27 | 2024-05-27 | -11422 | 0 | 2024 | 05 | 27 | 20240527 | 2020 | 2024 | 1.0006 | 2022 | 0.9382 | 38241.326 | 27525.2277 | -10716.0983 | 0 | 1350 | 0%
2022-01-12 | 2018 | Special Operations Command | Q964 |  | 2018-02-22 | 2018-09-13 | RQ CONSTRUCTION, LLC | N62473 | N6247318C1017 | N6247318C1017 | Q964,N6247318C1017 | 39378 | 38024 | 2021-03-31 | 2021-06-13 | -1354 | 74 | 2021 | 06 | 13 | 20210613 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 38471.4285 | 37175.6342 | -1295.7943 | 74 | 930 | 7.957%
2022-01-12 | 2021 | Special Operations Command | Q907 |  | 2021-02-07 | 2021-05-07 | Unkown | N40085 | N4008520D0036 #N4008521F5235 | N4008520D0036 | Q907,N4008520D0036 #N4008521F5235 | 44471 | 0 | 2023-07-26 | 2023-08-19 | -44471 | 24 | 2023 | 08 | 19 | 20230819 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 44498.1425 | 1050.9665 | -43447.176 | 24 | 810 | 2.963%
2021-09-13 | 2021 | Special Operations Command | P907 |  | 2021-01-07 | 2021-05-07 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520D0036 #N4008521F5235 | N4008520D0036 | P907,N4008520D0036 #N4008521F5235 | 44471 | 44471 | 2023-07-26 | 2023-07-26 | 0 | 0 | 2023 | 07 | 26 | 20230726 | 2021 | 2023 | 1.1227 | 2022 | 1.0276 | 49926.3357 | 49926.3357 | 0 | 0 | 810 | 0%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G | W9126G-11-P-0208 | W9126G11P0208 | 72481,W9126G-11-P-0208 | 46000 | 46000 | 2011-11-01 | 2011-11-01 | 0 | 0 | 2011 | 11 | 01 | 20111101 | 2011 | 2012 | 1.0006 | 2012 | 0.97698 | 46028.0757 | 46028.0757 | 0 | 0 | 68 | 0%
2022-01-12 | 2017 | Special Operations Command | Q966 |  | 2017-04-28 | 2017-09-28 | M A MORTENSON COMPANY | N62473 | N6247317D0819 | N6247317D0819 | Q966,N6247317D0819 | 46106 | 44895 | 2020-04-19 | 2020-11-20 | -1211 | 215 | 2020 | 11 | 20 | 20201120 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 47378.117 | 46166.3779 | -1211.7391 | 215 | 934 | 23.02%
2021-09-13 | 2016 | Special Operations Command | P920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N62473 | N6247315D2428 0003 | N6247315D2428 | P920,N6247315D2428 0003 | 47022 | 45951 | 2018-10-13 | 2019-12-27 | -1071 | 440 | 2019 | 12 | 27 | 20191227 | 2016 | 2020 | 1.3029 | 2018 | 1.2826 | 61262.7017 | 59889.0757 | -1373.626 | 440 | 753 | 58.43%
2022-01-12 | 2016 | Special Operations Command | Q920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N62473 | N6247315D2428 0003 | N6247315D2428 | Q920,N6247315D2428 0003 | 47022 | 45942 | 2018-10-13 | 2019-12-27 | -1080 | 440 | 2019 | 12 | 27 | 20191227 | 2016 | 2020 | 1.0006 | 2018 | 0.97698 | 47050.6995 | 45995.5636 | -1055.1359 | 440 | 753 | 58.43%
2021-09-13 | 2018 | Special Operations Command | P921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION, LLC | N62473 | N6247318D0820 | N6247318D0820 | P921,N6247318D0820 | 47550 | 45441 | 2021-02-15 | 2021-06-18 | -2109 | 123 | 2021 | 06 | 18 | 20210618 | 2018 | 2021 | 1.0507 | 2020 | 1.0276 | 49960.8295 | 47793.6398 | -2167.1897 | 123 | 935 | 13.16%
2022-01-12 | 2018 | Special Operations Command | Q921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION, LLC | N62473 | N6247318D0820 | N6247318D0820 | Q921,N6247318D0820 | 47550 | 45424 | 2021-02-15 | 2021-06-18 | -2126 | 123 | 2021 | 06 | 18 | 20210618 | 2018 | 2021 | 1.0006 | 2020 | 0.97698 | 47579.0218 | 45501.9671 | -2077.0546 | 123 | 935 | 13.16%
2021-09-13 | 2021 | Special Operations Command | P997 |  | 2020-10-14 | 2021-05-07 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008521F5236 | N4008520D0034 | P997,N4008520D0034 N4008521F5236 | 48989 | 0 | 2024-03-16 | 2024-03-16 | -48989 | 0 | 2024 | 03 | 16 | 20240316 | 2021 | 2024 | 1.0507 | 2023 | 1.0006 | 51472.7881 | 2453.8881 | -49018.9 | 0 | 1044 | 0%
2022-01-12 | 2018 | Special Operations Command | Q892 |  | 2017-11-07 | 2018-09-13 | RQ CONSTRUCTION, LLC | N62473 | N6247318C1017 | N6247318C1017 | Q892,N6247318C1017 | 49562 | 48220 | 2021-03-31 | 2021-06-13 | -1342 | 74 | 2021 | 06 | 13 | 20210613 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 48420.9696 | 47136.6594 | -1284.3101 | 74 | 930 | 7.957%
2021-09-13 | 2020 | Special Operations Command | P463 |  | 2019-08-29 | 2020-04-15 | HENSEL PHELPS CONSTRUCTION CO. | N62478 | N6247819D5029 | N6247819D5029 | P463,N6247819D5029 | 54279 | 61404 | 2022-04-15 | 2022-04-15 | 7125 | 0 | 2022 | 04 | 15 | 20220415 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 57030.9961 | 64160.3448 | 7129.3487 | 0 | 730 | 0%
2022-02-02 | 2021 | DoD Education Activity | AM00182 |  | 2021-04-29 | 2021-08-11 | Messer Construction | W912QR | W912QR-21-C-0033/59023911 | W912QR21C0033 | AM00182,W912QR-21-C-0033/59023911 | 58989 | 58989 | 2025-09-28 | 2024-10-09 | 0 | -354 | 2024 | 10 | 09 | 20241009 | 2021 | 2025 | 1.0276 | 2023 | 0.95701 | 60616.5736 | 60616.5736 | 0 | -354 | 1509 | -23.46%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB | W912GB-10-C-0031, ABG4 P00066 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00066 | 62000 | 68000 | 2016-10-30 | 2016-12-30 | 6000 | 61 | 2016 | 12 | 30 | 20161230 | 2012 | 2017 | 1.0993 | 2015 | 1.0507 | 68153.8231 | 74458.0287 | 6304.2056 | 61 | 1690 | 3.609%
2021-09-13 | 2016 | Special Operations Command | P1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N40085 | N4008518C0614 | N4008518C0614 | P1219,N4008518C0614 | 63726 | 65226 | 2020-01-12 | 2021-07-12 | 1500 | 547 | 2021 | 07 | 12 | 20210712 | 2018 | 2021 | 1.0751 | 2020 | 1.0276 | 68510.4014 | 70051.7881 | 1541.3867 | 547 | 745 | 73.42%
2022-01-12 | 2016 | Special Operations Command | Q1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N40085 | N4008518C0614 | N4008518C0614 | Q1219,N4008518C0614 | 64004 | 65183 | 2020-01-12 | 2021-12-17 | 1179 | 705 | 2021 | 12 | 17 | 20211217 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 65769.9432 | 66949.6627 | 1179.7196 | 705 | 745 | 94.63%
2021-12-31 | 2021 | Air Force Active | AJJY203001 |  | 2021-09-08 | 2021-10-08 | Navy Crane Center | N62742 | N6274221C1339 | N6274221C1339 | AJJY203001,N6274221C1339 | 66610 | 66610 | 2021-11-22 | 2021-11-22 | 0 | 0 | 2021 | 11 | 22 | 20211122 | 2022 | 2022 | 1.0006 | 2022 | 0.95701 | 66650.6549 | 66650.6549 | 0 | 0 | 45 | 0%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AA | S | XLWU203006,S/CLIN 1019AA | 73710 | 73710 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 75743.7427 | 75743.7427 | 0 | 0 | 745 | 0%
2022-02-02 | 2014 | DoD Education Activity | EU00072 | 720 | 2015-11-25 | 2016-04-22 | Federal Republic of Germany | W912GB | W912GB-12-C-0022 | W912GB12C0022 | EU00072,W912GB-12-C-0022 | 75891 | 85778 | 2019-04-19 | 2018-07-26 | 9887 | -267 | 2018 | 07 | 26 | 20180726 | 2016 | 2018 | 0.97698 | 2017 | 0.95701 | 74143.8159 | 83605.7938 | 9461.9779 | -267 | 1092 | -24.45%
2022-01-12 | 2018 | Special Operations Command | Q855 |  | 2017-11-08 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N62473 | N6247319C1238 | N6247319C1238 | Q855,N6247319C1238 | 96932 | 98243 | 2022-08-30 | 2023-02-10 | 1311 | 164 | 2023 | 02 | 10 | 20230210 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 99606.4641 | 100887.2819 | 1280.8178 | 164 | 1065 | 15.4%
2021-09-13 | 2018 | Special Operations Command | P855 |  | 2017-11-08 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N62473 | N6247319C1238 | N6247319C1238 | P855,N6247319C1238 | 96932 | 102065 | 2022-08-30 | 2022-12-07 | 5133 | 99 | 2022 | 12 | 07 | 20221207 | 2019 | 2023 | 1.0507 | 2021 | 1.0276 | 101846.5431 | 107121.1684 | 5274.6253 | 99 | 1065 | 9.296%
2021-12-31 | 2018 | Air Force Active | ASVF183100F |  | 2019-10-21 | 2019-11-20 | The Morganti Group, Inc (Pkg 2, Aprons),Danbury/CT | W912ER | W912ER20C0002 | W912ER20C0002 | ASVF183100F,W912ER20C0002 | 100000 | 350000 | 2020-01-04 | 2020-09-05 | 250000 | 245 | 2020 | 09 | 05 | 20200905 | 2020 | 2020 | 1.0507 | 2020 | 1.0006 | 105070.0936 | 355222.679 | 250152.5854 | 245 | 45 | 544.4%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AG | S | XLWU203006,S/CLIN 1019AG | 102203 | 102203 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 107384.7877 | 107384.7877 | 0 | 0 | 745 | 0%
2021-12-31 | 2018 | Air Force Active | ASVF183100F |  | 2019-03-06 | 2019-04-05 | The Morganti Group, Inc (Pkg 3, Dorm), Danbury, CT | W912ER | W912ER19C0008 | W912ER19C0008 | ASVF183100F,W912ER19C0008 | 118048 | 118048 | 2020-10-13 | 2021-02-18 | 0 | 128 | 2021 | 02 | 18 | 20210218 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 115330.2655 | 115330.2655 | 0 | 128 | 557 | 22.98%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB | W912GB-10-C-0031, ABG4 P00033 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00033 | 141234 | 142000 | 2015-03-30 | 2015-05-01 | 766 | 32 | 2015 | 05 | 01 | 20150501 | 2012 | 2015 | 1.0006 | 2014 | 1.0006 | 141320.201 | 142086.6685 | 766.4675 | 32 | 1110 | 2.883%
2021-12-31 | 2018 | Air Force Active | AGGN053009 |  | 2020-02-22 | 2020-03-23 | Original Award | W912BV | W912BV20C0005 | W912BV20C0005 | AGGN053009,W912BV20C0005 | 183861 | 183861 | 2022-04-22 | 2022-04-19 | 0 | -3 | 2022 | 04 | 19 | 20220419 | 2020 | 2022 | 1.0276 | 2021 | 0.95701 | 188933.9341 | 188933.9341 | 0 | -3 | 760 | -0.3947%
2022-01-13 | 2020 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB | W912GB-17-C-0005 | W912GB17C0005 | 72742,W912GB-17-C-0005 | 212000 | 212000 | 2021-09-26 | 2021-12-22 | 0 | 87 | 2021 | 12 | 22 | 20211222 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 217849.3211 | 217849.3211 | 0 | 87 | 361 | 24.1%
2021-12-31 | 2016 | Air Force Active | YWHG031002R2 |  | 2018-07-02 | 2019-01-31 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility | W912DQ | W912DQ19C4001 | W912DQ19C4001 | YWHG031002R2,W912DQ19C4001 | 224178 | 224178 | 2020-09-09 | 2020-09-09 | 0 | 0 | 2020 | 09 | 09 | 20200909 | 2019 | 2020 | 1.0507 | 2020 | 1.0006 | 235544.0344 | 235544.0344 | 0 | 0 | 587 | 0%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AB | S | XLWU203006,S/CLIN 1019AB | 237126 | 237126 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0751 | 2022 | 1.0276 | 254928.8741 | 254928.8741 | 0 | 0 | 745 | 0%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB | W912GB-10-C-0031, ABG4 P00023 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00023 | 261000 | 261000 | 2014-04-04 | 2014-04-04 | 0 | 0 | 2014 | 04 | 04 | 20140404 | 2012 | 2014 | 1.0993 | 2013 | 1.0751 | 286905.6101 | 286905.6101 | 0 | 0 | 750 | 0%
2022-01-13 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR | W912DR-10-F-0217 | W912DR10F0217 | 65731,W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30 | 0 | 0 | 2011 | 09 | 30 | 20110930 | 2010 | 2011 | 0.97698 | 2011 | 0.95701 | 274454.5341 | 274454.5341 | 0 | 0 | 403 | 0%
2021-12-31 | 2017 | Air Force Active | FTFA033003 |  | 2017-12-12 | 2018-01-11 | Pac Comm, Inc (Demo) | FA2823 | FA282318F4602 | FA282318F4602 | FTFA033003,FA282318F4602 | 300552 | 300552 | 2018-05-26 | 2018-05-26 | 0 | 0 | 2018 | 05 | 26 | 20180526 | 2018 | 2018 | 1.0006 | 2018 | 0.97698 | 300735.4394 | 300735.4394 | 0 | 0 | 135 | 0%
2021-12-13 | 2008 | Special Operations Command | 65272 |  | 2007-10-23 | 2011-06-21 | Atlantic Marine Construction Company, Inc | W912HN | W912HN-07-D-0024 | W912HN07D0024 | 65272,W912HN-07-D-0024 | 323348 | 343221 | 2011-11-27 | 2012-02-10 | 19873 | 75 | 2012 | 02 | 10 | 20120210 | 2011 | 2012 | 0.97698 | 2012 | 0.95701 | 315903.7907 | 334922.4907 | 19018.7 | 75 | 159 | 47.17%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB | W912GB-10-C-0031, P00071 | W912GB10C0031, | 76007,W912GB-10-C-0031, P00071 | 419000 | 419000 | 2020-03-30 | 2020-03-30 | 0 | 0 | 2020 | 03 | 30 | 20200330 | 2012 | 2020 | 1.0006 | 2016 | 1.0006 | 419255.7332 | 419255.7332 | 0 | 0 | 2937 | 0%
2022-01-13 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR | W912DR-09-C-0030 | W912DR09C0030 |  | 436000 | 436000 | 2010-08-08 | 2010-08-31 | 0 | 23 | 2010 | 08 | 31 | 20100831 | 2009 | 2010 | 0.97698 | 2010 | 0.9382 | 425962.2844 | 425962.2844 | 0 | 23 | 487 | 4.723%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB | W912GB-10-C-0031, ABG4 P00032 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00032 | 473000 | 492000 | 2014-10-16 | 2014-10-16 | 19000 | 0 | 2014 | 10 | 16 | 20141016 | 2012 | 2015 | 1.0751 | 2014 | 1.0276 | 508511.7509 | 528035.9825 | 19524.2316 | 0 | 945 | 0%
2021-12-31 | 2017 | Air Force Active | FTQW183001 |  | 2020-05-25 | 2020-06-24 | AECOM Technical Services, Inc | W911KB | W911KB19F0159 | W911KB19F0159 | FTQW183001,W911KB19F0159 | 560312 | 560312 | 2020-08-08 | 2020-08-08 | 0 | 0 | 2020 | 08 | 08 | 20200808 | 2020 | 2020 | 0.97698 | 2020 | 0.9382 | 547412.3383 | 547412.3383 | 0 | 0 | 45 | 0%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN | S/CLIN 1019AD | S | XLWU203006,S/CLIN 1019AD | 599343 | 599343 | 2023-03-12 | 2023-03-12 | 0 | 0 | 2023 | 03 | 12 | 20230312 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 599708.8041 | 599708.8041 | 0 | 0 | 745 | 0%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR | W912DR-08-C-0016 | W912DR08C0016 |  | 603000 | 604000 | 2013-10-31 | 2013-12-06 | 1000 | 36 | 2013 | 12 | 06 | 20131206 | 2008 | 2014 | 1.2581 | 2011 | 1.0993 | 758610.6243 | 759709.8795 | 1099.2552 | 36 | 1934 | 1.861%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB | W912GB-10-C-0031, ABG4 P00030 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00030 | 681000 | 1747000 | 2014-10-29 | 2015-01-21 | 1066000 | 84 | 2015 | 01 | 21 | 20150121 | 2012 | 2015 | 0.97698 | 2014 | 0.95701 | 665321.8249 | 1685496.6446 | 1020174.8197 | 84 | 958 | 8.768%
2021-12-31 | 2017 | Air Force Active | FTQW183001 |  | 2020-05-31 | 2020-06-30 | Sundance - EA II, LLC | W911KB | W911KB17F0055 | W911KB17F0055 | FTQW183001,W911KB17F0055 | 692488 | 692488 | 2020-08-14 | 2020-08-14 | 0 | 0 | 2020 | 08 | 14 | 20200814 | 2020 | 2020 | 1.0507 | 2020 | 1.0006 | 727597.7897 | 727597.7897 | 0 | 0 | 45 | 0%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR | W912DR-08-C-0078 | W912DR08C0078 |  | 706000 | 706000 | 2010-04-13 | 2010-04-13 | 0 | 0 | 2010 | 04 | 13 | 20100413 | 2009 | 2010 | 1.0006 | 2010 | 0.97698 | 706430.9013 | 706430.9013 | 0 | 0 | 197 | 0%
2021-10-08 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | M INC | W912PM | W912PM-16-F-0007 | W912PM16F0007 | 61064,W912PM-16-F-0007 | 770924 | 786940 | 2016-11-27 | 2017-05-23 | 16016 | 177 | 2017 | 05 | 23 | 20170523 | 2015 | 2017 | 1.0276 | 2016 | 1.0006 | 792194.67 | 808220.4452 | 16025.7752 | 177 | 783 | 22.61%
2021-12-31 | 2018 | Air Force Active | ASVF183100E |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER | W912ER20C0009 | W912ER20C0009 | ASVF183100E,W912ER20C0009 | 804821 | 806055 | 2023-03-28 | 2023-03-28 | 1234 | 0 | 2023 | 03 | 28 | 20230328 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 845626.1779 | 846860.9311 | 1234.7532 | 0 | 1082 | 0%
2021-12-31 | 2018 | Army Active | 91732 |  | 2018-07-30 | 2018-09-28 | MICHAEL M.TSONTOS S.A. | W912GB | W912GB17D0015 | W912GB17D0015 | 91732,W912GB17D0015 | 844000 | 1038000 | 2020-10-24 | 2022-03-18 | 194000 | 510 | 2022 | 03 | 18 | 20220318 | 2018 | 2022 | 0.97698 | 2020 | 0.95701 | 824569.1927 | 1010229.5258 | 185660.333 | 510 | 757 | 67.37%
2021-12-31 | 2017 | Missile Defense Agency | 673 |  | 2017-04-15 | 2017-08-03 | Indyne, Inc. | W912DY | W912DY-11-D-0002 | W912DY11D0002 | 673,W912DY-11-D-0002 | 877752 | 1098939 | 2019-06-27 | 2022-01-15 | 221187 | 933 | 2022 | 01 | 15 | 20220115 | 2017 | 2022 | 0.97698 | 2020 | 0.95701 | 857544.1446 | 1069222.7636 | 211678.619 | 933 | 693 | 134.6%
2022-01-12 | 2018 | Navy Active | N32446385 |  | 2018-07-05 | 2018-09-20 | STRUCTURAL ASSOCIATES, INC | N40085 | N4008517D5048 N4008518F6907 | N4008517D5048 | N32446385,N4008517D5048 N4008518F6907 | 975000 | 819000 | 2019-10-08 | 2019-10-08 | -156000 | 0 | 2019 | 10 | 08 | 20191008 | 2018 | 2020 | 1.0507 | 2019 | 1.0006 | 1024433.4125 | 868338.1991 | -156095.2133 | 0 | 383 | 0%
2022-01-06 | 2010 | Special Operations Command | 65266 |  | 2009-12-18 | 2010-06-30 | Lifecycle Construction Service, LLC | W912HN | W912HN-10-D-0033 | W912HN10D0033 | 65266,W912HN-10-D-0033 | 1007935 | 1024285 | 2011-07-22 | 2011-09-29 | 16350 | 69 | 2011 | 09 | 29 | 20110929 | 2010 | 2011 | 1.0276 | 2011 | 0.97698 | 1035745.073 | 1051718.6587 | 15973.5857 | 69 | 387 | 17.83%
2022-01-13 | 2009 | Defense Health Agency | 70354 | 70354-02 | 2017-07-12 | 2017-09-27 | BHATE Environmental Associates, Inc. | W912DY | W912DY-15-D-0081 | W912DY15D0081 | 70354,W912DY-15-D-0081 | 1118431 | 1474000 | 2018-12-31 | 2019-08-19 | 355569 | 231 | 2019 | 08 | 19 | 20190819 | 2017 | 2019 | 0.97698 | 2018 | 0.9382 | 1092682.1644 | 1426276.3121 | 333594.1477 | 231 | 460 | 50.22%
2021-12-31 | 2017 | Air Force Active | FTQW170100 |  | 2021-08-25 | 2021-09-24 | Bethel Environmental Solutions LLC | W911KB | W911KB21C0033 | W911KB21C0033 | FTQW170100,W911KB21C0033 | 1174838 | 1174838 | 2021-11-08 | 2021-11-08 | 0 | 0 | 2021 | 11 | 08 | 20211108 | 2021 | 2022 | 1.0993 | 2022 | 1.0507 | 1291446.7938 | 1291446.7938 | 0 | 0 | 45 | 0%
2022-01-07 | 2018 | Washington Headquarters Services | 91474A |  | 2018-03-06 | 2018-09-25 | MC DEAN | HQ0034 | HQ0034-17-D-0006 | HQ003417D0006 | 91474A,HQ0034-17-D-0006 | 1186116 | 1186116 | 2019-06-18 | 2019-06-18 | 0 | 0 | 2019 | 06 | 18 | 20190618 | 2018 | 2019 | 1.0006 | 2019 | 0.97698 | 1186839.9361 | 1186839.9361 | 0 | 0 | 266 | 0%
2022-01-12 | 2015 | Army National Guard | 260222 |  | 2018-04-06 | 2018-06-29 | Ripman Construction Co Inc. | Y18228 | Y18228 | Y18228 | 260222,Y18228 | 1200000 | 1777000 | 2019-10-04 | 2020-12-31 | 577000 | 454 | 2020 | 12 | 31 | 20201231 | 2018 | 2021 | 1.0751 | 2020 | 1.0276 | 1290093.237 | 1883013.3232 | 592920.0862 | 454 | 462 | 98.27%
2021-09-30 | 2017 | Air National Guard | TWLR159061 |  | 2017-06-28 | 2017-09-06 | Maron Construction Co. Inc. | 353453 | 3534532 | 3534532 | TWLR159061,3534532 | 1205000 | 1205000 | 2022-04-29 | 2022-04-29 | 0 | 0 | 2022 | 04 | 29 | 20220429 | 2017 | 2022 | 1.1743 | 2020 | 1.1519 | 1415053.7899 | 1415053.7899 | 0 | 0 | 1696 | 0%
2021-12-31 | 2018 | Air Force Active | EEEI180001 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB | W912GB15D0029 | W912GB15D0029 | EEEI180001,W912GB15D0029 | 1210326 | 1210326 | 2024-04-10 | 2024-04-10 | 0 | 0 | 2024 | 04 | 10 | 20240410 | 2020 | 2024 | 1.0507 | 2022 | 1.0276 | 1271690.6609 | 1271690.6609 | 0 | 0 | 1330 | 0%
2021-12-31 | 2019 | Air Force Active | SMYU073011 |  | 2019-06-27 | 2019-09-27 | Kumsung Construction Co., Ltd | W912UM | W912UM19C0017 | W912UM19C0017 | SMYU073011,W912UM19C0017 | 1227670 | 1227670 | 2021-02-21 | 2021-02-21 | 0 | 0 | 2021 | 02 | 21 | 20210221 | 2019 | 2021 | 1.0006 | 2020 | 0.95701 | 1228419.2983 | 1228419.2983 | 0 | 0 | 513 | 0%
2022-01-12 | 2016 | Marine Corps Active | M67029007 |  | 2016-10-25 | 2017-04-19 | TIDEWATER, INC | N40080 | N4008017C0024 AWD | N4008017C0024 | M67029007,N4008017C0024 AWD | 1257000 | 1311000 | 2018-04-19 | 2020-07-30 | 54000 | 833 | 2020 | 07 | 30 | 20200730 | 2017 | 2020 | 0.95701 | 2019 | 0.9382 | 1202964.1167 | 1253626.8121 | 50662.6955 | 833 | 365 | 228.2%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2018-04-30 | 2018-09-20 | Bhate Zapata | W912EP | W912EP-16-D-0008 &#x2f; 6465583 | W912EP16D0008 | DESC1513,W912EP-16-D-0008 &#x2f; 6465583 | 1300000 | 4390000 | 2019-07-06 | 2019-07-06 | 3090000 | 0 | 2019 | 07 | 06 | 20190706 | 2018 | 2019 | 1.1743 | 2019 | 1.0751 | 1526614.0472 | 4848604.1324 | 3321990.0852 | 0 | 289 | 0%
2022-02-02 | 2017 | DoD Education Activity | EU00183 |  | 2020-02-12 | 2020-07-22 | Staatliches Hochbauamt Amberg | W912GB | W912GB-17-C-0023/ 58997935 | W912GB17C0023 | EU00183,W912GB-17-C-0023/ 58997935 | 1304645 | 1415711 | 2021-04-29 | 2021-12-10 | 111066 | 225 | 2021 | 12 | 10 | 20211210 | 2020 | 2022 | 1.0006 | 2021 | 0.9382 | 1305441.2793 | 1409643.1856 | 104201.9063 | 225 | 281 | 80.07%
2021-10-01 | 2017 | DoD Education Activity | EU00183 |  | 2020-02-12 | 2020-07-22 | Staatliches Hochbauamt Amberg | W912GB | W912GB-17-C-0023/58997935 | W912GB17C0023 | EU00183,W912GB-17-C-0023/58997935 | 1304645 | 1396154 | 2021-04-29 | 2021-10-17 | 91509 | 171 | 2021 | 10 | 17 | 20211017 | 2020 | 2022 | 1.1519 | 2021 | 1.0751 | 1502778.2984 | 1601157.5834 | 98379.285 | 171 | 281 | 60.85%
2021-12-31 | 2017 | Air Force Active | QUUG064001 |  | 2019-04-17 | 2021-09-28 | Sociedad Espanola de Montajes | FA5575 | FA557521C0007 | FA557521C0007 | QUUG064001,FA557521C0007 | 1336116 | 1336116 | 2022-12-19 | 2022-12-19 | 0 | 0 | 2022 | 12 | 19 | 20221219 | 2021 | 2023 | 0.97698 | 2022 | 0.95701 | 1305355.5587 | 1305355.5587 | 0 | 0 | 447 | 0%
2022-01-12 | 2020 | Marine Corps Active | M00146249 |  | 2020-10-26 | 2021-02-18 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N40085 | N4008516D6303 N4008521F4682 | N4008516D6303 | M00146249,N4008516D6303 N4008521F4682 | 1368000 | 1369000 | 2022-03-05 | 2022-03-05 | 1000 | 0 | 2022 | 03 | 05 | 20220305 | 2021 | 2022 | 0.97698 | 2022 | 0.9382 | 1336505.5162 | 1337443.7142 | 938.1981 | 0 | 380 | 0%
2022-01-12 | 2021 | Navy Active | N610542101 |  | 2020-10-23 | 2021-03-05 | NIPPO CORPORATION | N40084 | N4008419D0075 N4008421F4145 | N4008419D0075 | N610542101,N4008419D0075 N4008421F4145 | 1382000 | 2107000 | 2024-05-01 | 2024-05-01 | 725000 | 0 | 2024 | 05 | 01 | 20240501 | 2021 | 2024 | 1.1227 | 2023 | 1.0751 | 1551532.3667 | 2330963.6974 | 779431.3307 | 0 | 1153 | 0%
2021-12-31 | 2017 | Air Force Active | EEEI150006 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB | W912GB15D0029 | W912GB15D0029 | EEEI150006,W912GB15D0029 | 1451631 | 1451631 | 2024-04-10 | 2024-04-10 | 0 | 0 | 2024 | 04 | 10 | 20240410 | 2020 | 2024 | 1.0993 | 2022 | 1.0276 | 1595712.9415 | 1595712.9415 | 0 | 0 | 1330 | 0%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR | W912DR-08-C-0038 | W912DR08C0038 |  | 1472000 | 1472000 | 2009-02-15 | 2009-02-13 | 0 | -2 | 2009 | 02 | 13 | 20090213 | 2008 | 2009 | 1.2581 | 2009 | 1.2319 | 1851865.4046 | 1851865.4046 | 0 | -2 | 198 | -1.01%
2022-01-13 | 2016 | Defense Health Agency | 80412 | 80412-02 | 2020-07-31 | 2020-09-21 | Su-Mo Builders Inc. | W9128A | W9128A-16-D-0011 TO W9128A20F0067 | W9128A16D0011 | 80412,W9128A-16-D-0011 TO W9128A20F0067 | 1484000 | 1484000 | 2022-05-02 | 2022-05-02 | 0 | 0 | 2022 | 05 | 02 | 20220502 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 1484905.7472 | 1484905.7472 | 0 | 0 | 588 | 0%
2021-12-31 | 2018 | Air Force Active | AJXF173021 |  | 2018-06-05 | 2018-07-05 | Oncore Group, LLC | N40080 | N4008018C2018 | N4008018C2018 | AJXF173021,N4008018C2018 | 1490854 | 1490854 | 2019-01-26 | 2019-01-26 | 0 | 0 | 2019 | 01 | 26 | 20190126 | 2018 | 2019 | 1.0751 | 2019 | 1.0006 | 1602783.8856 | 1602783.8856 | 0 | 0 | 205 | 0%
2022-01-06 | 2013 | Special Operations Command | 81483 |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F | W9128F-13-C-0006 | W9128F13C0006 | 81483,W9128F-13-C-0006 | 1513371 | 1642769 | 2014-09-15 | 2014-11-26 | 129398 | 72 | 2014 | 11 | 26 | 20141126 | 2013 | 2015 | 1.0006 | 2014 | 0.97698 | 1514294.6735 | 1640713.6361 | 126418.9626 | 72 | 369 | 19.51%
2021-12-31 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-21 | Vilmanto Statybos | W912GB | W912GB15D00560002 | W912GB15D00560002 | PAYZ15001B,W912GB15D00560002 | 1515821 | 1515821 | 2018-07-06 | 2018-07-06 | 0 | 0 | 2018 | 07 | 06 | 20180706 | 2017 | 2018 | 1.0276 | 2018 | 1.0006 | 1557644.2254 | 1557644.2254 | 0 | 0 | 592 | 0%
2022-01-06 | 2013 | Special Operations Command | 80233 |  | 2013-09-16 | 2014-01-22 | Trend Construction Inc | W912HN | W912HN-12-D-0030 | W912HN12D0030 | 80233,W912HN-12-D-0030 | 1531765 | 1570203 | 2015-02-27 | 2015-03-04 | 38438 | 5 | 2015 | 03 | 04 | 20150304 | 2014 | 2015 | 1.0751 | 2015 | 1.0507 | 1646766.3893 | 1687153.2319 | 40386.8426 | 5 | 401 | 1.247%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G | W9126G-13-C-0046 | W9126G13C0046 | 72481,W9126G-13-C-0046 | 1540000 | 623000 | 2014-10-24 | 2014-10-24 | -917000 | 0 | 2014 | 10 | 24 | 20141024 | 2013 | 2015 | 1.0993 | 2014 | 1.0507 | 1692853.0253 | 729360.2671 | -963492.7582 | 0 | 406 | 0%
2022-01-12 | 2015 | Army National Guard | 470035 |  | 2020-02-20 | 2020-04-14 | Marbury Construction | W912l7 | W912l7-18-R-0005 | W912l718R0005 | 470035,W912l7-18-R-0005 | 1606000 | 1536000 | 2021-01-20 | 2021-06-15 | -70000 | 146 | 2021 | 06 | 15 | 20210615 | 2020 | 2021 | 0.97698 | 2021 | 0.95701 | 1569026.2127 | 1502035.3709 | -66990.8418 | 146 | 281 | 51.96%
2022-01-13 | 2013 | Defense Health Agency | 58395 | 78210-02 | 2017-08-18 | 2017-09-27 | Doyon Project Services, LLC | W912DR | W912DR-17-D-0012 | W912DR17D0012 | 58395,W912DR-17-D-0012 | 1607000 | 1580000 | 2018-10-26 | 2019-05-11 | -27000 | 197 | 2019 | 05 | 11 | 20190511 | 2017 | 2019 | 1.0276 | 2018 | 0.97698 | 1651338.9577 | 1624960.5594 | -26378.3983 | 197 | 394 | 50%
2021-12-31 | 2017 | Air Force Active | LBPG150008 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB | W912GB17F0444 | W912GB17F0444 | LBPG150008,W912GB17F0444 | 1611283 | 1611283 | 2021-01-21 | 2021-01-21 | 0 | 0 | 2021 | 01 | 21 | 20210121 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 1612266.4333 | 1612266.4333 | 0 | 0 | 844 | 0%
2022-01-12 | 2020 | Navy Active | N476091924 |  | 2020-10-16 | 2021-01-22 | BARNHART-REESE CONSTRUCTION INC | N62473 | N6247317D4635 N6247321F4264 | N6247317D4635 | N476091924,N6247317D4635 N6247321F4264 | 1660000 | 4986000 | 2023-02-06 | 2023-02-06 | 3326000 | 0 | 2023 | 02 | 06 | 20230206 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 1784628.9778 | 5112658.9746 | 3328029.9967 | 0 | 745 | 0%
2021-08-31 | 2018 | Army Reserve | 91427 |  | 2018-06-25 | 2018-09-27 | BIM Contractors, LLC | W912QR | W912QR18C0037 | W912QR18C0037 | 91427,W912QR18C0037 | 1692000 | 1717000 | 2020-02-28 | 2020-10-02 | 25000 | 217 | 2020 | 10 | 02 | 20201002 | 2018 | 2021 | 0.97698 | 2020 | 0.9382 | 1653046.2963 | 1676501.2479 | 23454.9516 | 217 | 519 | 41.81%
2021-12-31 | 2017 | Air Force Active | LRCT150008 |  | 2017-07-28 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB | W912GB18F0021 | W912GB18F0021 | LRCT150008,W912GB18F0021 | 1711902 | 1711902 | 2022-05-06 | 2023-01-16 | 0 | 255 | 2023 | 01 | 16 | 20230116 | 2018 | 2023 | 1.0006 | 2021 | 0.97698 | 1712946.8453 | 1712946.8453 | 0 | 255 | 1591 | 16.03%
2021-11-16 | 2018 | Army National Guard | 270233 |  | 2021-01-12 | 2021-01-13 | Project One Construction, Inc. | 188046 | 188046 | 188046 | 270233,188046 | 1730000 | 1331000 | 2023-07-20 | 2021-11-27 | -399000 | -600 | 2021 | 11 | 27 | 20211127 | 2021 | 2022 | 1.0751 | 2022 | 1.0276 | 1859884.4167 | 1449875.5529 | -410008.8638 | -600 | 918 | -65.36%
2022-01-12 | 2020 | Marine Corps Reserve | N83447222 |  | 2020-05-08 | 2020-09-24 | N6945020C2575 AWD | N69450 | N6945020C2575 AWD | N6945020C2575 | N83447222,N6945020C2575 AWD | 1763000 | 1921000 | 2021-09-20 | 2021-09-21 | 158000 | 1 | 2021 | 09 | 21 | 20210921 | 2020 | 2021 | 1.0507 | 2021 | 1.0006 | 1852385.7499 | 2010482.1839 | 158096.434 | 1 | 361 | 0.277%
2022-02-28 | 2014 | Defense Information Systems Agency | 14DISA01 |  | 2017-04-12 | 2017-07-13 | Heartwood Pacific, LLC | N62742 | N6274217F0307 | N6274217F0307 | 14DISA01,N6274217F0307 | 1781248 | 1781248 | 2018-12-31 | 2022-01-15 | 0 | 1111 | 2022 | 01 | 15 | 20220115 | 2017 | 2022 | 0.97698 | 2020 | 0.95701 | 1740239.6036 | 1740239.6036 | 0 | 1111 | 536 | 207.3%
2021-08-31 | 2019 | Army Reserve | 90303 |  | 2018-11-02 | 2019-02-28 | Dean S.H. Pak, Inc. | W912QR | W912QR19C0009 | W912QR19C0009 | 90303,W912QR19C0009 | 1831000 | 1819000 | 2020-06-10 | 2020-10-14 | -12000 | 126 | 2020 | 10 | 14 | 20201014 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 1881519.3725 | 1869795.6399 | -11723.7326 | 126 | 468 | 26.92%
2022-01-12 | 2018 | Marine Corps Active | M006811599 |  | 2019-01-15 | 2019-02-27 | ORION CONSTRUCTION CORPORATION | N62473 | N6247318D5860 N6247319F4359 | N6247318D5860 | M006811599,N6247318D5860 N6247319F4359 | 1876000 | 2178000 | 2020-02-26 | 2020-04-16 | 302000 | 50 | 2020 | 04 | 16 | 20200416 | 2019 | 2020 | 1.1914 | 2020 | 1.1743 | 2234992.5189 | 2589636.7052 | 354644.1863 | 50 | 364 | 13.74%
2022-01-12 | 2016 | Marine Corps Active | M67001729 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N40085 | N4008516D6300 0003 | N4008516D6300 | M67001729,N4008516D6300 0003 | 1885000 | 2519000 | 2018-04-06 | 2021-04-22 | 634000 | 1112 | 2021 | 04 | 22 | 20210422 | 2016 | 2021 | 1.0507 | 2019 | 1.0006 | 1980571.2641 | 2614958.2208 | 634386.9567 | 1112 | 555 | 200.4%
2021-12-14 | 2021 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB | W912GB-17-C-0005 | W912GB17C0005 | 72742,W912GB-17-C-0005 | 1891000 | 1891000 | 2022-11-11 | 2022-11-11 | 0 | 0 | 2022 | 11 | 11 | 20221111 | 2020 | 2023 | 1.2082 | 2022 | 1.1743 | 2284756.0177 | 2284756.0177 | 0 | 0 | 772 | 0%
2022-01-12 | 2017 | Army National Guard | 371402 |  | 2021-09-28 | 2021-09-29 | Garanco Inc | W91242 | W91242-18-2-20019 | W9124218220019 | 371402,W91242-18-2-20019 | 1950000 | 4760000 | 2023-08-05 | 2023-08-05 | 2810000 | 0 | 2023 | 08 | 05 | 20230805 | 2021 | 2023 | 1.1227 | 2022 | 1.0507 | 2189209.9241 | 5141679.5539 | 2952469.6298 | 0 | 675 | 0%
2021-12-31 | 2017 | Air Force Active | LBPG150009 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB | W912GB17F0461 | W912GB17F0461 | LBPG150009,W912GB17F0461 | 1978602 | 1978602 | 2022-02-11 | 2022-02-11 | 0 | 0 | 2022 | 02 | 11 | 20220211 | 2018 | 2022 | 1.0276 | 2020 | 0.97698 | 2033193.8795 | 2033193.8795 | 0 | 0 | 1230 | 0%
2021-08-31 | 2018 | Army Active | 88028 |  | 2018-10-03 | 2018-12-06 | Fortis Networks, Inc. | W912DQ | W912DQ17D4016 | W912DQ17D4016 | 88028,W912DQ17D4016 | 1979000 | 1990000 | 2020-02-25 | 2020-09-29 | 11000 | 217 | 2020 | 09 | 29 | 20200929 | 2019 | 2020 | 1.0507 | 2020 | 1.0006 | 2079337.1521 | 2090343.8658 | 11006.7138 | 217 | 446 | 48.65%
2022-01-12 | 2018 | Marine Corps Active | M67004971 |  | 2017-12-12 | 2018-03-15 | DRACE CONSTRUCTION CORP. | N40085 | N4008516D5524 N4008518F5082 | N4008516D5524 | M67004971,N4008516D5524 N4008518F5082 | 1982000 | 1918000 | 2019-07-05 | 2019-07-05 | -64000 | 0 | 2019 | 07 | 05 | 20190705 | 2018 | 2019 | 1.0507 | 2019 | 1.0276 | 2082489.2549 | 2016723.4221 | -65765.8328 | 0 | 477 | 0%
2022-01-12 | 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N40085 | N4008515C9610 AWD | N4008515C9610 | N00129664,N4008515C9610 AWD | 1989000 | 1958000 | 2017-04-21 | 2017-04-21 | -31000 | 0 | 2017 | 04 | 21 | 20170421 | 2015 | 2017 | 0.97698 | 2016 | 0.95701 | 1943208.6781 | 1913541.3053 | -29667.3728 | 0 | 605 | 0%
2022-01-12 | 2019 | Army National Guard | 270220 |  | 2021-09-21 | 2021-09-30 | Brennan Construction of MN, Inc. | 12345- | 12345-Brennan | 12345Brennan | 270220,12345-Brennan | 2000000 | 4144000 | 2023-03-15 | 2023-03-15 | 2144000 | 0 | 2023 | 03 | 15 | 20230315 | 2021 | 2023 | 1.0276 | 2022 | 0.95701 | 2055182.2747 | 4107016.0584 | 2051833.7837 | 0 | 531 | 0%
2021-12-31 | 2017 | Air Force Active | LRCT150010 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB | W912GB18F0020 | W912GB18F0020 | LRCT150010,W912GB18F0020 | 2021357 | 2021357 | 2022-06-15 | 2023-01-16 | 0 | 215 | 2023 | 01 | 16 | 20230116 | 2018 | 2023 | 1.2581 | 2021 | 1.2082 | 2542989.8768 | 2542989.8768 | 0 | 215 | 1631 | 13.18%
2022-01-12 | 2017 | Marine Corps Reserve | M68479135 |  | 2018-08-16 | 2019-01-22 | OAK GROUP, INC., THE | N40085 | N4008517D5038 N4008519F4510 | N4008517D5038 | M68479135,N4008517D5038 N4008519F4510 | 2109000 | 2147000 | 2020-01-28 | 2020-10-31 | 38000 | 277 | 2020 | 10 | 31 | 20201031 | 2019 | 2021 | 1.2581 | 2020 | 1.2082 | 2653250.0939 | 2699162.695 | 45912.6011 | 277 | 371 | 74.66%
2022-01-12 | 2017 | Navy Active | N47608975 | N47608975A | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N40080 | N4008018C0311 AWD | N4008018C0311 | N47608975,N4008018C0311 AWD | 2145000 | 2043000 | 2020-02-02 | 2020-12-29 | -102000 | 331 | 2020 | 12 | 29 | 20201229 | 2018 | 2021 | 1.0751 | 2020 | 1.0276 | 2306041.6611 | 2201227.3651 | -104814.296 | 331 | 660 | 50.15%
2022-01-12 | 2019 | Army National Guard | 050220 |  | 2020-09-17 | 2020-09-23 | Ross Sparks Builders, Inc. | 975200 | 9752002 | 9752002 | 050220,9752002 | 2150000 | 1618000 | 2021-10-15 | 2022-04-30 | -532000 | 197 | 2022 | 04 | 30 | 20220430 | 2020 | 2022 | 1.1227 | 2021 | 1.0993 | 2413744.2753 | 1828940.503 | -584803.7724 | 197 | 387 | 50.9%
2021-12-31 | 2019 | Air Force Active | ZHTV093301 |  | 2019-07-17 | 2019-08-16 | ADAL Intelligence Production Facility, Golf Course | W912QR | W912QR19C0027 | W912QR19C0027 | ZHTV093301,W912QR19C0027 | 2173425 | 2173425 | 2020-06-11 | 2024-06-10 | 0 | 1460 | 2024 | 06 | 10 | 20240610 | 2019 | 2024 | 1.0276 | 2022 | 1.0006 | 2233392.2677 | 2233392.2677 | 0 | 1460 | 300 | 486.7%
2021-12-31 | 2018 | Air Force Reserve | DDPM130007 |  | 2018-06-29 | 2018-12-12 | Unified Sevices of Texas, Inc. | N69450 | N6945019F1275 | N6945019F1275 | DDPM130007,N6945019F1275 | 2179491 | 2179491 | 2020-09-14 | 2021-01-31 | 0 | 139 | 2021 | 01 | 31 | 20210131 | 2019 | 2021 | 1.0993 | 2020 | 1.0276 | 2395816.8396 | 2395816.8396 | 0 | 139 | 642 | 21.65%
2022-01-06 | 2012 | Special Operations Command | 69277 |  | 2012-04-24 | 2012-07-30 | Lifecyle Construction Services, LLC | W912HP | W912HP-11-D-0016 | W912HP11D0016 | 69277,W912HP-11-D-0016 | 2196113 | 2270078 | 2013-08-22 | 2013-12-18 | 73965 | 118 | 2013 | 12 | 18 | 20131218 | 2012 | 2014 | 1.0993 | 2013 | 1.0507 | 2414088.6597 | 2491803.7544 | 77715.0947 | 118 | 388 | 30.41%
2021-12-31 | 2017 | Air Force Active | ASVF164000 |  | 2017-09-16 | 2018-09-11 | RED HORSE | FA5710 | FA571018P0325 | FA571018P0325 | ASVF164000,FA571018P0325 | 2200000 | 2348000 | 2020-03-04 | 2021-09-21 | 148000 | 566 | 2021 | 09 | 21 | 20210921 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 2201342.7519 | 2342980.5317 | 141637.7798 | 566 | 540 | 104.8%
2021-08-31 | 2017 | Army Reserve | 88722 |  | 2017-01-12 | 2017-04-14 | OAC Action Contruction, Corp | W912QR | W912QR-17-C-0012 | W912QR17C0012 | 88722,W912QR-17-C-0012 | 2202000 | 2192000 | 2018-07-13 | 2020-10-30 | -10000 | 840 | 2020 | 10 | 30 | 20201030 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 2203343.9726 | 2193574.1954 | -9769.7772 | 840 | 455 | 184.6%
2022-02-28 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB | W912GB-15-C-011 | W912GB15C011 | 13DISA01,W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2022-01-30 | 0 | 2356 | 2022 | 01 | 30 | 20220130 | 2015 | 2022 | 1.1914 | 2019 | 1.1743 | 2644606.1264 | 2644606.1264 | 0 | 2356 | 0 | #DIV/0!
2021-12-30 | 2020 | Air National Guard | PBXP169102 |  | 2020-10-28 | 2021-04-02 | Massillon Construction & Supply, LLC | W50S8R | W50S8R21C0002 | W50S8R21C0002 | PBXP169102,W50S8R21C0002 | 2279117 | 2160653 | 2022-02-26 | 2022-02-26 | -118464 | 0 | 2022 | 02 | 26 | 20220226 | 2021 | 2022 | 1.0006 | 2022 | 0.95701 | 2280508.0403 | 2167136.5677 | -113371.4726 | 0 | 330 | 0%
2022-01-12 | 2019 | Navy Active | N00207711 |  | 2019-07-18 | 2019-09-13 | UP-SIDE MANAGEMENT COMPANY | N69450 | N6945019C5648 AWD | N6945019C5648 | N00207711,N6945019C5648 AWD | 2323000 | 2212000 | 2020-09-14 | 2020-09-14 | -111000 | 0 | 2020 | 09 | 14 | 20200914 | 2019 | 2020 | 1.0006 | 2020 | 0.9382 | 2324417.8239 | 2220277.8388 | -104139.9852 | 0 | 367 | 0%
2021-12-31 | 2019 | Air Force Active | MXRD153006 |  | 2019-07-07 | 2019-08-06 | Ritter & Paratore Contracting Inc | W912WJ | W912WJ19C0014 | W912WJ19C0014 | MXRD153006,W912WJ19C0014 | 2347000 | 2347000 | 2020-05-17 | 2020-04-26 | 0 | -21 | 2020 | 04 | 26 | 20200426 | 2019 | 2020 | 1.0507 | 2020 | 1.0276 | 2465995.0965 | 2465995.0965 | 0 | -21 | 285 | -7.368%
2021-12-31 | 2017 | Air Force Active | LRCT150009 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB | W912GB18F0020 | W912GB18F0020 | LRCT150009,W912GB18F0020 | 2356785 | 2356785 | 2022-08-25 | 2023-03-28 | 0 | 215 | 2023 | 03 | 28 | 20230328 | 2018 | 2023 | 1.1914 | 2021 | 1.1519 | 2807780.8334 | 2807780.8334 | 0 | 215 | 1702 | 12.63%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB | W912GB-10-C-0031, ABG4 P00058 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00058 | 2359000 | 3563000 | 2016-04-30 | 2017-04-30 | 1204000 | 365 | 2017 | 04 | 30 | 20170430 | 2013 | 2017 | 0.95701 | 2015 | 0.95701 | 2257591.3693 | 3409833.8485 | 1152242.4793 | 365 | 977 | 37.36%
2022-01-12 | 2017 | Army National Guard | 270127 |  | 2018-12-26 | 2019-01-18 | Eagle Construction Company, Inc. | 151541 | 151541 | 151541 | 270127,151541 | 2400000 | 2030000 | 2020-04-10 | 2020-04-17 | -370000 | 7 | 2020 | 04 | 17 | 20200417 | 2019 | 2020 | 1.0006 | 2020 | 0.97698 | 2401464.8203 | 2039983.0652 | -361481.7551 | 7 | 448 | 1.562%
2021-08-31 | 2019 | Army Active | 93016 |  | 2019-07-03 | 2019-08-29 | Perikin Enterprise, LLC | W9126G | W9126G19C0124 | W9126G19C0124 | 93016,W9126G19C0124 | 2404000 | 2469000 | 2020-09-22 | 2021-06-21 | 65000 | 272 | 2021 | 06 | 21 | 20210621 | 2019 | 2021 | 1.1227 | 2020 | 1.0751 | 2698902.9013 | 2768782.9517 | 69880.0503 | 272 | 390 | 69.74%
2021-12-31 | 2016 | Air Force Active | PAYZ16000B |  | 2020-03-31 | 2020-08-19 | Onaka Gumi Co., Ltd. | W912HV | W912HV20C0006 | W912HV20C0006 | PAYZ16000B,W912HV20C0006 | 2413198 | 2428538 | 2021-09-07 | 2021-12-14 | 15340 | 98 | 2021 | 12 | 14 | 20211214 | 2020 | 2022 | 1.1914 | 2021 | 1.1519 | 2874989.06 | 2892658.7089 | 17669.6489 | 98 | 384 | 25.52%
2021-12-31 | 2015 | Army Active | 86094 |  | 2019-02-11 | 2020-04-01 | Staatliches Hochbauamt Amberg | W912GB | W912GB-16-C-0006 | W912GB16C0006 | 86094,W912GB-16-C-0006 | 2418000 | 2835000 | 2021-09-05 | 2022-03-04 | 417000 | 180 | 2022 | 03 | 04 | 20220304 | 2020 | 2022 | 1.0507 | 2021 | 1.0276 | 2540594.8629 | 2969100.3672 | 428505.5043 | 180 | 522 | 34.48%
2021-12-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-16 | 2018-06-07 | CP02TP-Construction Services SATOC | W912DY | W912DY-14-D-0042 | W912DY14D0042 | 674,W912DY-14-D-0042 | 2432439 | 2432439 | 2018-10-31 | 2018-10-11 | 0 | -20 | 2018 | 10 | 11 | 20181011 | 2018 | 2019 | 1.0276 | 2019 | 0.97698 | 2499552.7585 | 2499552.7585 | 0 | -20 | 146 | -13.7%
2021-12-30 | 2018 | Air National Guard | FMKM119035 |  | 2020-09-28 | 2021-04-19 | Max Gray Construction | W912LM | W912LM21C0002 | W912LM21C0002 | FMKM119035,W912LM21C0002 | 2439785 | 2352600 | 2022-10-11 | 2022-10-11 | -87185 | 0 | 2022 | 10 | 11 | 20221011 | 2021 | 2023 | 1.1227 | 2022 | 1.0276 | 2739077.7101 | 2649487.1768 | -89590.5333 | 0 | 540 | 0%
2021-08-31 | 2018 | Army Reserve | 88585 |  | 2018-07-11 | 2018-09-29 | Hernandez Consulting | W912QR | W912QR18C0048 | W912QR18C0048 | 88585,W912QR18C0048 | 2459000 | 2644000 | 2020-01-26 | 2020-10-09 | 185000 | 257 | 2020 | 10 | 09 | 20201009 | 2018 | 2021 | 1.2581 | 2020 | 1.2082 | 3093571.3518 | 3317093.2256 | 223521.8738 | 257 | 484 | 53.1%
2021-12-31 | 2017 | Air Force Active | EPPW170003 |  | 2017-07-14 | 2017-09-21 | Wolff & Mueller & Erbud JV | W912GB | W912GB15D0060 | W912GB15D0060 | EPPW170003,W912GB15D0060 | 2463632 | 2463632 | 2020-03-26 | 2020-03-26 | 0 | 0 | 2020 | 03 | 26 | 20200326 | 2017 | 2020 | 1.0006 | 2019 | 0.95701 | 2465135.6575 | 2465135.6575 | 0 | 0 | 917 | 0%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR | W912DR-08-C-0053 | W912DR08C0053 |  | 2465000 | 2465000 | 2009-07-24 | 2009-07-24 | 0 | 0 | 2009 | 07 | 24 | 20090724 | 2008 | 2009 | 1.2082 | 2009 | 1.1914 | 2978277.9396 | 2978277.9396 | 0 | 0 | 302 | 0%
2022-01-12 | 2019 | Navy Active | N60508288 |  | 2019-07-26 | 2020-01-10 | EMR, INC. | N69450 | N6945018D1318 N6945020F0875 | N6945018D1318 | N60508288,N6945018D1318 N6945020F0875 | 2466000 | 4583000 | 2021-01-11 | 2022-03-30 | 2117000 | 443 | 2022 | 03 | 30 | 20220330 | 2020 | 2022 | 1.0751 | 2021 | 1.0006 | 2651141.602 | 4769433.6956 | 2118292.0935 | 443 | 367 | 120.7%
2022-01-12 | 2018 | Marine Corps Active | M00146766 |  | 2018-09-04 | 2018-09-29 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N40085 | N4008516D6303 N4008518F7217 | N4008516D6303 | M00146766,N4008516D6303 N4008518F7217 | 2468000 | 2431000 | 2020-01-08 | 2021-04-12 | -37000 | 460 | 2021 | 04 | 12 | 20210412 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 2536094.927 | 2499946.7514 | -36148.1755 | 460 | 466 | 98.71%
2022-01-12 | 2019 | Navy Active | N83447084 |  | 2019-07-31 | 2019-09-17 | UNIFIED SERVICES OF TEXAS | N69450 | N6945015D1618 N6945019F2598 | N6945015D1618 | N83447084,N6945015D1618 N6945019F2598 | 2500000 | 2480000 | 2020-09-20 | 2021-02-25 | -20000 | 158 | 2021 | 02 | 25 | 20210225 | 2019 | 2021 | 1.2082 | 2020 | 1.1914 | 3020565.8616 | 2996738.6493 | -23827.2124 | 158 | 369 | 42.82%
2021-12-31 | 2016 | Army Active | 86914 |  | 2017-07-03 | 2017-08-30 | Nan, Inc., dba Ocean House Builders | W9128A | W9128A-12-D-0012 | W9128A12D0012 | 86914,W9128A-12-D-0012 | 2523000 | 2591000 | 2018-12-12 | 2021-11-09 | 68000 | 1063 | 2021 | 11 | 09 | 20211109 | 2017 | 2022 | 0.97698 | 2020 | 0.95701 | 2464914.7787 | 2529991.5965 | 65076.8178 | 1063 | 469 | 226.7%
2022-01-12 | 2017 | Navy Active | N00245312 |  | 2017-04-25 | 2017-06-29 | SYNERGY ELECTRIC COMPANY INC | N62473 | N6247316D1862 N6247317F4054 | N6247316D1862 | N00245312,N6247316D1862 N6247317F4054 | 2527000 | 2463000 | 2018-12-15 | 2018-12-15 | -64000 | 0 | 2018 | 12 | 15 | 20181215 | 2017 | 2019 | 1.0006 | 2018 | 0.97698 | 2528542.3337 | 2466015.7598 | -62526.5739 | 0 | 534 | 0%
2022-01-12 | 2017 | Army National Guard | 420595 |  | 2021-09-18 | 2021-09-26 | Department of General Services - PA | W912KC | W912KC-17-2-2001 | W912KC1722001 | 420595,W912KC-17-2-2001 | 2567000 | 3382000 | 2023-11-20 | 2023-11-20 | 815000 | 0 | 2023 | 11 | 20 | 20231120 | 2021 | 2024 | 1.0276 | 2023 | 0.97698 | 2637826.4496 | 3434063.2885 | 796236.8389 | 0 | 785 | 0%
2022-01-12 | 2018 | Navy Active | N62688762 |  | 2018-01-25 | 2018-05-02 | TAZEWELL HOMELAND JV, LLC | N40085 | N4008518R1123 | N4008518R1123 | N62688762,N4008518R1123 | 2573000 | 2905000 | 2019-07-02 | 2021-01-03 | 332000 | 551 | 2021 | 01 | 03 | 20210103 | 2018 | 2021 | 1.2826 | 2020 | 1.2581 | 3300037.0115 | 3717713.1761 | 417676.1646 | 551 | 426 | 129.3%
2021-12-31 | 2017 | Air Force Active | LRCT150007 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB | W912GB18F0020 | W912GB18F0020 | LRCT150007,W912GB18F0020 | 2575083 | 2575083 | 2020-03-12 | 2020-10-13 | 0 | 215 | 2020 | 10 | 13 | 20201013 | 2018 | 2021 | 0.97698 | 2020 | 0.9382 | 2515798.7091 | 2515798.7091 | 0 | 215 | 806 | 26.67%
2021-08-31 | 2015 | Army Active | 81236 |  | 2017-09-28 | 2020-06-23 | LBB Landau | W912GB | W912GB-16-C-0003 | W912GB16C0003 | 81236,W912GB-16-C-0003 | 2579000 | 2740000 | 2021-05-31 | 2021-08-05 | 161000 | 66 | 2021 | 08 | 05 | 20210805 | 2020 | 2021 | 1.1743 | 2021 | 1.0993 | 3028567.4059 | 3205547.4949 | 176980.089 | 66 | 342 | 19.3%
2021-12-31 | 2015 | Army Active | 81234 |  | 2017-02-15 | 2018-09-14 | Aegis Security Insurance Company | W9126G | W9126G-17-C-0046 | W9126G17C0046 | 81234,W9126G-17-C-0046 | 2580000 | 2708000 | 2019-09-27 | 2022-03-31 | 128000 | 916 | 2022 | 03 | 31 | 20220331 | 2018 | 2022 | 0.97698 | 2020 | 0.9382 | 2520602.5086 | 2640691.8608 | 120089.3523 | 916 | 378 | 242.3%
2021-08-31 | 2019 | Army Active | 93000 |  | 2019-06-20 | 2019-07-29 | LGC Global, Inc. | W912DQ | W912DQ19D4001 | W912DQ19D4001 | 93000,W912DQ19D4001 | 2595000 | 2599000 | 2020-09-12 | 2021-03-22 | 4000 | 191 | 2021 | 03 | 22 | 20210322 | 2019 | 2021 | 1.0006 | 2020 | 0.9382 | 2596583.8369 | 2600336.6292 | 3752.7923 | 191 | 411 | 46.47%
2022-01-31 | 2014 | DLA Defense Distribution Center | DDCX1309 A |  | 2016-06-30 | 2016-09-27 | Belt Built CFM Construction Services JV, LLC | W912DR | W912DR-16-C-0049 &#x2f; 35958356 | W912DR16C0049 | DDCX1309 A,W912DR-16-C-0049 &#x2f; 35958356 | 2597449 | 2768000 | 2017-11-18 | 2019-10-25 | 170551 | 706 | 2019 | 10 | 25 | 20191025 | 2016 | 2020 | 1.0006 | 2018 | 0.97698 | 2599034.3316 | 2765658.8582 | 166624.5265 | 706 | 417 | 169.3%
2021-11-30 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB | W911KB18C0023 | W911KB18C0023 | 674,W911KB18C0023 | 2600710 | 2549000 | 2018-06-30 | 2018-06-30 | -51710 | 0 | 2018 | 06 | 30 | 20180630 | 2018 | 2018 | 1.0993 | 2018 | 1.0751 | 2858844.0204 | 2803251.7527 | -55592.2677 | 0 | 81 | 0%
2021-12-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB | W911KB-18-C-0023 | W911KB18C0023 | 674,W911KB-18-C-0023 | 2600710 | 2549000 | 2018-06-30 | 2018-06-30 | -51710 | 0 | 2018 | 06 | 30 | 20180630 | 2018 | 2018 | 1.0276 | 2018 | 0.97698 | 2672466.5468 | 2621947.0291 | -50519.5177 | 0 | 81 | 0%
2020-12-09 | 2011 | National Security Agency | 20489 |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN | W912HN-10-D-0056 | W912HN10D0056 | 20489,W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28 | 37000 | 59 | 2014 | 04 | 28 | 20140428 | 2014 | 2014 | 1.0507 | 2014 | 1.0276 | 2752836.4519 | 2790857.324 | 38020.8721 | 59 | 100 | 59%
2022-01-12 | 2017 | Navy Active | N32443614 | N32443614A | 2017-06-01 | 2017-12-14 | MEB GENERAL CONTRACTORS, INC. | N40085 | N4008518C1116 AWD | N4008518C1116 | N32443614,N4008518C1116 AWD | 2624000 | 2584000 | 2021-04-15 | 2021-06-30 | -40000 | 76 | 2021 | 06 | 30 | 20210630 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 2625601.5368 | 2587321.0558 | -38280.481 | 76 | 1218 | 6.24%
2022-01-12 | 2017 | Navy Active | N47608421 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N40080 | N4008017D0012 N4008017F4480 | N4008017D0012 | N47608421,N4008017D0012 N4008017F4480 | 2627000 | 2553000 | 2018-10-24 | 2020-06-16 | -74000 | 601 | 2020 | 06 | 16 | 20200616 | 2017 | 2020 | 0.97698 | 2019 | 0.95701 | 2566520.4612 | 2495701.5713 | -70818.8899 | 601 | 392 | 153.3%
2022-01-06 | 2010 | Special Operations Command | 69560 |  | 2009-11-04 | 2010-03-16 | CCI Group, LLC | W91278 | W91278-10-C-0041 | W9127810C0041 | 69560,W91278-10-C-0041 | 2643455 | 3157424 | 2011-08-01 | 2012-05-31 | 513969 | 304 | 2012 | 05 | 31 | 20120531 | 2010 | 2012 | 0.95701 | 2011 | 0.9382 | 2529818.2251 | 3012022.9462 | 482204.7211 | 304 | 503 | 60.44%
2022-01-13 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR | W912DR-07-C-0070 | W912DR07C0070 |  | 2657000 | 2657000 | 2008-06-13 | 2008-06-08 | 0 | -5 | 2008 | 06 | 08 | 20080608 | 2007 | 2008 | 1.2581 | 2008 | 1.2319 | 3342667.3777 | 3342667.3777 | 0 | -5 | 258 | -1.938%
2021-12-31 | 2016 | Air Force Active | RKMF103011 |  | 2019-03-13 | 2019-12-17 | BRISTOL | W912PL | W912PL20C0007 | W912PL20C0007 | RKMF103011,W912PL20C0007 | 2667515 | 5075675 | 2020-11-25 | 2022-05-05 | 2408160 | 526 | 2022 | 05 | 05 | 20220505 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 2669143.0958 | 4973781.1763 | 2304638.0805 | 526 | 344 | 152.9%
2022-01-12 | 2018 | Navy Active | N50092176 |  | 2017-09-14 | 2018-04-19 | CIVIL WORKS CONTRACTING LLC | N40085 | N4008517D0358 N4008518F5423 | N4008517D0358 | N50092176,N4008517D0358 N4008518F5423 | 2670000 | 2602000 | 2019-08-05 | 2019-08-05 | -68000 | 0 | 2019 | 08 | 05 | 20190805 | 2018 | 2019 | 1.0006 | 2019 | 0.95701 | 2671629.6125 | 2606552.7948 | -65076.8178 | 0 | 473 | 0%
2021-08-31 | 2019 | Army Active | 89203 |  | 2019-07-29 | 2019-10-07 | GBA Builders, LLC. | W912DQ | W912DQ20C4000 | W912DQ20C4000 | 89203,W912DQ20C4000 | 2714000 | 4499000 | 2020-12-02 | 2020-12-14 | 1785000 | 12 | 2020 | 12 | 14 | 20201214 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 2788882.3467 | 4532787.5707 | 1743905.2239 | 12 | 422 | 2.844%
2022-01-06 | 2010 | Special Operations Command | 69559 |  | 2009-12-11 | 2010-04-22 | Johnson Roofing & Construction Faith Construction-JV | W912HN | W912HN-10-C-0028 | W912HN10C0028 | 69559,W912HN-10-C-0028 | 2717800 | 3068801 | 2011-05-18 | 2011-11-02 | 351001 | 168 | 2011 | 11 | 02 | 20111102 | 2010 | 2012 | 1.0507 | 2011 | 1.0006 | 2855595.0035 | 3206810.234 | 351215.2306 | 168 | 391 | 42.97%
2022-01-12 | 2018 | Navy Active | N61755680 |  | 2018-08-03 | 2018-09-28 | RELIABLE BUILDERS, INC. | N40192 | N4019216D2704 N4019218F4410 | N4019216D2704 | N61755680,N4019216D2704 N4019218F4410 | 2804000 | 2385000 | 2019-09-27 | 2021-05-26 | -419000 | 607 | 2021 | 05 | 26 | 20210526 | 2018 | 2021 | 1.1519 | 2020 | 1.0993 | 3229836.7362 | 2769248.8027 | -460587.9335 | 607 | 364 | 166.8%
2022-01-12 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N62478 | N6247813D4007 0031 | N6247813D4007 | N62813058,N6247813D4007 0031 | 2810000 | 2673000 | 2016-05-18 | 2019-12-31 | -137000 | 1322 | 2019 | 12 | 31 | 20191231 | 2015 | 2020 | 1.1743 | 2018 | 1.1519 | 3299834.9789 | 3142029.1184 | -157805.8605 | 1322 | 541 | 244.4%
2022-01-06 | 2011 | Special Operations Command | 69759 |  | 2010-12-16 | 2011-07-26 | Holland and Holland, Inc. | W912HN | W912HN-11-C-0011 | W912HN11C0011 | 69759,W912HN-11-C-0011 | 2818574 | 2836413 | 2012-08-16 | 2012-10-18 | 17839 | 63 | 2012 | 10 | 18 | 20121018 | 2011 | 2013 | 0.97698 | 2012 | 0.95701 | 2753683.9903 | 2770756.1278 | 17072.1375 | 63 | 387 | 16.28%
2021-11-30 | 2018 | Air National Guard | XDQU139458 |  | 2019-06-14 | 2019-09-30 | Collins Construction Services, Inc. | W912JM | W912JM19C0012 | W912JM19C0012 | XDQU139458,W912JM19C0012 | 2842543 | 2930507 | 2020-11-15 | 2021-05-21 | 87964 | 187 | 2021 | 05 | 21 | 20210521 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 2844277.9227 | 2930216.7906 | 85938.8679 | 187 | 412 | 45.39%
2021-08-31 | 2019 | Army Active | 93019 |  | 2019-06-06 | 2019-07-29 | DAP Construction Management, LLC | W912DW | W912DW19C0015 | W912DW19C0015 | 93019,W912DW19C0015 | 2844000 | 2877000 | 2020-08-27 | 2020-10-07 | 33000 | 41 | 2020 | 10 | 07 | 20201007 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 2922469.1946 | 2955489.3359 | 33020.1413 | 41 | 395 | 10.38%
2022-01-12 | 2015 | Army National Guard | 411301 |  | 2017-04-18 | 2017-09-28 | Abacus Resource Management Co. | 140033 | 140033D002 | 140033D002 | 411301,140033D002 | 2850000 | 2850000 | 2018-12-29 | 2021-08-30 | 0 | 975 | 2021 | 08 | 30 | 20210830 | 2017 | 2021 | 1.0507 | 2019 | 1.0006 | 2994497.6672 | 2994497.6672 | 0 | 975 | 457 | 213.3%
2021-08-31 | 2018 | Army Active | 86711 |  | 2018-11-08 | 2019-02-08 | Windamir Development | W912HN | W912HN19C3001 | W912HN19C3001 | 86711,W912HN19C3001 | 2854000 | 2889000 | 2020-05-13 | 2021-03-16 | 35000 | 307 | 2021 | 03 | 16 | 20210316 | 2019 | 2021 | 1.0006 | 2020 | 0.95701 | 2855741.9154 | 2889237.3363 | 33495.4209 | 307 | 460 | 66.74%
2021-12-31 | 2017 | Air Force Active | MHMV053107 |  | 2019-10-30 | 2021-04-06 | QA Engineering, LLC | W912PP | W912PP19D0035 | W912PP19D0035 | MHMV053107,W912PP19D0035 | 2855784 | 2855784 | 2022-07-11 | 2022-07-11 | 0 | 0 | 2022 | 07 | 11 | 20220711 | 2021 | 2022 | 1.0006 | 2022 | 0.97698 | 2857527.0043 | 2857527.0043 | 0 | 0 | 461 | 0%
2021-12-31 | 2019 | Air Force Reserve | SXHT171217 |  | 2019-06-24 | 2019-09-28 | Roundhouse PBN | W912QR | W912QR17C0049 | W912QR17C0049 | SXHT171217,W912QR17C0049 | 2863596 | 2863596 | 2021-03-15 | 2021-08-12 | 0 | 150 | 2021 | 08 | 12 | 20210812 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 2942605.8705 | 2942605.8705 | 0 | 150 | 534 | 28.09%
2021-12-31 | 2016 | Air Force Active | MPLS113003A |  | 2018-11-30 | 2019-03-01 | Express Contracting | W9126G | W9126G19C0019 | W9126G19C0019 | MPLS113003A,W9126G19C0019 | 2872000 | 2872000 | 2020-06-30 | 2020-06-30 | 0 | 0 | 2020 | 06 | 30 | 20200630 | 2019 | 2020 | 1.0276 | 2020 | 1.0006 | 2951241.7464 | 2951241.7464 | 0 | 0 | 487 | 0%
2021-11-16 | 2010 | Special Operations Command | 69558 |  | 2009-11-02 | 2010-04-16 | Better Built Construction Inc. | W912QR | W912QR-10-C-0048 | W912QR10C0048 | 69558,W912QR-10-C-0048 | 2885585 | 3257458 | 2011-04-11 | 2011-06-24 | 371873 | 74 | 2011 | 06 | 24 | 20110624 | 2010 | 2011 | 1.0507 | 2011 | 1.0276 | 3031886.86 | 3414020.259 | 382133.399 | 74 | 360 | 20.56%
2022-01-12 | 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N62473 | N6247314D0068 0008 | N6247314D0068 | M67604132,N6247314D0068 0008 | 2887000 | 2712000 | 2017-10-30 | 2017-10-30 | -175000 | 0 | 2017 | 10 | 30 | 20171030 | 2016 | 2018 | 1.0507 | 2017 | 1.0006 | 3033373.6018 | 2858266.792 | -175106.8098 | 0 | 425 | 0%
2022-01-12 | 2018 | Army National Guard | 440061 |  | 2021-08-17 | 2021-09-02 | USPFO - RI | W912LD | W912LD-19-2-2001 | W912LD1922001 | 440061,W912LD-19-2-2001 | 2900000 | 3515000 | 2022-10-30 | 2022-10-29 | 615000 | -1 | 2022 | 10 | 29 | 20221029 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 2901769.9911 | 3490332.3871 | 588562.396 | -1 | 423 | -0.2364%
2021-12-31 | 2018 | Air Force Reserve | AWUB105005 |  | 2018-07-12 | 2019-03-30 | Justin J. Reeves, L.L.C. | N69450 | N6945019C2105 | N6945019C2105 | AWUB105005,N6945019C2105 | 2907892 | 2907892 | 2020-03-31 | 2021-08-27 | 0 | 514 | 2021 | 08 | 27 | 20210827 | 2019 | 2021 | 1.1914 | 2020 | 1.1519 | 3464348.0094 | 3464348.0094 | 0 | 514 | 367 | 140.1%
2022-01-06 | 2008 | Special Operations Command | 33019 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER | W912ER-12-C-0011 | W912ER12C0011 | 33019,W912ER-12-C-0011 | 2930589 | 3076695 | 2013-04-25 | 2015-01-21 | 146106 | 636 | 2015 | 01 | 21 | 20150121 | 2012 | 2015 | 0.97698 | 2014 | 0.95701 | 2863120.1492 | 3002945.3483 | 139825.1991 | 636 | 477 | 133.3%
2022-01-12 | 2017 | Navy Active | N002461017 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N62473 | N6247317C0815 AWD | N6247317C0815 | N002461017,N6247317C0815 AWD | 2943000 | 2782000 | 2018-12-12 | 2018-12-12 | -161000 | 0 | 2018 | 12 | 12 | 20181212 | 2017 | 2019 | 1.0276 | 2018 | 0.97698 | 3024200.7172 | 2866907.3048 | -157293.4124 | 0 | 440 | 0%
2022-01-06 | 2010 | Special Operations Command | 69275 |  | 2009-11-05 | 2010-03-31 | WECC Incorporated | W912HN | W912HN-10-C-0024 | W912HN10C0024 | 69275,W912HN-10-C-0024 | 2954015 | 3091827 | 2011-12-14 | 2012-02-13 | 137812 | 61 | 2012 | 02 | 13 | 20120213 | 2010 | 2012 | 0.97698 | 2011 | 0.95701 | 2886006.8292 | 3017894.5705 | 131887.7413 | 61 | 623 | 9.791%
2022-01-12 | 2017 | Navy Active | N42237671 |  | 2017-08-10 | 2018-01-16 | DESIGN BUILD INCORPORATED | N69450 | N6945016D1111 | N6945016D1111 | N42237671,N6945016D1111 | 2979000 | 2988000 | 2019-08-23 | 2019-11-22 | 9000 | 91 | 2019 | 11 | 22 | 20191122 | 2018 | 2020 | 1.0993 | 2019 | 1.0751 | 3274681.2742 | 3284356.9735 | 9675.6993 | 91 | 584 | 15.58%
2022-01-12 | 2019 | Army National Guard | 411104 |  | 2020-05-26 | 2020-07-10 | Silvercreek Contracting, LLC | 411104 | 411104A0001 | 411104A0001 | 411104,411104A0001 | 3000000 | 3000000 | 2020-12-31 | 2021-09-30 | 0 | 273 | 2021 | 09 | 30 | 20210930 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 3082773.412 | 3082773.412 | 0 | 273 | 174 | 156.9%
2022-01-12 | 2016 | Army National Guard | 411503 |  | 2020-05-29 | 2020-07-22 | Rotschy, Inc. | 411305 | 411305C001 | 411305C001 | 411503,411305C001 | 3000000 | 2979000 | 2021-01-31 | 2021-09-30 | -21000 | 242 | 2021 | 09 | 30 | 20210930 | 2020 | 2021 | 1.0507 | 2021 | 1.0276 | 3152102.8076 | 3130523.3937 | -21579.4139 | 242 | 193 | 125.4%
2022-01-12 | 2020 | Army National Guard | 190005 |  | 2020-09-08 | 2020-09-11 | Happe Commercial | 8425A0 | 8425A033 | 8425A033 | 190005,8425A033 | 3000000 | 2984000 | 2021-04-15 | 2021-04-15 | -16000 | 0 | 2021 | 04 | 15 | 20210415 | 2020 | 2021 | 1.0006 | 2021 | 0.97698 | 3001831.0253 | 2986199.3819 | -15631.6435 | 0 | 216 | 0%
2022-01-12 | 2018 | Army National Guard | 160174 |  | 2019-12-03 | 2019-12-12 | C-2 Construction Inc. | NGBID- | NGBID-20-B-0009 | NGBID20B0009 | 160174,NGBID-20-B-0009 | 3000000 | 2430000 | 2021-01-23 | 2021-12-14 | -570000 | 325 | 2021 | 12 | 14 | 20211214 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 3082773.412 | 2525896.1136 | -556877.2984 | 325 | 408 | 79.66%
2022-01-12 | 2020 | Army National Guard | 465001 |  | 2020-08-07 | 2020-08-20 | Ainsworth-Benning | W912MM | W912MM-20-2-2001 | W912MM2022001 | 465001,W912MM-20-2-2001 | 3000000 | 3593000 | 2021-08-27 | 2021-08-27 | 593000 | 0 | 2021 | 08 | 27 | 20210827 | 2020 | 2021 | 1.1227 | 2021 | 1.0751 | 3368015.2679 | 4005536.3425 | 637521.0746 | 0 | 372 | 0%
2022-01-12 | 2019 | Army National Guard | 260274 |  | 2019-12-18 | 2020-01-03 | Ripman Construction Co Inc. | Y20003 | Y20003 | Y20003 | 260274,Y20003 | 3000000 | 2904000 | 2020-10-02 | 2021-04-20 | -96000 | 200 | 2021 | 04 | 20 | 20210420 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 3082773.412 | 2988983.5512 | -93789.8608 | 200 | 273 | 73.26%
2022-01-12 | 2020 | Army National Guard | 571863 |  | 2021-02-25 | 2021-03-08 | TBD | NGB-01 | NGB-01 | NGB01 | 571863,NGB-01 | 3000000 | 2895000 | 2022-07-30 | 2022-07-30 | -105000 | 0 | 2022 | 07 | 30 | 20220730 | 2021 | 2022 | 1.0006 | 2022 | 0.95701 | 3001831.0253 | 2901344.7626 | -100486.2627 | 0 | 509 | 0%
2022-01-12 | 2020 | Army National Guard | 120330 |  | 2021-04-20 | 2021-06-03 | STG Contracting Group | W911YN | W911YN-20-2-2003 | W911YN2022003 | 120330,W911YN-20-2-2003 | 3000000 | 3000000 | 2022-11-18 | 2022-11-18 | 0 | 0 | 2022 | 11 | 18 | 20221118 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 3082773.412 | 3082773.412 | 0 | 0 | 533 | 0%
2021-12-30 | 2018 | Air National Guard | ULYB049040 |  | 2019-04-28 | 2019-09-25 | MCON, LLC | 413180 | 413180 | 413180 | ULYB049040,413180 | 3025568 | 3022957 | 2020-05-01 | 2020-08-09 | -2611 | 100 | 2020 | 08 | 09 | 20200809 | 2019 | 2020 | 1.0751 | 2020 | 1.0006 | 3252720.679 | 3250108.0854 | -2612.5936 | 100 | 219 | 45.66%
2022-01-12 | 2019 | Navy Active | N00207674 |  | 2019-02-08 | 2019-05-17 | DESBUILD INCORPORATEDDBA DES BUILD | N69450 | N6945016D1111 N6945019F0712 | N6945016D1111 | N00207674,N6945016D1111 N6945019F0712 | 3036000 | 3084000 | 2020-10-13 | 2021-05-20 | 48000 | 219 | 2021 | 05 | 20 | 20210520 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 3119766.693 | 3166661.6234 | 46894.9304 | 219 | 515 | 42.52%
2022-01-12 | 2020 | Marine Corps Active | M00264733 |  | 2020-07-23 | 2020-09-29 | TUCKMAN-BARBEE CONSTRUCTION | N40080 | N4008019D0018 N4008020F5390 | N4008019D0018 | M00264733,N4008019D0018 N4008020F5390 | 3040000 | 3042000 | 2021-11-10 | 2021-12-10 | 2000 | 30 | 2021 | 12 | 10 | 20211210 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 3123877.0575 | 3125831.0129 | 1953.9554 | 30 | 407 | 7.371%
2022-01-13 | 2014 | Defense Health Agency | 77000 | 77000-01 | 2021-07-31 | 2021-09-26 | BeltBuilt LLC | W912DR | W912DR-21-C-0052 | W912DR21C0052 | 77000,W912DR-21-C-0052 | 3052000 | 3052000 | 2022-12-06 | 2022-12-06 | 0 | 0 | 2022 | 12 | 06 | 20221206 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 3206739.2562 | 3206739.2562 | 0 | 0 | 436 | 0%
2022-01-06 | 2011 | Special Operations Command | 69261 |  | 2010-12-17 | 2011-09-30 | Komada, LLC | W912HN | W912HN-11-C-0016 | W912HN11C0016 | 69261,W912HN-11-C-0016 | 3103928 | 3227443 | 2013-01-08 | 2013-03-07 | 123515 | 58 | 2013 | 03 | 07 | 20130307 | 2011 | 2013 | 1.0006 | 2012 | 0.97698 | 3105822.4569 | 3226493.8596 | 120671.4027 | 58 | 466 | 12.45%
2021-12-30 | 2018 | Air National Guard | PSTE139022 |  | 2019-04-04 | 2019-09-30 | Expert Maintenance & Construction Services | W912QG | W912QG19C0006 | W912QG19C0006 | PSTE139022,W912QG19C0006 | 3123581 | 3035885 | 2021-04-22 | 2021-04-22 | -87696 | 0 | 2021 | 04 | 22 | 20210422 | 2019 | 2021 | 1.0276 | 2020 | 0.95701 | 3209764.1524 | 3125838.0257 | -83926.1266 | 0 | 570 | 0%
2021-12-30 | 2018 | Air National Guard | KNMD179040 |  | 2018-06-15 | 2019-05-07 | HI Technology Devel. Corp. | W912J6 | W912J61822021 | W912J61822021 | KNMD179040,W912J61822021 | 3126987 | 2868023 | 2021-05-23 | 2021-05-23 | -258964 | 0 | 2021 | 05 | 23 | 20210523 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 3213264.1278 | 2960262.0704 | -253002.0574 | 0 | 747 | 0%
2022-01-12 | 2018 | Marine Corps Active | M670011498 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N40085 | N4008514D7742 N4008519F4172 | N4008514D7742 | M670011498,N4008514D7742 N4008519F4172 | 3135000 | 3313000 | 2019-11-09 | 2021-08-21 | 178000 | 651 | 2021 | 08 | 21 | 20210821 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 3221498.2156 | 3399606.8564 | 178108.6408 | 651 | 360 | 180.8%
2022-01-12 | 2019 | Navy Active | N324141098 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519C9057 AWD | N4008519C9057 | N324141098,N4008519C9057 AWD | 3142000 | 3125000 | 2022-02-13 | 2022-07-15 | -17000 | 152 | 2022 | 07 | 15 | 20220715 | 2019 | 2022 | 1.2319 | 2021 | 1.1914 | 3870746.5427 | 3850493.4122 | -20253.1305 | 152 | 977 | 15.56%
2021-12-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A-IPO |  | 2019-04-07 | 2019-07-10 | Modular Management Group (MMG) | W912DQ | W912DQ-17-C-7002 | W912DQ17C7002 | NGA-016A-IPO,W912DQ-17-C-7002 | 3146064 | 3152406 | 2024-07-08 | 2024-07-08 | 6342 | 0 | 2024 | 07 | 08 | 20240708 | 2019 | 2024 | 1.0507 | 2022 | 1.0006 | 3305572.3891 | 3311918.2599 | 6345.8708 | 0 | 1825 | 0%
2021-12-31 | 2018 | Air Force Active | PTFL163006 |  | 2018-08-24 | 2018-09-28 | Sun Construction Services Inc. | W912DS | W912DS18C0027 | W912DS18C0027 | PTFL163006,W912DS18C0027 | 3159200 | 3307588 | 2019-11-09 | 2021-09-17 | 148388 | 678 | 2021 | 09 | 17 | 20210917 | 2018 | 2021 | 1.0993 | 2020 | 1.0507 | 3472767.0633 | 3628678.4738 | 155911.4105 | 678 | 407 | 166.6%
2021-12-31 | 2017 | Air Force Active | CADJ170001 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N33191 | N3319116D1035 | N3319116D1035 | CADJ170001,N3319116D1035 | 3194454 | 3410296 | 2020-02-06 | 2021-11-18 | 215842 | 651 | 2021 | 11 | 18 | 20211118 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 3196403.7087 | 3407276.533 | 210872.8243 | 651 | 647 | 100.6%
2022-01-06 | 2013 | Special Operations Command | 65052 |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN | W912HN-11-D-0003 | W912HN11D0003 | 65052,W912HN-11-D-0003 | 3199999 | 3271762 | 2014-12-03 | 2014-12-18 | 71763 | 15 | 2014 | 12 | 18 | 20141218 | 2013 | 2015 | 0.97698 | 2014 | 0.95701 | 3126327.7158 | 3195005.7698 | 68678.054 | 15 | 436 | 3.44%
2022-01-13 | 2014 | Defense Health Agency | 58395 | 78211 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR | W912DR-09-C-0026 | W912DR09C0026 |  | 3200000 | 3200000 | 2014-05-31 | 2023-05-25 | 0 | 3281 | 2023 | 05 | 25 | 20230525 | 2009 | 2023 | 0.97698 | 2016 | 0.95701 | 3126328.6928 | 3126328.6928 | 0 | 3281 | 1891 | 173.5%
2020-12-09 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR | W912DR-11-C-0034 | W912DR11C0034 | 17782,W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30 | 0 | 870 | 2015 | 11 | 30 | 20151130 | 2011 | 2016 | 1.0006 | 2014 | 0.97698 | 3201953.0937 | 3201953.0937 | 0 | 870 | 683 | 127.4%
2022-01-12 | 2021 | Army National Guard | 230139 |  | 2021-11-12 | 2021-11-19 | Sheridan Corporation | 230139 | 230139-D | 230139D | 230139,230139-D | 3200000 | 2908000 | 2021-05-23 | 2023-05-23 | -292000 | 730 | 2023 | 05 | 23 | 20230523 | 2022 | 2023 | 1.0751 | 2023 | 1.0006 | 3440248.632 | 3148070.4122 | -292178.2198 | 730 | -180 | -405.6%
2022-01-12 | 2018 | Marine Corps Active | M670011479 |  | 2018-11-06 | 2019-06-14 | SAUER, INC. | N40085 | N4008519C9053 AWD | N4008519C9053 | M670011479,N4008519C9053 AWD | 3247000 | 3532000 | 2020-10-26 | 2021-09-30 | 285000 | 339 | 2021 | 09 | 30 | 20210930 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 3172246.6455 | 3444995.0729 | 272748.4274 | 339 | 500 | 67.8%
2021-12-31 | 2021 | Missile Defense Agency | 689 |  | 2020-06-01 | 2021-09-30 | AYTEKIN SEROL INSAAT TAAHHUT MUHENDISLIK | W912GB | W912GB-18-F-0186 | W912GB18F0186 | 689,W912GB-18-F-0186 | 3260896 | 0 | 2023-10-01 | 2023-10-01 | -3260896 | 0 | 2023 | 10 | 01 | 20231001 | 2021 | 2024 | 1.0993 | 2023 | 1.0507 | 3584556.9213 | 158330.4423 | -3426226.4789 | 0 | 731 | 0%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G | W9126G-14-P-0150 | W9126G14P0150 | 72481,W9126G-14-P-0150 | 3279420 | 1538000 | 2015-08-27 | 2015-11-30 | -1741420 | 95 | 2015 | 11 | 30 | 20151130 | 2014 | 2016 | 1.1914 | 2015 | 1.1519 | 3906971.837 | 1901086.5698 | -2005885.2671 | 95 | 398 | 23.87%
2021-12-30 | 2020 | Air National Guard | FJRP189050 |  | 2021-05-14 | 2021-09-24 | Showalter Construction Company | W50S87 | W50S8721C5001 | W50S8721C5001 | FJRP189050,W50S8721C5001 | 3279911 | 3216900 | 2022-06-21 | 2022-06-21 | -63011 | 0 | 2022 | 06 | 21 | 20220621 | 2021 | 2022 | 1.0276 | 2022 | 0.97698 | 3370407.4749 | 3308847.132 | -61560.3429 | 0 | 270 | 0%
2022-01-06 | 2010 | Special Operations Command | 69366 |  | 2010-03-22 | 2010-08-31 | Atlantic Marine Construction Company, Inc | W912HN | W912HN-07-D-0024 | W912HN07D0024 | 69366,W912HN-07-D-0024 | 3292508 | 4036729 | 2011-09-21 | 2012-04-12 | 744221 | 204 | 2012 | 04 | 12 | 20120412 | 2010 | 2012 | 1.1519 | 2011 | 1.1227 | 3792533.2712 | 4628049.1681 | 835515.8969 | 204 | 386 | 52.85%
2022-01-12 | 2018 | Navy Active | N60495426 |  | 2018-11-07 | 2018-12-28 | J I GARCIA CONSTRUCTION INC | N62473 | N6247318D5817 N6247319F4162 | N6247318D5817 | N60495426,N6247318D5817 N6247319F4162 | 3295000 | 3234000 | 2019-10-25 | 2019-10-25 | -61000 | 0 | 2019 | 10 | 25 | 20191025 | 2019 | 2020 | 1.0276 | 2020 | 1.0006 | 3385912.7975 | 3324875.5667 | -61037.2308 | 0 | 301 | 0%
2022-01-12 | 2019 | Marine Corps Active | M006815002 |  | 2019-02-05 | 2019-03-25 | SYNERGY ELECTRIC COMPANY INC | N62473 | N6247319D2430 | N6247319D2430 | M006815002,N6247319D2430 | 3326000 | 3443000 | 2020-03-30 | 2020-03-20 | 117000 | -10 | 2020 | 03 | 20 | 20200320 | 2019 | 2020 | 1.1519 | 2020 | 1.0993 | 3831111.6207 | 3959724.4804 | 128612.8597 | -10 | 371 | -2.695%
2021-12-31 | 2019 | Air Force Active | NVZR153710 |  | 2019-08-09 | 2020-02-26 | HCR | W91278 | W9127820C0010 | W9127820C0010 | NVZR153710,W9127820C0010 | 3351127 | 3351127 | 2021-06-18 | 2021-06-18 | 0 | 0 | 2021 | 06 | 18 | 20210618 | 2020 | 2021 | 1.0993 | 2021 | 1.0507 | 3683743.8182 | 3683743.8182 | 0 | 0 | 478 | 0%
2022-01-13 | 2019 | Defense Health Agency | 86943 |  | 2019-09-10 | 2019-12-15 | NVE-HHI JV | W9128F | W9128F-20-C-0006 | W9128F20C0006 | 86943,W9128F-20-C-0006 | 3384000 | 3384000 | 2021-06-15 | 2021-07-15 | 0 | 30 | 2021 | 07 | 15 | 20210715 | 2020 | 2021 | 1.0507 | 2021 | 1.0276 | 3555571.9669 | 3555571.9669 | 0 | 30 | 548 | 5.474%
2022-01-06 | 2013 | Special Operations Command | 66597 |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR | W912QR-14-C-0019 | W912QR14C0019 | 66597,W912QR-14-C-0019 | 3384894 | 3480791 | 2015-10-21 | 2016-04-15 | 95897 | 177 | 2016 | 04 | 15 | 20160415 | 2014 | 2016 | 1.0006 | 2015 | 0.95701 | 3386959.9422 | 3478734.5245 | 91774.5823 | 177 | 554 | 31.95%
2021-08-31 | 2018 | Army Active | 89128 |  | 2018-11-29 | 2019-03-08 | Windamir Development | W912HN | W912HN19C3004 | W912HN19C3004 | 89128,W912HN19C3004 | 3402000 | 3548000 | 2020-07-26 | 2021-07-21 | 146000 | 360 | 2021 | 07 | 21 | 20210721 | 2019 | 2021 | 1.0751 | 2020 | 1.0507 | 3657414.3269 | 3810816.6635 | 153402.3366 | 360 | 506 | 71.15%
2022-01-12 | 2017 | Navy Active | N63005985 |  | 2018-02-13 | 2019-06-14 | JUDE & L CONSTRUCTION, LLC | N33191 | N3319119C0805 AWD | N3319119C0805 | N63005985,N3319119C0805 AWD | 3407000 | 3268000 | 2021-03-25 | 2021-03-25 | -139000 | 0 | 2021 | 03 | 25 | 20210325 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 3409079.4344 | 3273279.5318 | -135799.9026 | 0 | 650 | 0%
2022-01-13 | 2018 | Defense Health Agency | 86204 |  | 2020-04-21 | 2020-07-08 | Kimball Construction Company, Inc | W912BU | W912BU20C0033 | W912BU20C0033 | 86204,W912BU20C0033 | 3408000 | 3452000 | 2022-02-03 | 2022-02-22 | 44000 | 19 | 2022 | 02 | 22 | 20220222 | 2020 | 2022 | 0.97698 | 2021 | 0.9382 | 3329540.0578 | 3370820.7727 | 41280.7148 | 19 | 575 | 3.304%
2022-01-12 | 2021 | Marine Corps Active | M67400901U |  | 2021-05-18 | 2021-07-01 | ACTY CO.,LTD. | N40084 | N4008421C8000 AWD | N4008421C8000 | M67400901U,N4008421C8000 AWD | 3417000 | 3255000 | 2022-03-14 | 2022-03-14 | -162000 | 0 | 2022 | 03 | 14 | 20220314 | 2021 | 2022 | 0.97698 | 2022 | 0.9382 | 3338332.8573 | 3186344.7708 | -151988.0865 | 0 | 256 | 0%
2021-12-30 | 2018 | Air National Guard | HAAW179035 |  | 2020-04-30 | 2020-07-14 | SJ Thomas Co Inc | W50S8N | W50S8N20C0001 | W50S8N20C0001 | HAAW179035,W50S8N20C0001 | 3428805 | 3325800 | 2021-08-08 | 2021-08-08 | -103005 | 0 | 2021 | 08 | 08 | 20210808 | 2020 | 2021 | 1.1227 | 2021 | 1.0751 | 3849422.5302 | 3738684.152 | -110738.3782 | 0 | 390 | 0%
2022-01-12 | 2019 | Navy Active | N324461088 |  | 2019-05-23 | 2019-08-05 | TANTARA ASSOCIATES CORPORATION | N40085 | N4008517D5049 N4008519F6032 | N4008517D5049 | N324461088,N4008517D5049 N4008519F6032 | 3458000 | 3460000 | 2020-10-31 | 2021-07-30 | 2000 | 272 | 2021 | 07 | 30 | 20210730 | 2019 | 2021 | 1.0751 | 2020 | 1.0507 | 3717618.6779 | 3719720.0798 | 2101.4019 | 272 | 453 | 60.04%
2021-10-08 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-03-23 | 2018-08-02 | MIRAIT.T-ACTY JV | W912HV | W912HV15D0032 | W912HV15D0032 | AFSOC103022,W912HV15D0032 | 3470750 | 3587463 | 2019-02-04 | 2019-03-21 | 116713 | 45 | 2019 | 03 | 21 | 20190321 | 2018 | 2019 | 1.0276 | 2019 | 0.97698 | 3566511.9399 | 3680537.9401 | 114026.0002 | 45 | 186 | 24.19%
2022-01-06 | 2011 | Special Operations Command | 69278 |  | 2011-07-07 | 2011-09-25 | Iron Mike Construction, LLC | W9128F | W9128F-12-C-0011 | W9128F12C0011 | 69278,W9128F-12-C-0011 | 3505997 | 3578435 | 2013-08-09 | 2014-01-27 | 72438 | 171 | 2014 | 01 | 27 | 20140127 | 2011 | 2014 | 0.97698 | 2013 | 0.95701 | 3425280.9431 | 3494604.9802 | 69324.0371 | 171 | 684 | 25%
2021-12-31 | 2017 | Air Force Active | MAHG173002 |  | 2019-05-22 | 2020-05-28 | U-SMC/DeMaria JV, LLC | N69450 | N6945019D0921 | N6945019D0921 | MAHG173002,N6945019D0921 | 3591891 | 3591891 | 2021-06-25 | 2021-06-25 | 0 | 0 | 2021 | 06 | 25 | 20210625 | 2020 | 2021 | 0.97698 | 2021 | 0.9382 | 3509197.4671 | 3509197.4671 | 0 | 0 | 393 | 0%
2022-01-12 | 2019 | Navy Active | N60201195 |  | 2019-06-18 | 2019-08-16 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N69450 | N6945016D1112 N6945019F0716 | N6945016D1112 | N60201195,N6945016D1112 N6945019F0716 | 3600000 | 3750000 | 2020-08-29 | 2021-03-31 | 150000 | 214 | 2021 | 03 | 31 | 20210331 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 3782523.3691 | 3932614.9204 | 150091.5513 | 214 | 379 | 56.46%
2022-01-06 | 2008 | Special Operations Command | 33005 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER | W912ER-12-C-0011 | W912ER12C0011 | 33005,W912ER-12-C-0011 | 3603251 | 3763908 | 2013-04-25 | 2015-01-21 | 160657 | 636 | 2015 | 01 | 21 | 20150121 | 2012 | 2015 | 0.97698 | 2014 | 0.97698 | 3520295.9339 | 3677254.2429 | 156958.309 | 636 | 477 | 133.3%
2022-01-12 | 2016 | Marine Corps Active | M67001686 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N40085 | N4008516D6300 0003 | N4008516D6300 | M67001686,N4008516D6300 0003 | 3640000 | 3728000 | 2018-04-06 | 2021-04-22 | 88000 | 1112 | 2021 | 04 | 22 | 20210422 | 2016 | 2021 | 0.97698 | 2019 | 0.9382 | 3556198.888 | 3638760.3177 | 82561.4297 | 1112 | 555 | 200.4%
2022-01-13 | 2009 | Defense Health Agency | 70354 | 70354-01 | 2017-07-28 | 2017-09-25 | Anna Lisa Luna Construction, Inc. | W912-P | W912-PL-17-C-0042 | W912PL17C0042 | 70354,W912-PL-17-C-0042 | 3691544 | 4392000 | 2018-05-01 | 2018-08-14 | 700456 | 105 | 2018 | 08 | 14 | 20180814 | 2017 | 2018 | 1.0751 | 2018 | 1.0276 | 3968696.6237 | 4688479.0014 | 719782.3777 | 105 | 218 | 48.17%
2021-12-31 | 2018 | Air Force Active | RKMF173010 |  | 2019-03-04 | 2019-10-02 | Bristol Prime Contractors, LLC | W912PL | W912PL20C0001 | W912PL20C0001 | RKMF173010,W912PL20C0001 | 3698666 | 4146204 | 2020-11-11 | 2022-07-29 | 447538 | 625 | 2022 | 07 | 29 | 20220729 | 2020 | 2022 | 1.0751 | 2021 | 1.0276 | 3976353.3271 | 4436239.4095 | 459886.0824 | 625 | 406 | 153.9%
2022-01-12 | 2018 | Army National Guard | 200129 |  | 2021-03-11 | 2021-04-01 | Cheney Construction | W912JC | W912JC-19-2-2001 | W912JC1922001 | 200129,W912JC-19-2-2001 | 3700000 | 3408000 | 2021-06-22 | 2021-06-22 | -292000 | 0 | 2021 | 06 | 22 | 20210622 | 2021 | 2021 | 1.0993 | 2021 | 1.0006 | 4067244.2815 | 3775066.0617 | -292178.2198 | 0 | 82 | 0%
2021-08-31 | 2020 | Army Reserve | 90912 |  | 2020-01-13 | 2020-05-19 | James Dean Construction, Inc. | W912QR | W912QR20C0009 | W912QR20C0009 | 90912,W912QR20C0009 | 3703000 | 4862000 | 2021-07-22 | 2021-09-20 | 1159000 | 60 | 2021 | 09 | 20 | 20210920 | 2020 | 2021 | 1.0507 | 2021 | 1.0006 | 3890745.5655 | 5050452.9516 | 1159707.3861 | 60 | 429 | 13.99%
2021-12-31 | 2018 | Air Force Active | AEWV171012 |  | 2018-08-01 | 2019-03-01 | Black & Veatch Special Project | W912ER | W912ER18D0005 | W912ER18D0005 | AEWV171012,W912ER18D0005 | 3705150 | 3769955 | 2020-08-08 | 2022-03-31 | 64805 | 600 | 2022 | 03 | 31 | 20220331 | 2019 | 2022 | 1.0993 | 2021 | 1.0276 | 4072905.4459 | 4139498.4895 | 66593.0437 | 600 | 526 | 114.1%
2021-12-31 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-10 | 2018-06-21 | FIRE STATION NO. 2 | N69450 | N69450-18C2105 | N6945018C2105 | AWUB105003,N69450-18C2105 | 3774341 | 3774341 | 2019-10-08 | 2018-08-01 | 0 | -433 | 2018 | 08 | 01 | 20180801 | 2018 | 2018 | 1.0507 | 2018 | 1.0006 | 3965703.6209 | 3965703.6209 | 0 | -433 | 474 | -91.35%
2022-01-31 | 2018 | DLA Defense Reutilization and Marketing Service | DRMS1701 |  | 2018-06-26 | 2018-08-31 | EMR Inc | N91278 | N91278-16-C-0035 | N9127816C0035 | DRMS1701,N91278-16-C-0035 | 3788549 | 3788549 | 2019-07-06 | 2019-10-11 | 0 | 97 | 2019 | 10 | 11 | 20191011 | 2018 | 2020 | 1.0993 | 2019 | 1.0276 | 4164582.2312 | 4164582.2312 | 0 | 97 | 309 | 31.39%
2021-12-31 | 2018 | Air Force Active | LJYC183004 |  | 2018-08-29 | 2019-05-13 | EMTA INSAAT TAAHHUT VE TICARET ANONIUM SI | W912GB | W912GB19F0076 | W912GB19F0076 | LJYC183004,W912GB19F0076 | 3795142 | 3795142 | 2021-09-28 | 2021-09-28 | 0 | 0 | 2021 | 09 | 28 | 20210928 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 3899854.2841 | 3899854.2841 | 0 | 0 | 869 | 0%
2022-01-12 | 2018 | Marine Corps Active | M670011503 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N40085 | N4008514D7742 N4008519F4172 | N4008514D7742 | M670011503,N4008514D7742 N4008519F4172 | 3833000 | 4036000 | 2019-11-09 | 2021-08-21 | 203000 | 651 | 2021 | 08 | 21 | 20210821 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 3835339.44 | 4033665.9165 | 198326.4764 | 651 | 360 | 180.8%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G | W9126G-12-C-0038 | W9126G12C0038 | 72481,W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17 | 31000 | 120 | 2013 | 10 | 17 | 20131017 | 2012 | 2014 | 1.1519 | 2013 | 1.0993 | 4432386.5053 | 4466463.4168 | 34076.9115 | 120 | 335 | 35.82%
2022-01-13 | 2019 | Defense Health Agency | 93298 |  | 2020-02-17 | 2020-08-25 | GCBJV1, Pensacola, FL | N69450 | N6945019D0920 | N6945019D0920 | 93298,N6945019D0920 | 3859000 | 3910000 | 2021-09-10 | 2022-03-22 | 51000 | 193 | 2022 | 03 | 22 | 20220322 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 3965474.199 | 4016505.3264 | 51031.1274 | 193 | 381 | 50.66%
2021-12-31 | 2018 | Army Active | 91252 |  | 2019-05-10 | 2019-08-14 | Crowder Construction Company | W912PM | W912PM19C0027 | W912PM19C0027 | 91252,W912PM19C0027 | 3864000 | 4141000 | 2021-05-15 | 2022-02-11 | 277000 | 272 | 2022 | 02 | 11 | 20220211 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 3775041.8965 | 4040134.2277 | 265092.3312 | 272 | 640 | 42.5%
2021-08-31 | 2019 | Army Active | 82337 |  | 2019-06-28 | 2020-01-16 | National Native American Construction Inc. | W912DW | W912DW19C0016 | W912DW19C0016 | 82337,W912DW19C0016 | 3869000 | 3909000 | 2021-04-07 | 2021-06-30 | 40000 | 84 | 2021 | 06 | 30 | 20210630 | 2020 | 2021 | 1.0006 | 2021 | 0.95701 | 3871361.4123 | 3909641.8934 | 38280.481 | 84 | 447 | 18.79%
2021-12-30 | 2017 | DLA Defense Distribution Center | DDCX1701B |  | 2018-04-03 | 2018-08-30 | Bristol Construction Services | W9126G | W9126G-18-C-0066 | W9126G18C0066 | DDCX1701B,W9126G-18-C-0066 | 3881804 | 3881804 | 2020-09-30 | 2020-09-30 | 0 | 0 | 2020 | 09 | 30 | 20200930 | 2018 | 2020 | 1.2581 | 2019 | 1.2319 | 4883545.2004 | 4883545.2004 | 0 | 0 | 762 | 0%
2021-12-31 | 2017 | Air Force Active | KRSM113031 |  | 2019-01-11 | 2020-12-30 | The Povolny Group, Inc | W91238 | W9123821C0007 | W9123821C0007 | KRSM113031,W9123821C0007 | 3892900 | 3892900 | 2020-12-31 | 2023-03-20 | 0 | 809 | 2023 | 03 | 20 | 20230320 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 4090273.6732 | 4090273.6732 | 0 | 809 | 1 | 80900%
2021-12-31 | 2020 | Army Active | 92422 |  | 2021-04-01 | 2021-08-18 | EMR, Inc | W91278 | W91278-16-D-0035 | W9127816D0035 | 92422,W91278-16-D-0035 | 3929000 | 3929000 | 2022-11-01 | 2022-11-01 | 0 | 0 | 2022 | 11 | 01 | 20221101 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 4037405.5786 | 4037405.5786 | 0 | 0 | 440 | 0%
2021-12-31 | 2021 | Army Reserve | 90896 |  | 2021-03-17 | 2021-07-16 | LRG Construction JV, LLC | W912QR | W912QR21C0031 | W912QR21C0031 | 90896,W912QR21C0031 | 3962000 | 3962000 | 2022-09-15 | 2022-09-15 | 0 | 0 | 2022 | 09 | 15 | 20220915 | 2021 | 2022 | 1.0751 | 2022 | 1.0006 | 4259457.8375 | 4259457.8375 | 0 | 0 | 426 | 0%
2021-12-31 | 2020 | Air Force Active | AJJY183017 |  | 2020-06-15 | 2020-09-30 | Serrano Construction | N40192 | N4019218D2804 | N4019218D2804 | AJJY183017,N4019218D2804 | 3967372 | 3967372 | 2022-06-30 | 2022-06-30 | 0 | 0 | 2022 | 06 | 30 | 20220630 | 2020 | 2022 | 1.0993 | 2021 | 1.0507 | 4361154.3459 | 4361154.3459 | 0 | 0 | 638 | 0%
2021-08-31 | 2018 | Army Active | 80748 |  | 2018-08-07 | 2019-01-25 | Nicklaus Engineering, Inc | W912PL | W912PL19C0007 | W912PL19C0007 | 80748,W912PL19C0007 | 3994000 | 3994000 | 2021-04-15 | 2021-05-27 | 0 | 42 | 2021 | 05 | 27 | 20210527 | 2019 | 2021 | 0.97698 | 2020 | 0.9382 | 3902048.9997 | 3902048.9997 | 0 | 42 | 811 | 5.179%
2021-08-31 | 2018 | Army Active | 88844 |  | 2019-05-14 | 2019-11-12 | Tarver Land Development, LLC | W9126G | W9126G20C0004 | W9126G20C0004 | 88844,W9126G20C0004 | 3999000 | 3999000 | 2021-01-15 | 2021-07-26 | 0 | 192 | 2021 | 07 | 26 | 20210726 | 2020 | 2021 | 1.0006 | 2021 | 0.95701 | 4001440.7568 | 4001440.7568 | 0 | 192 | 430 | 44.65%
2021-12-31 | 2018 | Army Active | 86832 |  | 2018-04-24 | 2018-08-15 | Aytekin-Serol Eng Cons Trade Co. LTD. | W912GB | W912GB-15-D-0084 | W912GB15D0084 | 86832,W912GB-15-D-0084 | 4004000 | 9904000 | 2022-03-25 | 2023-10-01 | 5900000 | 555 | 2023 | 10 | 01 | 20231001 | 2018 | 2024 | 1.0276 | 2021 | 1.0006 | 4114474.9139 | 10018075.9304 | 5903601.0165 | 555 | 1318 | 42.11%
2021-12-31 | 2017 | Air Force Active | MAHG173003 |  | 2019-06-12 | 2020-05-28 | TU-SMC/DeMaria JV, LLC | N69450 | N6945019D0921 | N6945019D0921 | MAHG173003,N6945019D0921 | 4007591 | 4007591 | 2021-06-25 | 2021-06-25 | 0 | 0 | 2021 | 06 | 25 | 20210625 | 2020 | 2021 | 1.0993 | 2021 | 1.0507 | 4405365.2912 | 4405365.2912 | 0 | 0 | 393 | 0%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G | W9126G-12-P-0014 | W9126G12P0014 | 72481,W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16 | 0 | 620 | 2015 | 09 | 16 | 20150916 | 2012 | 2015 | 1.0993 | 2014 | 1.0751 | 4448685.8398 | 4448685.8398 | 0 | 620 | 487 | 127.3%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1707 |  | 2017-01-30 | 2017-08-07 | ASRC Builders | W911KB | W911KB-17-C-0030 | W911KB17C0030 | DESC1707,W911KB-17-C-0030 | 4088355 | 4129621 | 2018-12-15 | 2018-12-03 | 41266 | -12 | 2018 | 12 | 03 | 20181203 | 2017 | 2019 | 1.0276 | 2018 | 1.0006 | 4201157.3643 | 4242448.5507 | 41291.1864 | -12 | 495 | -2.424%
2022-01-06 | 2011 | Special Operations Command | 69449 |  | 2011-01-07 | 2011-05-23 | Barlovento, LLC | W91278 | W91278-10-D-0072 | W9127810D0072 | 69449,W91278-10-D-0072 | 4110280 | 4984696 | 2012-09-26 | 2012-12-18 | 874416 | 83 | 2012 | 12 | 18 | 20121218 | 2011 | 2013 | 1.0276 | 2012 | 1.0006 | 4223687.3 | 5098636.9926 | 874949.6926 | 83 | 492 | 16.87%
2022-01-13 | 2018 | Defense Health Agency | 87208 |  | 2018-10-12 | 2019-04-10 | Shinsampeikensetsu-Unite Corporation JV | W912HV | W912HV-19-C-0005 | W912HV19C0005 | 87208,W912HV-19-C-0005 | 4111000 | 4265000 | 2020-08-21 | 2021-01-30 | 154000 | 162 | 2021 | 01 | 30 | 20210130 | 2019 | 2021 | 1.0751 | 2020 | 1.0507 | 4419644.4144 | 4581452.3585 | 161807.9441 | 162 | 499 | 32.46%
2022-01-06 | 2018 | Special Operations Command | 81894 |  | 2018-06-19 | 2018-09-17 | Attaway Construction | W912PM | W912PM18C0019 | W912PM18C0019 | 81894,W912PM18C0019 | 4123177 | 4581868 | 2019-11-27 | 2020-10-30 | 458691 | 338 | 2020 | 10 | 30 | 20201030 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 4028252.0502 | 4467224.8534 | 438972.8032 | 338 | 436 | 77.52%
2022-01-12 | 2020 | Army National Guard | 260269 |  | 2020-09-10 | 2020-09-25 | Ripman Construction Co Inc. | Y20410 | Y20410 | Y20410 | 260269,Y20410 | 4141000 | 4055000 | 2021-11-05 | 2021-11-05 | -86000 | 0 | 2021 | 11 | 05 | 20211105 | 2020 | 2022 | 1.0751 | 2021 | 1.0006 | 4451896.7453 | 4365844.2559 | -86052.4894 | 0 | 406 | 0%
2021-08-31 | 2016 | Army Active | 88231 |  | 2018-08-20 | 2019-04-01 | Call Associates, Inc | W912DS | W912DS19C0008 | W912DS19C0008 | 88231,W912DS19C0008 | 4185000 | 5123000 | 2020-04-25 | 2020-11-20 | 938000 | 209 | 2020 | 11 | 20 | 20201120 | 2019 | 2021 | 1.0993 | 2020 | 1.0276 | 4600383.059 | 5564263.5458 | 963880.4868 | 209 | 390 | 53.59%
2022-01-12 | 2018 | Navy Active | N00216485 |  | 2018-06-28 | 2018-08-22 | GFP GROUP, L.L.C. | N69450 | N6945016D0615 N6945018F2384 | N6945016D0615 | N00216485,N6945016D0615 N6945018F2384 | 4213000 | 4597000 | 2020-03-14 | 2021-01-30 | 384000 | 322 | 2021 | 01 | 30 | 20210130 | 2018 | 2021 | 1.0751 | 2020 | 1.0507 | 4529302.3395 | 4932771.4989 | 403469.1594 | 322 | 570 | 56.49%
2022-01-12 | 2020 | Navy Active | N601911026 |  | 2020-07-23 | 2020-12-11 | TAZEWELL-BGI JV, LLC | N40085 | N4008518D1144 N4008521F4343 | N4008518D1144 | N601911026,N4008518D1144 N4008521F4343 | 4218000 | 4419000 | 2022-06-10 | 2022-10-18 | 201000 | 130 | 2022 | 10 | 18 | 20221018 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 4431856.5474 | 4632979.2261 | 201122.6787 | 130 | 546 | 23.81%
2022-02-02 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278 | W91278-12-D-0037/54560299 | W9127812D0037 | AM00048,W91278-12-D-0037/54560299 | 4286000 | 4286000 | 2020-06-10 | 2021-10-15 | 0 | 492 | 2021 | 10 | 15 | 20211015 | 2016 | 2022 | 1.0993 | 2019 | 1.0751 | 4711407.8353 | 4711407.8353 | 0 | 492 | 1349 | 36.47%
2021-11-30 | 2021 | Air National Guard | XHEA189054 |  | 2021-03-29 | 2021-08-30 | Granite Construction Compnay | 101191 | 10119102 | 10119102 | XHEA189054,10119102 | 4329586 | 3350722 | 2022-08-30 | 2022-08-30 | -978864 | 0 | 2022 | 08 | 30 | 20220830 | 2021 | 2022 | 1.0276 | 2022 | 0.97698 | 4449044.202 | 3492715.8865 | -956328.3155 | 0 | 365 | 0%
2021-12-30 | 2021 | Air National Guard | XHEA189054 |  | 2021-03-29 | 2021-08-30 | Granite Construction Compnay | F9K3CE | F9K3CE1084MW01 | F9K3CE1084MW01 | XHEA189054,F9K3CE1084MW01 | 4329586 | 3350722 | 2022-08-30 | 2022-08-30 | -978864 | 0 | 2022 | 08 | 30 | 20220830 | 2021 | 2022 | 1.0993 | 2022 | 1.0507 | 4759319.973 | 3730826.6521 | -1028493.3209 | 0 | 365 | 0%
2021-12-31 | 2016 | Air Force Active | FNWZ100071A |  | 2018-05-09 | 2018-08-08 | Basecom Construction Services | W4126C | W4126C18C0049 | W4126C18C0049 | FNWZ100071A,W4126C18C0049 | 4378953 | 4378953 | 2019-10-22 | 2019-11-20 | 0 | 29 | 2019 | 11 | 20 | 20191120 | 2018 | 2020 | 1.1519 | 2019 | 1.0507 | 5043974.0604 | 5043974.0604 | 0 | 29 | 440 | 6.591%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC17U3 |  | 2019-07-02 | 2019-09-12 | The Ross Group | N62473 | N6247319F5135 | N6247319F5135 | DESC17U3,N6247319F5135 | 4384341 | 4883963 | 2021-01-15 | 2022-02-05 | 499622 | 386 | 2022 | 02 | 05 | 20220205 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 4505309.9547 | 4993429.5153 | 488119.5607 | 386 | 491 | 78.62%
2021-12-31 | 2018 | Air Force Active | PTFL163001 |  | 2018-08-24 | 2019-02-27 | RANCO CONSTRUCTION INC | W912DS | W912DS18B00210013 | W912DS18B00210013 | PTFL163001,W912DS18B00210013 | 4427200 | 4557949 | 2021-03-08 | 2021-03-08 | 130749 | 0 | 2021 | 03 | 08 | 20210308 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 4651663.1832 | 4782491.9848 | 130828.8016 | 0 | 740 | 0%
2020-12-09 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR | W912DR-10-C-0035 | W912DR10C0035 | 21372,W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29 | -242000 | 277 | 2012 | 06 | 29 | 20120629 | 2010 | 2012 | 1.1743 | 2011 | 1.1519 | 5217497.0859 | 4938745.1279 | -278751.958 | 277 | 396 | 69.95%
2022-01-06 | 2013 | Special Operations Command | 69257 |  | 2013-05-15 | 2015-04-01 | Pease Construction Inc | W912DW | W912DW-15-C-0003 | W912DW15C0003 | 69257,W912DW-15-C-0003 | 4484160 | 5129236 | 2016-09-15 | 2017-03-24 | 645076 | 190 | 2017 | 03 | 24 | 20170324 | 2015 | 2017 | 1.0006 | 2016 | 0.97698 | 4486896.8702 | 5117121.7476 | 630224.8774 | 190 | 533 | 35.65%
2021-12-30 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV | W912BV-15-C-0017 | W912BV15C0017 | DESC1502,W912BV-15-C-0017 | 4556371 | 4733000 | 2016-10-23 | 2017-09-08 | 176629 | 320 | 2017 | 09 | 08 | 20170908 | 2015 | 2017 | 1.1227 | 2016 | 1.0993 | 5115309.0314 | 5309469.3801 | 194160.3487 | 320 | 538 | 59.48%
2022-01-06 | 2008 | Special Operations Command | 33003 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER | W912ER-12-C-0011 | W912ER12C0011 | 33003,W912ER-12-C-0011 | 4574738 | 5123284 | 2013-04-25 | 2015-03-05 | 548546 | 679 | 2015 | 03 | 05 | 20150305 | 2012 | 2015 | 1.0006 | 2014 | 0.97698 | 4577530.1537 | 5113447.3722 | 535917.2185 | 679 | 477 | 142.3%
2022-01-12 | 2019 | Navy Active | N62863812 |  | 2020-05-14 | 2020-09-23 | CONSTRUCTORA SAN JOSE SA | N62470 | N6247020C0009 AWD | N6247020C0009 | N62863812,N6247020C0009 AWD | 4598802.63 | 5169000 | 2022-06-30 | 2022-06-30 | 570197.37 | 0 | 2022 | 06 | 30 | 20220630 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 4831966.2272 | 5402511.6124 | 570545.3853 | 0 | 645 | 0%
2022-01-06 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R. C. Construction Co., Inc. | W912HN | W912HN17C0008 | W912HN17C0008 | 61065,W912HN17C0008 | 4609000 | 5099620 | 2018-12-01 | 2019-07-18 | 490620 | 229 | 2019 | 07 | 18 | 20190718 | 2017 | 2019 | 1.0276 | 2018 | 0.95701 | 4736167.552 | 5205696.7922 | 469529.2402 | 229 | 498 | 45.98%
2021-12-31 | 2020 | Army Active | 91328 |  | 2020-06-25 | 2020-09-15 | Weldin Construction, LLC | W912BV | W912BV17D0017 | W912BV17D0017 | 91328,W912BV17D0017 | 4623000 | 4623000 | 2021-11-09 | 2021-11-09 | 0 | 0 | 2021 | 11 | 09 | 20211109 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 4857390.4265 | 4857390.4265 | 0 | 0 | 420 | 0%
2021-12-31 | 2018 | Air Force Reserve | VKAG159026 |  | 2020-06-01 | 2020-09-29 | Ocean Construction Services, Inc. | W912QR | W912QR20C0056 | W912QR20C0056 | VKAG159026,W912QR20C0056 | 4628152 | 4628152 | 2022-07-08 | 2022-10-06 | 0 | 90 | 2022 | 10 | 06 | 20221006 | 2020 | 2023 | 1.0006 | 2022 | 0.95701 | 4630976.7545 | 4630976.7545 | 0 | 90 | 647 | 13.91%
2022-01-12 | 2019 | Navy Reserve | N00206493 |  | 2019-10-03 | 2020-01-09 | DAWSON FEDERAL, INC. | N69450 | N6945018D1320 N6945020F0873 | N6945018D1320 | N00206493,N6945018D1320 N6945020F0873 | 4632000 | 4478000 | 2021-01-28 | 2021-10-19 | -154000 | 264 | 2021 | 10 | 19 | 20211019 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 4866846.7349 | 4712752.7423 | -154093.9926 | 264 | 385 | 68.57%
2021-12-31 | 2018 | Army Active | 92022 |  | 2019-06-07 | 2019-07-25 | Siler Excavating LLC | W912HN | W912HN19C3008 | W912HN19C3008 | 92022,W912HN19C3008 | 4635000 | 4775000 | 2020-06-17 | 2021-11-02 | 140000 | 503 | 2021 | 11 | 02 | 20211102 | 2019 | 2022 | 1.0993 | 2021 | 1.0507 | 5095047.904 | 5242146.0351 | 147098.131 | 503 | 328 | 153.4%
2021-12-31 | 2020 | Air Force Active | BIKF190002 |  | 2019-11-15 | 2020-09-21 | Icelandic Prime Contractors | N62470 | N6247020C0010 | N6247020C0010 | BIKF190002,N6247020C0010 | 4671392 | 4671392 | 2023-07-14 | 2023-07-14 | 0 | 0 | 2023 | 07 | 14 | 20230714 | 2020 | 2023 | 1.2082 | 2022 | 1.1743 | 5644098.8806 | 5644098.8806 | 0 | 0 | 1026 | 0%
2021-12-30 | 2021 | Air National Guard | FJRP199040 |  | 2021-05-19 | 2021-09-30 | Brantley Construction Services LLC | W50S87 | W50S8721C5002 | W50S8721C5002 | FJRP199040,W50S8721C5002 | 4690132 | 4598700 | 2023-01-23 | 2023-01-23 | -91432 | 0 | 2023 | 01 | 23 | 20230123 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 4692994.5835 | 4605493.0599 | -87501.5236 | 0 | 480 | 0%
2021-12-30 | 2019 | Air National Guard | PSTE089064 |  | 2020-08-13 | 2021-09-30 | CCCS International LLC | W912QG | W912QG21C0004 | W912QG21C0004 | PSTE089064,W912QG21C0004 | 4748809 | 4571407 | 2023-10-30 | 2023-10-30 | -177402 | 0 | 2023 | 10 | 30 | 20231030 | 2021 | 2024 | 1.0006 | 2023 | 0.97698 | 4751707.3965 | 4578389.5956 | -173317.8009 | 0 | 760 | 0%
2021-12-31 | 2021 | Air Force Active | ACJP183018 |  | 2021-03-31 | 2021-08-30 | J.I. Garcia Construction, Inc. | N62473 | N6247318D5817 | N6247318D5817 | ACJP183018,N6247318D5817 | 4749000 | 4749000 | 2022-11-13 | 2022-11-13 | 0 | 0 | 2022 | 11 | 13 | 20221113 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 4751898.5131 | 4751898.5131 | 0 | 0 | 440 | 0%
2021-12-31 | 2019 | Air Force Active | CRWU173001 |  | 2020-07-15 | 2020-09-25 | Iron Mike Construction | W9128F | W9128F20C0048 | W9128F20C0048 | CRWU173001,W9128F20C0048 | 4763991 | 4849127 | 2021-12-12 | 2022-03-01 | 85136 | 79 | 2022 | 03 | 01 | 20220301 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 5005529.8021 | 5090717.7642 | 85187.9621 | 79 | 443 | 17.83%
2022-01-06 | 2012 | Special Operations Command | 43055 |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN | W912HN-10-D-0063 | W912HN10D0063 | 43055,W912HN-10-D-0063 | 4773799 | 5344212 | 2013-11-22 | 2014-11-12 | 570413 | 355 | 2014 | 11 | 12 | 20141112 | 2012 | 2015 | 1.0006 | 2014 | 0.9382 | 4776712.649 | 5311873.0216 | 535160.3727 | 355 | 577 | 61.53%
2021-03-31 | 2018 | National Security Agency | 30439 |  | 2018-07-19 | 2018-09-30 | Alutiiq Construction Services, LLC | W9128A | W9128A-18-C-0016 | W9128A18C0016 | 30439,W9128A-18-C-0016 | 4800000 | 4800000 | 2020-03-01 | 2021-03-25 | 0 | 389 | 2021 | 03 | 25 | 20210325 | 2018 | 2021 | 1.1519 | 2020 | 1.0993 | 5528964.4556 | 5528964.4556 | 0 | 389 | 518 | 75.1%
2022-01-12 | 2019 | Marine Corps Active | M67865238 |  | 2019-01-03 | 2019-03-08 | Teehee Engineering Inc. | N62473 | N6247319C2425 | N6247319C2425 | M67865238,N6247319C2425 | 4828000 | 7006000 | 2020-04-06 | 2020-04-06 | 2178000 | 0 | 2020 | 04 | 06 | 20200406 | 2019 | 2020 | 1.1227 | 2020 | 1.0993 | 5420259.2378 | 7814437.0879 | 2394177.8501 | 0 | 395 | 0%
2022-01-31 | 2013 | DLA Defense Distribution Center | DCX1305 |  | 2016-12-21 | 2017-06-01 | Lobar Inc | W912DR | W912DR-17-C-0022 | W912DR17C0022 | DCX1305,W912DR-17-C-0022 | 4831000 | 4865000 | 2019-06-26 | 2020-03-02 | 34000 | 250 | 2020 | 03 | 02 | 20200302 | 2017 | 2020 | 1.0006 | 2019 | 0.97698 | 4833948.5611 | 4867165.8035 | 33217.2424 | 250 | 755 | 33.11%
2022-01-06 | 2009 | Special Operations Command | 60815 |  | 2008-12-12 | 2009-04-30 | Porter-Metcon | W912HN | W912HN-09-C-0022 | W912HN09C0022 | 60815,W912HN-09-C-0022 | 4847000 | 5753585 | 2010-11-24 | 2011-04-12 | 906585 | 139 | 2011 | 04 | 12 | 20110412 | 2009 | 2011 | 0.97698 | 2010 | 0.95701 | 4735410.9918 | 5603023.7394 | 867612.7476 | 139 | 573 | 24.26%
2022-01-12 | 2017 | Navy Active | N62588308 |  | 2018-08-09 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N62470 | N6247019C5009 AWD | N6247019C5009 | N62588308,N6247019C5009 AWD | 4894000 | 4760000 | 2021-02-09 | 2021-07-21 | -134000 | 162 | 2021 | 07 | 21 | 20210721 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 5029031.0261 | 4894949.2403 | -134081.7858 | 162 | 782 | 20.72%
2021-12-31 | 2019 | Air Force Active | ZHTV093301 |  | 2019-10-20 | 2019-11-19 | Add/Alter Intelligence Production Facility, Road and Utilities Relocation | W912QR | W912QR19B00160005 | W912QR19B00160005 | ZHTV093301,W912QR19B00160005 | 4911384 | 4911384 | 2020-10-14 | 2024-06-10 | 0 | 1335 | 2024 | 06 | 10 | 20240610 | 2020 | 2024 | 1.1743 | 2022 | 1.0993 | 5767529.0812 | 5767529.0812 | 0 | 1335 | 330 | 404.5%
2021-12-31 | 2017 | Air Force Active | CADJ170002 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N33191 | N3319116D1035 | N3319116D1035 | CADJ170002,N3319116D1035 | 4911856 | 5442283 | 2020-02-06 | 2022-04-11 | 530427 | 795 | 2022 | 04 | 11 | 20220411 | 2018 | 2022 | 1.2581 | 2020 | 1.2319 | 6179413.1785 | 6832865.9081 | 653452.7296 | 795 | 647 | 122.9%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC1914 |  | 2019-07-16 | 2019-09-30 | UST General Contracting, LLC | W91236 | W9123619C0043 / 56747799 | W9123619C0043 | DESC1914,W9123619C0043 / 56747799 | 4917000 | 5048000 | 2020-12-04 | 2021-09-30 | 131000 | 300 | 2021 | 09 | 30 | 20210930 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 5052665.6223 | 5180649.7032 | 127984.0809 | 300 | 431 | 69.61%
2021-12-31 | 2022 | Army Reserve | 92098 |  | 2021-08-17 | 2021-11-12 | G.M. HILL ENGINEERING, INC. | W912QR | W912QR20D0024 | W912QR20D0024 | 92098,W912QR20D0024 | 4924000 | 4924000 | 2023-07-15 | 2023-07-15 | 0 | 0 | 2023 | 07 | 15 | 20230715 | 2022 | 2023 | 0.97698 | 2023 | 0.95701 | 4810638.276 | 4810638.276 | 0 | 0 | 610 | 0%
2021-12-31 | 2016 | Air Force Reserve | PDPG120514 |  | 2018-08-20 | 2018-09-14 | Lead Builders Inc | W912QR | W912QR18C0031 | W912QR18C0031 | PDPG120514,W912QR18C0031 | 4968200 | 5056600 | 2019-11-08 | 2021-05-31 | 88400 | 570 | 2021 | 05 | 31 | 20210531 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 5105278.2885 | 5193732.2427 | 88453.9542 | 570 | 420 | 135.7%
2022-01-06 | 2019 | Special Operations Command | 87438 |  | 2019-05-28 | 2020-11-30 | Archer Western Federal JV | W912QR | W912QR21C0003 | W912QR21C0003 | 87438,W912QR21C0003 | 4970375 | 5035427 | 2022-05-01 | 2022-05-01 | 65052 | 0 | 2022 | 05 | 01 | 20220501 | 2021 | 2022 | 1.0751 | 2022 | 1.0006 | 5343539.3107 | 5408631.0146 | 65091.704 | 0 | 517 | 0%
2021-12-30 | 2018 | Air National Guard | CEKT149052 |  | 2018-06-30 | 2018-12-18 | LAROSA BUILDING GROUP, LLC | W91ZRS | W91ZRS18R50010002 | W91ZRS18R50010002 | CEKT149052,W91ZRS18R50010002 | 4979466 | 4990118 | 2024-12-26 | 2024-12-26 | 10652 | 0 | 2024 | 12 | 26 | 20241226 | 2019 | 2025 | 1.2082 | 2022 | 1.1914 | 6016322.0035 | 6029012.3768 | 12690.3733 | 0 | 2200 | 0%
2021-12-31 | 2017 | Army Active | 89215 |  | 2019-02-12 | 2019-11-13 | C&C Contractors | W912HN | W912HN20C3002 | W912HN20C3002 | 89215,W912HN20C3002 | 4996000 | 5081000 | 2021-01-09 | 2021-11-30 | 85000 | 325 | 2021 | 11 | 30 | 20211130 | 2020 | 2022 | 1.0751 | 2021 | 1.0507 | 5371088.1767 | 5460397.7562 | 89309.5795 | 325 | 423 | 76.83%
2022-01-12 | 2019 | Army National Guard | 171510 |  | 2019-09-10 | 2019-09-13 | Vissering Construction Company | W91SMC | W91SMC-19-2-2001 | W91SMC1922001 | 171510,W91SMC-19-2-2001 | 5000000 | 4555000 | 2020-10-16 | 2021-11-18 | -445000 | 398 | 2021 | 11 | 18 | 20211118 | 2019 | 2022 | 1.0751 | 2021 | 1.0006 | 5375388.4875 | 4930116.8854 | -445271.6021 | 398 | 399 | 99.75%
2021-12-31 | 2020 | Air Force Active | XQPZ174006 |  | 2020-09-23 | 2021-01-29 | JBI Inc | W9128F | W9128F21C0013 | W9128F21C0013 | XQPZ174006,W9128F21C0013 | 5040100 | 5040100 | 2023-02-27 | 2023-02-27 | 0 | 0 | 2023 | 02 | 27 | 20230227 | 2021 | 2023 | 1.2082 | 2022 | 1.0993 | 6089581.5997 | 6089581.5997 | 0 | 0 | 759 | 0%
2021-12-31 | 2019 | Air Force Reserve | MAHG063004 |  | 2019-10-01 | 2019-12-11 | EMR, Inc. | N69450 | N6945020F0870 | N6945020F0870 | MAHG063004,N6945020F0870 | 5057057 | 5057057 | 2020-10-31 | 2021-08-30 | 0 | 303 | 2021 | 08 | 30 | 20210830 | 2020 | 2021 | 1.0993 | 2021 | 1.0507 | 5558996.2607 | 5558996.2607 | 0 | 303 | 325 | 93.23%
2021-12-31 | 2018 | Army Active | 86518 |  | 2019-04-24 | 2019-07-17 | Doyon Management Services, LLC | W912DW | W912DW19C0012 | W912DW19C0012 | 86518,W912DW19C0012 | 5076000 | 5223000 | 2020-08-15 | 2022-03-09 | 147000 | 571 | 2022 | 03 | 09 | 20220309 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 5079098.0948 | 5219778.8627 | 140680.7678 | 571 | 395 | 144.6%
2021-12-31 | 2018 | Army Active | 91528 |  | 2019-01-15 | 2019-06-18 | Ral Investment Corporation dba Silverstrand Construction | W912PL | W912PL19C0017 | W912PL19C0017 | 91528,W912PL19C0017 | 5099000 | 5443000 | 2020-09-15 | 2021-11-30 | 344000 | 441 | 2021 | 11 | 30 | 20211130 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 5239687.2093 | 5575767.5438 | 336080.3345 | 441 | 455 | 96.92%
2022-01-06 | 2008 | Special Operations Command | 65396 |  | 2007-10-09 | 2008-02-14 | Walbridge Aldinger Company | W912HN | W912HN-07-D-0054 | W912HN07D0054 |  | 5143000 | 5507227 | 2009-04-05 | 2009-06-16 | 364227 | 72 | 2009 | 06 | 16 | 20090616 | 2008 | 2009 | 1.0276 | 2009 | 1.0006 | 5284901.2193 | 5649350.5223 | 364449.303 | 72 | 416 | 17.31%
2021-12-31 | 2016 | Army Active | 87980 |  | 2019-02-12 | 2019-11-12 | C&C Contractors | W912HN | W912HN20C3001 | W912HN20C3001 | 87980,W912HN20C3001 | 5155000 | 5230000 | 2021-01-09 | 2021-11-30 | 75000 | 325 | 2021 | 11 | 30 | 20211130 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 5416363.3243 | 5491409.1 | 75045.7756 | 325 | 424 | 76.65%
2021-12-31 | 2017 | Air Force Active | GHLN083004 |  | 2017-05-16 | 2017-06-15 | W9128F16R0011 | W9128F | W9128F16D00550001 | W9128F16D00550001 | GHLN083004,W9128F16D00550001 | 5168580 | 5168580 | 2019-01-21 | 2020-12-31 | 0 | 710 | 2020 | 12 | 31 | 20201231 | 2017 | 2021 | 1.2319 | 2019 | 1.2082 | 6367365.7434 | 6367365.7434 | 0 | 710 | 585 | 121.4%
2021-12-30 | 2019 | Air National Guard | FJRP199080 |  | 2019-03-28 | 2019-07-12 | GVA-AVM Joint Venture | W91242 | W9124219C5007 | W9124219C5007 | FJRP199080,W9124219C5007 | 5224985 | 5049432 | 2020-08-26 | 2020-08-26 | -175553 | 0 | 2020 | 08 | 26 | 20200826 | 2019 | 2020 | 1.1914 | 2020 | 1.1519 | 6224841.3572 | 6022627.5453 | -202213.8119 | 0 | 411 | 0%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB | W912GB-10-C-0031, ABG4 P00039 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00039 | 5235000 | 7121000 | 2025-12-30 | 2027-09-30 | 1886000 | 639 | 2027 | 09 | 30 | 20270930 | 2012 | 2027 | 1.0006 | 2020 | 0.97698 | 5238195.1392 | 7080775.1125 | 1842579.9733 | 639 | 5038 | 12.68%
2022-01-06 | 2009 | Special Operations Command | 33017 |  | 2008-10-15 | 2009-03-03 | CCSI/Barlovento, LLC, JV | W91278 | W91278-09-C-0010 | W9127809C0010 |  | 5240500 | 6602985 | 2010-09-28 | 2011-06-08 | 1362485 | 253 | 2011 | 06 | 08 | 20110608 | 2009 | 2011 | 1.0006 | 2010 | 0.95701 | 5243698.4961 | 6547613.0263 | 1303914.5302 | 253 | 574 | 44.08%
2020-12-09 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR | W912DR-13-C-0021 | W912DR13C0021 | 25047,W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04 | 539000 | 423 | 2015 | 05 | 04 | 20150504 | 2013 | 2015 | 1.0507 | 2014 | 1.0006 | 5519332.0161 | 6058660.9903 | 539328.9742 | 423 | 381 | 111%
2022-01-13 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Services Inc. | N40080 | N4008010D0498 DO 0025 | N4008010D0498 | 80306,N4008010D0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25 | -69000 | 102 | 2014 | 03 | 25 | 20140325 | 2013 | 2014 | 1.0751 | 2014 | 1.0276 | 5682860.7089 | 5611956.9205 | -70903.7885 | 102 | 92 | 110.9%
2021-12-31 | 2018 | Army Active | 89946 |  | 2019-10-29 | 2020-01-31 | CCI Utility and Construction Services, LLC | W91278 | W9127820C0008 | W9127820C0008 | 89946,W9127820C0008 | 5292000 | 5551000 | 2021-05-22 | 2021-12-10 | 259000 | 202 | 2021 | 12 | 10 | 20211210 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 5295229.9287 | 5548267.1572 | 253037.2286 | 202 | 477 | 42.35%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB | W912GB-10-C-0031, ABG4 P00043 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6586000 | 2016-04-30 | 2017-07-30 | 1265000 | 456 | 2017 | 07 | 30 | 20170730 | 2012 | 2017 | 1.0006 | 2015 | 0.97698 | 5324247.6286 | 6560124.4399 | 1235876.8114 | 456 | 1507 | 30.26%
2021-08-31 | 2019 | Army Active | 93022 |  | 2019-03-29 | 2019-05-31 | TBI | W911KB | W911KB-17-D-0012 | W911KB17D0012 | 93022,W911KB-17-D-0012 | 5379000 | 6563000 | 2020-09-09 | 2021-07-28 | 1184000 | 322 | 2021 | 07 | 28 | 20210728 | 2019 | 2021 | 1.1227 | 2020 | 1.0751 | 6038851.3754 | 7311743.3692 | 1272891.9938 | 322 | 467 | 68.95%
2022-01-06 | 2019 | Special Operations Command | 66813 |  | 2018-09-17 | 2019-05-23 | Howard W. Pence, Inc | W912QR | W912QR-15-D-0001 | W912QR15D0001 | 66813,W912QR-15-D-0001 | 5405390 | 5682502 | 2020-12-03 | 2021-06-17 | 277112 | 196 | 2021 | 06 | 17 | 20210617 | 2019 | 2021 | 1.1914 | 2020 | 1.1743 | 6439768.7694 | 6765186.517 | 325417.7476 | 196 | 560 | 35%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB | W912GB-10-C-0031, ABG4 P00062 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4 P00062 | 5444000 | 6199000 | 2016-12-15 | 2017-12-15 | 755000 | 365 | 2017 | 12 | 15 | 20171215 | 2012 | 2018 | 1.0276 | 2015 | 1.0006 | 5594206.1517 | 6349666.9597 | 755460.808 | 365 | 1736 | 21.03%
2021-12-31 | 2019 | Army Active | 81316 |  | 2020-03-10 | 2020-06-23 | Anna Lisa Luna Construction, Inc. | W912PL | W912PL20C0019 | W912PL20C0019 | 81316,W912PL20C0019 | 5481000 | 5800000 | 2021-08-18 | 2021-12-12 | 319000 | 116 | 2021 | 12 | 12 | 20211212 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 5484345.2833 | 5789632.1196 | 305286.8363 | 116 | 421 | 27.55%
2022-01-12 | 2018 | Army National Guard | 080220 |  | 2020-04-07 | 2020-04-13 | Iron Mike Construction, LLC | W912LC | W912LC-18-2-2001 | W912LC1822001 | 080220,W912LC-18-2-2001 | 5519955 | 6000000 | 2021-05-01 | 2021-12-31 | 480045 | 244 | 2021 | 12 | 31 | 20211231 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 5523324.0591 | 5982732.8971 | 459408.838 | 244 | 383 | 63.71%
2021-12-30 | 2021 | Air National Guard | DPEZ029038 |  | 2021-04-23 | 2021-11-15 | Raxor Cosulting | W50S8W | W50S8W22C0001 | W50S8W22C0001 | DPEZ029038,W50S8W22C0001 | 5527675 | 5375875 | 2023-02-28 | 2023-02-28 | -151800 | 0 | 2023 | 02 | 28 | 20230228 | 2022 | 2023 | 1.1743 | 2023 | 1.1227 | 6491251.0025 | 6320829.43 | -170421.5726 | 0 | 470 | 0%
2021-12-31 | 2016 | Air Force Active | MPLS083737R5 |  | 2019-05-27 | 2019-06-26 | SB Demo | W9126G | W9126G19C0035 | W9126G19C0035 | MPLS083737R5,W9126G19C0035 | 5546178 | 5546178 | 2019-07-26 | 2022-10-03 | 0 | 1165 | 2022 | 10 | 03 | 20221003 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 5699203.3589 | 5699203.3589 | 0 | 1165 | 30 | 3883%
2021-12-31 | 2019 | Air Force Active | RKMF123009 |  | 2019-04-17 | 2019-08-27 | GUARDIAN/EC JV LLC | W912PL | W912PL19C0024 | W912PL19C0024 | RKMF123009,W912PL19C0024 | 5555674 | 5822833 | 2021-06-02 | 2022-07-29 | 267159 | 422 | 2022 | 07 | 29 | 20220729 | 2019 | 2022 | 1.0507 | 2021 | 1.0276 | 5837351.8711 | 6111882.0918 | 274530.2207 | 422 | 645 | 65.43%
2020-12-09 | 2012 | National Security Agency | 23051 | 2 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR | W912DR-12-F-0081 | W912DR12F0081 | 23051,W912DR-12-F-0081 | 5621000 | 5621000 | 2014-02-14 | 2015-09-30 | 0 | 593 | 2015 | 09 | 30 | 20150930 | 2013 | 2015 | 0.97698 | 2014 | 0.9382 | 5491591.7444 | 5491591.7444 | 0 | 593 | 138 | 429.7%
2022-01-13 | 2019 | Defense Health Agency | 89839 |  | 2021-06-14 | 2021-08-25 | RQ-AECOM JV | N69450 | N6945018D1317 | N6945018D1317 | 89839,N6945018D1317 | 5634000 | 5634000 | 2023-06-02 | 2023-06-02 | 0 | 0 | 2023 | 06 | 02 | 20230602 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 5789448.4678 | 5789448.4678 | 0 | 0 | 646 | 0%
2021-12-31 | 2020 | Air Force Active | RKMF203001 |  | 2020-06-15 | 2020-09-16 | GUARDIAN | W912PL | W912PL20C0035 | W912PL20C0035 | RKMF203001,W912PL20C0035 | 5659450 | 5659450 | 2021-12-01 | 2021-12-01 | 0 | 0 | 2021 | 12 | 01 | 20211201 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 5662904.1988 | 5662904.1988 | 0 | 0 | 441 | 0%
2022-01-06 | 2018 | Special Operations Command | CZQZ103006 |  | 2018-04-26 | 2018-09-28 | Walga Ross Group JV | W912PP | W912PP18C0022 | W912PP18C0022 | CZQZ103006,W912PP18C0022 | 5732950 | 5868773 | 2020-01-13 | 2020-05-27 | 135823 | 135 | 2020 | 05 | 27 | 20200527 | 2018 | 2020 | 1.0276 | 2019 | 0.97698 | 5891128.6108 | 6023824.6552 | 132696.0444 | 135 | 472 | 28.6%
2022-01-12 | 2019 | Marine Corps Active | M00146199 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N40085 | N4008520C8501 AWD | N4008520C8501 | M00146199,N4008520C8501 AWD | 5813000 | 128433000 | 2022-07-14 | 2022-12-30 | 122620000 | 169 | 2022 | 12 | 30 | 20221230 | 2020 | 2023 | 1.0751 | 2022 | 1.0507 | 6249426.6555 | 135086375.4104 | 128836948.7549 | 169 | 934 | 18.09%
2021-12-31 | 2019 | Army Active | 93021 |  | 2019-10-24 | 2020-04-07 | Anderson Burton Construction, Inc. | W9128A | W9128A-16-D-0005 | W9128A16D0005 | 93021,W9128A-16-D-0005 | 5827000 | 5827000 | 2022-01-08 | 2022-01-08 | 0 | 0 | 2022 | 01 | 08 | 20220108 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 6122434.3532 | 6122434.3532 | 0 | 0 | 641 | 0%
2022-01-12 | 2020 | Marine Corps Active | M670011800 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N40085 | N4008521C0017 | N4008521C0017 | M670011800,N4008521C0017 | 5850000 | 82095000 | 2026-07-23 | 2027-03-20 | 76245000 | 240 | 2027 | 03 | 20 | 20270320 | 2021 | 2027 | 0.97698 | 2024 | 0.9382 | 5715319.6415 | 77248231.0831 | 71532911.4416 | 240 | 2039 | 11.77%
2022-01-12 | 2020 | Marine Corps Active | M670011801 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N40085 | N4008521C0017 | N4008521C0017 | M670011801,N4008521C0017 | 5850000 | 59867000 | 2026-07-23 | 2027-03-20 | 54017000 | 240 | 2027 | 03 | 20 | 20270320 | 2021 | 2027 | 1.0006 | 2024 | 0.9382 | 5853570.4994 | 56532215.3593 | 50678644.8599 | 240 | 2039 | 11.77%
2022-01-06 | 2009 | Special Operations Command | 63027 |  | 2008-11-24 | 2009-03-27 | Phil Howry Company | W912PP | W912PP-09-C-0006 | W912PP09C0006 | 63027,W912PP-09-C-0006 | 5885533 | 6043246 | 2010-09-10 | 2011-06-02 | 157713 | 265 | 2011 | 06 | 02 | 20110602 | 2009 | 2011 | 0.95701 | 2010 | 0.9382 | 5632525.8603 | 5780491.8916 | 147966.0314 | 265 | 532 | 49.81%
2022-01-12 | 2020 | Army National Guard | 330050 |  | 2020-09-03 | 2020-09-21 | Turnstone Corporation | W912TF | W912TF-18-2-2001 | W912TF1822001 | 330050,W912TF-18-2-2001 | 5950000 | 6539000 | 2022-09-02 | 2022-09-02 | 589000 | 0 | 2022 | 09 | 02 | 20220902 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 5953631.5336 | 6529071.4086 | 575439.875 | 0 | 711 | 0%
2021-12-30 | 2020 | Air National Guard | ULYB169010 |  | 2020-06-09 | 2020-09-02 | Lee Grover | W50S7G | W50S7G20C0001 | W50S7G20C0001 | ULYB169010,W50S7G20C0001 | 5962100 | 5653014 | 2022-03-31 | 2022-03-31 | -309086 | 0 | 2022 | 03 | 31 | 20220331 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 6264384.0497 | 5955109.4016 | -309274.6481 | 0 | 575 | 0%
2022-01-06 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services | W912HN | W912HN-13-D-0002 | W912HN13D0002 | 79456,W912HN-13-D-0002 | 5997470 | 6178195 | 2016-11-11 | 2017-02-13 | 180725 | 94 | 2017 | 02 | 13 | 20170213 | 2015 | 2017 | 1.0751 | 2016 | 1.0276 | 6447746.2384 | 6633457.6467 | 185711.4083 | 94 | 438 | 21.46%
2022-01-12 | 2019 | Army National Guard | 160193 |  | 2020-09-16 | 2020-09-18 | HC Company | W912J7 | W912J7-19-2-2002 | W912J71922002 | 160193,W912J7-19-2-2002 | 6000000 | 5515000 | 2021-08-20 | 2021-10-30 | -485000 | 71 | 2021 | 10 | 30 | 20211030 | 2020 | 2022 | 1.1227 | 2021 | 1.0751 | 6736030.5358 | 6214617.8525 | -521412.6833 | 71 | 336 | 21.13%
2022-01-12 | 2015 | Army National Guard | 411300 |  | 2019-06-13 | 2019-09-20 | Fortis Construction, Inc | 179997 | 179997D002 | 179997D002 | 411300,179997D002 | 6031000 | 5900000 | 2020-09-30 | 2021-01-19 | -131000 | 111 | 2021 | 01 | 19 | 20210119 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 6197402.1493 | 6069418.0684 | -127984.0809 | 111 | 376 | 29.52%
2021-12-30 | 2018 | Air National Guard | ULYB049040 |  | 2019-07-02 | 2019-08-21 | Lee Grover Construction | W912NS | W912NS19C6003 | W912NS19C6003 | ULYB049040,W912NS19C6003 | 6052456 | 6136064 | 2021-03-23 | 2021-03-23 | 83608 | 0 | 2021 | 03 | 23 | 20210323 | 2019 | 2021 | 1.1227 | 2020 | 1.0993 | 6794921.4054 | 6886827.9351 | 91906.5297 | 0 | 580 | 0%
2021-12-31 | 2015 | Air Force Active | MPLS3274JB |  | 2015-02-17 | 2015-06-03 | Solis Constructors, Inc. | W9126G | W9126G14D00500002 | W9126G14D00500002 | MPLS3274JB,W9126G14D00500002 | 6077000 | 6133616 | 2016-08-31 | 2018-06-12 | 56616 | 650 | 2018 | 06 | 12 | 20180612 | 2015 | 2018 | 1.0751 | 2017 | 1.0006 | 6533247.1677 | 6589897.7228 | 56650.5551 | 650 | 455 | 142.9%
2022-01-12 | 2017 | Navy Active | N62995737 |  | 2016-09-09 | 2017-02-28 | ENVIRONMENTAL CHEMICAL CORPORATION | N33191 | N3319116D1010 JN01 | N3319116D1010 | N62995737,N3319116D1010 JN01 | 6096000 | 12446000 | 2018-08-22 | 2021-01-21 | 6350000 | 883 | 2021 | 01 | 21 | 20210121 | 2017 | 2021 | 1.2581 | 2019 | 1.0993 | 7669138.2516 | 14649408.8429 | 6980270.5913 | 883 | 540 | 163.5%
2021-08-31 | 2020 | Army Active | 71725 |  | 2020-02-19 | 2020-04-29 | Intec Group, LLC | W912QR | W912QR20C0019 | W912QR20C0019 | 71725,W912QR20C0019 | 6106000 | 6333000 | 2021-05-12 | 2021-08-31 | 227000 | 111 | 2021 | 08 | 31 | 20210831 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 6274471.4846 | 6496245.4262 | 221773.9416 | 111 | 378 | 29.37%
2021-12-31 | 2015 | Army Active | 86404 |  | 2017-05-09 | 2017-09-26 | MICHAEL M.TSONTOS S.A. | W912GB | W912GB17D0015 | W912GB17D0015 | 86404,W912GB17D0015 | 6121000 | 6783000 | 2019-12-13 | 2022-02-28 | 662000 | 808 | 2022 | 02 | 28 | 20220228 | 2017 | 2022 | 0.95701 | 2020 | 0.9382 | 5857870.611 | 6478957.7298 | 621087.1188 | 808 | 808 | 100%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1603 |  | 2017-12-12 | 2018-08-10 | Bietergemeinschaft UVB | W912GB | W912GB-14-C-0005 | W912GB14C0005 | DESC1603,W912GB-14-C-0005 | 6125000 | 6125000 | 2019-06-02 | 2019-06-02 | 0 | 0 | 2019 | 06 | 02 | 20190602 | 2018 | 2019 | 1.1914 | 2019 | 1.1519 | 7297083.7836 | 7297083.7836 | 0 | 0 | 296 | 0%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC18S2 |  | 2019-07-16 | 2019-09-20 | Diversified Constr. | W912BV | W912BV19C0022 / 56986550 | W912BV19C0022 | DESC18S2,W912BV19C0022 / 56986550 | 6186000 | 6717000 | 2020-12-31 | 2021-10-01 | 531000 | 274 | 2021 | 10 | 01 | 20211001 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 6356678.7756 | 6875453.943 | 518775.1675 | 274 | 468 | 58.55%
2021-12-31 | 2018 | Army Active | 87205 |  | 2020-02-25 | 2020-04-30 | Allen-Batchelor Construction Co., Inc. | W912HN | W912HN20C3004 | W912HN20C3004 | 87205,W912HN20C3004 | 6187000 | 10773000 | 2022-10-01 | 2022-10-01 | 4586000 | 0 | 2022 | 10 | 01 | 20221001 | 2020 | 2023 | 1.0276 | 2022 | 0.95701 | 6357706.3667 | 10746563.5178 | 4388857.1511 | 0 | 884 | 0%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC19S2 |  | 2019-05-31 | 2019-06-28 | Dawson Pond | PLACE | PLACE HOLDER | PLACE | DESC19S2,PLACE HOLDER | 6193389 | 7190107 | 2022-10-03 | 2023-03-03 | 996718 | 151 | 2023 | 03 | 03 | 20230303 | 2019 | 2023 | 0.97698 | 2021 | #VALUE! | 6050803.0426 | #VALUE! | #VALUE! | 151 | 1193 | 12.66%
2021-12-31 | 2018 | Air Force Active | MSET153509 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153509,DIOCB2076 | 6211718 | 6211718 | 2023-12-26 | 2023-12-26 | 0 | 0 | 2023 | 12 | 26 | 20231226 | 2019 | 2024 | 1.0507 | 2022 | 0.97698 | 6526657.9159 | 6526657.9159 | 0 | 0 | 1868 | 0%
2022-01-31 | 2015 | DLA Defense Supply Center Richmond | DSCR1501 |  | 2016-11-08 | 2017-12-14 | SAW Contracting | W91236 | W91236-18-C-0008 | W9123618C0008 | DSCR1501,W91236-18-C-0008 | 6253160 | 7509000 | 2019-08-12 | 2020-10-12 | 1255840 | 427 | 2020 | 10 | 12 | 20201012 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 6425691.7964 | 7682298.288 | 1256606.4916 | 427 | 606 | 70.46%
2021-09-30 | 2017 | Air National Guard | LSGA019179 |  | 2018-05-22 | 2018-10-26 | ABBA Constrution Inc-Hold | W911YN | W911YN19C0001 | W911YN19C0001 | LSGA019179,W911YN19C0001 | 6346208 | 6410955 | 2024-04-20 | 2024-04-20 | 64747 | 0 | 2024 | 04 | 20 | 20240420 | 2019 | 2024 | 1.0507 | 2022 | 1.0276 | 6667966.6847 | 6734500.1281 | 66533.4434 | 0 | 2003 | 0%
2021-08-31 | 2019 | Army Active | 89227 |  | 2019-06-18 | 2019-08-19 | Heritage General Contracting | W911KB | W911KB-17-D-0010 | W911KB17D0010 | 89227,W911KB-17-D-0010 | 6390000 | 6770000 | 2020-11-21 | 2021-03-09 | 380000 | 108 | 2021 | 03 | 09 | 20210309 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 6713978.9801 | 7094210.91 | 380231.9299 | 108 | 460 | 23.48%
2021-12-30 | 2019 | Air National Guard | FMKM179063 |  | 2021-06-01 | 2021-10-06 | Max Gray Construction | W912LM | W912LM21R10010002 | W912LM21R10010002 | FMKM179063,W912LM21R10010002 | 6397054 | 6232840 | 2022-10-31 | 2022-10-31 | -164214 | 0 | 2022 | 10 | 31 | 20221031 | 2022 | 2023 | 1.1227 | 2023 | 0.97698 | 7181791.8472 | 7021358.4285 | -160433.4187 | 0 | 390 | 0%
2022-01-12 | 2017 | Navy Active | N61151190 | N61151190A | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N40080 | N4008017C0030 AWD | N4008017C0030 | N61151190,N4008017C0030 AWD | 6546000 | 4583000 | 2020-01-13 | 2021-02-11 | -1963000 | 395 | 2021 | 02 | 11 | 20210211 | 2017 | 2021 | 0.97698 | 2019 | 0.9382 | 6395296.1322 | 4553613.3312 | -1841682.801 | 395 | 991 | 39.86%
2022-01-06 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | AU AUTHUM KI, INC | W912PL | W912PL-14-C-0020 | W912PL14C0020 | 53542,W912PL-14-C-0020 | 6546920 | 6674183 | 2016-02-07 | 2016-02-20 | 127263 | 13 | 2016 | 02 | 20 | 20160220 | 2014 | 2016 | 1.0507 | 2015 | 1.0276 | 6878854.971 | 7009629.3019 | 130774.3309 | 13 | 500 | 2.6%
2021-08-31 | 2019 | Army Active | 74618 |  | 2019-02-22 | 2019-05-15 | Relyant Global LLC | W9128F | W9128F19C0022 | W9128F19C0022 | 74618,W9128F19C0022 | 6560000 | 6633000 | 2020-06-09 | 2020-12-01 | 73000 | 175 | 2020 | 12 | 01 | 20201201 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 6740997.861 | 6812317.2343 | 71319.3733 | 175 | 391 | 44.76%
2021-12-31 | 2018 | Air Force Active | ZHTV153201 |  | 2020-01-27 | 2020-04-14 | Butt Construction | W912QR | W912QR20C0011 | W912QR20C0011 | ZHTV153201,W912QR20C0011 | 6610000 | 6610000 | 2021-09-15 | 2021-09-15 | 0 | 0 | 2021 | 09 | 15 | 20210915 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 6792377.4178 | 6792377.4178 | 0 | 0 | 519 | 0%
2022-01-06 | 2008 | Special Operations Command | A73010 |  | 2009-02-13 | 2009-09-01 | IAP Worldwide Services, Inc. | W912ER | W912ER-09-C-0035 | W912ER09C0035 |  | 6639338 | 6799124 | 2011-02-05 | 2012-11-15 | 159786 | 649 | 2012 | 11 | 15 | 20121115 | 2009 | 2013 | 0.97698 | 2011 | 0.9382 | 6486485.2783 | 6636396.1942 | 149910.916 | 649 | 522 | 124.3%
2022-01-06 | 2010 | Special Operations Command | 64669 |  | 2010-03-29 | 2010-09-30 | Sauer, Inc. | W912HN | W912HN-10-C-0063 | W912HN10C0063 | 64669,W912HN-10-C-0063 | 6661700 | 7560146 | 2012-04-14 | 2013-03-01 | 898446 | 321 | 2013 | 03 | 01 | 20130301 | 2010 | 2013 | 1.0276 | 2012 | 0.97698 | 6845503.8796 | 7723265.6011 | 877761.7215 | 321 | 562 | 57.12%
2021-12-30 | 2018 | Air National Guard | CEKT139029 |  | 2018-06-30 | 2018-11-20 | LAROSA BUILDING GROUP, LLC | W91ZRS | W91ZRS18R00020002 | W91ZRS18R00020002 | CEKT139029,W91ZRS18R00020002 | 6707992 | 6353569 | 2024-05-20 | 2024-05-20 | -354423 | 0 | 2024 | 05 | 20 | 20240520 | 2019 | 2024 | 1.0276 | 2022 | 1.0006 | 6893073.1285 | 6538433.8094 | -354639.3192 | 0 | 2008 | 0%
2022-01-12 | 2020 | Navy Reserve | N00206475 |  | 2020-01-30 | 2020-08-13 | B.L. HARBERT INTERNATIONAL, L.L.C. | N69450 | N6945019D0908 N6945020F0891 | N6945019D0908 | N00206475,N6945019D0908 N6945020F0891 | 6796000 | 26130000 | 2023-03-06 | 2023-03-06 | 19334000 | 0 | 2023 | 03 | 06 | 20230306 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 6983509.3694 | 25872396.5401 | 18888887.1707 | 0 | 935 | 0%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1708 |  | 2017-03-31 | 2017-08-04 | NIPPO Corporation | W912HV | W912HV-17-C-0008 | W912HV17C0008 | DESC1708,W912HV-17-C-0008 | 6804938 | 6817433 | 2019-09-08 | 2022-09-08 | 12495 | 1096 | 2022 | 09 | 08 | 20220908 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 6809091.3379 | 6821298.6745 | 12207.3366 | 1096 | 765 | 143.3%
2021-12-30 | 2019 | Air National Guard | LKLW099101 |  | 2019-06-24 | 2019-08-12 | State of PA per MCCA | 421901 | 42190131 | 42190131 | LKLW099101,42190131 | 6923749 | 6767841 | 2021-11-07 | 2021-11-07 | -155908 | 0 | 2021 | 11 | 07 | 20211107 | 2019 | 2022 | 1.0507 | 2021 | 1.0276 | 7274789.5539 | 7114579.8749 | -160209.679 | 0 | 818 | 0%
2021-12-31 | 2019 | Army Active | 91311 |  | 2019-07-02 | 2019-08-26 | TDX Quality, LLC | W912HN | W912HN19C3010 | W912HN19C3010 | 91311,W912HN19C3010 | 6927000 | 6943000 | 2020-12-10 | 2021-10-14 | 16000 | 308 | 2021 | 10 | 14 | 20211014 | 2019 | 2022 | 1.0993 | 2021 | 1.0276 | 7614540.8482 | 7630982.3064 | 16441.4582 | 308 | 472 | 65.25%
2021-12-31 | 2017 | Missile Defense Agency | 653 |  | 2017-02-01 | 2017-07-25 | AMES 1/Conam JV | W911KB | W911KB-17-C-0029 | W911KB17C0029 | 653,W911KB-17-C-0029 | 6954581 | 8191098 | 2019-08-14 | 2021-09-29 | 1236517 | 777 | 2021 | 09 | 29 | 20210929 | 2017 | 2021 | 1.2082 | 2019 | 1.1914 | 8402707.9803 | 9875845.6372 | 1473137.6569 | 777 | 750 | 103.6%
2021-12-31 | 2015 | Army Reserve | 67567 |  | 2018-02-01 | 2018-08-09 | RELYANT GLOBAL LLC | W912QR | W912QR18C0026 | W912QR18C0026 | 67567,W912QR18C0026 | 7030000 | 7358000 | 2019-12-22 | 2021-12-15 | 328000 | 724 | 2021 | 12 | 15 | 20211215 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 7034290.7027 | 7354739.3937 | 320448.691 | 724 | 500 | 144.8%
2021-12-31 | 2020 | Army Active | 91397 |  | 2020-08-13 | 2020-09-24 | A.R. CHESSON CONSTRUCTION COMPANY | W912HN | W912HN20C3011 | W912HN20C3011 | 91397,W912HN20C3011 | 7034000 | 7027000 | 2021-11-15 | 2021-12-22 | -7000 | 37 | 2021 | 12 | 22 | 20211222 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 7228076.0601 | 7221237.216 | -6838.844 | 37 | 417 | 8.873%
2020-12-09 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10 | MWHL10-3001 | MWHL103001 | 18054,MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31 | 231000 | 576 | 2014 | 08 | 31 | 20140831 | 2012 | 2014 | 1.1227 | 2013 | 1.0751 | 7954129.391 | 8202472.3392 | 248342.9481 | 576 | 173 | 332.9%
2021-12-31 | 2015 | Air Force Active | PAYZ15001B |  | 2016-10-30 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB | W912GB15D00500002 | W912GB15D00500002 | PAYZ15001B,W912GB15D00500002 | 7097718 | 7097718 | 2018-07-07 | 2018-07-07 | 0 | 0 | 2018 | 07 | 07 | 20180707 | 2017 | 2018 | 1.2581 | 2018 | 1.2319 | 8929360.3368 | 8929360.3368 | 0 | 0 | 585 | 0%
2022-01-12 | 2019 | Navy Active | N00620258 |  | 2018-11-14 | 2019-02-26 | TOMPCO, INC | N44255 | N4425517D4014 N4425519F4091 | N4425517D4014 | N00620258,N4425517D4014 N4425519F4091 | 7114000 | 7063000 | 2021-03-08 | 2021-01-29 | -51000 | -38 | 2021 | 01 | 29 | 20210129 | 2019 | 2021 | 1.2581 | 2020 | 1.2082 | 8949844.0817 | 8888224.5381 | -61619.5436 | -38 | 741 | -5.128%
2022-01-12 | 2020 | Navy Active | N62863605 |  | 2020-09-03 | 2021-04-12 | UTE CASTELLANO COBRA MACC | N33191 | N3319119D0801 N3319121F4133 | N3319119D0801 | N62863605,N3319119D0801 N3319121F4133 | 7127000 | 9126000 | 2023-01-17 | 2023-01-17 | 1999000 | 0 | 2023 | 01 | 17 | 20230117 | 2021 | 2023 | 1.0006 | 2022 | 0.9382 | 7131349.9058 | 9006807.8371 | 1875457.9313 | 0 | 645 | 0%
2022-01-06 | 2009 | Special Operations Command | 63711 |  | 2010-10-28 | 2011-03-30 | Carothers Construction, Inc. | W91278 | W91278-07-D-0026 | W9127807D0026 | 63711,W91278-07-D-0026 | 7175815 | 9584934 | 2012-10-13 | 2013-10-10 | 2409119 | 362 | 2013 | 10 | 10 | 20131010 | 2011 | 2014 | 0.97698 | 2013 | 0.95701 | 7010611.3527 | 9316167.2077 | 2305555.855 | 362 | 563 | 64.3%
2022-01-06 | 2008 | Special Operations Command | 65397 |  | 2007-11-26 | 2008-03-28 | ACC Construction Co. | W912HN | W912HN-07-D-0042 | W912HN07D0042 |  | 7184356 | 7193709 | 2010-04-21 | 2010-07-31 | 9353 | 101 | 2010 | 07 | 31 | 20100731 | 2008 | 2010 | 1.0276 | 2009 | 0.97698 | 7382580.5531 | 7391718.2257 | 9137.6726 | 101 | 754 | 13.4%
2022-01-06 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278 | W91278-11-D-0029 | W9127811D0029 | 79438,W91278-11-D-0029 | 7193631 | 7896819 | 2016-04-19 | 2016-10-26 | 703188 | 190 | 2016 | 10 | 26 | 20161026 | 2014 | 2017 | 1.0006 | 2016 | 1.0006 | 7198021.5735 | 7901638.7585 | 703617.185 | 190 | 600 | 31.67%
2021-12-08 | 2017 | Washington Headquarters Services | 87744 |  | 2019-03-27 | 2020-01-21 | M.A. Mortenson Company | W912DR | W912DR-16-D-0017 | W912DR16D0017 | 87744,W912DR-16-D-0017 | 7232827 |  | 2021-08-13 | 2021-08-13 | -7232827 | 0 | 2021 | 08 | 13 | 20210813 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 7432388.9231 | 366078.1169 | -7066310.8063 | 0 | 570 | 0%
2021-12-30 | 2018 | Air National Guard | LRXQ159097 |  | 2021-06-24 | 2021-09-29 | Codaray Construction | W9127Q | W9127Q21C0015 | W9127Q21C0015 | LRXQ159097,W9127Q21C0015 | 7233035 | 7123500 | 2022-12-28 | 2022-12-28 | -109535 | 0 | 2022 | 12 | 28 | 20221228 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 7432602.6621 | 7325589.4079 | -107013.2542 | 0 | 455 | 0%
2021-12-30 | 2019 | Air National Guard | RQLH059034 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N69450 | N6945021C0005 | N6945021C0005 | RQLH059034,N6945021C0005 | 7261649 | 6401000 | 2024-10-01 | 2024-10-01 | -860649 | 0 | 2024 | 10 | 01 | 20241001 | 2021 | 2025 | 1.1743 | 2023 | 1.0507 | 8527488.7455 | 7623204.0358 | -904284.7097 | 0 | 1300 | 0%
2022-01-12 | 2019 | Marine Corps Active | M670011525F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011525F,N4008520C0044 AWD | 7375000 | 7549000 | 2020-12-29 | 2025-01-11 | 174000 | 1474 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0276 | 2023 | 0.97698 | 7578484.6379 | 7748478.7606 | 169994.1227 | 1474 | 158 | 932.9%
2022-01-12 | 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N62473 | N6247315D2403 0003 | N6247315D2403 | N63042218,N6247315D2403 0003 | 7386000 | 7509000 | 2017-11-16 | 2020-09-17 | 123000 | 1036 | 2020 | 09 | 17 | 20200917 | 2016 | 2020 | 1.0751 | 2018 | 1.0276 | 7940523.8737 | 8066917.5836 | 126393.7099 | 1036 | 555 | 186.7%
2021-11-16 | 2019 | Army National Guard | 390285 |  | 2020-08-06 | 2020-09-02 | USPFO - OH | W91364 | W91364-20-B-0001 | W9136420B0001 | 390285,W91364-20-B-0001 | 7400000 | 6945000 | 2022-09-30 | 2022-09-30 | -455000 | 0 | 2022 | 09 | 30 | 20220930 | 2020 | 2022 | 1.0751 | 2021 | 1.0276 | 7955574.9614 | 7488020.9939 | -467553.9675 | 0 | 758 | 0%
2022-01-12 | 2019 | Army National Guard | 390285 |  | 2020-08-06 | 2020-09-30 | USPFO for Ohio | W91364 | W9136420C0002 | W9136420C0002 | 390285,W9136420C0002 | 7400000 | 6945000 | 2022-09-30 | 2022-09-30 | -455000 | 0 | 2022 | 09 | 30 | 20220930 | 2020 | 2022 | 1.1227 | 2021 | 1.0276 | 8307770.9942 | 7840217.0267 | -467553.9675 | 0 | 730 | 0%
2021-12-30 | 2019 | DLA Defense Energy Support Center | DESC1609 |  | 2018-08-01 | 2019-06-28 | SES Energy Services, LLC | W9128F | W9128F19C0032 / 42718510 | W9128F19C0032 | DESC1609,W9128F19C0032 / 42718510 | 7499541 | 7716000 | 2019-07-06 | 2021-07-15 | 216459 | 740 | 2021 | 07 | 15 | 20210715 | 2019 | 2021 | 1.1743 | 2020 | 1.0993 | 8806849.7216 | 9044793.4054 | 237943.6838 | 740 | 8 | 9250%
2020-12-09 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10 | MWHL10-3001 | MWHL103001 | 18052,MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14 | 691000 | 467 | 2014 | 05 | 14 | 20140514 | 2011 | 2014 | 1.0507 | 2013 | 1.0276 | 7949603.2807 | 8659668.7566 | 710065.4759 | 467 | 689 | 67.78%
2021-12-30 | 2019 | Air National Guard | MUHJ179000 |  | 2020-11-03 | 2020-12-23 | Ocean Construction Services | W91236 | W9123621C2013 | W9123621C2013 | MUHJ179000,W9123621C2013 | 7644604 | 6748367 | 2023-01-31 | 2023-01-31 | -896237 | 0 | 2023 | 01 | 31 | 20230131 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 7855527.3189 | 6979923.7412 | -875603.5777 | 0 | 769 | 0%
2021-12-31 | 2017 | Air Force Active | FTFA043000 |  | 2018-06-07 | 2019-03-15 | Speegle | W91278 | W9127816D0031 | W9127816D0031 | FTFA043000,W9127816D0031 | 7687194 | 7712303 | 2020-03-16 | 2020-03-16 | 25109 | 0 | 2020 | 03 | 16 | 20200316 | 2019 | 2020 | 1.0006 | 2020 | 0.9382 | 7691885.8156 | 7715443.0308 | 23557.2152 | 0 | 367 | 0%
2022-01-06 | 2019 | Special Operations Command | 80772 |  | 2020-07-10 | 2021-05-10 | HSU Development, Inc | W912DR | W912DR-17-D-0015 | W912DR17D0015 | 80772,W912DR-17-D-0015 | 7745692 | 8571497 | 2023-06-10 | 2023-04-05 | 825805 | -66 | 2023 | 04 | 05 | 20230405 | 2021 | 2023 | 1.0751 | 2022 | 1.0276 | 8327220.7208 | 9175810.62 | 848589.8992 | -66 | 761 | -8.673%
2022-01-13 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR | W912DR-15-C-0025 | W912DR15C0025 | 58395,W912DR-15-C-0025 | 7750000 | 7335000 | 2017-03-31 | 2017-05-04 | -415000 | 34 | 2017 | 05 | 04 | 20170504 | 2015 | 2017 | 1.0507 | 2016 | 0.97698 | 8142932.2529 | 7737486.5006 | -405445.7523 | 34 | 560 | 6.071%
2022-01-12 | 2021 | Army National Guard | 481315 |  | 2021-09-01 | 2021-09-20 | SMR Construction, Inc | W912l1 | W912l1-20-2-2002 | W912l12022002 | 481315,W912l1-20-2-2002 | 7800000 | 9228000 | 2023-03-15 | 2023-03-15 | 1428000 | 0 | 2023 | 03 | 15 | 20230315 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 7804760.6658 | 9199884.845 | 1395124.1792 | 0 | 541 | 0%
2021-12-30 | 2018 | Air National Guard | KJAQ159096 |  | 2020-09-23 | 2021-02-19 | Ahtna Environmental Inc | W50S8Z | W50S8Z21C0001 | W50S8Z21C0001 | KJAQ159096,W50S8Z21C0001 | 7873129 | 7697582 | 2022-05-05 | 2022-05-05 | -175547 | 0 | 2022 | 05 | 05 | 20220505 | 2021 | 2022 | 1.0006 | 2022 | 0.95701 | 7877934.2995 | 7709933.7094 | -168000.5901 | 0 | 440 | 0%
2022-01-13 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR | W912DR-09-C-0052 | W912DR09C0052 |  | 7915345 | 37771000 | 2013-06-01 | 2015-06-10 | 29855655 | 739 | 2015 | 06 | 10 | 20150610 | 2009 | 2015 | 0.97698 | 2012 | 0.9382 | 7733115.6834 | 35743633.4242 | 28010517.7408 | 739 | 1387 | 53.28%
2021-12-31 | 2021 | Army Reserve | 88752 |  | 2021-08-23 | 2021-09-29 | R. ZOPPO CORPORATION | W912QR | W912QR21C0054 | W912QR21C0054 | 88752,W912QR21C0054 | 7933000 | 7933000 | 2023-11-08 | 2023-11-08 | 0 | 0 | 2023 | 11 | 08 | 20231108 | 2021 | 2024 | 1.0276 | 2023 | 0.95701 | 8151880.4925 | 8151880.4925 | 0 | 0 | 770 | 0%
2021-12-31 | 2017 | Army Active | 77538 |  | 2018-02-12 | 2018-07-09 | GEC-HHI Joint Venture | W91238 | W9123818C0020 | W9123818C0020 | 77538,W9123818C0020 | 7970000 | 10413000 | 2020-02-22 | 2022-01-23 | 2443000 | 701 | 2022 | 01 | 23 | 20220123 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 8189901.3646 | 10634392.4296 | 2444491.065 | 701 | 593 | 118.2%
2021-12-31 | 2018 | Air Force Active | PTFL163010 |  | 2019-06-12 | 2019-09-25 | TDX Quality | W912DS | W912DS19B007 | W912DS19B007 | PTFL163010,W912DS19B007 | 7994996 | 8056120 | 2021-03-19 | 2021-05-14 | 61124 | 56 | 2021 | 05 | 14 | 20210514 | 2019 | 2021 | 1.2082 | 2020 | 1.1743 | 9659764.7926 | 9731543.8365 | 71779.0439 | 56 | 541 | 10.35%
2021-11-19 | 2018 | Air National Guard | XHZG179037 |  | 2019-06-10 | 2019-10-03 | Military Construction Cooperative Agreement | W9128F | W9128F21C0040 | W9128F21C0040 | XHZG179037,W9128F21C0040 | 8000000 | 8000000 | 2020-11-01 | 2020-11-01 | 0 | 0 | 2020 | 11 | 01 | 20201101 | 2020 | 2021 | 0.97698 | 2021 | 0.9382 | 7815821.732 | 7815821.732 | 0 | 0 | 395 | 0%
2021-11-30 | 2018 | Air National Guard | XHZG179037 |  | 2019-09-15 | 2019-10-03 | Military Construction Cooperative Agreement | W912L1 | W912L1922101 | W912L1922101 | XHZG179037,W912L1922101 | 8000000 | 8000000 | 2020-11-01 | 2020-11-01 | 0 | 0 | 2020 | 11 | 01 | 20201101 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 8220729.0987 | 8220729.0987 | 0 | 0 | 395 | 0%
2021-12-30 | 2018 | Air National Guard | XHZG179037 |  | 2019-09-15 | 2019-10-03 | MCCA: | W912L6 | W912L61922101 | W912L61922101 | XHZG179037,W912L61922101 | 8000000 | 8000000 | 2020-11-01 | 2020-11-01 | 0 | 0 | 2020 | 11 | 01 | 20201101 | 2020 | 2021 | 1.0751 | 2021 | 1.0276 | 8600621.5799 | 8600621.5799 | 0 | 0 | 395 | 0%
2021-12-31 | 2018 | Air Force Active | FTFA163003 |  | 2018-06-28 | 2018-09-28 | Speegle Constrcution, Inc | W91278 | W9127818C0026 | W9127818C0026 | FTFA163003,W9127818C0026 | 8007902 | 8052184 | 2020-08-22 | 2020-09-25 | 44282 | 34 | 2020 | 09 | 25 | 20200925 | 2018 | 2020 | 1.2319 | 2019 | 1.1914 | 9865232.0118 | 9917987.8426 | 52755.8309 | 34 | 694 | 4.899%
2022-01-12 | 2020 | Army National Guard | 280408 |  | 2020-07-20 | 2020-07-31 | Chris Albrition Construction | NGB22- | NGB22-20-C-0002 | NGB2220C0002 | 280408,NGB22-20-C-0002 | 8100000 | 6069000 | 2021-09-30 | 2022-05-14 | -2031000 | 226 | 2022 | 05 | 14 | 20220514 | 2020 | 2022 | 1.1227 | 2021 | 1.0507 | 9093641.2233 | 6959667.6226 | -2133973.6007 | 226 | 426 | 53.05%
2021-12-31 | 2018 | Air Force Active | NVZR153711 |  | 2019-07-19 | 2019-09-26 | Southeast Cherokee Constr. Inc | W91278 | W9127816D0015 | W9127816D0015 | NVZR153711,W9127816D0015 | 8163765 | 8163765 | 2021-06-17 | 2021-06-17 | 0 | 0 | 2021 | 06 | 17 | 20210617 | 2019 | 2021 | 1.0751 | 2020 | 1.0276 | 8776681.6791 | 8776681.6791 | 0 | 0 | 630 | 0%
2021-12-30 | 2018 | Air National Guard | TDKA169004 |  | 2020-07-17 | 2021-03-01 | Qayaq Gov. Solutions | W50S6V | W50S6V21C0001 | W50S6V21C0001 | TDKA169004,W50S6V21C0001 | 8176132 | 7902831 | 2022-03-26 | 2022-03-26 | -273301 | 0 | 2022 | 03 | 26 | 20220326 | 2021 | 2022 | 1.0507 | 2022 | 1.0006 | 8590669.5441 | 8317201.7371 | -273467.807 | 0 | 390 | 0%
2021-12-30 | 2019 | Air National Guard | JLQN049119 |  | 2019-02-18 | 2019-06-01 | A. WBE-CCI Joint Venture One, LLC | W91SMC | W91SMC19C6001 | W91SMC19C6001 | JLQN049119,W91SMC19C6001 | 8184676 | 7901690 | 2023-10-18 | 2023-10-18 | -282986 | 0 | 2023 | 10 | 18 | 20231018 | 2019 | 2024 | 1.0751 | 2022 | 1.0006 | 8799162.6288 | 8516003.9106 | -283158.7182 | 0 | 1600 | 0%
2021-12-31 | 2018 | Air Force Active | ASVF183100C |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc, (Pkg 2, Aprons) | W912ER | W912ER20C0009 | W912ER20C0009 | ASVF183100C,W912ER20C0009 | 8267668 | 8267668 | 2023-03-28 | 2023-03-28 | 0 | 0 | 2023 | 03 | 28 | 20230328 | 2020 | 2023 | 1.0006 | 2022 | 0.95701 | 8272714.1032 | 8272714.1032 | 0 | 0 | 1082 | 0%
2022-01-06 | 2012 | Special Operations Command | 60272 |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN | W912HN-10-D-0049 | W912HN10D0049 | 60272,W912HN-10-D-0049 | 8290317 | 8465679 | 2014-03-06 | 2015-02-18 | 175362 | 349 | 2015 | 02 | 18 | 20150218 | 2012 | 2015 | 1.0507 | 2014 | 1.0006 | 8710643.8305 | 8886112.8612 | 175469.0308 | 349 | 590 | 59.15%
2021-12-31 | 2019 | Army Active | 75157 |  | 2020-05-22 | 2020-08-13 | NASCO | W9126G | W9126G20C0005 | W9126G20C0005 | 75157,W9126G20C0005 | 8315000 | 8403000 | 2022-02-25 | 2022-05-28 | 88000 | 92 | 2022 | 05 | 28 | 20220528 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 8544420.307 | 8630394.346 | 85974.0391 | 92 | 561 | 16.4%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC1909 |  | 2019-08-01 | 2019-09-30 | Rockford | W91236 | W9123619C0044 / 56765125 | W9123619C0044 | DESC1909,W9123619C0044 / 56765125 | 8330000 | 8453000 | 2020-12-04 | 2021-08-16 | 123000 | 255 | 2021 | 08 | 16 | 20210816 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 8559834.174 | 8682909.2461 | 123075.072 | 255 | 431 | 59.16%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC19I1 |  | 2019-03-29 | 2019-06-10 | Diversified Construction of Oklahoma | W9126G | W9126G19C0026 / 56924533 | W9126G19C0026 | DESC19I1,W9126G19C0026 / 56924533 | 8330000 | 8453000 | 2020-09-30 | 2022-02-28 | 123000 | 516 | 2022 | 02 | 28 | 20220228 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 8138224.3784 | 8253622.7404 | 115398.362 | 516 | 478 | 107.9%
2021-12-31 | 2018 | Air Force Active | MHMV083126A |  | 2020-08-14 | 2020-11-20 | Encanto Facillity Services 2 | W912PP | W912PP19D0037 | W912PP19D0037 | MHMV083126A,W912PP19D0037 | 8427275 | 8427275 | 2022-04-11 | 2022-04-11 | 0 | 0 | 2022 | 04 | 11 | 20220411 | 2021 | 2022 | 1.1743 | 2022 | 1.0751 | 9896304.9189 | 9896304.9189 | 0 | 0 | 507 | 0%
2022-01-06 | 2015 | Special Operations Command | 57442 |  | 2016-03-23 | 2017-03-17 | Brantley Construction Services, LLC | W912HN | W912HN-17-C-0006 | W912HN17C0006 | 57442,W912HN-17-C-0006 | 8456354 | 8826862 | 2018-10-19 | 2019-02-07 | 370508 | 111 | 2019 | 02 | 07 | 20190207 | 2017 | 2019 | 0.97698 | 2018 | 0.95701 | 8261669.4208 | 8616250.0325 | 354580.6117 | 111 | 581 | 19.1%
2022-01-06 | 2016 | Special Operations Command | 76518 |  | 2015-11-23 | 2016-03-17 | Bristol Environmental Remediation Servic | W912DY | W912DY-12-D-0053 | W912DY12D0053 | 76518,W912DY-12-D-0053 | 8465006 | 9128867 | 2017-05-17 | 2018-01-12 | 663861 | 240 | 2018 | 01 | 12 | 20180112 | 2016 | 2018 | 1.0006 | 2017 | 0.97698 | 8470172.5468 | 9118749.9506 | 648577.4038 | 240 | 426 | 56.34%
2022-01-06 | 2011 | Special Operations Command | 69573 |  | 2011-05-26 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN | W912HN-10-D-0058 | W912HN10D0058 | 69573,W912HN-10-D-0058 | 8487000 | 9279066 | 2013-03-29 | 2014-01-23 | 792066 | 300 | 2014 | 01 | 23 | 20140123 | 2011 | 2014 | 1.0006 | 2013 | 0.97698 | 8492179.9706 | 9266010.8026 | 773830.832 | 300 | 550 | 54.55%
2021-12-30 | 2018 | Air National Guard | WEAS079054 |  | 2020-04-17 | 2020-06-15 | Wescott Construction | W912KZ | W912KZ1922101 | W912KZ1922101 | WEAS079054,W912KZ1922101 | 8489791 | 7662000 | 2021-11-17 | 2021-11-17 | -827791 | 0 | 2021 | 11 | 17 | 20211117 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 8294336.6247 | 7502130.6827 | -792205.942 | 0 | 520 | 0%
2022-01-12 | 2018 | Army National Guard | 190130 |  | 2018-08-27 | 2018-08-30 | Rochon Corp of Iowa | C85148 | C85148014 | C85148014 | 190130,C85148014 | 8500000 | 6667000 | 2019-12-31 | 2021-04-30 | -1833000 | 486 | 2021 | 04 | 30 | 20210430 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 8304310.5902 | 6550107.5466 | -1754203.0436 | 486 | 488 | 99.59%
2021-12-30 | 2015 | DLA Defense Energy Support Center | DESC1463 |  | 2015-04-14 | 2015-09-30 | Structural Asspcoates Omc. | W9128F | W9128F-15-C-0032 | W9128F15C0032 | DESC1463,W9128F-15-C-0032 | 8518820 | 8267000 | 2017-04-16 | 2017-06-15 | -251820 | 60 | 2017 | 06 | 15 | 20170615 | 2015 | 2017 | 1.0507 | 2016 | 1.0006 | 8950732.1464 | 8698758.4501 | -251973.6963 | 60 | 564 | 10.64%
2022-01-12 | 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N62478 | N6247814D4001 KB01 | N6247814D4001 | N62813036,N6247814D4001 KB01 | 8520000 | 9184000 | 2018-03-26 | 2021-02-06 | 664000 | 1048 | 2021 | 02 | 06 | 20210206 | 2016 | 2021 | 1.0006 | 2019 | 0.97698 | 8525200.1119 | 9173913.3157 | 648713.2038 | 1048 | 790 | 132.7%
2021-12-31 | 2018 | Air Force Reserve | KNMD624007 |  | 2020-09-01 | 2020-12-17 | Hensel Phelps Construction Co. | N62478 | N6247820D4003 | N6247820D4003 | KNMD624007,N6247820D4003 | 8552000 | 8552000 | 2022-07-11 | 2022-07-11 | 0 | 0 | 2022 | 07 | 11 | 20220711 | 2021 | 2022 | 1.0751 | 2022 | 1.0276 | 9194064.4689 | 9194064.4689 | 0 | 0 | 571 | 0%
2022-01-12 | 2018 | Army National Guard | 350200 |  | 2018-09-25 | 2018-09-27 | Jaynes Corporation | W912J3 | W912J3-16-2-2001 | W912J31622001 | 350200,W912J3-16-2-2001 | 8600000 | 10566000 | 2020-10-01 | 2021-02-26 | 1966000 | 148 | 2021 | 02 | 26 | 20210226 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 8837283.7811 | 10758021.9718 | 1920738.1906 | 148 | 735 | 20.14%
2022-01-12 | 2016 | Marine Corps Active | M67004972 |  | 2016-12-14 | 2017-03-22 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N69450 | N6945016D1112 WE01 | N6945016D1112 | M67004972,N6945016D1112 WE01 | 8625000 | 8378000 | 2019-01-28 | 2019-02-23 | -247000 | 26 | 2019 | 02 | 23 | 20190223 | 2017 | 2019 | 1.0276 | 2018 | 1.0006 | 8862973.5596 | 8615822.8051 | -247150.7544 | 26 | 677 | 3.84%
2021-12-30 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS | W912DS-14-C-0030 | W912DS14C0030 | DESC1501,W912DS-14-C-0030 | 8637000 | 9333465 | 2016-05-11 | 2020-11-03 | 696465 | 1637 | 2020 | 11 | 03 | 20201103 | 2014 | 2021 | 1.0751 | 2018 | 1.0006 | 9285446.0732 | 9982336.1549 | 696890.0817 | 1637 | 589 | 277.9%
2021-08-31 | 2017 | Army Active | 75660 |  | 2018-02-28 | 2018-12-21 | Zodiac-Poettker Joint Venture II, LLC | W912DQ | W912DQ19C4000 | W912DQ19C4000 | 75660,W912DQ19C4000 | 8690000 | 9023000 | 2020-02-05 | 2020-11-20 | 333000 | 289 | 2020 | 11 | 20 | 20201120 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 9130591.1326 | 9463794.3764 | 333203.2438 | 289 | 411 | 70.32%
2022-01-12 | 2016 | Navy Active | N41557635 |  | 2016-06-24 | 2017-08-01 | TIKIGAQ CONSTRUCTION, LLC | N40192 | N4019217C1305 AWD | N4019217C1305 | N41557635,N4019217C1305 AWD | 8715000 | 11425000 | 2019-02-22 | 2022-01-09 | 2710000 | 1052 | 2022 | 01 | 09 | 20220109 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 8955456.7619 | 11667110.7881 | 2711654.0262 | 1052 | 570 | 184.6%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1706 |  | 2017-09-18 | 2017-09-19 | Cape Environemental | N63450 | N63450-17-C-1305 | N6345017C1305 | DESC1706,N63450-17-C-1305 | 8783275 | 8783275 | 2019-04-04 | 2019-04-26 | 0 | 22 | 2019 | 04 | 26 | 20190426 | 2017 | 2019 | 0.97698 | 2018 | 0.95701 | 8581063.9528 | 8581063.9528 | 0 | 22 | 562 | 3.915%
2022-01-12 | 2016 | Marine Corps Active | M67400606 |  | 2016-07-20 | 2016-09-15 | NAVY STANDARD DOCUMENT | N40085 | N4008516C5505 AWD | N4008516C5505 | M67400606,N4008516C5505 AWD | 8792000 | 8792000 | 2019-08-03 | 2018-03-26 | 0 | -495 | 2018 | 03 | 26 | 20180326 | 2016 | 2018 | 1.0751 | 2017 | 1.0006 | 9452083.1163 | 9452083.1163 | 0 | -495 | 1052 | -47.05%
2022-01-06 | 2019 | Special Operations Command | 81899 |  | 2019-01-10 | 2019-04-19 | A4 Construction Co. | W9128F | W9128F19C0016 | W9128F19C0016 | 81899,W9128F19C0016 | 8794325 | 9276699 | 2021-05-31 | 2022-08-15 | 482374 | 441 | 2022 | 08 | 15 | 20220815 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 8591859.5566 | 9044421.9099 | 452562.3533 | 441 | 773 | 57.05%
2022-02-28 | 2015 | Defense Information Systems Agency | 15DISA02 |  | 2018-05-02 | 2018-08-09 | Cockram Construction Australia Pty Ltd. 675 Victoria Street, Abbotsford Victoria 3067, Austrialia | N62742 | N6274218C1306 | N6274218C1306 | 15DISA02,N6274218C1306 | 8794967 | 12189000 | 2019-03-31 | 2020-03-31 | 3394033 | 366 | 2020 | 03 | 31 | 20200331 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 8800334.9358 | 12116229.5458 | 3315894.61 | 366 | 234 | 156.4%
2022-01-06 | 2019 | Special Operations Command | 67039 |  | 2018-11-27 | 2019-05-23 | Howard W. Pence, Inc | W912QR | W912QR19C0017 | W912QR19C0017 | 67039,W912QR19C0017 | 8825159 | 9122816 | 2020-12-03 | 2021-02-16 | 297657 | 75 | 2021 | 02 | 16 | 20210216 | 2019 | 2021 | 1.1743 | 2020 | 1.0751 | 10363547.4601 | 10683551.8623 | 320004.4022 | 75 | 560 | 13.39%
2022-01-12 | 2016 | Navy Active | M62613603 |  | 2016-03-01 | 2018-12-18 | Awarded by Other Agency | N40084 | N40084USACE02 AWD | N40084USACE02 | M62613603,N40084USACE02 AWD | 8904000 | 8904000 | 2020-07-08 | 2021-03-12 | 0 | 247 | 2021 | 03 | 12 | 20210312 | 2019 | 2021 | 1.0751 | 2020 | 1.0276 | 9572491.8185 | 9572491.8185 | 0 | 247 | 568 | 43.49%
2021-12-31 | 2015 | Army Active | 76093 |  | 2018-06-29 | 2019-05-31 | ARS Aleut Construction | W91238 | W9123819C0015 | W9123819C0015 | 76093,W9123819C0015 | 8916000 | 10402000 | 2020-06-02 | 2022-02-25 | 1486000 | 633 | 2022 | 02 | 25 | 20220225 | 2019 | 2022 | 1.2826 | 2021 | 1.2581 | 11435340.0678 | 13304818.3228 | 1869478.2549 | 633 | 368 | 172%
2022-01-13 | 2018 | Defense Health Agency | 67402 |  | 2019-07-29 | 2020-01-30 | SGS, LLC | W9126G | W9126G-20-C-0009 | W9126G20C0009 | 67402,W9126G-20-C-0009 | 8996000 | 9321000 | 2022-04-03 | 2022-04-03 | 325000 | 0 | 2022 | 04 | 03 | 20220403 | 2020 | 2022 | 1.1227 | 2021 | 1.0276 | 10099555.1167 | 10433522.2363 | 333967.1196 | 0 | 794 | 0%
2022-01-12 | 2019 | Marine Corps Active | M006815001 |  | 2019-01-30 | 2019-04-09 | BARNHART-REESE CONSTRUCTION INC | N62473 | N6247317D4635 | N6247317D4635 | M006815001,N6247317D4635 | 9032000 | 8888000 | 2020-10-15 | 2021-08-25 | -144000 | 314 | 2021 | 08 | 25 | 20210825 | 2019 | 2021 | 1.1519 | 2020 | 1.1227 | 10403668.1173 | 10242003.3845 | -161664.7329 | 314 | 555 | 56.58%
2022-01-12 | 2019 | Navy Active | N61056512 |  | 2018-10-31 | 2019-04-19 | Awarded by Other Agency | N40084 | N40084USACE01 AWD | N40084USACE01 | N61056512,N40084USACE01 AWD | 9050000 | 9050000 | 2020-12-31 | 2020-12-31 | 0 | 0 | 2020 | 12 | 31 | 20201231 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 8841648.3343 | 8841648.3343 | 0 | 0 | 622 | 0%
2022-01-06 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt, LLC | W9128F | W9128F-16-C-0033 | W9128F16C0033 | 47942,W9128F-16-C-0033 | 9065868 | 9433554 | 2018-05-30 | 2018-10-10 | 367686 | 133 | 2018 | 10 | 10 | 20181010 | 2016 | 2019 | 1.0006 | 2018 | 0.97698 | 9071401.278 | 9430622.3066 | 359221.0287 | 133 | 705 | 18.87%
2022-01-12 | 2018 | Navy Active | N00213731 |  | 2019-06-25 | 2019-09-19 | BURNS & MCDONNELL ENGINEERINGCOMPANY, INC. | N69450 | N6945016D0100 N6945019F0105 | N6945016D0100 | N00213731,N6945016D0100 N6945019F0105 | 9097000 | 8772000 | 2020-11-30 | 2021-12-23 | -325000 | 388 | 2021 | 12 | 23 | 20211223 | 2019 | 2022 | 1.1519 | 2021 | 1.1227 | 10478539.511 | 10113671.1903 | -364868.3207 | 388 | 438 | 88.58%
2021-12-31 | 2019 | Air Force Active | SGBP1047602 |  | 2019-03-18 | 2019-05-20 | Sapper Construction - PARKING LOT, USSTRATCOM | W9128F | W9128F19C0023 | W9128F19C0023 | SGBP1047602,W9128F19C0023 | 9132924 | 9132924 | 2019-06-19 | 2020-08-21 | 0 | 429 | 2020 | 08 | 21 | 20200821 | 2019 | 2020 | 1.1914 | 2020 | 1.1519 | 10880605.9783 | 10880605.9783 | 0 | 429 | 30 | 1430%
2021-12-30 | 2020 | Air National Guard | TUMR189003 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N69450 | N6945021C0031 | N6945021C0031 | TUMR189003,N6945021C0031 | 9201235 | 7791000 | 2024-02-28 | 2024-02-28 | -1410235 | 0 | 2024 | 02 | 28 | 20240228 | 2021 | 2024 | 1.0751 | 2023 | 1.0276 | 9892042.5379 | 8442897.5503 | -1449144.9876 | 0 | 923 | 0%
2022-01-31 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N62470 | N6247016C6003 | N6247016C6003 | AM00115,N6247016C6003 | 9233000 | 8557000 | 2019-03-27 | 2021-04-21 | -676000 | 756 | 2021 | 04 | 21 | 20210421 | 2016 | 2021 | 1.0507 | 2019 | 1.0507 | 9701121.7408 | 8990847.9081 | -710273.8326 | 756 | 980 | 77.14%
2022-01-06 | 2008 | Special Operations Command | 53712A |  | 2008-05-16 | 2008-10-16 | Rush-PEAK Three, JV | W91278 | W91278-09-C-0003 | W9127809C0003 |  | 9243000 | 9544521 | 2010-06-05 | 2010-06-07 | 301521 | 2 | 2010 | 06 | 07 | 20100607 | 2009 | 2010 | 1.0006 | 2010 | 0.97698 | 9248641.389 | 9543220.6871 | 294579.2981 | 2 | 597 | 0.335%
2022-01-07 | 2019 | Washington Headquarters Services | 87645 |  | 2019-07-22 | 2019-09-30 | John C. Grimberg Co, Inc. | W912DR | W912DR19C0057 | W912DR19C0057 | 87645,W912DR19C0057 | 9255000 | 9255000 | 2021-04-23 | 2022-04-22 | 0 | 364 | 2022 | 04 | 22 | 20220422 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 9949844.0903 | 9949844.0903 | 0 | 364 | 571 | 63.75%
2021-12-31 | 2019 | Air Force Active | FTQW1053834 |  | 2019-01-03 | 2019-07-18 | F-35 Aircraft Maintenance Unit Admin | W911KB | W911KB19R0008 | W911KB19R0008 | FTQW1053834,W911KB19R0008 | 9258084 | 9258084 | 2021-03-10 | 2022-06-17 | 0 | 464 | 2022 | 06 | 17 | 20220617 | 2019 | 2022 | 1.1914 | 2021 | 1.1743 | 11029716.6732 | 11029716.6732 | 0 | 464 | 601 | 77.2%
2022-01-12 | 2021 | Army National Guard | 411508 |  | 2021-09-23 | 2021-09-27 | Fowler General Construction, Inc. | 219995 | 219995C001 | 219995C001 | 411508,219995C001 | 9300000 | 7792000 | 2023-10-30 | 2023-10-30 | -1508000 | 0 | 2023 | 10 | 30 | 20231030 | 2021 | 2024 | 1.0006 | 2023 | 0.9382 | 9305676.1785 | 7890873.497 | -1414802.6815 | 0 | 763 | 0%
2022-01-12 | 2021 | Army National Guard | 310140 |  | 2021-01-14 | 2021-02-06 | Perry Reid Construction | W91243 | W91243-18-2-2001 | W912431822001 | 310140,W91243-18-2-2001 | 9300000 | 8685000 | 2022-09-20 | 2022-09-20 | -615000 | 0 | 2022 | 09 | 20 | 20220920 | 2021 | 2022 | 1.0006 | 2022 | 0.95701 | 9305676.1785 | 8717113.7825 | -588562.396 | 0 | 591 | 0%
2022-01-06 | 2010 | Special Operations Command | 61874 |  | 2010-06-16 | 2010-09-30 | Windamir Development, Inc | W912HN | W912HN-10-D-0059 | W912HN10D0059 | 61874,W912HN-10-D-0059 | 9327304 | 12372455 | 2012-03-16 | 2013-06-04 | 3045151 | 445 | 2013 | 06 | 04 | 20130604 | 2010 | 2013 | 1.0507 | 2012 | 1.0276 | 9800207.0418 | 12929377.2213 | 3129170.1795 | 445 | 533 | 83.49%
2022-01-12 | 2016 | Marine Corps Active | M673991232 |  | 2017-06-27 | 2017-09-26 | PROCAL ELECTRIC INC | N62473 | N6247316D1861 N6247317F4699 | N6247316D1861 | M673991232,N6247316D1861 N6247317F4699 | 9329000 | 11004000 | 2019-04-19 | 2021-04-23 | 1675000 | 735 | 2021 | 04 | 23 | 20210423 | 2017 | 2021 | 1.0751 | 2019 | 1.0507 | 10029399.8399 | 11789323.9075 | 1759924.0676 | 735 | 570 | 128.9%
2022-01-06 | 2012 | Special Operations Command | 73018 |  | 2012-06-06 | 2012-08-27 | Solis Constructors, Inc. | W912PP | W912PP-12-C-0025 | W912PP12C0025 | 73018,W912PP-12-C-0025 | 9329356 | 9703739 | 2014-04-10 | 2014-08-26 | 374383 | 138 | 2014 | 08 | 26 | 20140826 | 2012 | 2014 | 1.1519 | 2013 | 1.0751 | 10746182.8579 | 11148673.6715 | 402490.8136 | 138 | 591 | 23.35%
2021-12-31 | 2016 | Air Force Reserve | FGWB009002 |  | 2017-01-06 | 2017-09-21 | DRACE CONSTRUCTION COMPANY | W912QR | W912QR17C0038 | W912QR17C0038 | FGWB009002,W912QR17C0038 | 9397411 | 10249989 | 2019-06-06 | 2022-03-03 | 852578 | 1001 | 2022 | 03 | 03 | 20220303 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 9656696.2575 | 10509794.6215 | 853098.364 | 1001 | 623 | 160.7%
2022-01-12 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N62742 | N6274214MP00028 | N6274214MP00028 | N61054011,N6274214MP00028 | 9458000 | 8792000 | 2017-01-17 | 2017-01-17 | -666000 | 0 | 2017 | 01 | 17 | 20170117 | 2014 | 2017 | 1.1914 | 2016 | 1.1519 | 11267888.7224 | 10500744.9042 | -767143.8182 | 0 | 851 | 0%
2022-01-12 | 2020 | Marine Corps Active | M00243312 |  | 2020-03-02 | 2020-05-29 | BRISTOL DESIGN BUILD SERVICES, LLC | N62473 | N6247317D4627 N6247320F4683 | N6247317D4627 | M00243312,N6247317D4627 N6247320F4683 | 9525039 | 10133000 | 2022-02-03 | 2022-02-03 | 607961 | 0 | 2022 | 02 | 03 | 20220203 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 9530852.5292 | 10124816.8787 | 593964.3495 | 0 | 615 | 0%
2022-01-06 | 2010 | Special Operations Command | 63035 |  | 2010-08-10 | 2010-10-25 | A4 Construction Company, Inc. | W912PP | W912PP-11-C-0002 | W912PP11C0002 | 63035,W912PP-11-C-0002 | 9529882 | 14296126 | 2012-08-07 | 2013-09-10 | 4766244 | 399 | 2013 | 09 | 10 | 20130910 | 2011 | 2013 | 1.1227 | 2012 | 1.0993 | 10698929.3591 | 15938247.9141 | 5239318.555 | 399 | 652 | 61.2%
2022-01-13 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2016-08-25 | Surety Company | N69450 | N6945012C0754 | N6945012C0754 | 71503,N6945012C0754 | 9548000 | 2026000 | 2017-12-25 | 2019-05-10 | -7522000 | 501 | 2019 | 05 | 10 | 20190510 | 2016 | 2019 | 1.0276 | 2018 | 1.0006 | 9811440.1793 | 2284849.1885 | -7526590.9908 | 501 | 487 | 102.9%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1710 |  | 2016-06-15 | 2016-09-20 | RELIABLE CONTRACTING GROUP, LLC | W912HN | W912HN-16-C-0017 / 43104748 | W912HN16C0017 | DESC1710,W912HN-16-C-0017 / 43104748 | 9568000 | 10447000 | 2018-04-26 | 2019-08-27 | 879000 | 488 | 2019 | 08 | 27 | 20190827 | 2016 | 2019 | 1.0276 | 2018 | 1.0006 | 9831992.0021 | 10711528.4925 | 879536.4904 | 488 | 583 | 83.7%
2022-01-06 | 2011 | Special Operations Command | 66443 |  | 2010-12-23 | 2011-06-20 | SFL+A Architects, PA | W912HN | W912HN-11-D-0003 | W912HN11D0003 | 66443,W912HN-11-D-0003 | 9591000 | 10179482 | 2013-01-09 | 2013-05-31 | 588482 | 142 | 2013 | 05 | 31 | 20130531 | 2011 | 2013 | 1.0006 | 2012 | 0.97698 | 9596853.788 | 10171787.5885 | 574933.8006 | 142 | 569 | 24.96%
2021-12-31 | 2019 | Army Active | 82254 |  | 2019-06-18 | 2019-09-30 | ACC Construction Company, Inc. | W912PM | W912PM19C0043 | W912PM19C0043 | 82254,W912PM19C0043 | 9649000 | 9750000 | 2021-06-30 | 2021-11-29 | 101000 | 152 | 2021 | 11 | 29 | 20211129 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 9654889.1878 | 9753563.9371 | 98674.7494 | 152 | 639 | 23.79%
2021-12-08 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Cherokee Nation | HQ0034 | HQ0034-13-C-0133 | HQ003413C0133 | 80001,HQ0034-13-C-0133 | 9669575 |  | 2019-04-02 | 2021-09-22 | -9669575 | 904 | 2021 | 09 | 22 | 20210922 | 2013 | 2021 | 0.97698 | 2017 | 0.95701 | 9446959.303 | 193059.7419 | -9253899.5611 | 904 | 2010 | 44.98%
2022-01-06 | 2011 | Special Operations Command | 66444 |  | 2011-04-10 | 2011-08-10 | Pacific Tech Sauer JV V | W912HN | W912HN-11-C-0009 | W912HN11C0009 | 66444,W912HN-11-C-0009 | 9674000 | 9864411 | 2013-01-16 | 2013-05-31 | 190411 | 135 | 2013 | 05 | 31 | 20130531 | 2011 | 2013 | 1.0006 | 2012 | 0.97698 | 9679904.4463 | 9865931.7503 | 186027.304 | 135 | 525 | 25.71%
2022-01-07 | 2018 | Washington Headquarters Services | 87637 |  | 2018-07-05 | 2020-03-27 | Sauer Incorporated | W912DR | W912DR-20-C-0014 | W912DR20C0014 | 87637,W912DR-20-C-0014 | 9711000 | 9711000 | 2022-06-21 | 2022-12-31 | 0 | 193 | 2022 | 12 | 31 | 20221231 | 2020 | 2023 | 1.1227 | 2022 | 1.0507 | 10902265.4222 | 10902265.4222 | 0 | 193 | 816 | 23.65%
2021-08-31 | 2017 | Army Reserve | 74732 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR | W912QR18C0005 | W912QR18C0005 | 74732,W912QR18C0005 | 9745000 | 10726000 | 2019-06-13 | 2020-12-14 | 981000 | 550 | 2020 | 12 | 14 | 20201214 | 2018 | 2021 | 1.0507 | 2020 | 1.0006 | 10239080.6199 | 11220679.3652 | 981598.7453 | 550 | 576 | 95.49%
2022-01-06 | 2012 | Special Operations Command | 76373 |  | 2012-03-01 | 2012-06-21 | GSC Construction, Inc. | W912HN | W912HN-10-D-0049 | W912HN10D0049 | 76373,W912HN-10-D-0049 | 9771161 | 11158105 | 2014-04-17 | 2014-10-03 | 1386944 | 169 | 2014 | 10 | 03 | 20141003 | 2012 | 2015 | 1.0507 | 2014 | 1.0006 | 10266568.0071 | 11654358.517 | 1387790.5099 | 169 | 665 | 25.41%
2022-01-06 | 2019 | Special Operations Command | 69251 |  | 2018-12-20 | 2019-04-05 | Sauer | W912PM | W912PM19C0016 | W912PM19C0016 | 69251,W912PM19C0016 | 9776000 | 9834566 | 2020-05-20 | 2020-10-28 | 58566 | 161 | 2020 | 10 | 28 | 20201028 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 10045730.9586 | 10102948.6356 | 57217.6769 | 161 | 411 | 39.17%
2022-01-12 | 2021 | Army National Guard | 400602 |  | 2019-06-26 | 2021-08-04 | Flintco, LLC | W912L6 | W912L6-19-2-2014 | W912L61922014 | 400602,W912L6-19-2-2014 | 9800000 | 9323000 | 2023-02-23 | 2023-02-25 | -477000 | 2 | 2023 | 02 | 25 | 20230225 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 9574381.6216 | 9126861.1448 | -447520.4769 | 2 | 568 | 0.3521%
2022-01-31 | 2021 | DLA Defense Energy Support Center | DESC2104A |  | 2021-01-01 | 2021-09-30 | WHH Nisqually-Garco JV 2 | W912DW | W912DW21C0021 | W912DW21C0021 | DESC2104A,W912DW21C0021 | 9845000 | 9845000 | 2023-05-23 | 2022-01-01 | 0 | -507 | 2022 | 01 | 01 | 20220101 | 2021 | 2022 | 1.1743 | 2022 | 1.1227 | 11561165.6112 | 11561165.6112 | 0 | -507 | 600 | -84.5%
2021-12-31 | 2018 | Air Force Active | ASVF183100B |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER | W912ER20C0009 | W912ER20C0009 | ASVF183100B,W912ER20C0009 | 9862845 | 9856753 | 2023-03-28 | 2023-03-28 | -6092 | 0 | 2023 | 03 | 28 | 20230328 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 10362900.4717 | 10356804.7535 | -6095.7182 | 0 | 1082 | 0%
2021-12-31 | 2019 | Air Force Reserve | CTGB169002 |  | 2019-04-23 | 2019-08-01 | NISOU LGC JV, LLC | W912QR | W912QR19C0026 | W912QR19C0026 | CTGB169002,W912QR19C0026 | 9928185 | 9928185 | 2020-10-27 | 2022-02-28 | 0 | 489 | 2022 | 02 | 28 | 20220228 | 2019 | 2022 | 1.0993 | 2021 | 1.0751 | 10913609.0993 | 10913609.0993 | 0 | 489 | 453 | 107.9%
2021-12-30 | 2015 | DLA Defense Energy Support Center | DESC1404 |  | 2015-04-23 | 2016-01-21 | Gilbane Federal | N39430 | N39430-15-D-1634 JM01 | N3943015D1634 | DESC1404,N39430-15-D-1634 JM01 | 9960000 | 10140442 | 2017-11-13 | 2017-12-13 | 180442 | 30 | 2017 | 12 | 13 | 20171213 | 2016 | 2018 | 1.0006 | 2017 | 0.97698 | 9966079.0041 | 10142366.8172 | 176287.8131 | 30 | 662 | 4.532%
2021-12-31 | 2021 | Army Reserve | 81564 |  | 2021-08-02 | 2021-09-28 | Range & Civil Const | W912QR | W912QR21C0046 | W912QR21C0046 | 81564,W912QR21C0046 | 9972000 | 9972000 | 2023-11-03 | 2023-11-03 | 0 | 0 | 2023 | 11 | 03 | 20231103 | 2021 | 2024 | 1.0276 | 2023 | 0.95701 | 10247138.8216 | 10247138.8216 | 0 | 0 | 766 | 0%
2022-01-06 | 2009 | Special Operations Command | 59990 |  | 2009-03-25 | 2009-09-28 | American International Contractors, Inc. | W912ER | W912ER-09-C-0055 | W912ER09C0055 | 59990,W912ER-09-C-0055 | 9978000 | 10839492 | 2011-01-26 | 2012-08-15 | 861492 | 567 | 2012 | 08 | 15 | 20120815 | 2009 | 2012 | 0.97698 | 2011 | 0.95701 | 9748283.6552 | 10572741.8595 | 824458.2043 | 567 | 485 | 116.9%
2022-01-06 | 2012 | Special Operations Command | NVZR123709 |  | 2012-05-15 | 2012-07-31 | The Clement Group, LLC | W91278 | W91278-11-D-0028 | W9127811D0028 | NVZR123709,W91278-11-D-0028 | 9981550 | 10581450 | 2014-01-19 | 2015-01-07 | 599900 | 353 | 2015 | 01 | 07 | 20150107 | 2012 | 2015 | 1.0276 | 2014 | 0.97698 | 10256952.3169 | 10843041.249 | 586088.9321 | 353 | 537 | 65.74%
2021-12-31 | 2020 | Air Force Reserve | AJXF223744 |  | 2020-06-01 | 2020-09-23 | Kinsley Construction, Inc. | W912QR | W912QR20C0049 | W912QR20C0049 | AJXF223744,W912QR20C0049 | 9992147 | 9992147 | 2022-05-26 | 2022-05-26 | 0 | 0 | 2022 | 05 | 26 | 20220526 | 2020 | 2022 | 1.1227 | 2021 | 1.0751 | 11217901.2184 | 11217901.2184 | 0 | 0 | 610 | 0%
2022-01-12 | 2017 | Navy Active | N68436438 |  | 2017-01-20 | 2018-04-23 | VET INDUSTRIAL INC | N44255 | N4425517D4007 N4425518F4134 | N4425517D4007 | N68436438,N4425517D4007 N4425518F4134 | 10040000 | 10445000 | 2019-10-30 | 2020-08-14 | 405000 | 289 | 2020 | 08 | 14 | 20200814 | 2018 | 2020 | 0.97698 | 2019 | 0.95701 | 9808856.2736 | 10196446.1441 | 387589.8705 | 289 | 555 | 52.07%
2022-01-13 | 2018 | Defense Health Agency | 76934 |  | 2018-05-24 | 2019-02-08 | Gilbane Federal JV | W912HN | W912HN-19-C-3002 | W912HN19C3002 | 76934,W912HN-19-C-3002 | 10042000 | 2562000 | 2021-03-14 | 2021-07-12 | -7480000 | 120 | 2021 | 07 | 12 | 20210712 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 10048129.0521 | 2740335.7327 | -7307793.3194 | 120 | 765 | 15.69%
2022-01-12 | 2018 | Navy Active | N66691911 |  | 2018-06-18 | 2018-12-12 | AKTOR S.A. - TSONTOS S.A. J/V | N62470 | N6247019C5006 AWD | N6247019C5006 | N66691911,N6247019C5006 AWD | 10141000 | 3548000 | 2021-02-14 | 2021-10-04 | -6593000 | 232 | 2021 | 10 | 04 | 20211004 | 2019 | 2022 | 1.0751 | 2021 | 1.0507 | 10902362.9303 | 3975091.6602 | -6927271.2701 | 232 | 795 | 29.18%
2021-12-31 | 2020 | Air Force Active | ZNRE204308 |  | 2020-02-05 | 2020-08-18 | Improve MFH PAIP 8A | W912HV | W912HV17D001520F004 | W912HV17D001520F004 | ZNRE204308,W912HV17D001520F004 | 10150068 | 10150068 | 2022-09-06 | 2022-09-06 | 0 | 0 | 2022 | 09 | 06 | 20220906 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 10430119.9202 | 10430119.9202 | 0 | 0 | 749 | 0%
2021-12-31 | 2017 | Air Force Active | LJYC133003 |  | 2017-11-08 | 2018-05-01 | Aytekin Serol Insaat Taan | W912GB | W912GB18C0013 | W912GB18C0013 | LJYC133003,W912GB18C0013 | 10199660 | 10199660 | 2021-05-22 | 2021-05-22 | 0 | 0 | 2021 | 05 | 22 | 20210522 | 2018 | 2021 | 1.0993 | 2020 | 1.0751 | 11212029.4077 | 11212029.4077 | 0 | 0 | 1117 | 0%
2022-01-31 | 2021 | DLA Defense Energy Support Center | DESC2104B |  | 2021-01-01 | 2021-02-04 | WHH Nisqually-Garco JV 2 | W912DW | W912DW21C0022 | W912DW21C0022 | DESC2104B,W912DW21C0022 | 10279000 | 10279000 | 2023-05-23 | 2022-06-11 | 0 | -346 | 2022 | 06 | 11 | 20220611 | 2021 | 2022 | 1.1743 | 2022 | 1.1227 | 12070819.8393 | 12070819.8393 | 0 | -346 | 838 | -41.29%
2022-01-06 | 2020 | Special Operations Command | 86021 |  | 2020-02-28 | 2020-07-20 | Russell Construction Co | W912PM | W912PM20C0018 | W912PM20C0018 | 86021,W912PM20C0018 | 10284300 | 10681863 | 2022-09-09 | 2023-02-06 | 397563 | 150 | 2023 | 02 | 06 | 20230206 | 2020 | 2023 | 0.97698 | 2022 | 0.9382 | 10047531.9297 | 10420524.7669 | 372992.8372 | 150 | 781 | 19.21%
2021-12-31 | 2016 | Army Reserve | 77163 |  | 2019-08-02 | 2019-09-29 | Trans4Fed, LLC | W912QR | W912QR19C0045 | W912QR19C0045 | 77163,W912QR19C0045 | 10304000 | 10389000 | 2021-06-23 | 2022-04-29 | 85000 | 310 | 2022 | 04 | 29 | 20220429 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 10588299.0792 | 10673350.9582 | 85051.8791 | 310 | 633 | 48.97%
2021-12-31 | 2020 | Air Force Active | PAF180300 |  | 2019-12-05 | 2020-05-28 | ICON SI (Aust) Pty Ltd | N62742 | N6274220C1303 | N6274220C1303 | PAF180300,N6274220C1303 | 10310997 | 10421366 | 2022-02-03 | 2022-02-27 | 110369 | 24 | 2022 | 02 | 27 | 20220227 | 2020 | 2022 | 1.1743 | 2021 | 1.1227 | 12108394.5083 | 12232302.6673 | 123908.159 | 24 | 616 | 3.896%
2021-12-30 | 2019 | Air National Guard | PBXP929798 |  | 2019-10-25 | 2020-02-18 | CANCO, LLC | W50S8R | W50S8R20C0003 | W50S8R20C0003 | PBXP929798,W50S8R20C0003 | 10316495 | 10365100 | 2022-05-25 | 2022-05-25 | 48605 | 0 | 2022 | 05 | 25 | 20220525 | 2020 | 2022 | 1.1227 | 2021 | 1.0507 | 11582037.5571 | 11633106.8761 | 51069.319 | 0 | 827 | 0%
2021-12-31 | 2018 | Air Force Reserve | YTPM059004 |  | 2019-04-08 | 2019-08-01 | P & S Construction, Inc. | W912QR | W912QR19C0020 | W912QR19C0020 | YTPM059004,W912QR19C0020 | 10383981 | 9832232 | 2020-12-12 | 2021-08-12 | -551749 | 243 | 2021 | 08 | 12 | 20210812 | 2019 | 2021 | 1.0507 | 2020 | 1.0276 | 10910458.5546 | 10343486.1722 | -566972.3824 | 243 | 499 | 48.7%
2021-12-31 | 2017 | Air Force Active | AGGN173001 |  | 2017-01-06 | 2017-07-06 | SGS, LLC | W912BV | W912BV17C0010 | W912BV17C0010 | AGGN173001,W912BV17C0010 | 10428748 | 10774827 | 2018-12-01 | 2019-10-15 | 346079 | 318 | 2019 | 10 | 15 | 20191015 | 2017 | 2020 | 1.0006 | 2019 | 0.97698 | 10435113.1006 | 10773224.5717 | 338111.4711 | 318 | 513 | 61.99%
2021-12-31 | 2018 | Air Force Active | ASVF183100D |  | 2018-06-28 | 2019-04-05 | The Morganti Group, Inc / Danbury, CT (Pkg 3, Dorm) | W912ER | W912ER19C0008 | W912ER19C0008 | ASVF183100D,W912ER19C0008 | 10434344 | 10393609 | 2020-08-29 | 2021-10-09 | -40735 | 406 | 2021 | 10 | 09 | 20211009 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 11217730.5224 | 11175871.5974 | -41858.925 | 406 | 512 | 79.3%
2021-12-31 | 2020 | Army Active | 89057 |  | 2020-01-16 | 2020-05-29 | Sauer | W912PM | W912PM20C0014 | W912PM20C0014 | 89057,W912PM20C0014 | 10480000 | 10674000 | 2022-03-10 | 2022-11-30 | 194000 | 265 | 2022 | 11 | 30 | 20221130 | 2020 | 2023 | 0.97698 | 2022 | 0.9382 | 10238726.4689 | 10420736.8934 | 182010.4245 | 265 | 650 | 40.77%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G | W9126G-09-D-0096-0002 | W9126G09D00960002 | 72481,W9126G-09-D-0096-0002 | 10488000 | 10634000 | 2012-07-05 | 2012-12-31 | 146000 | 179 | 2012 | 12 | 31 | 20121231 | 2011 | 2013 | 1.1227 | 2012 | 1.0751 | 11774581.3766 | 11931542.7204 | 156961.3438 | 179 | 384 | 46.61%
2022-01-12 | 2019 | Navy Active | N60508253 |  | 2019-05-13 | 2021-05-12 | WEBCO L.L.C. | N69450 | N6945019D1085 N6945021F0280 | N6945019D1085 | N60508253,N6945019D1085 N6945021F0280 | 10500000 | 16343000 | 2024-05-11 | 2024-05-11 | 5843000 | 0 | 2024 | 05 | 11 | 20240511 | 2021 | 2024 | 1.0006 | 2023 | 0.9382 | 10506408.5886 | 15988299.8806 | 5481891.2919 | 0 | 1095 | 0%
2021-12-31 | 2021 | Air Force Reserve | QJKL100004 |  | 2021-06-01 | 2021-09-22 | L.S.Black Construction, LLC | W912QR | W912QR21C0043 | W912QR21C0043 | QJKL100004,W912QR21C0043 | 10511086 | 10511086 | 2024-09-22 | 2024-09-22 | 0 | 0 | 2024 | 09 | 22 | 20240922 | 2021 | 2024 | 1.0276 | 2023 | 0.95701 | 10801098.8174 | 10801098.8174 | 0 | 0 | 1096 | 0%
2021-12-30 | 2020 | Air National Guard | XGFG189001 |  | 2020-08-20 | 2021-04-15 | J. H. FINDORFF & SON, INC. | W50S9F | W50S9F21C0001 | W50S9F21C0001 | XGFG189001,W50S9F21C0001 | 10552313 | 9135750 | 2023-01-07 | 2023-01-07 | -1416563 | 0 | 2023 | 01 | 07 | 20230107 | 2021 | 2023 | 1.0751 | 2022 | 1.0276 | 11344556.3632 | 9888908.779 | -1455647.5843 | 0 | 632 | 0%
2022-01-13 | 2018 | Defense Health Agency | 77140 |  | 2018-06-22 | 2019-01-24 | Walga Ross Group JV | W912DQ | W912DQ-19-F-4003 | W912DQ19F4003 | 77140,W912DQ-19-F-4003 | 10585000 | 10530000 | 2020-09-16 | 2021-10-29 | -55000 | 408 | 2021 | 10 | 29 | 20211029 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 10877052.1887 | 10822018.6199 | -55033.5688 | 408 | 601 | 67.89%
2022-01-06 | 2012 | Special Operations Command | 60821 |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN | W912HN-10-D-0060 | W912HN10D0060 | 60821,W912HN-10-D-0060 | 10605000 | 10926290 | 2014-06-06 | 2015-03-06 | 321290 | 273 | 2015 | 03 | 06 | 20150306 | 2012 | 2015 | 1.1227 | 2014 | 1.0751 | 11905933.9721 | 12251345.6855 | 345411.7134 | 273 | 770 | 35.45%
2022-01-06 | 2018 | Special Operations Command | FTEV153003 |  | 2018-07-27 | 2018-09-27 | Leebcor Services, LLC | W91278 | W91278-16-D-0033 | W9127816D0033 | FTEV153003,W91278-16-D-0033 | 10689719 | 11218212 | 2020-04-23 | 2021-10-30 | 528493 | 555 | 2021 | 10 | 30 | 20211030 | 2018 | 2022 | 0.97698 | 2020 | 0.9382 | 10443617.2586 | 10939448.3684 | 495831.1098 | 555 | 574 | 96.69%
2022-01-06 | 2017 | Special Operations Command | AFSOC103010 |  | 2020-07-24 | 2021-04-14 | NIPPO CORPORATION | W912HV | W912HV21C0002 | W912HV21C0002 | AFSOC103010,W912HV21C0002 | 10759517 | 10759517 | 2023-06-04 | 2023-06-04 | 0 | 0 | 2023 | 06 | 04 | 20230604 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 10766083.9827 | 10766083.9827 | 0 | 0 | 781 | 0%
2022-01-06 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278 | W91278-10-D-0058 | W9127810D0058 | 68526,W91278-10-D-0058 | 10815034 | 12431294 | 2016-11-17 | 2017-04-20 | 1616260 | 154 | 2017 | 04 | 20 | 20170420 | 2015 | 2017 | 1.0276 | 2016 | 1.0006 | 11113433.0884 | 12730679.5594 | 1617246.471 | 154 | 588 | 26.19%
2021-12-31 | 2018 | Air Force Active | UHHZ163000 |  | 2018-12-12 | 2020-05-20 | Hensel Phelps, Orlando, FL | W912HN | W912HN20F4009 | W912HN20F4009 | UHHZ163000,W912HN20F4009 | 10827560 | 10827560 | 2021-12-10 | 2021-12-10 | 0 | 0 | 2021 | 12 | 10 | 20211210 | 2020 | 2022 | 1.0006 | 2021 | 0.9382 | 10834168.5122 | 10834168.5122 | 0 | 0 | 569 | 0%
2022-01-12 | 2017 | Navy Active | N62588307 |  | 2018-04-03 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N62470 | N6247019C5009 AWD | N6247019C5009 | N62588307,N6247019C5009 AWD | 10833000 | 11195000 | 2021-02-09 | 2021-07-21 | 362000 | 162 | 2021 | 07 | 21 | 20210721 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 11131894.7908 | 11494115.7345 | 362220.9437 | 162 | 782 | 20.72%
2021-12-31 | 2021 | Air Force Active | LRCT190001 |  | 2021-03-08 | 2021-06-04 | Eiffage Infraestructura SA | W912GB | W912GB21D0019 | W912GB21D0019 | LRCT190001,W912GB21D0019 | 10852364 | 10852364 | 2023-11-06 | 2023-11-06 | 0 | 0 | 2023 | 11 | 06 | 20231106 | 2021 | 2024 | 0.97698 | 2023 | 0.9382 | 10602517.7993 | 10602517.7993 | 0 | 0 | 885 | 0%
2022-01-06 | 2009 | Special Operations Command | 43010 |  | 2009-06-15 | 2009-09-28 | Big D Construction Corp | W912PP | W912PP-09-C-0034 | W912PP09C0034 | 43010,W912PP-09-C-0034 | 10882320 | 16423555 | 2011-05-09 | 2012-02-02 | 5541235 | 269 | 2012 | 02 | 02 | 20120202 | 2009 | 2012 | 0.95701 | 2011 | 0.9382 | 10414511.1105 | 15613287.0635 | 5198775.9529 | 269 | 588 | 45.75%
2022-01-12 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N40080 | N4008017C0014 AWD | N4008017C0014 | M00264635,N4008017C0014 AWD | 10883000 | 12110000 | 2018-03-25 | 2021-07-29 | 1227000 | 1222 | 2021 | 07 | 29 | 20210729 | 2017 | 2021 | 1.2082 | 2019 | 1.1519 | 13149127.3089 | 14562468.8479 | 1413341.539 | 1222 | 494 | 247.4%
2022-01-12 | 2020 | Marine Corps Active | M67695009 |  | 2020-06-26 | 2020-09-16 | THE CLEMENT GROUP LLC | N69450 | N6945019D0918 N6945020F0894 | N6945019D0918 | M67695009,N6945019D0918 N6945020F0894 | 10933245 | 12625000 | 2022-03-25 | 2022-03-25 | 1691755 | 0 | 2022 | 03 | 25 | 20220325 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 10681536.734 | 12300566.614 | 1619029.88 | 0 | 555 | 0%
2022-01-12 | 2019 | Army National Guard | 410818 |  | 2019-09-24 | 2019-09-30 | Apollo INC. | 410818 | 410818D002 | 410818D002 | 410818,410818D002 | 11000000 | 10773000 | 2021-10-22 | 2021-11-22 | -227000 | 31 | 2021 | 11 | 22 | 20211122 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 11557710.2944 | 11330571.7469 | -227138.5476 | 31 | 753 | 4.117%
2022-01-12 | 2018 | Navy Active | N60201421 |  | 2017-10-16 | 2018-08-03 | DESBUILD INCORPORATEDDBA DES BUILD | N69450 | N6945016D1111 N6945018F0723 | N6945016D1111 | N60201421,N6945016D1111 N6945018F0723 | 11062000 | 11655000 | 2020-08-04 | 2022-06-25 | 593000 | 690 | 2022 | 06 | 25 | 20220625 | 2018 | 2022 | 1.2082 | 2020 | 1.1743 | 13365399.8246 | 14061770.6938 | 696370.8692 | 690 | 732 | 94.26%
2022-02-02 | 2016 | DoD Education Activity | AM00110 | 27 | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278 | W91278-12-D-0037/57076763 | W9127812D0037 | AM00110,W91278-12-D-0037/57076763 | 11115000 | 11115000 | 2020-05-28 | 2022-09-01 | 0 | 826 | 2022 | 09 | 01 | 20220901 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 11421675.4915 | 11421675.4915 | 0 | 826 | 1157 | 71.39%
2021-12-31 | 2017 | Air Force Active | AJXF093000 |  | 2017-08-02 | 2018-05-24 | EDIFICE, LLC | N40080 | N4008017D0009 | N4008017D0009 | AJXF093000,N4008017D0009 | 11179388 | 11179388 | 2020-02-25 | 2020-02-25 | 0 | 0 | 2020 | 02 | 25 | 20200225 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 11186211.2475 | 11186211.2475 | 0 | 0 | 642 | 0%
2022-01-12 | 2020 | Army National Guard | 270203 |  | 2020-12-29 | 2021-01-08 | Donlar Construction Company | 187596 | 187596 | 187596 | 270203,187596 | 11200000 | 12435000 | 2022-08-20 | 2022-08-20 | 1235000 | 0 | 2022 | 08 | 20 | 20220820 | 2021 | 2022 | 1.0006 | 2022 | 0.9382 | 11206835.8279 | 12365510.4378 | 1158674.6099 | 0 | 589 | 0%
2022-01-12 | 2021 | Army National Guard | 470030 |  | 2021-11-02 | 2021-11-16 | USPFO - TN | W912L7 | W912L7-19-2-2001 | W912L71922001 | 470030,W912L7-19-2-2001 | 11200000 | 12806000 | 2023-11-16 | 2023-11-16 | 1606000 | 0 | 2023 | 11 | 16 | 20231116 | 2022 | 2024 | 1.0276 | 2023 | 0.97698 | 11509020.7382 | 13078046.9509 | 1569026.2127 | 0 | 730 | 0%
2022-01-12 | 2019 | Navy Reserve | N42237643 |  | 2018-12-03 | 2019-08-09 | WINDAMIR DEVELOPMENT INC | N69450 | N6945019D0922 N6945019F0864 | N6945019D0922 | N42237643,N6945019D0922 N6945019F0864 | 11207000 | 11489000 | 2021-10-03 | 2022-05-04 | 282000 | 213 | 2022 | 05 | 04 | 20220504 | 2019 | 2022 | 1.1519 | 2021 | 1.0993 | 12908980.1363 | 13218970.1058 | 309989.9696 | 213 | 786 | 27.1%
2022-01-12 | 2016 | Navy Active | N60495111 |  | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N62473 | N6247315D2404 N6247317F4334 | N6247315D2404 | N60495111,N6247315D2404 N6247317F4334 | 11253000 | 10656000 | 2019-02-25 | 2020-07-18 | -597000 | 509 | 2020 | 07 | 18 | 20200718 | 2017 | 2020 | 1.1914 | 2019 | 1.1519 | 13406381.0313 | 12718716.0771 | -687664.9542 | 509 | 557 | 91.38%
2021-12-31 | 2021 | Air Force Reserve | DDPM414396 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N69450 | N6945021C0038 | N6945021C0038 | DDPM414396,N6945021C0038 | 11259595 | 11259595 | 2024-09-30 | 2024-09-30 | 0 | 0 | 2024 | 09 | 30 | 20240930 | 2021 | 2024 | 1.0276 | 2023 | 0.97698 | 11570260.032 | 11570260.032 | 0 | 0 | 1097 | 0%
2021-12-31 | 2019 | Air Force Reserve | RVKQ079104 |  | 2019-04-29 | 2019-07-03 | LGC Global, Inc. | W912QR | W912QR19C0021 | W912QR19C0021 | RVKQ079104,W912QR19C0021 | 11311046 | 11333785 | 2021-07-23 | 2021-12-08 | 22739 | 138 | 2021 | 12 | 08 | 20211208 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 11050639.8922 | 11072401.3887 | 21761.4965 | 138 | 751 | 18.38%
2022-01-12 | 2018 | Navy Active | N3379A505 |  | 2018-06-12 | 2018-10-26 | ECC MEZZ LLC | N62470 | N6247019D5002 N6247019F9001 | N6247019D5002 | N3379A505,N6247019D5002 N6247019F9001 | 11315000 | 11866000 | 2020-06-18 | 2021-11-30 | 551000 | 530 | 2021 | 11 | 30 | 20211130 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 11627193.719 | 12178530.0173 | 551336.2983 | 530 | 601 | 88.19%
2022-01-12 | 2018 | Navy Reserve | N83447077 |  | 2018-05-14 | 2018-09-26 | EMR, INC. | N69450 | N6945018D1318 N6945018F0894 | N6945018D1318 | N83447077,N6945018D1318 N6945018F0894 | 11343000 | 11156000 | 2019-12-31 | 2020-12-31 | -187000 | 366 | 2020 | 12 | 31 | 20201231 | 2018 | 2021 | 1.1227 | 2020 | 1.0993 | 12734465.728 | 12528905.0035 | -205560.7245 | 366 | 461 | 79.39%
2022-01-12 | 2019 | Marine Corps Active | M67865222 |  | 2018-11-16 | 2019-03-14 | Granite Construction, Inc | N62473 | N62473-19-C-5826 | N6247319C5826 | M67865222,N62473-19-C-5826 | 11358000 | 12413000 | 2020-09-27 | 2021-02-06 | 1055000 | 132 | 2021 | 02 | 06 | 20210206 | 2019 | 2021 | 1.0006 | 2020 | 0.9382 | 11364932.2619 | 12354731.2201 | 989798.9582 | 132 | 563 | 23.45%
2022-01-13 | 2018 | Defense Health Agency | 77987 |  | 2018-03-22 | 2018-09-21 | JJ Brun JV LLC | W9128F | W9128F-18-0281 | W9128F180281 | 77987,W9128F-18-0281 | 11396000 | 13579000 | 2021-06-17 | 2023-01-30 | 2183000 | 592 | 2023 | 01 | 30 | 20230130 | 2018 | 2023 | 1.0006 | 2021 | 0.97698 | 11402955.4549 | 13535697.81 | 2132742.3551 | 592 | 1000 | 59.2%
2021-12-31 | 2019 | Army Active | 88542 |  | 2019-06-24 | 2019-09-25 | EIFFAGE INFRAESTRUCTURAS SA | W912GB | W912GB19D0039 | W912GB19D0039 | 88542,W912GB19D0039 | 11399000 | 11717000 | 2022-04-17 | 2022-04-17 | 318000 | 0 | 2022 | 04 | 17 | 20220417 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 11976939.9678 | 12295134.0565 | 318194.0887 | 0 | 935 | 0%
2022-01-12 | 2020 | Army National Guard | 531201 |  | 2020-06-02 | 2020-09-25 | Fowler General Construction, Inc. | 2018-5 | 2018-586 G (1-1) | 2018586 | 531201,2018-586 G (1-1) | 11400000 | 10861000 | 2022-03-21 | 2022-03-21 | -539000 | 0 | 2022 | 03 | 21 | 20220321 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 11977990.6688 | 11438661.6946 | -539328.9742 | 0 | 542 | 0%
2022-01-12 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N40085 | N4008510D5331 0006 | N4008510D5331 | N60191815,N4008510D5331 0006 | 11446000 | 19696000 | 2016-10-25 | 2021-02-12 | 8250000 | 1571 | 2021 | 02 | 12 | 20210212 | 2014 | 2021 | 0.97698 | 2018 | 0.95701 | 11182486.943 | 19077836.1573 | 7895349.2143 | 1571 | 770 | 204%
2022-01-12 | 2020 | Marine Corps Active | M670011483 |  | 2020-07-17 | 2020-09-25 | SAUER, INC. | N40085 | N4008520D0035 N4008520F6732 | N4008520D0035 | M670011483,N4008520D0035 N4008520F6732 | 11460484 | 12119000 | 2021-09-28 | 2022-06-22 | 658516 | 267 | 2022 | 06 | 22 | 20220622 | 2020 | 2022 | 1.1914 | 2021 | 1.1519 | 13653569.2977 | 14412092.5388 | 758523.2411 | 267 | 368 | 72.55%
2021-12-31 | 2019 | Air Force Reserve | CTGB989003 |  | 2020-06-01 | 2020-09-16 | Messer Construction Co. | W912QR | W912QR20C0039 | W912QR20C0039 | CTGB989003,W912QR20C0039 | 11471000 | 11471000 | 2022-05-04 | 2022-05-04 | 0 | 0 | 2022 | 05 | 04 | 20220504 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 11206911.3859 | 11206911.3859 | 0 | 0 | 595 | 0%
2022-01-06 | 2017 | Special Operations Command | 85958 |  | 2017-12-01 | 2019-04-11 | Windamir Development, Inc. | W912PM | W912PM19C0020 | W912PM19C0020 | 85958,W912PM19C0020 | 11507959 | 12710896 | 2021-04-28 | 2022-04-08 | 1202937 | 345 | 2022 | 04 | 08 | 20220408 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 11514982.7881 | 12666207.9636 | 1151225.1755 | 345 | 748 | 46.12%
2021-12-31 | 2019 | Air Force Active | MSET153505 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153505,DIOCB2076 | 11543865 | 11543865 | 2022-07-04 | 2022-07-04 | 0 | 0 | 2022 | 07 | 04 | 20220704 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 11862373.3647 | 11862373.3647 | 0 | 0 | 1328 | 0%
2022-01-12 | 2017 | Navy Reserve | N00206500 |  | 2016-11-04 | 2017-06-29 | SAUER, INC. | N69450 | N6945017C1613 AWD | N6945017C1613 | N00206500,N6945017C1613 AWD | 11589000 | 12630000 | 2019-07-27 | 2020-09-03 | 1041000 | 404 | 2020 | 09 | 03 | 20200903 | 2017 | 2020 | 1.0006 | 2019 | 0.97698 | 11596073.2508 | 12613107.0537 | 1017033.8029 | 404 | 758 | 53.3%
2022-01-12 | 2021 | Army National Guard | 550148 |  | 2021-08-23 | 2021-09-14 | Miron Construction | W912J2 | W912J2-20-2-2001 | W912J22022001 | 550148,W912J2-20-2-2001 | 11600000 | 9051000 | 2023-05-19 | 2023-05-19 | -2549000 | 0 | 2023 | 05 | 19 | 20230519 | 2021 | 2023 | 1.0006 | 2022 | 0.9382 | 11607079.9646 | 9215613.0977 | -2391466.8669 | 0 | 612 | 0%
2022-01-12 | 2017 | Navy Active | N00246947 |  | 2017-01-30 | 2017-03-30 | REYES CONSTRUCTION INC | N62473 | N6247314D0068 0009 | N6247314D0068 | N00246947,N6247314D0068 0009 | 11659000 | 15037000 | 2018-10-06 | 2020-03-31 | 3378000 | 542 | 2020 | 03 | 31 | 20200331 | 2017 | 2020 | 1.0276 | 2019 | 1.0006 | 11980685.0702 | 15360746.8048 | 3380061.7345 | 542 | 555 | 97.66%
2020-12-09 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR | W912DR-10-C-0079 | W912DR10C0079 | 17781,W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30 | 0 | 284 | 2012 | 05 | 30 | 20120530 | 2010 | 2012 | 0.97698 | 2011 | 0.95701 | 11430639.283 | 11430639.283 | 0 | 284 | 422 | 67.3%
2022-01-06 | 2010 | Special Operations Command | 66227 |  | 2010-07-01 | 2010-09-25 | Caddell Construction CO., INC | W912HN | W912HN-07-D-0056 | W912HN07D0056 | 66227,W912HN-07-D-0056 | 11713000 | 12285692 | 2012-05-02 | 2013-06-07 | 572692 | 401 | 2013 | 06 | 07 | 20130607 | 2010 | 2013 | 0.97698 | 2012 | 0.95701 | 11443339.9933 | 11991413.1245 | 548073.1312 | 401 | 585 | 68.55%
2022-01-12 | 2018 | Marine Corps Reserve | M67861650 |  | 2018-12-13 | 2019-03-19 | NAVY STANDARD DOCUMENT | USACE | USACE | USACE | M67861650,USACE | 11741000 | 11065000 | 2020-11-20 | 2020-11-20 | -676000 | 0 | 2020 | 11 | 20 | 20201120 | 2019 | 2021 | 1.1914 | 2020 | 1.1227 | 13987765.0127 | 13228838.9057 | -758926.107 | 0 | 612 | 0%
2022-01-07 | 2018 | Washington Headquarters Services | 88963 |  | 2019-05-22 | 2020-01-07 | HSU Development, Inc | W912DR | W912DR-17-D-0015 | W912DR17D0015 | 88963,W912DR-17-D-0015 | 11774418 |  | 2022-01-20 | 2022-01-20 | -11774418 | 0 | 2022 | 01 | 20 | 20220120 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 12099287.5841 | 595943.5734 | -11503344.0107 | 0 | 744 | 0%
2022-01-06 | 2009 | Special Operations Command | 26542 |  | 2009-04-09 | 2009-09-10 | Heery International, Inc. | W912HN | W912HN-09-C-0050 | W912HN09C0050 | 26542,W912HN-09-C-0050 | 11777057 | 12749904 | 2011-07-02 | 2012-09-24 | 972847 | 450 | 2012 | 09 | 24 | 20120924 | 2009 | 2012 | 0.97698 | 2011 | 0.95701 | 11505922.2549 | 12436948.5333 | 931026.2784 | 450 | 660 | 68.18%
2022-01-06 | 2016 | Special Operations Command | CZQZ083021 |  | 2016-06-16 | 2017-02-08 | SHEFFIELD KORTE JOINT VENTURE | W912PP | W912PP-14-D-0025 | W912PP14D0025 | CZQZ083021,W912PP-14-D-0025 | 11900000 | 11940630 | 2018-11-13 | 2018-11-09 | 40630 | -4 | 2018 | 11 | 09 | 20181109 | 2017 | 2019 | 1.2581 | 2018 | 1.2319 | 14970922.7681 | 15020976.3747 | 50053.6066 | -4 | 643 | -0.6221%
2022-01-06 | 2016 | Special Operations Command | 81897 |  | 2015-12-18 | 2016-11-18 | BUTT CONSTRUCTION COMPANY, INC | W912QR | W912QR-17-C-0002 | W912QR17C0002 | 81897,W912QR-17-C-0002 | 11975000 | 12544449 | 2018-08-26 | 2019-01-30 | 569449 | 157 | 2019 | 01 | 30 | 20190130 | 2017 | 2019 | 1.1743 | 2018 | 1.1519 | 14062464.0116 | 14718393.8617 | 655929.8501 | 157 | 646 | 24.3%
2022-01-12 | 2020 | Army National Guard | 290186 |  | 2020-05-28 | 2020-07-10 | Pro-Prost Joint Venture | T1809- | T1809-01 | T180901 | 290186,T1809-01 | 12000000 | 9934000 | 2021-08-18 | 2021-12-15 | -2066000 | 119 | 2021 | 12 | 15 | 20211215 | 2020 | 2022 | 1.1227 | 2021 | 1.0751 | 13472061.0716 | 11250950.5486 | -2221110.523 | 119 | 404 | 29.46%
2022-01-12 | 2021 | Army National Guard | 491201 |  | 2021-09-20 | 2021-09-29 | Hogan & Associated Construction Inc. | 227155 | 2271555 | 2271555 | 491201,2271555 | 12000000 | 13043000 | 2023-10-30 | 2023-10-30 | 1043000 | 0 | 2023 | 10 | 30 | 20231030 | 2021 | 2024 | 1.0751 | 2023 | 1.0006 | 12900932.3699 | 13944568.9564 | 1043636.5865 | 0 | 761 | 0%
2022-01-12 | 2020 | Army National Guard | 010908 |  | 2020-07-10 | 2021-07-12 | Nearen Construction Company | AC-20- | AC-20-C-0014-S | AC20C0014S | 010908,AC-20-C-0014-S | 12000000 | 11894000 | 2021-09-30 | 2022-07-12 | -106000 | 285 | 2022 | 07 | 12 | 20220712 | 2021 | 2022 | 1.0507 | 2022 | 1.0006 | 12608411.2303 | 12502346.5341 | -106064.6962 | 285 | 80 | 356.2%
2022-01-12 | 2021 | Army National Guard | 180202 |  | 2021-09-08 | 2021-09-21 | Messer Construction Co. | MDI-SA | MDI-SAB-21-C-0012 | MDISAB21C0012 | 180202,MDI-SAB-21-C-0012 | 12000000 | 13716000 | 2023-04-01 | 2023-04-01 | 1716000 | 0 | 2023 | 04 | 01 | 20230401 | 2021 | 2023 | 1.1227 | 2022 | 1.0507 | 13472061.0716 | 15275063.8776 | 1803002.8059 | 0 | 557 | 0%
2021-12-31 | 2017 | Air Force Active | FTFA033003 |  | 2017-08-28 | 2017-09-30 | The Green-Simmons Company, Inc | W91278 | W9127816D0016 | W9127816D0016 | FTFA033003,W9127816D0016 | 12034000 | 12208303 | 2019-07-29 | 2020-02-20 | 174303 | 206 | 2020 | 02 | 20 | 20200220 | 2017 | 2020 | 0.97698 | 2019 | 0.95701 | 11756949.8403 | 11923759.9075 | 166810.0672 | 206 | 667 | 30.88%
2020-12-09 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR | W912DR-10-C-0033 | W912DR10C0033 | 21120,W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18 | 1700000 | 456 | 2014 | 04 | 18 | 20140418 | 2010 | 2014 | 1.1914 | 2012 | 1.1519 | 14367809.0498 | 16325983.9611 | 1958174.9114 | 456 | 871 | 52.35%
2021-12-31 | 2021 | Air Force Active | LRCT210002 |  | 2020-11-26 | 2021-09-21 | Sociedad Espanola De Montajes Industrial (SEMI) | W912GB | W912GB21F0202 | W912GB21F0202 | LRCT210002,W912GB21F0202 | 12163401 | 12163401 | 2023-12-13 | 2023-12-13 | 0 | 0 | 2023 | 12 | 13 | 20231213 | 2021 | 2024 | 1.0006 | 2023 | 0.97698 | 12170824.8317 | 12170824.8317 | 0 | 0 | 813 | 0%
2022-01-12 | 2017 | Navy Active | N62688610 | N62688610A | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N40085 | N4008517C0307 AWD | N4008517C0307 | N62688610,N4008517C0307 AWD | 12166000 | 12166000 | 2019-10-25 | 2020-12-30 | 0 | 432 | 2020 | 12 | 30 | 20201230 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 12501673.7769 | 12501673.7769 | 0 | 432 | 785 | 55.03%
2021-12-30 | 2018 | Air National Guard | KJAQ119006 |  | 2019-12-04 | 2020-02-25 | AWBE-Cornerstone JV Cnstr | W50S8Z | W50S8Z20C0001 | W50S8Z20C0001 | KJAQ119006,W50S8Z20C0001 | 12181613 | 11876137 | 2021-03-26 | 2021-03-26 | -305476 | 0 | 2021 | 03 | 26 | 20210326 | 2020 | 2021 | 1.0751 | 2021 | 1.0507 | 13096180.4558 | 12775216.5367 | -320963.9191 | 0 | 395 | 0%
2022-01-06 | 2018 | Special Operations Command | 63850 |  | 2018-04-18 | 2018-08-27 | 4K Global-ACC JV LLC | W912PM | W912PM18C0015 | W912PM18C0015 | 63850,W912PM18C0015 | 12187034 | 14781112 | 2020-06-24 | 2021-05-11 | 2594078 | 321 | 2021 | 05 | 11 | 20210511 | 2018 | 2021 | 0.97698 | 2020 | 0.9382 | 11906460.6482 | 14340219.6074 | 2433758.9592 | 321 | 667 | 48.13%
2021-12-31 | 2019 | Air Force Active | GJLK1053425 |  | 2020-06-25 | 2020-09-24 | Garco Construction INC | W912DW | W912DW20C0015 | W912DW20C0015 | GJLK1053425,W912DW20C0015 | 12230000 | 12230000 | 2020-09-24 | 2023-06-05 | 0 | 984 | 2023 | 06 | 05 | 20230605 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 12850072.4455 | 12850072.4455 | 0 | 984 | 0 | #DIV/0!
2021-12-31 | 2019 | Air Force Active | AGGN213001 |  | 2018-10-29 | 2019-06-17 | SGS, LLC; Yukon OK | W912BV | W912BV19C0011 | W912BV19C0011 | AGGN213001,W912BV19C0011 | 12250972 | 12250972 | 2021-02-14 | 2021-02-14 | 0 | 0 | 2021 | 02 | 14 | 20210214 | 2019 | 2021 | 1.0006 | 2020 | 0.95701 | 12258449.28 | 12258449.28 | 0 | 0 | 608 | 0%
2021-08-31 | 2018 | Army Active | 86479 |  | 2018-06-25 | 2018-09-25 | Gilbane Federal | W912HN | W912HN18C3003 | W912HN18C3003 | 86479,W912HN18C3003 | 12255000 | 12784000 | 2020-03-21 | 2020-10-04 | 529000 | 197 | 2020 | 10 | 04 | 20201004 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 12593129.3881 | 13122452.2589 | 529322.8708 | 197 | 543 | 36.28%
2022-01-06 | 2009 | Special Operations Command | 60743 |  | 2009-04-15 | 2009-09-14 | IronBridge Construction | W912HN | W912HN-09-C-0046 | W912HN09C0046 | 60743,W912HN-09-C-0046 | 12273879 | 13140227 | 2011-03-24 | 2012-03-05 | 866348 | 347 | 2012 | 03 | 05 | 20120305 | 2009 | 2012 | 0.97698 | 2011 | 0.9382 | 11991306.2779 | 12804112.2949 | 812806.0169 | 347 | 556 | 62.41%
2022-01-06 | 2019 | Special Operations Command | 79447 |  | 2019-01-09 | 2019-05-03 | A4 Construction Co. | W9128F | W9128F19C0018 | W9128F19C0018 | 79447,W9128F19C0018 | 12309817 | 13873974 | 2021-05-31 | 2022-06-04 | 1564157 | 369 | 2022 | 06 | 04 | 20220604 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 12649458.8515 | 14214570.5218 | 1565111.6704 | 369 | 759 | 48.62%
2021-12-31 | 2019 | Air Force Active | XLWU193005 |  | 2019-08-12 | 2019-09-23 | Green Simmons Company INC | W91278 | W9127819F0486 | W9127819F0486 | XLWU193005,W9127819F0486 | 12369134 | 12369134 | 2021-11-09 | 2021-11-09 | 0 | 0 | 2021 | 11 | 09 | 20211109 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 12376683.3992 | 12376683.3992 | 0 | 0 | 778 | 0%
2021-12-31 | 2017 | Air Force Active | SXHT013001 |  | 2017-02-16 | 2017-06-01 | LEEBC O R SER VIC ES, LLC | W91278 | W9127816D0033 | W9127816D0033 | SXHT013001,W9127816D0033 | 12383350 | 12447196 | 2019-03-12 | 2020-05-27 | 63846 | 442 | 2020 | 05 | 27 | 20200527 | 2017 | 2020 | 1.0993 | 2019 | 1.0276 | 13612462.02 | 13678069.6037 | 65607.5838 | 442 | 649 | 68.1%
2022-01-12 | 2019 | Navy Active | N60514343 |  | 2019-06-04 | 2019-09-20 | ISLANDS MECHANICAL CONTRACTOR | N69450 | N6945018D1313 N6945019F1007 | N6945018D1313 | N60514343,N6945018D1313 N6945019F1007 | 12440000 | 11911000 | 2021-09-20 | 2022-03-11 | -529000 | 172 | 2022 | 03 | 11 | 20220311 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 12447592.6517 | 11930771.4396 | -516821.212 | 172 | 731 | 23.53%
2021-12-31 | 2016 | Air Force Active | WWYK093003 |  | 2016-09-09 | 2017-03-13 | Walsh Federal JV (Chicago/IL) | W912BV | W912BV17C0005 | W912BV17C0005 | WWYK093003,W912BV17C0005 | 12472000 | 12809463 | 2018-11-08 | 2019-01-12 | 337463 | 65 | 2019 | 01 | 12 | 20190112 | 2017 | 2019 | 1.0751 | 2018 | 1.0507 | 13408369.0431 | 13762941.733 | 354572.6899 | 65 | 605 | 10.74%
2021-12-31 | 2021 | Air Force Active | LRCT210001 |  | 2021-03-17 | 2021-08-09 | Tepe Bozdemir Joint Venture | W912GB | W912GB21C0022 | W912GB21C0022 | LRCT210001,W912GB21C0022 | 12482193 | 12482193 | 2024-03-09 | 2024-03-09 | 0 | 0 | 2024 | 03 | 09 | 20240309 | 2021 | 2024 | 0.97698 | 2023 | 0.9382 | 12194824.414 | 12194824.414 | 0 | 0 | 943 | 0%
2022-01-12 | 2019 | Marine Corps Active | M00681574 |  | 2019-07-09 | 2019-08-22 | BARNHART-REESE CONSTRUCTION INC | N62473 | N6247317D4635 N6247319F5115 | N6247317D4635 | M00681574,N6247317D4635 N6247319F5115 | 12715000 | 12544000 | 2021-06-07 | 2021-08-25 | -171000 | 79 | 2021 | 08 | 25 | 20210825 | 2019 | 2021 | 1.0507 | 2020 | 1.0276 | 13359662.3994 | 13183944.3149 | -175718.0845 | 79 | 655 | 12.06%
2021-12-31 | 2019 | Air Force Active | PNQS103165 |  | 2019-07-17 | 2019-09-30 | Bear Brothers, INC | W91278 | W9127819C0037 | W9127819C0037 | PNQS103165,W9127819C0037 | 12768107 | 12768107 | 2021-05-26 | 2021-05-26 | 0 | 0 | 2021 | 05 | 26 | 20210526 | 2019 | 2021 | 1.0006 | 2020 | 0.9382 | 12775899.9091 | 12775899.9091 | 0 | 0 | 604 | 0%
2022-01-12 | 2019 | Army National Guard | 300031 |  | 2019-02-26 | 2019-02-27 | Swank Enterprises - Valier | W9124V | W9124V-16-2-2001 | W9124V1622001 | 300031,W9124V-16-2-2001 | 12806888 | 16905621 | 2020-12-04 | 2020-12-04 | 4098733 | 0 | 2020 | 12 | 04 | 20201204 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 12512044.1936 | 16434580.9659 | 3922536.7723 | 0 | 646 | 0%
2022-01-06 | 2009 | Special Operations Command | 65678 |  | 2008-11-13 | 2009-03-31 | J&S Construction Co., Inc. | W912QR | W912QR-09-C-0023 | W912QR09C0023 | 65678,W912QR-09-C-0023 | 12824050 | 13455100 | 2010-08-09 | 2010-08-21 | 631050 | 12 | 2010 | 08 | 21 | 20100821 | 2009 | 2010 | 0.95701 | 2010 | 0.9382 | 12272770.0717 | 12864819.9604 | 592049.8887 | 12 | 496 | 2.419%
2022-01-12 | 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N62473 | N6247316C0601 AWD | N6247316C0601 | M67399222,N6247316C0601 AWD | 12948000 | 15099000 | 2019-03-04 | 2020-02-14 | 2151000 | 347 | 2020 | 02 | 14 | 20200214 | 2016 | 2020 | 1.0507 | 2018 | 1.0276 | 13604475.7175 | 15814824.2539 | 2210348.5364 | 347 | 915 | 37.92%
2022-01-12 | 2019 | Navy Active | N00620253 |  | 2018-10-12 | 2019-03-11 | BETHEL-WEBCOR JV-1 | N44255 | N4425517D4032 XN4425519F4123 | N4425517D4032 | N00620253,N4425517D4032 XN4425519F4123 | 12949000 | 13813000 | 2020-11-28 | 2021-07-06 | 864000 | 220 | 2021 | 07 | 06 | 20210706 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 13306277.6374 | 14150386.3845 | 844108.7471 | 220 | 628 | 35.03%
2022-01-31 | 2020 | DLA Defense Energy Support Center | DESC19S4 |  | 2020-04-28 | 2020-09-11 | SGJV, LLC | W91278 | W9127820C0027 &#x2f; 68228349 | W9127820C0027 | DESC19S4,W9127820C0027 &#x2f; 68228349 | 13051000 | 13051000 | 2021-10-16 | 2022-02-22 | 0 | 129 | 2022 | 02 | 22 | 20220222 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 13712697.9139 | 13712697.9139 | 0 | 129 | 400 | 32.25%
2021-12-31 | 2019 | Air Force Active | ULDF123001 |  | 2019-07-18 | 2020-01-17 | FOUR TRIBES ENTERPRISES, LLC | W912DS | W912DS20C0005 | W912DS20C0005 | ULDF123001,W912DS20C0005 | 13147968 | 13147968 | 2021-08-03 | 2021-09-10 | 0 | 38 | 2021 | 09 | 10 | 20210910 | 2020 | 2021 | 1.0993 | 2021 | 1.0507 | 14452972.341 | 14452972.341 | 0 | 38 | 564 | 6.738%
2022-01-06 | 2011 | Special Operations Command | 63052 |  | 2011-05-24 | 2011-09-24 | KL House Construction Co. | W912PP | W912PP-12-C-0002 | W912PP12C0002 | 63052,W912PP-12-C-0002 | 13260000 | 16851420 | 2013-03-25 | 2013-05-31 | 3591420 | 67 | 2013 | 05 | 31 | 20130531 | 2011 | 2013 | 0.97698 | 2012 | 0.95701 | 12954724.5207 | 16391756.651 | 3437032.1303 | 67 | 548 | 12.23%
2021-12-31 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB | W911KB-14-C-0011 | W911KB14C0011 | 634,W911KB-14-C-0011 | 13300000 | 15604000 | 2016-01-06 | 2016-05-02 | 2304000 | 117 | 2016 | 05 | 02 | 20160502 | 2014 | 2016 | 1.2826 | 2015 | 1.2082 | 17058100.3704 | 19841853.8685 | 2783753.4981 | 117 | 642 | 18.22%
2021-12-31 | 2017 | Missile Defense Agency | 657 |  | 2018-04-05 | 2018-09-07 | White Mountain Construction Company LLC | W911KB | W911KB-18-R-0006 | W911KB18R0006 | 657,W911KB-18-R-0006 | 13335000 | 14660442 | 2020-09-30 | 2020-09-29 | 1325442 | -1 | 2020 | 09 | 29 | 20200929 | 2018 | 2020 | 1.0276 | 2019 | 1.0006 | 13702927.8164 | 15029178.7891 | 1326250.9726 | -1 | 754 | -0.1326%
2021-12-31 | 2017 | Air Force Active | PNQS072140 |  | 2018-01-01 | 2019-05-08 | Southeast Cherokee | W91278 | W9127819C0017 | W9127819C0017 | PNQS072140,W9127819C0017 | 13341000 | 13341000 | 2021-04-20 | 2021-04-20 | 0 | 0 | 2021 | 04 | 20 | 20210420 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 13033859.7158 | 13033859.7158 | 0 | 0 | 713 | 0%
2021-12-31 | 2020 | Army Active | 91996 |  | 2020-06-30 | 2020-09-22 | James Construction Group | W9126G | W9126G20C0038 | W9126G20C0038 | 91996,W9126G20C0038 | 13350000 | 13141000 | 2022-07-12 | 2022-08-08 | -209000 | 27 | 2022 | 08 | 08 | 20220808 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 13358148.0627 | 13158132.5493 | -200015.5134 | 27 | 658 | 4.103%
2022-01-06 | 2008 | Special Operations Command | 65272 |  | 2007-10-23 | 2008-03-28 | Walbridge Aldinger Company | W912HN | W912HN-07-D-0054 | W912HN07D0054 |  | 13354750 | 13733299 | 2010-04-23 | 2010-06-11 | 378549 | 49 | 2010 | 06 | 11 | 20100611 | 2008 | 2010 | 1.0276 | 2009 | 0.97698 | 13723222.7414 | 14093056.679 | 369833.9376 | 49 | 756 | 6.481%
2022-01-06 | 2011 | Special Operations Command | 64484 |  | 2011-03-21 | 2011-07-21 | Sauer Incoporated | W912HN | W912HN-11-C-0010 | W912HN11C0010 | 64484,W912HN-11-C-0010 | 13388000 | 15616478 | 2014-06-10 | 2015-04-16 | 2228478 | 310 | 2015 | 04 | 16 | 20150416 | 2011 | 2015 | 1.0993 | 2013 | 1.0751 | 14716828.7679 | 17112615.7651 | 2395786.9972 | 310 | 1055 | 29.38%
2021-12-31 | 2017 | Army Active | 74877 |  | 2020-10-28 | 2021-08-19 | Walsh Federal LLC | W91238 | W9123821C0011 | W9123821C0011 | 74877,W9123821C0011 | 13438000 | 13438000 | 2022-11-26 | 2023-02-24 | 0 | 90 | 2023 | 02 | 24 | 20230224 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 14119319.1761 | 14119319.1761 | 0 | 90 | 464 | 19.4%
2022-01-12 | 2019 | Navy Active | N63042392 |  | 2019-05-09 | 2019-07-30 | POWER PRO PLUS INC. | N62473 | N6247319D2428 N6247319F4769 | N6247319D2428 | N63042392,N6247319D2428 N6247319F4769 | 13545000 | 13520000 | 2021-05-06 | 2021-05-06 | -25000 | 0 | 2021 | 05 | 06 | 20210506 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 13918721.9553 | 13894297.5124 | -24424.4429 | 0 | 646 | 0%
2021-12-30 | 2021 | Air National Guard | KKGA169022 |  | 2021-03-16 | 2021-07-20 | Gast Construction | W901UZ | W901UZ21C0001 | W901UZ21C0001 | KKGA169022,W901UZ21C0001 | 13557321 | 13039500 | 2022-08-19 | 2022-08-19 | -517821 | 0 | 2022 | 08 | 19 | 20220819 | 2021 | 2022 | 1.0751 | 2022 | 1.0276 | 14575173.4448 | 14043065.1745 | -532108.2703 | 0 | 395 | 0%
2021-12-13 | 2011 | Special Operations Command | 63052 |  | 2011-05-24 | 2011-10-26 | Speegle Construction, Inc. | W912PP | W912PP-12-C-0003 | W912PP12C0003 | 63052,W912PP-12-C-0003 | 13613730 | 13829042 | 2014-03-12 | 2014-06-04 | 215312 | 84 | 2014 | 06 | 04 | 20140604 | 2012 | 2014 | 1.0006 | 2013 | 1.0006 | 13622039.0281 | 13837482.442 | 215443.4139 | 84 | 868 | 9.677%
2021-12-08 | 2010 | Washington Headquarters Services | 80001A |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034 | HQ0034-13-F-0027 | HQ003413F0027 | 80001A,HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2020-04-30 | 0 | 1916 | 2020 | 04 | 30 | 20200430 | 2013 | 2020 | 1.0751 | 2017 | 1.0276 | 14706281.3202 | 14706281.3202 | 0 | 1916 | 488 | 392.6%
2021-11-30 | 2019 | Missile Defense Agency | 659 |  | 2019-09-23 | 2019-12-18 | CP04-RED POINT CONSTRUCTION, LLC | W911KB | W911KB20C0002 | W911KB20C0002 | 659,W911KB20C0002 | 13820000 | 15307457 | 2021-06-14 | 2021-08-16 | 1487457 | 63 | 2021 | 08 | 16 | 20210816 | 2020 | 2021 | 1.0507 | 2021 | 1.0006 | 14520686.9336 | 16009051.7907 | 1488364.8571 | 63 | 544 | 11.58%
2021-12-31 | 2019 | Missile Defense Agency | 659 |  | 2019-09-23 | 2019-12-18 | CP04-RED POINT CONSTRUCTION, LLC | W911KB | W911KB-20-C-0002 | W911KB20C0002 | 659,W911KB-20-C-0002 | 13820000 | 15307457 | 2021-06-14 | 2021-08-16 | 1487457 | 63 | 2021 | 08 | 16 | 20210816 | 2020 | 2021 | 1.0006 | 2021 | 0.9382 | 13828434.9233 | 15223964.202 | 1395529.2787 | 63 | 544 | 11.58%
2021-12-31 | 2018 | Air Force Active | ALUA113023 |  | 2019-05-29 | 2019-09-26 | MVL USA, Inc. / Houston / TX | W912ER | W912ER19C0016 | W912ER19C0016 | ALUA113023,W912ER19C0016 | 13890460 | 13734951 | 2021-01-20 | 2021-11-23 | -155509 | 307 | 2021 | 11 | 23 | 20211123 | 2019 | 2022 | 1.1519 | 2021 | 1.0751 | 15999970.7525 | 15832786.4949 | -167184.2577 | 307 | 482 | 63.69%
2020-12-09 | 2017 | National Security Agency | 31067 |  | 2015-04-15 | 2018-01-18 | Hensel-Phelps | W912DR | W912DR-15-D-0032 DO 0003 | W912DR15D0032 | 31067,W912DR-15-D-0032 DO 0003 | 13900000 | 14104547 | 2019-01-29 | 2019-05-22 | 204547 | 113 | 2019 | 05 | 22 | 20190522 | 2018 | 2019 | 1.0993 | 2019 | 1.0507 | 15279647.4361 | 15494565.1604 | 214917.7243 | 113 | 376 | 30.05%
2022-01-06 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278 | W91278-11-D-0029 | W9127811D0029 | 61064,W91278-11-D-0029 | 13951000 | 14300613 | 2016-05-10 | 2017-02-15 | 349613 | 281 | 2017 | 02 | 15 | 20170215 | 2015 | 2017 | 1.0276 | 2016 | 1.0006 | 14335923.957 | 14685750.3405 | 349826.3834 | 281 | 582 | 48.28%
2021-12-31 | 2017 | Army Active | 85794 |  | 2018-05-25 | 2019-01-18 | Odyssey International | W912HN | W912HN19C3000 | W912HN19C3000 | 85794,W912HN19C3000 | 14000000 | 14777000 | 2020-06-14 | 2021-12-06 | 777000 | 540 | 2021 | 12 | 06 | 20211206 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 15051087.7649 | 15849526.0786 | 798438.3137 | 540 | 513 | 105.3%
2022-01-12 | 2019 | Marine Corps Active | M00264724 |  | 2019-06-05 | 2019-08-15 | G-W MANAGEMENT SERVICES, LLC | N40080 | N4008019D0015 N4008019F4870 | N4008019D0015 | M00264724,N4008019D0015 N4008019F4870 | 14142000 | 13771000 | 2021-01-30 | 2021-07-01 | -371000 | 152 | 2021 | 07 | 01 | 20210701 | 2019 | 2021 | 1.0751 | 2020 | 1.0276 | 15203748.7979 | 14822512.486 | -381236.312 | 152 | 534 | 28.46%
2022-01-12 | 2019 | Marine Corps Active | M670011524F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011524F,N4008520C0044 AWD | 14143000 | 14259000 | 2021-06-16 | 2025-01-11 | 116000 | 1305 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0507 | 2023 | 1.0006 | 14860063.3358 | 14976134.1355 | 116070.7996 | 1305 | 327 | 399.1%
2021-12-31 | 2018 | Air Force Active | BIKF180001 |  | 2018-05-02 | 2018-12-06 | Iceland Prime Contractor, LTD | N62470 | N6247018R4005 | N6247018R4005 | BIKF180001,N6247018R4005 | 14146220 | 14146220 | 2021-10-20 | 2021-10-20 | 0 | 0 | 2021 | 10 | 20 | 20211020 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 14536530.2989 | 14536530.2989 | 0 | 0 | 1049 | 0%
2022-01-12 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N69450 | N6945013D1762 0002 | N6945013D1762 | N00213678,N6945013D1762 0002 | 14151000 | 14261000 | 2018-01-08 | 2018-01-08 | 110000 | 0 | 2018 | 01 | 08 | 20180108 | 2014 | 2018 | 1.0006 | 2016 | 1.0006 | 14159636.9464 | 14269704.084 | 110067.1376 | 0 | 1242 | 0%
2021-12-31 | 2018 | Army Active | 91742 |  | 2019-05-17 | 2019-09-05 | Nakasato Contracting, LLC | W9128A | W9128A19C0006 | W9128A19C0006 | 91742,W9128A19C0006 | 14200000 | 15266000 | 2021-09-23 | 2022-03-01 | 1066000 | 159 | 2022 | 03 | 01 | 20220301 | 2019 | 2022 | 1.0751 | 2021 | 1.0507 | 15266103.3044 | 16386150.502 | 1120047.1976 | 159 | 749 | 21.23%
2022-01-12 | 2018 | Navy Reserve | N42237642 |  | 2018-05-04 | 2018-09-12 | LEEBCOR SERVICES LLC | N69450 | N6945016D1113 N6945018F0731 | N6945016D1113 | N42237642,N6945016D1113 N6945018F0731 | 14240000 | 15692000 | 2020-01-06 | 2021-10-16 | 1452000 | 649 | 2021 | 10 | 16 | 20211016 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 14248691.2669 | 15667262.9112 | 1418571.6443 | 649 | 481 | 134.9%
2022-01-13 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR | W912DR-09-C-0052 | W912DR09C0052 |  | 14398000 | 17919000 | 2013-06-01 | 2015-06-10 | 3521000 | 739 | 2015 | 06 | 10 | 20150610 | 2009 | 2015 | 0.97698 | 2012 | #N/A | 14066525.1621 | #N/A | #N/A | 739 | 1387 | 53.28%
2021-12-31 | 2020 | Air Force Active | BIKF190003 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N62470 | N6247020C0010 | N6247020C0010 | BIKF190003,N6247020C0010 | 14404448 | 14404448 | 2023-07-14 | 2023-07-14 | 0 | 0 | 2023 | 07 | 14 | 20230714 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 14801883.1031 | 14801883.1031 | 0 | 0 | 1026 | 0%
2022-01-12 | 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N69450 | N6945016D1110 0001 | N6945016D1110 | N60201424,N6945016D1110 0001 | 14616000 | 15831000 | 2019-02-05 | 2019-02-05 | 1215000 | 0 | 2019 | 02 | 05 | 20190205 | 2016 | 2019 | 0.97698 | 2018 | 0.95701 | 14279506.3043 | 15442275.9158 | 1162769.6116 | 0 | 936 | 0%
2022-01-12 | 2019 | Marine Corps Active | M00681334 |  | 2019-06-21 | 2019-08-22 | I E PACIFIC INC | N62473 | N6247317D4628 N6247319F5136 | N6247317D4628 | M00681334,N6247317D4628 N6247319F5136 | 14684000 | 14959000 | 2021-08-06 | 2021-10-13 | 275000 | 68 | 2021 | 10 | 13 | 20211013 | 2019 | 2022 | 1.2082 | 2021 | 1.1914 | 17741595.6449 | 18069219.8148 | 327624.1699 | 68 | 715 | 9.51%
2022-01-06 | 2012 | Special Operations Command | 73021 |  | 2012-06-06 | 2012-09-12 | K. L. HOUSE CONSTRUCTION COMPANY | W912PP | W912PP-12-C-0033 | W912PP12C0033 | 73021,W912PP-12-C-0033 | 14700000 | 15132847 | 2014-08-09 | 2014-11-24 | 432847 | 107 | 2014 | 11 | 24 | 20141124 | 2012 | 2015 | 1.0507 | 2014 | 1.0006 | 15445303.7571 | 15878414.9417 | 433111.1846 | 107 | 696 | 15.37%
2022-05-03 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2021-03-08 | 2021-04-30 | Structural Associates, Inc | W91278 | W9127821C0012 &#x2f; 34813933 | W9127821C0012 | DESC1513,W9127821C0012 &#x2f; 34813933 | 14758000 | 14809000 | 2022-10-17 | 2023-01-03 | 51000 | 78 | 2023 | 01 | 03 | 20230103 | 2021 | 2023 | 0.97698 | 2022 | #N/A | 14418237.14 | #N/A | #N/A | 78 | 535 | 14.58%
2022-01-13 | 2017 | Defense Health Agency | 14022 |  | 2017-04-28 | 2017-09-13 | Mirait T-Acty JV | W912-H | W912-HV-17-D-0014 | W912HV17D0014 | 14022,W912-HV-17-D-0014 | 14781000 | 15015000 | 2019-10-26 | 2020-11-30 | 234000 | 401 | 2020 | 11 | 30 | 20201130 | 2017 | 2021 | 1.0276 | 2019 | 0.97698 | 15188824.601 | 15417437.3867 | 228612.7857 | 401 | 773 | 51.88%
2022-01-12 | 2019 | Navy Active | N00245110 |  | 2019-04-19 | 2019-08-12 | SOLPAC CONSTRUCTION INC | N62473 | N6247318D5855 N6247319F5055 | N6247318D5855 | N00245110,N6247318D5855 N6247319F5055 | 14817000 | 13884000 | 2021-03-23 | 2021-03-23 | -933000 | 0 | 2021 | 03 | 23 | 20210323 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 15225817.882 | 14292248.4331 | -933569.4489 | 0 | 589 | 0%
2022-01-06 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912QR | W912QR-15-C-0021 | W912QR15C0021 | 36977,W912QR-15-C-0021 | 14851238 | 15516050 | 2017-03-03 | 2017-10-17 | 664812 | 228 | 2017 | 10 | 17 | 20171017 | 2015 | 2018 | 1.1743 | 2017 | 1.1227 | 17440083.4992 | 18186449.1547 | 746365.6554 | 228 | 561 | 40.64%
2021-12-31 | 2018 | Army Active | 90722 |  | 2019-07-11 | 2019-08-30 | Intercontinental Construction Contracting, INC. | W912DS | W912DS19C0018 | W912DS19C0018 | 90722,W912DS19C0018 | 14893000 | 17784000 | 2021-09-01 | 2022-07-30 | 2891000 | 332 | 2022 | 07 | 30 | 20220730 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 15303914.8084 | 18128357.3868 | 2824442.5784 | 332 | 733 | 45.29%
2021-11-16 | 2018 | Army National Guard | 511503 |  | 2018-09-11 | 2018-09-12 | S. B. Ballard Construction Company | PC123- | PC123-18312-000 | PC12318312000 | 511503,PC123-18312-000 | 15000000 | 16999000 | 2020-08-31 | 2021-09-16 | 1999000 | 381 | 2021 | 09 | 16 | 20210916 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 14654665.7474 | 16567732.7873 | 1913067.0399 | 381 | 719 | 52.99%
2022-01-12 | 2019 | Army National Guard | 460115 |  | 2019-02-07 | 2019-02-15 | RCS Construction, Inc. | W912MM | W912MM-17-2-2001 | W912MM1722001 | 460115,W912MM-17-2-2001 | 15000000 | 13023000 | 2020-11-15 | 2020-11-15 | -1977000 | 0 | 2020 | 11 | 15 | 20201115 | 2019 | 2021 | 1.1519 | 2020 | 1.0993 | 17278013.9238 | 15104786.3712 | -2173227.5526 | 0 | 639 | 0%
2022-01-12 | 2021 | Army National Guard | 210054 |  | 2021-09-15 | 2021-09-27 | Monarch Construction | 785 22 | 785 22000000107 | 785 | 210054,785 22000000107 | 15000000 | 16511000 | 2023-09-27 | 2023-09-27 | 1511000 | 0 | 2023 | 09 | 27 | 20230927 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 15009155.1266 | 16455200.2979 | 1446045.1712 | 0 | 730 | 0%
2022-01-12 | 2021 | Army National Guard | 340132 |  | 2021-09-05 | 2021-09-22 | DMD Contracting | W912KN | W912KN-19-2-2001 | W912KN1922001 | 340132,W912KN-19-2-2001 | 15000000 | 13530000 | 2023-06-15 | 2023-06-15 | -1470000 | 0 | 2023 | 06 | 15 | 20230615 | 2021 | 2023 | 1.1914 | 2022 | 1.1227 | 17870409.2659 | 16220081.7846 | -1650327.4813 | 0 | 631 | 0%
2022-01-06 | 2010 | Special Operations Command | 60833 |  | 2010-05-17 | 2010-10-29 | Caddell Construction CO., INC | W91278 | W91278-07-D-0036 | W9127807D0036 | 60833,W91278-07-D-0036 | 15072000 | 15260312 | 2012-08-31 | 2012-12-20 | 188312 | 111 | 2012 | 12 | 20 | 20121220 | 2011 | 2013 | 1.0276 | 2012 | 1.0006 | 15487853.622 | 15676280.5567 | 188426.9347 | 111 | 672 | 16.52%
2022-01-06 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F | W9128F-14-C-0030 | W9128F14C0030 | 69446,W9128F-14-C-0030 | 15083965 | 16145285 | 2016-02-08 | 2016-06-08 | 1061320 | 121 | 2016 | 06 | 08 | 20160608 | 2014 | 2016 | 1.0507 | 2015 | 1.0006 | 15848736.1419 | 16910703.9099 | 1061967.7679 | 121 | 564 | 21.45%
2022-01-07 | 2015 | Washington Headquarters Services | 80011 |  | 2018-08-20 | 2019-05-09 | Cherokee Nations Environmental Solutions | HQ0034 | HQ0034-19-C-0043 | HQ003419C0043 | 80011,HQ0034-19-C-0043 | 15100000 |  | 2021-06-21 | 2022-04-15 | -15100000 | 298 | 2022 | 04 | 15 | 20220415 | 2019 | 2022 | 1.1519 | 2021 | 1.0507 | 17393200.6833 | 1527616.5518 | -15865584.1315 | 298 | 774 | 38.5%
2021-12-31 | 2018 | Air Force Active | ASVF183100F |  | 2018-02-23 | 2018-08-22 | The Morganti Group, Inc. (Pkg 1, LSA), Danbury, CT | W912ER | W912ER18C0029 | W912ER18C0029 | ASVF183100F,W912ER18C0029 | 15147990 | 16339259 | 2020-03-04 | 2021-02-07 | 1191269 | 340 | 2021 | 02 | 07 | 20210207 | 2018 | 2021 | 1.2082 | 2020 | 1.1914 | 18302200.5866 | 19721431.5583 | 1419230.9717 | 340 | 560 | 60.71%
2022-01-06 | 2008 | Special Operations Command | 65392 |  | 2007-10-18 | 2008-03-21 | TJC Engineering Inc | W912QR | W912QR-08-C-0012 | W912QR08C0012 |  | 15161429 | 15519395 | 2009-08-11 | 2010-03-11 | 357966 | 212 | 2010 | 03 | 11 | 20100311 | 2008 | 2010 | 1.0006 | 2009 | 0.97698 | 15170682.6535 | 15520407.4587 | 349724.8053 | 212 | 508 | 41.73%
2021-08-31 | 2019 | Army Active | 94606 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL | W912PL20C0002 | W912PL20C0002 | 94606,W912PL20C0002 | 15233000 | 14906000 | 2021-06-08 | 2021-06-29 | -327000 | 21 | 2021 | 06 | 29 | 20210629 | 2020 | 2021 | 1.0751 | 2021 | 1.0276 | 16376658.5659 | 16040636.264 | -336022.3019 | 21 | 580 | 3.621%
2021-12-31 | 2015 | Army Active | 85711 |  | 2017-05-09 | 2017-09-28 | BRYAN 77 CONSTRUCTION JV | W912GB | W912GB17C0019 | W912GB17C0019 | 85711,W912GB17C0019 | 15238000 | 18732000 | 2020-12-09 | 2021-11-10 | 3494000 | 336 | 2021 | 11 | 10 | 20211110 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 15658433.7508 | 19154566.2849 | 3496132.5342 | 336 | 1168 | 28.77%
2022-01-06 | 2016 | Special Operations Command | TMKH003003 |  | 2017-04-07 | 2018-06-07 | Leebcor Services, LLC. | W912PM | W912PM18C0013 | W912PM18C0013 | TMKH003003,W912PM18C0013 | 15241121 | 15194631 | 2020-01-22 | 2020-08-20 | -46490 | 211 | 2020 | 08 | 20 | 20200820 | 2018 | 2020 | 1.0006 | 2019 | 0.95701 | 15250423.2928 | 15205931.8037 | -44491.4891 | 211 | 594 | 35.52%
2021-12-31 | 2019 | Air Force Active | FTQW1054329 |  | 2019-06-07 | 2019-09-30 | F-35 A Conventional Munitions Maintenance facility | W911KB | W911KB19C0030 | W911KB19C0030 | FTQW1054329,W911KB19C0030 | 15241345 | 15241345 | 2021-07-31 | 2022-01-25 | 0 | 178 | 2022 | 01 | 25 | 20220125 | 2019 | 2022 | 1.0993 | 2021 | 1.0276 | 16754127.9174 | 16754127.9174 | 0 | 178 | 670 | 26.57%
2020-12-09 | 2011 | National Security Agency | 23994 |  | 2012-04-26 | 2012-06-18 | JAAAT | W912HN | W912HN-10-D-0063 | W912HN10D0063 | 23994,W912HN-10-D-0063 | 15315000 | 16526000 | 2014-01-30 | 2014-12-23 | 1211000 | 327 | 2014 | 12 | 23 | 20141223 | 2012 | 2015 | 1.0006 | 2014 | 0.95701 | 15324347.3843 | 16483288.9477 | 1158941.5635 | 327 | 591 | 55.33%
2022-01-12 | 2015 | Navy Active | N61151190 |  | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N40080 | N4008017C0030 AWD | N4008017C0030 | N61151190,N4008017C0030 AWD | 15316000 | 14741000 | 2019-09-06 | 2021-02-11 | -575000 | 524 | 2021 | 02 | 11 | 20210211 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 15738585.8595 | 15163234.913 | -575350.9465 | 524 | 862 | 60.79%
2022-01-12 | 2019 | Marine Corps Active | M670011520F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011520F,N4008520C0044 AWD | 15383000 | 15577000 | 2019-10-25 | 2025-01-11 | 194000 | 1905 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0276 | 2023 | 1.0006 | 15807434.4657 | 16001552.872 | 194118.4063 | 1905 | -273 | -697.8%
2022-01-06 | 2011 | Special Operations Command | 65395 |  | 2011-06-27 | 2011-09-19 | JAAAT Technical. Services, LLC | W912HN | W912HN-10-D-0057 | W912HN10D0057 | 65395,W912HN-10-D-0057 | 15391578 | 15637173 | 2013-06-19 | 2014-05-30 | 245595 | 345 | 2014 | 05 | 30 | 20140530 | 2011 | 2014 | 1.1227 | 2013 | 1.0751 | 17279689.9004 | 17543723.6075 | 264033.7071 | 345 | 639 | 53.99%
2021-12-13 | 2013 | Special Operations Command | 69287 |  | 2013-06-03 | 2014-09-27 | Sauer Incorporated | W91278 | W91278-11-D-0067 | W9127811D0067 | 69287,W91278-11-D-0067 | 15404000 | 25866356 | 2016-12-02 | 2018-03-15 | 10462356 | 468 | 2018 | 03 | 15 | 20180315 | 2014 | 2018 | 1.1227 | 2016 | 1.0993 | 17293635.7289 | 28794435.0837 | 11500799.3547 | 468 | 797 | 58.72%
2021-12-31 | 2018 | Air Force Active | ASHE143008 |  | 2018-01-04 | 2018-09-28 | CMC | N62470 | N6247018C4004 | N6247018C4004 | ASHE143008,N6247018C4004 | 15453726 | 16235042 | 2022-08-23 | 2022-08-23 | 781316 | 0 | 2022 | 08 | 23 | 20220823 | 2018 | 2022 | 1.0993 | 2020 | 1.0507 | 16987588.8384 | 17808518.2908 | 820929.4524 | 0 | 1425 | 0%
2022-02-02 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278 | W91278-12-D-0037/54560300 | W9127812D0037 | AM00048,W91278-12-D-0037/54560300 | 15500000 | 15500000 | 2020-06-10 | 2021-10-15 | 0 | 492 | 2021 | 10 | 15 | 20211015 | 2016 | 2022 | 0.97698 | 2019 | 0.95701 | 15143154.6057 | 15143154.6057 | 0 | 492 | 1349 | 36.47%
2021-10-14 | 2020 | Defense Health Agency | 94638 |  | 2021-04-19 | 2021-09-27 | RQ Construction | N40085 | N4008520D0034 | N4008520D0034 | 94638,N4008520D0034 | 15542000 | 15542000 | 2024-07-15 |  | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2021 | #VALUE! | 1.0006 | #VALUE! | 0.97698 | 15551485.9319 | 15551485.9319 | 0 | #VALUE! | 1022 | #VALUE!
2022-01-06 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN | W912HN-10-D-0063 | W912HN10D0063 | 69758,W912HN-10-D-0063 | 15649974 | 19104823 | 2014-04-08 | 2016-12-06 | 3454849 | 973 | 2016 | 12 | 06 | 20161206 | 2012 | 2017 | 0.97698 | 2015 | 0.97698 | 15289675.8617 | 18664986.3486 | 3375310.4869 | 973 | 568 | 171.3%
2022-01-12 | 2014 | Navy Active | N60495393 |  | 2017-02-28 | 2018-04-19 | WALTERS, K. G. CONSTRUCTION CO., IN | N62473 | N6247318C2205 AWD | N6247318C2205 | N60495393,N6247318C2205 AWD | 15675000 | 15520000 | 2020-05-08 | 2020-11-30 | -155000 | 206 | 2020 | 11 | 30 | 20201130 | 2018 | 2021 | 1.0507 | 2020 | 1.0006 | 16469737.1696 | 16314642.5666 | -155094.603 | 206 | 750 | 27.47%
2021-12-30 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-19 | Middle Eastern Builders | W912HN | W912HN-12C-0016 | W912HN12C0016 | DESC1353,W912HN-12C-0016 | 15685100 | 16568000 | 2018-05-23 | 2018-09-21 | 882900 | 121 | 2018 | 09 | 21 | 20180921 | 2015 | 2018 | 1.0507 | 2017 | 1.0006 | 16480349.249 | 17363788.1198 | 883438.8708 | 121 | 1008 | 12%
2021-11-16 | 2017 | Army National Guard | 371301 |  | 2017-07-24 | 2017-09-25 | Daniels and Daniels Construction Company INC. | W91242 | W91242-17-C-0005 | W9124217C0005 | 371301,W91242-17-C-0005 | 15729000 | 16942000 | 2019-08-17 | 2020-05-01 | 1213000 | 258 | 2020 | 05 | 01 | 20200501 | 2017 | 2020 | 1.0507 | 2019 | 1.0006 | 16526475.0201 | 17740215.3647 | 1213740.3446 | 258 | 691 | 37.34%
2022-01-12 | 2021 | Army National Guard | 411510 |  | 2021-09-23 | 2021-09-28 | Fowler General Construction, Inc. | 219995 | 219995C003 | 219995C003 | 411510,219995C003 | 15735000 | 8333000 | 2023-10-30 | 2023-10-30 | -7402000 | 0 | 2023 | 10 | 30 | 20231030 | 2021 | 2024 | 0.97698 | 2023 | 0.95701 | 15372744.369 | 8288941.3528 | -7083803.0163 | 0 | 762 | 0%
2022-01-13 | 2020 | Defense Health Agency | 89906 |  | 2020-08-04 | 2020-09-30 | Soltek Pacific Construction Co. | N62473 | N6247318D5855 | N6247318D5855 | 89906,N6247318D5855 | 15767000 | 15980000 | 2022-10-30 | 2022-10-30 | 213000 | 0 | 2022 | 10 | 30 | 20221030 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 16566401.6557 | 16779531.6585 | 213130.0028 | 0 | 760 | 0%
2022-01-12 | 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N62473 | N6247314D0039 0011 | N6247314D0039 | N61065202,N6247314D0039 0011 | 15972000 | 14709000 | 2018-06-10 | 2019-12-11 | -1263000 | 549 | 2019 | 12 | 11 | 20191211 | 2016 | 2020 | 1.1519 | 2018 | 1.1519 | 18397629.2261 | 16942820.4537 | -1454808.7724 | 549 | 650 | 84.46%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 81412 | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | W912GB10C0031, | 76007,W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2027-09-30 | -1832000 | 639 | 2027 | 09 | 30 | 20270930 | 2012 | 2027 | 1.1227 | 2020 | 1.0751 | 17984078.8589 | 16014536.5171 | -1969542.3418 | 639 | 5038 | 12.68%
2022-01-06 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Delta Mechanical Contractors, LLC | W91278 | W91278-16-C-0021 | W9127816C0021 | FTEV073010,W91278-16-C-0021 | 16065430 | 16483443 | 2018-09-15 | 2021-11-30 | 418013 | 1172 | 2021 | 11 | 30 | 20211130 | 2016 | 2022 | 1.0751 | 2019 | 1.0507 | 17271585.4936 | 17710792.1439 | 439206.6503 | 1172 | 774 | 151.4%
2020-12-09 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10 | MWHL10-3001 | MWHL103001 | 18053,MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31 | 353000 | 484 | 2014 | 05 | 31 | 20140531 | 2012 | 2014 | 1.0507 | 2013 | 1.0006 | 16911031.5626 | 17264247.0133 | 353215.4506 | 484 | 352 | 137.5%
2021-12-31 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-05 | 2018-02-01 | Okland Construction, Co. Inc. | W912PL | W912PL18C0013 | W912PL18C0013 | NUEX093016,W912PL18C0013 | 16223496 | 16246162 | 2020-02-26 | 2020-04-11 | 22666 | 45 | 2020 | 04 | 11 | 20200411 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 16233397.8773 | 16255542.0543 | 22144.1769 | 45 | 755 | 5.96%
2022-01-13 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G | W9126G-12-C-0051 | W9126G12C0051 | 72754,W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02 | 6516000 | 766 | 2016 | 09 | 02 | 20160902 | 2012 | 2016 | 1.1519 | 2014 | 1.0993 | 18797327.2815 | 25960074.2379 | 7162746.9564 | 766 | 676 | 113.3%
2022-01-12 | 2018 | Navy Reserve | N63042366 |  | 2018-06-04 | 2019-04-11 | SOLPAC CONSTRUCTION INC | N62473 | N6247318D5855 | N6247318D5855 | N63042366,N6247318D5855 | 16347000 | 16549000 | 2021-03-26 | 2022-03-02 | 202000 | 341 | 2022 | 03 | 02 | 20220302 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 15970654.7315 | 16163971.1608 | 193316.4292 | 341 | 715 | 47.69%
2022-01-06 | 2018 | Special Operations Command | 79443 |  | 2018-09-07 | 2018-12-19 | ACC | W912PM | W912PM19C0007 | W912PM19C0007 | 79443,W912PM19C0007 | 16474525 | 17708403 | 2020-12-27 | 2021-08-18 | 1233878 | 234 | 2021 | 08 | 18 | 20210818 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 16929075.8819 | 18163706.9692 | 1234631.0873 | 234 | 739 | 31.66%
2022-01-12 | 2020 | Army National Guard | 220304 |  | 2021-07-29 | 2021-09-07 | Mapp Construction | LA21-C | LA21-C-116 | LA21C116 | 220304,LA21-C-116 | 16500000 | 17876000 | 2023-02-24 | 2023-02-24 | 1376000 | 0 | 2023 | 02 | 24 | 20230224 | 2021 | 2023 | 1.0993 | 2022 | 1.0751 | 18137710.9852 | 19617017.897 | 1479306.9117 | 0 | 535 | 0%
2022-01-06 | 2008 | Special Operations Command | 65394 |  | 2007-11-26 | 2008-03-28 | ACC Construction Co. | W912HN | W912HN-07-D-0042 | W912HN07D0042 |  | 16571575 | 16883761 | 2010-04-21 | 2010-07-31 | 312186 | 101 | 2010 | 07 | 31 | 20100731 | 2008 | 2010 | 1.0751 | 2009 | 1.0276 | 17815730.6948 | 18136530.2616 | 320799.5668 | 101 | 754 | 13.4%
2022-01-06 | 2016 | Special Operations Command | CZQZ133003 |  | 2016-12-13 | 2018-10-05 | Federal Contracting, Inc. | W912PP | W912PP19C0001 | W912PP19C0001 | CZQZ133003,W912PP19C0001 | 16606634 | 16964180 | 2021-05-16 | 2022-02-22 | 357546 | 282 | 2022 | 02 | 22 | 20220222 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 16616769.7225 | 16958945.5443 | 342175.8218 | 282 | 954 | 29.56%
2021-12-31 | 2019 | Air Force Active | XLWU193006 |  | 2019-08-26 | 2019-09-26 | Southeast Cherokee Const INC | W91278 | W9127810518 | W9127810518 | XLWU193006,W9127810518 | 16624000 | 16614000 | 2021-11-02 | 2021-11-02 | -10000 | 0 | 2021 | 11 | 02 | 20211102 | 2019 | 2022 | 1.0993 | 2021 | 1.0507 | 18274018.6314 | 18263511.6221 | -10507.0094 | 0 | 768 | 0%
2022-01-06 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278 | W91278-11-D-0068 | W9127811D0068 | 76366,W91278-11-D-0068 | 16664200 | 19188822 | 2015-09-12 | 2016-01-27 | 2524622 | 137 | 2016 | 01 | 27 | 20160127 | 2012 | 2016 | 1.0276 | 2014 | 0.97698 | 17123984.2309 | 19590483.6674 | 2466499.4366 | 137 | 1145 | 11.97%
2022-01-07 | 2020 | Washington Headquarters Services | 92232 |  | 2020-03-12 | 2021-03-25 | Grunley Construction Company, Inc. | W912DR | W912DR-21-C-0009 | W912DR21C0009 | 92232,W912DR-21-C-0009 | 16690000 | 16690000 | 2023-04-30 | 2023-06-30 | 0 | 61 | 2023 | 06 | 30 | 20230630 | 2021 | 2023 | 1.2319 | 2022 | 1.1743 | 20561031.126 | 20561031.126 | 0 | 61 | 766 | 7.963%
2021-12-31 | 2018 | Army Active | 65699 |  | 2018-08-16 | 2018-09-30 | Leebcor Services, LLC | W91278 | W91278-16-D-0033 | W9127816D0033 | 65699,W91278-16-D-0033 | 16707000 | 18188000 | 2020-10-28 | 2021-11-30 | 1481000 | 398 | 2021 | 11 | 30 | 20211130 | 2018 | 2022 | 0.97698 | 2020 | 0.95701 | 16322366.7095 | 17739701.5199 | 1417334.8105 | 398 | 759 | 52.44%
2021-12-31 | 2018 | Air Force Active | MSET153506 |  | 2018-06-04 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153506,DIOCB2076 | 16724478 | 16724478 | 2022-12-21 | 2022-12-21 | 0 | 0 | 2022 | 12 | 21 | 20221221 | 2019 | 2023 | 1.0507 | 2021 | 1.0006 | 17572424.6863 | 17572424.6863 | 0 | 0 | 1498 | 0%
2022-01-06 | 2017 | Special Operations Command | LXEZ123484 |  | 2018-04-12 | 2019-05-30 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV | W912HV-16-D-0009 | W912HV16D0009 | LXEZ123484,W912HV-16-D-0009 | 16739026 | 17190622 | 2021-09-27 | 2021-09-29 | 451596 | 2 | 2021 | 09 | 29 | 20210929 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 16749242.5268 | 17190441.7557 | 441199.2289 | 2 | 851 | 0.235%
2022-01-06 | 2008 | Special Operations Command | 61772 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER | W912ER-12-C-0011 | W912ER12C0011 | 61772,W912ER-12-C-0011 | 16750710 | 17544730 | 2013-04-25 | 2015-01-21 | 794020 | 636 | 2015 | 01 | 21 | 20150121 | 2012 | 2015 | 1.0751 | 2014 | 1.0276 | 18008314.7381 | 18824242.653 | 815927.9149 | 636 | 477 | 133.3%
2022-01-06 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN | W912HN-10-D-0055 | W912HN10D0055 | 69458,W912HN-10-D-0055 | 16772305 | 19445395 | 2014-06-03 | 2016-03-04 | 2673090 | 640 | 2016 | 03 | 04 | 20160304 | 2012 | 2016 | 1.1227 | 2014 | 1.0751 | 18829793.106 | 21703572.5484 | 2873779.4424 | 640 | 623 | 102.7%
2021-12-31 | 2021 | Air Force Reserve | DDPM414415 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N69450 | N6945021C0038 | N6945021C0038 | DDPM414415,N6945021C0038 | 16788096 | 16788096 | 2024-09-30 | 2024-09-30 | 0 | 0 | 2024 | 09 | 30 | 20240930 | 2021 | 2024 | 1.0276 | 2023 | 0.97698 | 17251298.6624 | 17251298.6624 | 0 | 0 | 1097 | 0%
2022-01-06 | 2018 | Special Operations Command | 81903 |  | 2018-10-30 | 2019-03-25 | KYUDENKO CORPORATION | W912HV | W912HV19C0004 | W912HV19C0004 | 81903,W912HV19C0004 | 16975565 | 17857223 | 2021-04-18 | 2022-04-06 | 881658 | 353 | 2022 | 04 | 06 | 20220406 | 2019 | 2022 | 1.0507 | 2021 | 0.97698 | 17836242.0322 | 18697602.2518 | 861360.2196 | 353 | 755 | 46.75%
2022-01-06 | 2019 | Special Operations Command | 80774 |  | 2019-06-10 | 2019-09-30 | ACC | W912PM | W912PM19C0042 | W912PM19C0042 | 80774,W912PM19C0042 | 17061326 | 17061326 | 2022-01-06 | 2022-01-06 | 0 | 0 | 2022 | 01 | 06 | 20220106 | 2019 | 2022 | 1.1914 | 2021 | 1.0993 | 20326191.8826 | 20326191.8826 | 0 | 0 | 829 | 0%
2022-01-31 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F | W9128F-15-C-0032 | W9128F15C0032 | DESC1507,W9128F-15-C-0032 | 17178089 | 17906802 | 2017-03-23 | 2018-05-16 | 728713 | 419 | 2018 | 05 | 16 | 20180516 | 2015 | 2018 | 0.97698 | 2017 | 0.95701 | 16782610.165 | 17479997.2694 | 697387.1045 | 419 | 540 | 77.59%
2021-12-30 | 2015 | DLA Defense Energy Support Center | DESC1507 |  | 2015-02-02 | 2016-08-16 | Cape Environemental | N40080 | N40080-16-C-0161 | N4008016C0161 | DESC1507,N40080-16-C-0161 | 17178089 | 18765895 | 2018-02-07 | 2018-10-15 | 1587806 | 250 | 2018 | 10 | 15 | 20181015 | 2016 | 2019 | 1.0507 | 2018 | 1.0006 | 18049034.1885 | 19637809.2929 | 1588775.1043 | 250 | 540 | 46.3%
2022-01-12 | 2016 | Navy Active | N68436401 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N44255 | N4425517C8002 AWD | N4425517C8002 | N68436401,N4425517C8002 AWD | 17270000 | 17652000 | 2020-01-04 | 2021-07-06 | 382000 | 549 | 2021 | 07 | 06 | 20210706 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 17746498.9419 | 18128732.0924 | 382233.1506 | 549 | 830 | 66.14%
2022-01-12 | 2020 | Marine Corps Active | M670011507F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | M670011507F,N4008520D0034 N4008520F6501 | 17318680 | 21230000 | 2024-05-27 | 2025-01-07 | 3911320 | 225 | 2025 | 01 | 07 | 20250107 | 2020 | 2025 | 1.2581 | 2023 | 1.2082 | 21787951.3214 | 26513711.1878 | 4725759.8664 | 225 | 1350 | 16.67%
2021-12-31 | 2018 | Army Reserve | 88731 |  | 2018-06-29 | 2019-06-05 | Caribe General Constructors | W912QR | W912QR19C0018 | W912QR19C0018 | 88731,W912QR19C0018 | 17399000 | 18625000 | 2020-12-19 | 2022-02-15 | 1226000 | 423 | 2022 | 02 | 15 | 20220215 | 2019 | 2022 | 1.0993 | 2021 | 1.0276 | 19125941.4201 | 20385768.1545 | 1259826.7344 | 423 | 563 | 75.13%
2021-12-30 | 2014 | DLA Defense Energy Support Center | DESC1502 B |  | 2015-01-19 | 2015-05-04 | Rockford Corporation | W912BV | W912BV-15-C-0017 | W912BV15C0017 | DESC1502 B,W912BV-15-C-0017 | 17410000 | 17410000 | 2016-10-23 | 2021-11-18 | 0 | 1852 | 2021 | 11 | 18 | 20211118 | 2015 | 2022 | 1.0507 | 2019 | 1.0276 | 18292703.2933 | 18292703.2933 | 0 | 1852 | 538 | 344.2%
2022-01-12 | 2018 | Army National Guard | 230135 |  | 2018-07-20 | 2018-08-14 | Devoe Construction | 230135 | 230135-D | 230135D | 230135,230135-D | 17500000 | 18990000 | 2020-09-01 | 2021-12-31 | 1490000 | 486 | 2021 | 12 | 31 | 20211231 | 2018 | 2022 | 1.1743 | 2020 | 1.1519 | 20550573.7122 | 22266856.4286 | 1716282.7164 | 486 | 749 | 64.89%
2022-01-12 | 2021 | Marine Corps Active | N41557296 |  | 2020-08-18 | 2021-03-17 | CORE TECH-HDCC-KAJIMA LLC | N62742 | N6274219D1330 N6274221F9928 | N6274219D1330 | N41557296,N6274219D1330 N6274221F9928 | 17683000 | 17949000 | 2023-03-28 | 2023-03-28 | 266000 | 0 | 2023 | 03 | 28 | 20230328 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 18170894.0816 | 18430770.1542 | 259876.0726 | 0 | 741 | 0%
2022-01-12 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N62742 | N6274214C1300 AWD | N6274214C1300 | M00318884,N6274214C1300 AWD | 17720000 | 16256000 | 2016-12-18 | 2019-10-24 | -1464000 | 1040 | 2019 | 10 | 24 | 20191024 | 2014 | 2020 | 1.1914 | 2017 | 1.0993 | 21110910.1461 | 19501600.5169 | -1609309.6292 | 1040 | 810 | 128.4%
2022-01-12 | 2017 | Navy Reserve | M68479777 |  | 2017-07-25 | 2020-02-05 | OAK GROUP, INC., THE | N40085 | N4008517D5038 N4008520F4527 | N4008517D5038 | M68479777,N4008517D5038 N4008520F4527 | 17729000 | 25256000 | 2021-08-30 | 2022-06-01 | 7527000 | 275 | 2022 | 06 | 01 | 20220601 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 18627876.8918 | 26159470.9344 | 7531594.0425 | 275 | 572 | 48.08%
2022-01-12 | 2020 | Marine Corps Active | M00146246F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520C0055 AWD | N4008520C0055 | M00146246F,N4008520C0055 AWD | 17747042 | 19387000 | 2025-08-12 | 2025-08-12 | 1639958 | 0 | 2025 | 08 | 12 | 20250812 | 2020 | 2025 | 1.0006 | 2023 | 0.9382 | 17757873.7611 | 19296479.1829 | 1538605.4218 | 0 | 1826 | 0%
2022-01-12 | 2019 | Marine Corps Active | M670011300F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011300F,N4008520C0044 AWD | 17826000 | 18328000 | 2024-10-12 | 2025-01-11 | 502000 | 91 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0006 | 2023 | 0.97698 | 17836879.9525 | 18327322.7661 | 490442.8137 | 91 | 1541 | 5.905%
2022-01-12 | 2019 | Marine Corps Active | N62813216 |  | 2019-09-06 | 2020-02-03 | RORE, INC. | N62478 | N6247818D4024 N6274220F4001 | N6247818D4024 | N62813216,N6247818D4024 N6274220F4001 | 17897000 | 17831000 | 2020-12-29 | 2022-06-30 | -66000 | 548 | 2022 | 06 | 30 | 20220630 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 18804394.649 | 18738354.3665 | -66040.2826 | 548 | 330 | 166.1%
2021-12-31 | 2017 | Air Force Active | FTQW170100 |  | 2017-03-21 | 2017-06-06 | Silver Mountain Construction LLC | W911KB | W911KB17C0021 | W911KB17C0021 | FTQW170100,W911KB17C0021 | 17956192 | 18837872 | 2019-04-27 | 2019-04-27 | 881680 | 0 | 2019 | 04 | 27 | 20190427 | 2017 | 2019 | 1.0751 | 2018 | 1.0507 | 19304301.5511 | 20230683.5522 | 926382.0011 | 0 | 690 | 0%
2022-01-06 | 2017 | Special Operations Command | 74813 |  | 2017-11-16 | 2018-06-15 | ACC Construction Co., Inc. | W912PM | W912PM18C0014 | W912PM18C0014 | 74813,W912PM18C0014 | 17972005 | 24165689 | 2020-09-04 | 2021-11-01 | 6193684 | 423 | 2021 | 11 | 01 | 20211101 | 2018 | 2022 | 1.2082 | 2020 | 1.1914 | 21714249.9073 | 29093161.1035 | 7378911.1962 | 423 | 812 | 52.09%
2022-01-12 | 2019 | Marine Corps Active | N41557295 |  | 2019-04-15 | 2019-09-16 | NAN INC. DBAOCEAN HOUSE BUILDERS | N62742 | N6274219C1301 AWD | N6274219C1301 | N41557295,N6274219C1301 AWD | 18002000 | 16749000 | 2021-12-04 | 2021-12-04 | -1253000 | 0 | 2021 | 12 | 04 | 20211204 | 2019 | 2022 | 1.2581 | 2021 | 1.1914 | 22647609.3841 | 21154834.5301 | -1492774.854 | 0 | 810 | 0%
2022-01-12 | 2021 | Army National Guard | 040037 |  | 2021-05-02 | 2021-05-24 | Lloyd Construction Company | CTR054 | CTR054747 | CTR054747 | 040037,CTR054747 | 18100000 | 17120000 | 2022-08-26 | 2022-08-26 | -980000 | 0 | 2022 | 08 | 26 | 20220826 | 2021 | 2022 | 1.0006 | 2022 | 0.97698 | 18111047.1861 | 17153609.024 | -957438.1622 | 0 | 459 | 0%
2022-01-12 | 2019 | Navy Active | N62863811 |  | 2020-12-28 | 2021-08-30 | ACCIONA CMS JV, LLC | N62470 | N6247021D0011 N6247021F9009 | N6247021D0011 | N62863811,N6247021D0011 N6247021F9009 | 18113697.55 | 18131000 | 2024-04-16 | 2024-04-16 | 17302.45 | 0 | 2024 | 04 | 16 | 20240416 | 2021 | 2024 | 0.97698 | 2023 | 0.95701 | 17696678.8697 | 17713237.5224 | 16558.6527 | 0 | 960 | 0%
2021-08-31 | 2015 | Army Active | 77831 |  | 2018-02-26 | 2019-05-07 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV | W912HV16D0009 | W912HV16D0009 | 77831,W912HV16D0009 | 18324000 | 18905000 | 2021-05-25 | 2021-06-25 | 581000 | 31 | 2021 | 06 | 25 | 20210625 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 18829580.0006 | 19397204.0539 | 567624.0533 | 31 | 749 | 4.139%
2022-01-12 | 2016 | Marine Corps Reserve | N50092152 |  | 2019-05-02 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519C9061 AWD | N4008519C9061 | N50092152,N4008519C9061 AWD | 18501000 | 17819000 | 2021-09-14 | 2022-01-14 | -682000 | 122 | 2022 | 01 | 14 | 20220114 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 18075064.7329 | 17435213.6528 | -639851.0801 | 122 | 715 | 17.06%
2022-01-06 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-26 | Engineering Design Technologies, Inc. | W912HN | W912HN-11-D-0002 | W912HN11D0002 | 71224,W912HN-11-D-0002 | 18525847 | 23524962 | 2014-07-30 | 2015-04-27 | 4999115 | 271 | 2015 | 04 | 27 | 20150427 | 2012 | 2015 | 1.0006 | 2014 | 0.95701 | 18537154.0983 | 23321367.2726 | 4784213.1742 | 271 | 672 | 40.33%
2022-01-06 | 2010 | Special Operations Command | 66315 |  | 2010-04-27 | 2010-08-05 | Sauer Inc | W912HN | W912HN-10-C-0054 | W912HN10C0054 | 66315,W912HN-10-C-0054 | 18649100 | 22880316 | 2013-02-11 | 2014-07-22 | 4231216 | 526 | 2014 | 07 | 22 | 20140722 | 2010 | 2014 | 1.0507 | 2012 | 1.0006 | 19594626.8229 | 23828425.3108 | 4233798.4879 | 526 | 921 | 57.11%
2022-01-13 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 | N4008013C0151 | N4008013C0151 | 71408,N4008013C0151 | 18688000 | 21664000 | 2016-12-06 | 2019-02-15 | 2976000 | 801 | 2019 | 02 | 15 | 20190215 | 2013 | 2019 | 1.0006 | 2016 | 0.95701 | 18699406.0671 | 21547473.8564 | 2848067.7893 | 801 | 1499 | 53.44%
2022-01-12 | 2018 | Marine Corps Active | M00318887 |  | 2018-04-04 | 2018-12-28 | KIEWIT INFRASTRUCTURE WEST CO. | N62742 | N6274219C1321 AWD | N6274219C1321 | M00318887,N6274219C1321 AWD | 18697000 | 19344000 | 2020-08-19 | 2021-01-25 | 647000 | 159 | 2021 | 01 | 25 | 20210125 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 19644955.3977 | 20292350.2889 | 647394.8911 | 159 | 600 | 26.5%
2022-01-13 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 | N62473 10 D 5412 DO 0007 | N62473 | 72808,N62473 10 D 5412 DO 0007 | 18703000 | 19971000 | 2015-03-16 | 2017-04-28 | 1268000 | 774 | 2017 | 04 | 28 | 20170428 | 2014 | 2017 | 1.2319 | 2016 | 1.2082 | 23040920.6201 | 24572951.6252 | 1532031.005 | 774 | 444 | 174.3%
2022-01-12 | 2020 | Marine Corps Active | M626132001 |  | 2020-11-13 | 2021-02-11 | SANKYO REINETSU CO., LTD. | N40084 | N4008420D0073 N4008421F4127 | N4008420D0073 | M626132001,N4008420D0073 N4008421F4127 | 18797000 | 17902000 | 2023-07-02 | 2023-07-02 | -895000 | 0 | 2023 | 07 | 02 | 20230702 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 19750025.4913 | 18854479.2354 | -895546.2559 | 0 | 871 | 0%
2021-12-31 | 2020 | Army Reserve | 81802 |  | 2020-07-30 | 2020-09-29 | LS Black Constructors | W912QR | W912QR20C0052 | W912QR20C0052 | 81802,W912QR20C0052 | 18824000 | 19077000 | 2022-12-17 | 2022-12-17 | 253000 | 0 | 2022 | 12 | 17 | 20221217 | 2020 | 2023 | 1.0751 | 2022 | 1.0006 | 20237262.5776 | 20490416.994 | 253154.4165 | 0 | 809 | 0%
2021-12-31 | 2018 | Army Reserve | 77074 |  | 2019-08-05 | 2019-09-27 | RBC Constuction | W912QR | W912QR19C0046 | W912QR19C0046 | 77074,W912QR19C0046 | 18838000 | 19063000 | 2021-04-22 | 2022-05-10 | 225000 | 383 | 2022 | 05 | 10 | 20220510 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 19793104.2297 | 20018241.5566 | 225137.3269 | 383 | 573 | 66.84%
2021-10-14 | 2020 | Defense Health Agency | 94639 |  | 2021-04-19 | 2021-09-27 | RQ Construction | N40085 | N4008520D0034 | N4008520D0034 | 94639,N4008520D0034 | 18842000 | 18842000 | 2024-07-15 |  | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2021 | #VALUE! | 1.0006 | #VALUE! | 0.95701 | 18853500.0597 | 18853500.0597 | 0 | #VALUE! | 1022 | #VALUE!
2021-12-31 | 2019 | Army Active | 61388 |  | 2019-03-15 | 2019-06-14 | ETERNA SA | W91278 | W9127819C0019 | W9127819C0019 | 61388,W9127819C0019 | 18881000 | 18977000 | 2022-07-14 | 2022-10-13 | 96000 | 91 | 2022 | 10 | 13 | 20221013 | 2019 | 2023 | 1.1519 | 2021 | 1.0751 | 21748412.0597 | 21851619.5187 | 103207.459 | 91 | 1126 | 8.082%
2022-01-12 | 2017 | Navy Active | N32446285 |  | 2017-01-17 | 2017-06-29 | L.S. BLACK CONSTRUCTORS-LOEFFELCONSTRUCTION | N40085 | N4008517C5056 AWD | N4008517C5056 | N32446285,N4008517C5056 AWD | 18927000 | 19723000 | 2019-05-10 | 2021-01-21 | 796000 | 622 | 2021 | 01 | 21 | 20210121 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 19449217.4564 | 20245703.2885 | 796485.8321 | 622 | 680 | 91.47%
2022-01-12 | 2017 | Navy Active | N60495440 |  | 2017-07-20 | 2018-08-06 | STRAUB CONSTRUCTION, INC. | N62473 | N6247316D1887 N6247318F4874 | N6247316D1887 | N60495440,N6247316D1887 N6247318F4874 | 18936000 | 18999000 | 2020-08-25 | 2020-10-17 | 63000 | 53 | 2020 | 10 | 17 | 20201017 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 19458465.7767 | 19521504.2282 | 63038.4515 | 53 | 750 | 7.067%
2021-08-31 | 2018 | Army Active | 73375 |  | 2018-07-13 | 2018-09-25 | HHI Corporation | W9128F | W9128F18C0037 | W9128F18C0037 | 73375,W9128F18C0037 | 18943000 | 19040000 | 2020-06-24 | 2020-12-01 | 97000 | 160 | 2020 | 12 | 01 | 20201201 | 2018 | 2021 | 1.2082 | 2020 | 1.1914 | 22887431.6468 | 23002993.6268 | 115561.9799 | 160 | 638 | 25.08%
2021-11-30 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | W911KB | W911KB18C0028 | W911KB18C0028 | 674,W911KB18C0028 | 18965310 | 19525000 | 2018-10-30 | 2018-10-11 | 559690 | -19 | 2018 | 10 | 11 | 20181011 | 2018 | 2019 | 1.0276 | 2019 | 1.0006 | 19488584.4729 | 20048616.0751 | 560031.6022 | -19 | 176 | -10.8%
2021-12-31 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | W911KB | W911KB-18-C-0028 | W911KB18C0028 | 674,W911KB-18-C-0028 | 18965310 | 19525000 | 2018-10-30 | 2018-10-11 | 559690 | -19 | 2018 | 10 | 11 | 20181011 | 2018 | 2019 | 1.0276 | 2019 | 1.0006 | 19488584.4729 | 20048616.0751 | 560031.6022 | -19 | 176 | -10.8%
2022-01-12 | 2021 | Navy Active | N61065243 |  | 2021-05-05 | 2021-08-12 | REYES CONSTRUCTION INC | N62473 | N6247318D5862 N6247321F5105 | N6247318D5862 | N61065243,N6247318D5862 N6247321F5105 | 18993300 | 21649000 | 2023-08-27 | 2023-08-27 | 2655700 | 0 | 2023 | 08 | 27 | 20230827 | 2021 | 2023 | 0.97698 | 2022 | 0.95701 | 18556030.8627 | 21097567.7001 | 2541536.8374 | 0 | 745 | 0%
2022-01-12 | 2018 | Army National Guard | 240149 |  | 2018-09-17 | 2018-09-18 | Towson Mechanical Inc. | M-900- | M-900-160-0004 | M9001600004 | 240149,M-900-160-0004 | 19000000 | 17704000 | 2021-04-23 | 2021-06-30 | -1296000 | 68 | 2021 | 06 | 30 | 20210630 | 2018 | 2021 | 0.97698 | 2020 | #N/A | 18562576.6134 | #N/A | #N/A | 68 | 948 | 7.173%
2022-01-12 | 2016 | Army National Guard | 530041 |  | 2018-01-19 | 2018-06-28 | TDX Quality, LLC | W912DW | W912DW-18-C-0015 | W912DW18C0015 | 530041,W912DW-18-C-0015 | 19000000 | 20635000 | 2020-04-17 | 2021-12-30 | 1635000 | 622 | 2021 | 12 | 30 | 20211230 | 2018 | 2022 | 1.2082 | 2020 | 1.1914 | 22956300.5485 | 24904175.1585 | 1947874.61 | 622 | 659 | 94.39%
2022-01-12 | 2018 | Army National Guard | 200151 |  | 2018-09-12 | 2018-09-14 | Straub Construction Co., Inc. | W912JC | W912JC-18-2-20001 | W912JC18220001 | 200151,W912JC-18-2-20001 | 19000000 | 18828000 | 2020-05-14 | 2021-11-01 | -172000 | 536 | 2021 | 11 | 01 | 20211101 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 19011596.4937 | 18843556.3265 | -168040.1672 | 536 | 608 | 88.16%
2021-12-31 | 2018 | Air Force Active | FTQW180107 |  | 2017-12-28 | 2018-03-23 | Callahan/Watterson Joint Ventu | W911KB | W911KB18C0018 | W911KB18C0018 | FTQW180107,W911KB18C0018 | 19051000 | 24167601 | 2020-02-14 | 2020-08-11 | 5116601 | 179 | 2020 | 08 | 11 | 20200811 | 2018 | 2020 | 1.0751 | 2019 | 1.0507 | 20481305.2149 | 25857322.674 | 5376017.4591 | 179 | 693 | 25.83%
2022-01-06 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278 | W91278-11-D-0068 | W9127811D0068 | 76371,W91278-11-D-0068 | 19092800 | 20598546 | 2015-09-12 | 2016-01-27 | 1505746 | 137 | 2016 | 01 | 27 | 20160127 | 2012 | 2016 | 0.97698 | 2014 | 0.95701 | 18653240.1455 | 20094257.1755 | 1441017.0301 | 137 | 1145 | 11.97%
2022-01-12 | 2019 | Marine Corps Active | M670011199F |  | 2019-10-15 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011199F,N4008520C0044 AWD | 19142000 | 19343000 | 2024-10-12 | 2025-01-11 | 201000 | 91 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.2826 | 2023 | 1.2319 | 24550838.894 | 24798458.2623 | 247619.3683 | 91 | 1541 | 5.905%
2022-01-12 | 2019 | Navy Reserve | N61065160 |  | 2018-11-01 | 2019-01-24 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318D5853 N6247319F4183 | N6247318D5853 | N61065160,N6247318D5853 N6247319F4183 | 19180000 | 20082000 | 2021-02-07 | 2021-06-01 | 902000 | 114 | 2021 | 06 | 01 | 20210601 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 19191706.3552 | 20072940.2555 | 881233.9003 | 114 | 745 | 15.3%
2022-01-12 | 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N62470 | N6247016C6001 AWD | N6247016C6001 | N62863712,N6247016C6001 AWD | 19252000 | 22395000 | 2018-05-23 | 2022-02-24 | 3143000 | 1373 | 2022 | 02 | 24 | 20220224 | 2016 | 2022 | 1.0993 | 2019 | 1.0507 | 21162861.3265 | 24465214.3679 | 3302353.0414 | 1373 | 915 | 150.1%
2021-12-31 | 2017 | Air Force Active | DXEB053005 |  | 2017-04-26 | 2018-04-30 | Bethel-Unit JV | W911KB | W911KB18C0006 | W911KB18C0006 | DXEB053005,W911KB18C0006 | 19278001 | 20221652 | 2020-04-11 | 2021-10-11 | 943651 | 548 | 2021 | 10 | 11 | 20211011 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 19809902.9732 | 20754129.9229 | 944226.9496 | 548 | 712 | 76.97%
2021-08-31 | 2016 | Army Reserve | 77186 |  | 2017-04-03 | 2017-07-13 | ACC Construction Co, Inc. | W912QR | W912QR17C0021 | W912QR17C0021 | 77186,W912QR17C0021 | 19332000 | 19415000 | 2019-08-31 | 2020-12-15 | 83000 | 472 | 2020 | 12 | 15 | 20201215 | 2017 | 2021 | 1.1914 | 2019 | 1.1227 | 23031383.4619 | 23124565.2176 | 93181.7557 | 472 | 779 | 60.59%
2022-01-06 | 2016 | Special Operations Command | ANZY163001 |  | 2017-09-15 | 2018-02-22 | Southeast Cherokee Construction, Inc | W91278 | W91278-16-D-0015 | W9127816D0015 | ANZY163001,W91278-16-D-0015 | 19344000 | 20218608 | 2019-10-03 | 2022-01-31 | 874608 | 851 | 2022 | 01 | 31 | 20220131 | 2018 | 2022 | 1.0276 | 2020 | 0.97698 | 19877722.9607 | 20732195.4874 | 854472.5267 | 851 | 588 | 144.7%
2022-01-06 | 2011 | Special Operations Command | 63049 |  | 2011-06-14 | 2011-09-09 | Speegle Construction, Inc. | W912PP | W912PP-11-C-0029 | W912PP11C0029 | 63049,W912PP-11-C-0029 | 19432000 | 20310963 | 2013-12-01 | 2014-04-11 | 878963 | 131 | 2014 | 04 | 11 | 20140411 | 2011 | 2014 | 1.0507 | 2013 | 1.0507 | 20417220.5856 | 21340747.8323 | 923527.2467 | 131 | 814 | 16.09%
2022-01-12 | 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLPAC CONSTRUCTION INC | N62473 | N6247310D5411 0012 | N6247310D5411 | M00681970,N6247310D5411 0012 | 19459000 | 23408000 | 2018-04-27 | 2020-11-27 | 3949000 | 945 | 2020 | 11 | 27 | 20201127 | 2016 | 2021 | 1.0507 | 2019 | 1.0507 | 20445589.5109 | 24594807.5066 | 4149217.9957 | 945 | 849 | 111.3%
2022-01-12 | 2021 | Navy Active | N360423271 |  | 2020-10-30 | 2021-03-25 | SYNERGY ELECTRIC COMPANY INC | N62473 | N6247319D2430 N6247321F4370 | N6247319D2430 | N360423271,N6247319D2430 N6247321F4370 | 19465544 | 49122000 | 2023-05-03 | 2023-10-16 | 29656456 | 166 | 2023 | 10 | 16 | 20231016 | 2021 | 2024 | 1.0993 | 2023 | 1.0276 | 21397600.6814 | 51872312.0319 | 30474711.3505 | 166 | 769 | 21.59%
2022-05-02 | 2018 | DLA Defense Energy Support Center | DESC1714 |  | 2018-08-09 | 2019-06-07 | Creative Times Inc | W91238 | W9123819C0010 | W9123819C0010 | DESC1714,W9123819C0010 | 19480000 | 20000032 | 2021-07-07 | 2022-01-31 | 520032 | 208 | 2022 | 01 | 31 | 20220131 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 19031525.9173 | 19529202.7952 | 497676.8779 | 208 | 761 | 27.33%
2022-01-06 | 2013 | Special Operations Command | CZQZ083013 |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP | W912PP-14-C-0014 | W912PP14C0014 | CZQZ083013,W912PP-14-C-0014 | 19481987 | 19876398 | 2015-11-22 | 2015-10-15 | 394411 | -38 | 2015 | 10 | 15 | 20151015 | 2014 | 2016 | 1.0507 | 2015 | 1.0006 | 20469741.9733 | 20864393.6988 | 394651.7255 | -38 | 549 | -6.922%
2022-01-12 | 2019 | Navy Active | N69232777 |  | 2019-05-30 | 2019-08-28 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318D5853 N6247319F5130 | N6247318D5853 | N69232777,N6247318D5853 N6247319F5130 | 19686000 | 21473000 | 2021-01-11 | 2021-11-24 | 1787000 | 317 | 2021 | 11 | 24 | 20211124 | 2019 | 2022 | 1.2082 | 2021 | 1.1743 | 23785143.8209 | 25883650.9766 | 2098507.1556 | 317 | 502 | 63.15%
2021-12-31 | 2020 | Army Reserve | 86823 |  | 2019-11-01 | 2020-03-26 | Harkins Builders | W912QR | W912QR20C0012 | W912QR20C0012 | 86823,W912QR20C0012 | 19751000 | 20351000 | 2022-03-28 | 2021-12-02 | 600000 | -116 | 2021 | 12 | 02 | 20211202 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 20295952.5536 | 20882139.1835 | 586186.6299 | -116 | 732 | -15.85%
2021-12-31 | 2020 | Air Force Active | BIKF190001 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N62470 | N6247020C0010 | N6247020C0010 | BIKF190001,N6247020C0010 | 19776676 | 19776676 | 2023-07-14 | 2023-07-14 | 0 | 0 | 2023 | 07 | 14 | 20230714 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 20779371.9814 | 20779371.9814 | 0 | 0 | 1026 | 0%
2021-12-31 | 2019 | Air Force Active | FTQW180109 |  | 2018-09-27 | 2019-02-28 | GHEMM Company, Inc | W911KB | W911KB19C0013 | W911KB19C0013 | FTQW180109,W911KB19C0013 | 19794920 | 20495551 | 2020-07-30 | 2020-12-29 | 700631 | 152 | 2020 | 12 | 29 | 20201229 | 2019 | 2021 | 1.1914 | 2020 | 1.0006 | 23582888.119 | 24283946.7434 | 701058.6244 | 152 | 518 | 29.34%
2021-12-31 | 2017 | Air Force Active | NZAS173001 |  | 2019-05-20 | 2019-06-19 | MMDF | W912DW | W912DW19C0008 | W912DW19C0008 | NZAS173001,W912DW19C0008 | 19868428 | 19868428 | 2021-03-10 | 2021-09-17 | 0 | 191 | 2021 | 09 | 17 | 20210917 | 2019 | 2021 | 1.0006 | 2020 | 0.97698 | 19880554.5316 | 19880554.5316 | 0 | 191 | 630 | 30.32%
2021-12-31 | 2016 | Air Force Active | NZAS043002 |  | 2019-05-06 | 2019-06-05 | Construct MMDF | W912DW | W912DW19C008 | W912DW19C008 | NZAS043002,W912DW19C008 | 19868428 | 19868428 | 2020-12-26 | 2020-08-31 | 0 | -117 | 2020 | 08 | 31 | 20200831 | 2019 | 2020 | 1.0276 | 2020 | 1.0006 | 20416620.5257 | 20416620.5257 | 0 | -117 | 570 | -20.53%
2022-01-12 | 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N44255 | N4425516C7002 AWD | N4425516C7002 | N68436431,N4425516C7002 AWD | 19943000 | 22666000 | 2017-11-14 | 2021-08-06 | 2723000 | 1361 | 2021 | 08 | 06 | 20210806 | 2016 | 2021 | 1.0507 | 2019 | 1.0006 | 20954128.7638 | 23678790.7245 | 2724661.9607 | 1361 | 460 | 295.9%
2022-01-12 | 2017 | Army National Guard | 440064 |  | 2017-09-06 | 2017-09-13 | Marion Construction Co Inc | W912LD | W912LD-15-2-2001 | W912LD1522001 | 440064,W912LD-15-2-2001 | 20000000 | 20595000 | 2020-02-28 | 2021-09-30 | 595000 | 580 | 2021 | 09 | 30 | 20210930 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 20012206.8355 | 20593508.5768 | 581301.7413 | 580 | 898 | 64.59%
2022-01-12 | 2017 | Army National Guard | 420502 |  | 2021-09-20 | 2021-09-29 | USPFO - PA | W912DR | W912DR-17-D-0014 | W912DR17D0014 | 420502,W912DR-17-D-0014 | 20000000 | 15725000 | 2023-08-10 | 2023-08-10 | -4275000 | 0 | 2023 | 08 | 10 | 20230810 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 19539554.3299 | 15528757.6034 | -4010796.7265 | 0 | 680 | 0%
2022-01-12 | 2016 | Navy Active | N00204723 |  | 2016-11-23 | 2017-06-28 | EMR, INC. | N69450 | N6945017D0507 N6945017F1003 | N6945017D0507 | N00204723,N6945017D0507 N6945017F1003 | 20056000 | 19270000 | 2019-10-16 | 2020-09-20 | -786000 | 340 | 2020 | 09 | 20 | 20200920 | 2017 | 2020 | 1.0507 | 2019 | 0.97698 | 21072857.9696 | 20304953.4844 | -767904.4852 | 340 | 840 | 40.48%
2022-01-12 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N40085 | N4008510D5331 0005 | N4008510D5331 | M67001726,N4008510D5331 0005 | 20159000 | 20079000 | 2019-02-01 | 2019-02-01 | -80000 | 0 | 2019 | 02 | 01 | 20190201 | 2014 | 2019 | 1.0276 | 2017 | 1.0006 | 20715209.7376 | 20635160.9103 | -80048.8273 | 0 | 1708 | 0%
2021-12-30 | 2020 | Air National Guard | XDQU109057 |  | 2020-06-23 | 2020-09-25 | Ashford Leebcor Enterprises IV LLC | W50S70 | W50S7020C0002 | W50S7020C0002 | XDQU109057,W50S7020C0002 | 20213955 | 20422750 | 2022-01-23 | 2022-03-27 | 208795 | 63 | 2022 | 03 | 27 | 20220327 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 20226292.4212 | 20426111.7471 | 199819.326 | 63 | 485 | 12.99%
2021-12-31 | 2019 | Army Reserve | 90202 |  | 2020-02-18 | 2020-09-04 | WHH Nisqually-Garco JVW | W912QR | W912QR20C0035 | W912QR20C0035 | 90202,W912QR20C0035 | 20217000 | 20217000 | 2022-06-22 | 2022-06-22 | 0 | 0 | 2022 | 06 | 22 | 20220622 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 19751558.4944 | 19751558.4944 | 0 | 0 | 656 | 0%
2021-12-30 | 2019 | Air National Guard | KNMD189008 |  | 2019-06-24 | 2020-08-07 | Pacific Federal Contractors, LLC | W912J6 | W912J620C0001 | W912J620C0001 | KNMD189008,W912J620C0001 | 20236741 | 18275318 | 2023-03-05 | 2023-03-05 | -1961423 | 0 | 2023 | 03 | 05 | 20230305 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 21262762.7074 | 19300142.569 | -1962620.1384 | 0 | 940 | 0%
2021-12-31 | 2018 | Army Active | 77102 |  | 2018-03-15 | 2018-09-21 | Creative Times Dayschool, Inc | W912PL | W912PL-18-C-0036 | W912PL18C0036 | 77102,W912PL-18-C-0036 | 20265000 | 23382000 | 2020-06-05 | 2022-01-25 | 3117000 | 599 | 2022 | 01 | 25 | 20220125 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 20824134.3982 | 23943036.8335 | 3118902.4353 | 599 | 623 | 96.15%
2022-05-03 | 2018 | DLA Defense Energy Support Center | DESC1608 |  | 2018-10-21 | 2019-03-20 | MEB | N69450 | N69450-19-c-1304 | N6945019c1304 | DESC1608,N69450-19-c-1304 | 20334000 | 20334000 | 2021-08-31 | 2021-03-01 | 0 | -183 | 2021 | 03 | 01 | 20210301 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 20895038.1867 | 20895038.1867 | 0 | -183 | 895 | -20.45%
2021-10-31 | 2014 | Army Active | 78712 |  | 2016-08-15 | 2017-08-08 | Staatliches Hochbauamt Amberg | W912GB | W912GB-12-C-0012 | W912GB12C0012 | 78712,W912GB-12-C-0012 | 20384000 | 20400000 | 2019-11-25 | 2021-09-21 | 16000 | 666 | 2021 | 09 | 21 | 20210921 | 2017 | 2021 | 1.1914 | 2019 | 1.1519 | 24284694.8317 | 24303124.7132 | 18429.8815 | 666 | 839 | 79.38%
2021-12-31 | 2019 | Air Force Reserve | SXHT203000 |  | 2020-06-01 | 2020-09-24 | Patriot Construction | W912QR | W912QR20C0050 | W912QR20C0050 | SXHT203000,W912QR20C0050 | 20438870 | 20438870 | 2022-07-25 | 2022-10-23 | 0 | 90 | 2022 | 10 | 23 | 20221023 | 2020 | 2023 | 1.0993 | 2022 | 1.0507 | 22467534.3591 | 22467534.3591 | 0 | 90 | 669 | 13.45%
2022-01-07 | 2019 | Washington Headquarters Services | 88790 |  | 2019-10-25 | 2020-03-27 | Grunley Construction Company, Inc. | W912DR | W912DR-20-C-0015 | W912DR20C0015 | 88790,W912DR-20-C-0015 | 20553000 | 20553000 | 2022-07-05 | 2022-09-08 | 0 | 65 | 2022 | 09 | 08 | 20220908 | 2020 | 2022 | 1.0006 | 2021 | 0.9382 | 20565544.3545 | 20565544.3545 | 0 | 65 | 830 | 7.831%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | N62470 | N62470-17-C-5003 | N6247017C5003 | DESC1701,N62470-17-C-5003 | 20577000 | 21577000 | 2020-11-30 | 2021-10-24 | 1000000 | 328 | 2021 | 10 | 24 | 20211024 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 20589559.0027 | 21566536.7192 | 976977.7165 | 328 | 1449 | 22.64%
2021-09-30 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | w | w | DESC1701,w | 20577000 | 20577000 | 2019-01-07 | 2019-01-07 | 0 | 0 | 2019 | 01 | 07 | 20190107 | 2017 | 2019 | 1.0006 | 2018 | 0.97698 | 20589559.0027 | 20589559.0027 | 0 | 0 | 756 | 0%
2021-12-31 | 2018 | Army Active | 75718 |  | 2018-07-02 | 2019-05-09 | Tocci Building Corporation | W912WJ | W912WJ19C0011 | W912WJ19C0011 | 75718,W912WJ19C0011 | 20612000 | 26382000 | 2021-06-02 | 2021-11-26 | 5770000 | 177 | 2021 | 11 | 26 | 20211126 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 21180708.5229 | 26817869.947 | 5637161.4242 | 177 | 755 | 23.44%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236 | W91236-16-C-0025 | W9123616C0025 | DESC1607,W91236-16-C-0025 | 20646000 | 21280000 | 2019-10-12 | 2019-12-12 | 634000 | 61 | 2019 | 12 | 12 | 20191212 | 2016 | 2020 | 1.0276 | 2018 | 1.0006 | 21215646.6215 | 21850033.5782 | 634386.9567 | 61 | 1121 | 5.442%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236 | W91236-16-R-0008-0005 | W9123616R00080005 | DESC1607,W91236-16-R-0008-0005 | 20646000 | 21088000 | 2019-10-12 | 2021-06-30 | 442000 | 627 | 2021 | 06 | 30 | 20210630 | 2016 | 2021 | 1.0276 | 2019 | 1.0006 | 21215646.6215 | 21657916.3926 | 442269.7711 | 627 | 1121 | 55.93%
2021-12-31 | 2019 | Army Reserve | 80690 |  | 2019-06-10 | 2019-09-27 | LS Black Constructors | W912QR | W912QR19C0051 | W912QR19C0051 | 80690,W912QR19C0051 | 20684000 | 21581000 | 2021-08-22 | 2021-12-05 | 897000 | 105 | 2021 | 12 | 05 | 20211205 | 2019 | 2022 | 1.1519 | 2021 | 1.0993 | 23825229.3333 | 24811261.2578 | 986031.9245 | 105 | 695 | 15.11%
2022-01-06 | 2020 | Special Operations Command | 92594 |  | 2020-02-12 | 2020-06-19 | Sauer Incorporated | W912PM | W912PM20C0016 | W912PM20C0016 | 92594,W912PM20C0016 | 20768000 | 22105601 | 2022-03-03 | 2022-08-23 | 1337601 | 173 | 2022 | 08 | 23 | 20220823 | 2020 | 2022 | 1.1227 | 2021 | 1.0751 | 23315647.028 | 24753672.0312 | 1438025.0032 | 173 | 622 | 27.81%
2022-01-12 | 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N62742 | N6274216C1317 AWD | N6274216C1317 | N41557230,N6274216C1317 AWD | 20799000 | 16445000 | 2019-01-29 | 2019-01-29 | -4354000 | 0 | 2019 | 01 | 29 | 20190129 | 2016 | 2019 | 1.1227 | 2018 | 1.0507 | 23350449.8524 | 18775697.9777 | -4574751.8747 | 0 | 1169 | 0%
2021-09-30 | 2017 | Air National Guard | FJRP159073 |  | 2018-02-23 | 2018-10-30 | Bodell Construction Company | W91242 | W9124219C5001 | W9124219C5001 | FJRP159073,W9124219C5001 | 20879519 | 20323383 | 2021-01-27 | 2021-01-27 | -556136 | 0 | 2021 | 01 | 27 | 20210127 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 21455608.6763 | 20912276.197 | -543332.4793 | 0 | 820 | 0%
2021-12-31 | 2017 | Army Active | 62380 |  | 2018-08-13 | 2018-08-22 | Staatliches Hochbauamt Amberg | W912GB | W912GB-16-C-0007 | W912GB16C0007 | 62380,W912GB-16-C-0007 | 20950000 | 23278000 | 2022-05-11 | 2023-07-15 | 2328000 | 430 | 2023 | 07 | 15 | 20230715 | 2018 | 2023 | 0.97698 | 2021 | 0.95701 | 20467683.1606 | 22695607.157 | 2227923.9965 | 430 | 1358 | 31.66%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1702 |  | 2017-02-09 | 2017-09-30 | MEB General Contractors, Inc. | W91299 | W91299-17-C-0011 | W9129917C0011 | DESC1702,W91299-17-C-0011 | 20973000 | 21083000 | 2019-06-25 | 2019-09-23 | 110000 | 90 | 2019 | 09 | 23 | 20190923 | 2017 | 2019 | 1.1227 | 2018 | 1.0993 | 23545794.7379 | 23666712.8112 | 120918.0732 | 90 | 633 | 14.22%
2022-01-12 | 2019 | Navy Active | N62604855 |  | 2019-02-22 | 2019-05-15 | EMR, INC. | N69450 | N6945017D0507 N6945019F0710 | N6945017D0507 | N62604855,N6945017D0507 N6945019F0710 | 21022000 | 21246000 | 2022-06-30 | 2022-06-30 | 224000 | 0 | 2022 | 06 | 30 | 20220630 | 2019 | 2022 | 1.2826 | 2021 | 1.2581 | 26962059.0967 | 27243864.7018 | 281805.605 | 0 | 1142 | 0%
2022-01-06 | 2018 | Special Operations Command | 79453 |  | 2018-01-12 | 2019-01-23 | ACC Construction Co., Inc. | W912PM | W912PM19C0011 | W912PM19C0011 | 79453,W912PM19C0011 | 21039018 | 22062531 | 2021-11-03 | 2022-07-22 | 1023513 | 261 | 2022 | 07 | 22 | 20220722 | 2019 | 2022 | 1.0751 | 2021 | 1.0006 | 22618579.0289 | 23642716.7217 | 1024137.6927 | 261 | 1015 | 25.71%
2021-12-31 | 2018 | Army Active | 55199 |  | 2018-07-11 | 2019-10-15 | WHH Nisqually-Garco JV | W912DW | W912DW20C0001 | W912DW20C0001 | 55199,W912DW20C0001 | 21087000 | 21620000 | 2021-11-29 | 2022-03-27 | 533000 | 118 | 2022 | 03 | 27 | 20220327 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 21668814.3131 | 22189543.436 | 520729.1229 | 118 | 776 | 15.21%
2021-12-31 | 2016 | Army Reserve | 86882 |  | 2017-06-27 | 2017-11-09 | Cox Construction Co. | W912QR | W912QR18C0003 | W912QR18C0003 | 86882,W912QR18C0003 | 21180000 | 24451000 | 2019-12-18 | 2021-10-05 | 3271000 | 657 | 2021 | 10 | 05 | 20211005 | 2018 | 2022 | 1.1914 | 2020 | 1.1519 | 25233017.8834 | 29000776.7864 | 3767758.903 | 657 | 769 | 85.44%
2022-01-12 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV | W912SV-13-R-0001 | W912SV13R0001 | 250065,W912SV-13-R-0001 | 21279000 | 21661000 | 2015-07-30 | 2017-05-17 | 382000 | 657 | 2017 | 05 | 17 | 20170517 | 2014 | 2017 | 1.0276 | 2016 | 1.0006 | 21866111.8115 | 22248344.962 | 382233.1506 | 657 | 636 | 103.3%
2022-01-31 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP | W912PP-15-C-003 | W912PP15C003 | DESC1407,W912PP-15-C-003 | 21288300 | 22083000 | 2017-02-01 | 2017-07-18 | 794700 | 167 | 2017 | 07 | 18 | 20170718 | 2015 | 2017 | 1.0507 | 2016 | 0.97698 | 22367636.7328 | 23144040.9241 | 776404.1913 | 167 | 671 | 24.89%
2021-12-31 | 2017 | National Security Agency | 35161 |  | 2021-08-09 | 2021-08-24 | Grunley Construction | W912DR | W912DR-21-C-0016 | W912DR21C0016 | 35161,W912DR-21-C-0016 | 21386000 | 21386000 | 2024-03-28 | 2024-03-28 | 0 | 0 | 2024 | 03 | 28 | 20240328 | 2021 | 2024 | 0.97698 | 2023 | 0.9382 | 20893645.445 | 20893645.445 | 0 | 0 | 947 | 0%
2022-01-12 | 2018 | Marine Corps Active | M00264542 |  | 2018-08-08 | 2019-05-30 | ARCHER WESTERN FEDERAL JV | N40080 | N4008019C0023 AWD | N4008019C0023 | M00264542,N4008019C0023 AWD | 21419000 | 20882000 | 2020-10-30 | 2022-02-14 | -537000 | 472 | 2022 | 02 | 14 | 20220214 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 22009974.5707 | 21485337.5369 | -524637.0338 | 472 | 519 | 90.94%
2021-12-31 | 2018 | Army Active | 55112 |  | 2018-08-14 | 2019-02-22 | ACC Construction Co. | W912HN | W912HN19C3003 | W912HN19C3003 | 55112,W912HN19C3003 | 21437000 | 22385000 | 2020-10-08 | 2021-12-01 | 948000 | 419 | 2021 | 12 | 01 | 20211201 | 2019 | 2022 | 1.0751 | 2021 | 1.0006 | 23046440.6011 | 23995019.2051 | 948578.604 | 419 | 594 | 70.54%
2021-12-30 | 2018 | DLA Defense Energy Support Center | DESC1709 |  | 2018-09-20 | 2018-09-21 | Tfs-Aptim JV | N40192 | N40192-18-C-1300 | N4019218C1300 | DESC1709,N40192-18-C-1300 | 21445996 | 21445996 | 2019-12-15 | 2019-12-15 | 0 | 0 | 2019 | 12 | 15 | 20191215 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 21459085.3873 | 21459085.3873 | 0 | 0 | 450 | 0%
2021-12-31 | 2018 | Air Force Active | RKMF063004 |  | 2018-08-16 | 2019-07-03 | Record Steel and Construction, Inc., dba RSCI | W912PL | W912PL19C0023 | W912PL19C0023 | RKMF063004,W912PL19C0023 | 21623000 | 22289225 | 2021-08-02 | 2021-12-20 | 666225 | 140 | 2021 | 12 | 20 | 20211220 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 22219603.1627 | 22870490.1419 | 650886.9792 | 140 | 761 | 18.4%
2021-12-08 | 2014 | Washington Headquarters Services | 80007 |  | 2017-04-24 | 2018-05-23 | Grunley Construction Company, Inc. | HQ0034 | HQ0034-18-C-0042 | HQ003418C0042 | 80007,HQ0034-18-C-0042 | 21716999 | 21716999 | 2020-09-23 | 2021-10-23 | 0 | 395 | 2021 | 10 | 23 | 20211023 | 2018 | 2022 | 0.97698 | 2020 | #N/A | 21217024.0921 | #N/A | #N/A | 395 | 854 | 46.25%
2021-12-31 | 2020 | Army Active | 87933 |  | 2020-03-06 | 2020-09-25 | Structural Associates, Inc. | W912DS | W912DS20C0025 | W912DS20C0025 | 87933,W912DS20C0025 | 21732000 | 21702000 | 2022-10-11 | 2022-10-11 | -30000 | 0 | 2022 | 10 | 11 | 20221011 | 2020 | 2023 | 0.97698 | 2022 | 0.9382 | 21231679.7349 | 21203533.7929 | -28145.9419 | 0 | 746 | 0%
2022-01-12 | 2016 | Marine Corps Active | M00146222 |  | 2019-01-23 | 2019-04-18 | SAUER, INC. | N40085 | N4008519C9021 | N4008519C9021 | M00146222,N4008519C9021 | 21793000 | 22197000 | 2021-06-10 | 2021-06-10 | 404000 | 0 | 2021 | 06 | 10 | 20210610 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 21291275.3756 | 21677908.2341 | 386632.8585 | 0 | 784 | 0%
2021-12-30 | 2019 | Air National Guard | RQLH189009 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N69450 | N6945021C0005 | N6945021C0005 | RQLH189009,N6945021C0005 | 21831459 | 19244906 | 2024-10-01 | 2024-10-01 | -2586553 | 0 | 2024 | 10 | 01 | 20241001 | 2021 | 2025 | 1.0276 | 2023 | 0.97698 | 22433813.7836 | 19906809.1401 | -2527004.6435 | 0 | 1300 | 0%
2022-01-12 | 2017 | Navy Active | N62863621 |  | 2017-03-07 | 2017-08-31 | CONSTRUCCIONES FELIPE CASTELLANOCOBRA INSTALACIONES Y SERVICIOS | N62470 | N6247017C5006 AWD | N6247017C5006 | N62863621,N6247017C5006 AWD | 21868000 | 23489000 | 2023-06-09 | 2023-01-08 | 1621000 | -152 | 2023 | 01 | 08 | 20230108 | 2017 | 2023 | 1.2082 | 2020 | 1.1743 | 26421493.705 | 28325063.99 | 1903570.285 | -152 | 2108 | -7.211%
2022-01-13 | 2018 | Defense Health Agency | 14042 |  | 2018-06-06 | 2019-09-28 | Whiting Turner Contracting Co | N40085 | N4008519C9266 | N4008519C9266 | 14042,N4008519C9266 | 21895000 | 22225000 | 2021-10-30 | 2022-04-01 | 330000 | 153 | 2022 | 04 | 01 | 20220401 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 22499107.9521 | 22829309.3648 | 330201.4128 | 153 | 763 | 20.05%
2022-01-13 | 2019 | Defense Health Agency | 89902 |  | 2020-02-25 | 2020-08-18 | Korte Construction Company | N69450 | N6945019D0910 | N6945019D0910 | 89902,N6945019D0910 | 21895000 | 22895000 | 2022-09-03 | 2022-10-05 | 1000000 | 32 | 2022 | 10 | 05 | 20221005 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 23005096.9906 | 24005707.3324 | 1000610.3418 | 32 | 746 | 4.29%
2021-12-30 | 2020 | Air National Guard | XGFG189004 |  | 2020-11-04 | 2021-07-19 | CONTI FEDERAL SERVICES, INC | W9128F | W9128F21C0039 | W9128F21C0039 | XGFG189004,W9128F21C0039 | 21978910 | 19678800 | 2022-11-11 | 2022-11-11 | -2300110 | 0 | 2022 | 11 | 11 | 20221111 | 2021 | 2023 | 1.0276 | 2022 | 0.95701 | 22585333.1244 | 20384100.1933 | -2201232.9311 | 0 | 480 | 0%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB | W912GB-16-C-0038 | W912GB16C0038 | 76007,W912GB-16-C-0038 | 21988000 | 24175000 | 2018-07-30 | 2018-12-30 | 2187000 | 153 | 2018 | 12 | 30 | 20181230 | 2012 | 2019 | 1.0507 | 2016 | 1.0006 | 23102812.1776 | 25291146.9951 | 2188334.8175 | 153 | 2328 | 6.572%
2021-12-31 | 2019 | Army Active | 92518 |  | 2018-12-17 | 2020-02-27 | Bates Engineers/Contractors, Inc | W91278 | W9127816D0018 | W9127816D0018 | 92518,W9127816D0018 | 21993000 | 23127000 | 2022-03-11 | 2022-03-16 | 1134000 | 5 | 2022 | 03 | 16 | 20220316 | 2020 | 2022 | 1.0507 | 2021 | 1.0006 | 23108065.6823 | 24242757.8099 | 1134692.1276 | 5 | 743 | 0.6729%
2022-01-06 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR | W912QR-14-C-0016 | W912QR14C0016 | 69447,W912QR-14-C-0016 | 22123180 | 22825995 | 2016-02-13 | 2016-02-15 | 702815 | 2 | 2016 | 02 | 15 | 20160215 | 2014 | 2016 | 1.0751 | 2015 | 1.0006 | 23784137.4156 | 24487381.3729 | 703243.9574 | 2 | 684 | 0.2924%
2022-05-03 | 2020 | DLA Defense Energy Support Center | DECS1913 |  | 2020-05-28 | 2020-09-15 | Nova Group, Inc. | W9128F | W9128F20C0039 / 59008927 | W9128F20C0039 | DECS1913,W9128F20C0039 / 59008927 | 22124000 | 22201000 | 2022-11-30 | 2022-11-30 | 77000 | 0 | 2022 | 11 | 30 | 20221130 | 2020 | 2023 | 1.0993 | 2022 | 1.0507 | 24319922.2932 | 24400826.2653 | 80903.9721 | 0 | 806 | 0%
2021-12-31 | 2019 | Air Force Active | MSET153503 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153503,DIOCB2076 | 22219318 | 22219318 | 2024-01-21 | 2024-01-21 | 0 | 0 | 2024 | 01 | 21 | 20240121 | 2019 | 2024 | 0.97698 | 2022 | 0.9382 | 21707778.5617 | 21707778.5617 | 0 | 0 | 1894 | 0%
2022-01-06 | 2012 | Special Operations Command | 83011 |  | 2012-05-15 | 2012-08-31 | Okland Geneva Joint Venture | W912PP | W912PP-12-C-0023 | W912PP12C0023 | 83011,W912PP-12-C-0023 | 22227916 | 24626857 | 2014-05-01 | 2014-03-05 | 2398941 | -57 | 2014 | 03 | 05 | 20140305 | 2012 | 2014 | 1.1227 | 2013 | 1.0751 | 24954653.4873 | 27533701.454 | 2579047.9667 | -57 | 608 | -9.375%
2021-12-31 | 2018 | Air Force Active | MSET153513 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153513,DIOCB2076 | 22251003 | 22251003 | 2023-09-30 | 2023-09-30 | 0 | 0 | 2023 | 09 | 30 | 20230930 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 22864933.4797 | 22864933.4797 | 0 | 0 | 1781 | 0%
2022-05-03 | 2019 | DLA Defense Energy Support Center | DESC1905 |  | 2019-05-01 | 2019-08-01 | WHH Nisqually-Garco JV 2 | W912DW | W912DW19C0017 / 56848368 | W912DW19C0017 | DESC1905,W912DW19C0017 / 56848368 | 22312000 | 23258000 | 2022-05-31 | 2021-10-30 | 946000 | -213 | 2021 | 10 | 30 | 20211030 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 22927613.4563 | 23874190.8397 | 946577.3833 | -213 | 1034 | -20.6%
2021-12-31 | 2020 | Army Active | 62856 |  | 2020-04-14 | 2020-07-21 | Walsh Motor City JV | W912QR | W912QR20C0027 | W912QR20C0027 | 62856,W912QR20C0027 | 22344000 | 23010000 | 2022-10-28 | 2022-10-28 | 666000 | 0 | 2022 | 10 | 28 | 20221028 | 2020 | 2023 | 1.0006 | 2022 | 0.97698 | 22357637.4766 | 23008304.6358 | 650667.1592 | 0 | 829 | 0%
2022-01-13 | 2013 | Defense Health Agency | 72419 |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM | W912UM-13-C-0025 | W912UM13C0025 | 72419,W912UM-13-C-0025 | 22361000 | 24475000 | 2017-08-08 | 2020-06-20 | 2114000 | 1047 | 2020 | 06 | 20 | 20200620 | 2013 | 2020 | 1.1914 | 2017 | 1.1519 | 26640014.773 | 29075062.8686 | 2435048.0957 | 1047 | 1412 | 74.15%
2020-12-31 | 2016 | National Security Agency | 32122 |  | 2016-04-01 | 2016-05-23 | Argo | WH12DR | WH12DR-14-D-0019 | WH12DR14D0019 | 32122,WH12DR-14-D-0019 | 22375000 | 31400000 | 2018-06-08 | 2021-01-06 | 9025000 | 943 | 2021 | 01 | 06 | 20210106 | 2016 | 2021 | 1.0276 | 2019 | 0.95701 | 22992351.698 | 31629385.2324 | 8637033.5344 | 943 | 746 | 126.4%
2021-12-31 | 2017 | Air Force Active | FSPM053503C |  | 2017-05-12 | 2018-05-22 | I.E. Pacific, INC | W912PL | W912PL8C0024 | W912PL8C0024 | FSPM053503C,W912PL8C0024 | 22414000 | 22537509 | 2020-06-18 | 2020-08-28 | 123509 | 71 | 2020 | 08 | 28 | 20200828 | 2018 | 2020 | 1.0751 | 2019 | 1.0276 | 24096791.5116 | 24223708.2654 | 126916.7538 | 71 | 758 | 9.367%
2022-01-12 | 2018 | Marine Corps Active | M00146990 |  | 2019-04-30 | 2021-05-27 | WHITING-TURNER CONTRACTING CO | N40085 | N4008521C0035 AWD | N4008521C0035 | M00146990,N4008521C0035 AWD | 22677000 | 21604000 | 2023-05-01 | 2023-01-05 | -1073000 | -116 | 2023 | 01 | 05 | 20230105 | 2021 | 2023 | 1.0006 | 2022 | 0.9382 | 22690840.7204 | 21684154.197 | -1006686.5234 | -116 | 704 | -16.48%
2022-01-06 | 2014 | Special Operations Command | 76365 |  | 2015-07-15 | 2015-11-12 | B. L. Harbert International, LLC | W912QR | W912QR-16-C-0002 | W912QR16C0002 | 76365,W912QR-16-C-0002 | 22740000 | 23868765 | 2017-10-02 | 2018-01-24 | 1128765 | 114 | 2018 | 01 | 24 | 20180124 | 2016 | 2018 | 1.0276 | 2017 | 1.0006 | 23367422.4631 | 24496876.3955 | 1129453.9324 | 114 | 690 | 16.52%
2021-08-31 | 2019 | Army Active | 74989 |  | 2018-11-09 | 2019-03-08 | Carothers | W9126G | W9126G19C0020 | W9126G19C0020 | 74989,W9126G19C0020 | 22822000 | 23434000 | 2020-10-07 | 2021-06-20 | 612000 | 256 | 2021 | 06 | 20 | 20210620 | 2019 | 2021 | 1.1914 | 2020 | 1.1519 | 27189232.0177 | 27894174.9858 | 704942.9681 | 256 | 579 | 44.21%
2022-01-13 | 2018 | Defense Health Agency | 14041 |  | 2018-06-13 | 2019-09-28 | Whiting Turner Contracting Co | N62470 | N6247016D6006 | N6247016D6006 | 14041,N6247016D6006 | 22911000 | 23032000 | 2021-10-30 | 2022-03-01 | 121000 | 122 | 2022 | 03 | 01 | 20220301 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 24631105.1272 | 24755443.6548 | 124338.5276 | 122 | 763 | 15.99%
2022-01-12 | 2020 | Marine Corps Active | M670011529F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011529F,N4008520C0044 AWD | 22970805 | 24310000 | 2024-10-12 | 2025-01-11 | 1339195 | 91 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0993 | 2023 | 1.0507 | 25250777.1023 | 26657870.5421 | 1407093.4398 | 91 | 1541 | 5.905%
2022-01-12 | 2019 | Navy Active | N61065241 |  | 2019-06-17 | 2019-08-19 | REYES CONSTRUCTION INC | N62473 | N6247318D5862 N6247319F4995 | N6247318D5862 | N61065241,N6247318D5862 N6247319F4995 | 23001000 | 22091000 | 2021-04-15 | 2021-08-30 | -910000 | 137 | 2021 | 08 | 30 | 20210830 | 2019 | 2021 | 1.1743 | 2020 | 1.0751 | 27010499.7688 | 26032179.0641 | -978320.7047 | 137 | 605 | 22.64%
2022-01-12 | 2014 | Marine Corps Active | M00264588 |  | 2017-02-10 | 2018-09-29 | WHITING-TURNER CONTRACTING CO | N40080 | N4008018C0034 AWD | N4008018C0034 | M00264588,N4008018C0034 AWD | 23040000 | 21739000 | 2020-06-06 | 2021-04-09 | -1301000 | 307 | 2021 | 04 | 09 | 20210409 | 2018 | 2021 | 1.1227 | 2020 | 1.0751 | 25866357.2575 | 24467681.1731 | -1398676.0844 | 307 | 616 | 49.84%
2022-01-06 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN | W912HN-10-D-0061 | W912HN10D0061 | 69493,W912HN-10-D-0061 | 23085000 | 26553696 | 2016-05-17 | 2016-12-16 | 3468696 | 213 | 2016 | 12 | 16 | 20161216 | 2014 | 2017 | 1.2319 | 2016 | 1.2082 | 28439269.2357 | 32630239.1245 | 4190969.8888 | 213 | 761 | 27.99%
2021-12-30 | 2016 | DLA Defense Energy Support Center | DESC1605 |  | 2016-06-23 | 2017-06-02 | STRUCTURAL ASSOCIATES | W912BU | W912BU16R00370006 | W912BU16R00370006 | DESC1605,W912BU16R00370006 | 23170900 | 23170900 | 2019-06-16 | 2019-06-26 | 0 | 10 | 2019 | 06 | 26 | 20190626 | 2017 | 2019 | 1.1914 | 2018 | 1.1519 | 27604897.7373 | 27604897.7373 | 0 | 10 | 744 | 1.344%
2021-12-31 | 2018 | Air Force Active | MSET153501 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153501,DIOCB2076 | 23292923 | 23292923 | 2021-10-05 | 2021-10-05 | 0 | 0 | 2021 | 10 | 05 | 20211005 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 25041702.0267 | 25041702.0267 | 0 | 0 | 1056 | 0%
2022-01-12 | 2018 | Marine Corps Active | M67004977 |  | 2018-07-18 | 2019-03-07 | B.L. HARBERT INTERNATIONAL, L.L.C. | N40085 | N4008519C9126 | N4008519C9126 | M67004977,N4008519C9126 | 23298000 | 23913000 | 2021-04-29 | 2021-05-27 | 615000 | 28 | 2021 | 05 | 27 | 20210527 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 24479230.4036 | 25094605.7638 | 615375.3602 | 28 | 784 | 3.571%
2022-01-12 | 2019 | Navy Active | N32443256 |  | 2021-09-02 | 2021-11-29 | W.M. JORDAN COMPANY INC. | N40085 | N4008519D9089 N4008522F4169 | N4008519D9089 | N32443256,N4008519D9089 N4008522F4169 | 23304851 | 25344000 | 2024-01-28 | 2024-01-28 | 2039149 | 0 | 2024 | 01 | 28 | 20240128 | 2022 | 2024 | 1.0751 | 2023 | 1.0006 | 25054525.5535 | 27094919.1313 | 2040393.5778 | 0 | 790 | 0%
2021-12-31 | 2017 | Air Force Active | QSEU083023 |  | 2020-06-23 | 2020-09-03 | McKnight Construction | W912HN | W912HN20C3007 | W912HN20C3007 | QSEU083023,W912HN20C3007 | 23471929 | 23471929 | 2023-05-03 | 2023-05-03 | 0 | 0 | 2023 | 05 | 03 | 20230503 | 2020 | 2023 | 1.0507 | 2022 | 0.97698 | 24661977.7667 | 24661977.7667 | 0 | 0 | 972 | 0%
2021-12-31 | 2017 | Air Force Active | GJKZ040009 |  | 2018-08-10 | 2018-12-28 | GARCO Construction | W912DW | W912DW19C0002 | W912DW19C0002 | GJKZ040009,W912DW19C0002 | 23481000 | 23481000 | 2021-11-14 | 2021-11-14 | 0 | 0 | 2021 | 11 | 14 | 20211114 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 24128867.4959 | 24128867.4959 | 0 | 0 | 1052 | 0%
2022-01-12 | 2018 | Marine Corps Active | M62204930 |  | 2017-03-07 | 2018-04-18 | M A MORTENSON COMPANY | N62473 | N6247318D5850 N6247318F4497 | N6247318D5850 | M62204930,N6247318D5850 N6247318F4497 | 23592000 | 23136000 | 2020-05-02 | 2020-05-17 | -456000 | 15 | 2020 | 05 | 17 | 20200517 | 2018 | 2020 | 1.0276 | 2019 | 1.0006 | 24242930.1121 | 23786651.7963 | -456278.3158 | 15 | 745 | 2.013%
2022-01-12 | 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N62470 | N6247017C5005 AWD | N6247017C5005 | N62995407,N6247017C5005 AWD | 23632000 | 22817000 | 2019-04-23 | 2021-11-30 | -815000 | 952 | 2021 | 11 | 30 | 20211130 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 24284033.7576 | 23468536.3291 | -815497.4285 | 952 | 882 | 107.9%
2022-01-13 | 2016 | Defense Health Agency | 77986 |  | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB | W912GB-13-C-0005 | W912GB13C0005 | 77986,W912GB-13-C-0005 | 23667000 | 27070000 | 2019-06-04 | 2022-07-11 | 3403000 | 1133 | 2022 | 07 | 11 | 20220711 | 2017 | 2022 | 1.0751 | 2020 | 1.0276 | 25443863.8665 | 28940756.5069 | 3496892.6404 | 1133 | 902 | 125.6%
2021-12-31 | 2016 | Air Force Active | VKAG013004R5 |  | 2017-08-21 | 2019-06-28 | Walsh Federal Construction Contract-SJ ATCT | W912HN | W912HN19C3006 | W912HN19C3006 | VKAG013004R5,W912HN19C3006 | 23716745 | 23716745 | 2019-07-28 | 2021-08-09 | 0 | 743 | 2021 | 08 | 09 | 20210809 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 24371116.9686 | 24371116.9686 | 0 | 743 | 30 | 2477%
2022-01-06 | 2011 | Special Operations Command | 63051 |  | 2011-02-23 | 2011-08-03 | Sundt Construction, Inc. | W912PP | W912PP-11-C-0016 | W912PP11C0016 | 63051,W912PP-11-C-0016 | 23743780 | 24809756 | 2012-10-04 | 2012-10-10 | 1065976 | 6 | 2012 | 10 | 10 | 20121010 | 2011 | 2013 | 1.0006 | 2012 | 0.97698 | 23758271.8208 | 24799706.6191 | 1041434.7983 | 6 | 428 | 1.402%
2021-08-31 | 2017 | Army Reserve | 77134 |  | 2018-01-05 | 2018-04-26 | LS Black Constructor | W912QR | W912QR18C0015 | W912QR18C0015 | 77134,W912QR18C0015 | 23840000 | 24589000 | 2020-05-14 | 2021-01-05 | 749000 | 236 | 2021 | 01 | 05 | 20210105 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 23291148.7612 | 24007950.7687 | 716802.0075 | 236 | 749 | 31.51%
2022-01-12 | 2016 | Navy Active | N61064416 |  | 2018-04-19 | 2018-09-06 | HELIX ELECTRIC, INC. | N62478 | N6247818C1516 AWD | N6247818C1516 | N61064416,N6247818C1516 AWD | 23932000 | 26696000 | 2020-05-28 | 2022-06-17 | 2764000 | 750 | 2022 | 06 | 17 | 20220617 | 2018 | 2022 | 1.0276 | 2020 | 0.95701 | 24592311.0988 | 27237492.3386 | 2645181.2398 | 750 | 630 | 119%
2022-01-12 | 2021 | Navy Active | N62863620 |  | 2021-09-01 | 2021-12-21 | ACCIONA CMS JV, LLC | N62470 | N6247021D0011 N6247022F9001 | N6247021D0011 | N62863620,N6247021D0011 N6247022F9001 | 23932976.31 | 25766000 | 2024-07-01 | 2024-07-01 | 1833023.69 | 0 | 2024 | 07 | 01 | 20240701 | 2022 | 2024 | 1.0276 | 2023 | 0.97698 | 24593314.3463 | 26384137.6453 | 1790823.2989 | 0 | 923 | 0%
2022-01-07 | 2018 | Washington Headquarters Services | 91474 |  | 2019-03-08 | 2019-06-28 | Grunley Construction Company, Inc. | W912DR | W912DR-17-D-0002 | W912DR17D0002 | 91474,W912DR-17-D-0002 | 24006000 | 24006000 | 2021-01-22 | 2023-02-28 | 0 | 767 | 2023 | 02 | 28 | 20230228 | 2019 | 2023 | 1.0993 | 2021 | 1.0276 | 26388720.6007 | 26388720.6007 | 0 | 767 | 574 | 133.6%
2021-12-31 | 2017 | Air Force Active | PAF150400 |  | 2017-11-21 | 2018-05-18 | AECOM | N62742 | N6274218C1314 | N6274218C1314 | PAF150400,N6274218C1314 | 24132780 | 33953429 | 2019-11-15 | 2020-04-06 | 9820649 | 143 | 2020 | 04 | 06 | 20200406 | 2018 | 2020 | 1.0276 | 2019 | 1.0006 | 24798630.8474 | 34625273.7997 | 9826642.9523 | 143 | 546 | 26.19%
2021-12-31 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | W911KB | W911KB-18-C-0015 | W911KB18C0015 | 657,W911KB-18-C-0015 | 24399601 | 24558572 | 2019-08-30 | 2019-06-27 | 158971 | -64 | 2019 | 06 | 27 | 20190627 | 2018 | 2019 | 1.0751 | 2019 | 1.0006 | 26231466.8628 | 26390534.8894 | 159068.0266 | -64 | 561 | -11.41%
2021-12-31 | 2016 | Army Active | 86409 |  | 2020-01-17 | 2020-09-03 | Tuckman Barbee Construction Co., Inc. | W912DR | W912DR20C0042 | W912DR20C0042 | 86409,W912DR20C0042 | 24482000 | 24603000 | 2022-10-27 | 2022-09-27 | 121000 | -30 | 2022 | 09 | 27 | 20220927 | 2020 | 2022 | 0.97698 | 2021 | 0.95701 | 23918368.4552 | 24034166.9104 | 115798.4551 | -30 | 784 | -3.827%
2020-12-09 | 2016 | National Security Agency | 31934 |  | 2015-07-08 | 2015-09-15 | Whiting-Turner | W912DR | W912DR-15-C-0026 | W912DR15C0026 | 31934,W912DR-15-C-0026 | 24554985 | 26455691 | 2016-12-31 | 2017-02-28 | 1900706 | 59 | 2017 | 02 | 28 | 20170228 | 2015 | 2017 | 1.0507 | 2016 | 1.0006 | 25799945.7195 | 27701811.7997 | 1901866.0803 | 59 | 473 | 12.47%
2021-12-31 | 2019 | Air Force Active | LKTC203102 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL | W912PL19C0028 | W912PL19C0028 | LKTC203102,W912PL19C0028 | 24652900 | 25087883 | 2021-11-02 | 2022-05-23 | 434983 | 202 | 2022 | 05 | 23 | 20220523 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 25902825.1016 | 26338073.5899 | 435248.4883 | 202 | 768 | 26.3%
2022-01-13 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER | W912ER-11-D-0009-0012 | W912ER11D00090012 | 81436,W912ER-11-D-0009-0012 | 24784000 | 26972000 | 2019-04-20 | 2020-01-20 | 2188000 | 275 | 2020 | 01 | 20 | 20200120 | 2016 | 2020 | 0.97698 | 2018 | 0.95701 | 24213415.7256 | 26307358.0384 | 2093942.3128 | 275 | 1129 | 24.36%
2022-01-12 | 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N62742 | N6274217C1320 AWD | N6274217C1320 | M00318902,N6274217C1320 AWD | 24797000 | 29732000 | 2019-06-06 | 2021-08-13 | 4935000 | 799 | 2021 | 08 | 13 | 20210813 | 2017 | 2021 | 1.0507 | 2019 | 1.0276 | 26054231.1065 | 31125393.3692 | 5071162.2628 | 799 | 930 | 85.91%
2021-12-31 | 2017 | Air Force Active | WWYK193003 |  | 2017-12-22 | 2019-02-07 | Record Steel and Construction | W912BV | W912BV19C0002 | W912BV19C0002 | WWYK193003,W912BV19C0002 | 24873819 | 24873819 | 2020-11-24 | 2020-11-24 | 0 | 0 | 2020 | 11 | 24 | 20201124 | 2019 | 2021 | 1.1519 | 2020 | 1.0993 | 28651346.068 | 28651346.068 | 0 | 0 | 656 | 0%
2022-01-06 | 2020 | Special Operations Command | 81165 |  | 2020-07-24 | 2020-09-18 | ACC CONSTRUCTION CO., INC. | W912PM | W912PM20C0031 | W912PM20C0031 | 81165,W912PM20C0031 | 24885638 | 25356619 | 2023-03-08 | 2023-06-18 | 470981 | 102 | 2023 | 06 | 18 | 20230618 | 2020 | 2023 | 0.97698 | 2022 | 0.95701 | 24312713.7867 | 24763448.2678 | 450734.481 | 102 | 901 | 11.32%
2022-01-06 | 2016 | Special Operations Command | 79439 |  | 2018-04-06 | 2018-08-14 | ARCHER WESTERN FEDERAL JV | W912PM | W912PM18C0016 | W912PM18C0016 | 79439,W912PM18C0016 | 24955000 | 36737863 | 2020-05-07 | 2021-11-15 | 11782863 | 557 | 2021 | 11 | 15 | 20211115 | 2018 | 2022 | 0.97698 | 2020 | 0.9382 | 24380478.9151 | 35435138.1781 | 11054659.263 | 557 | 632 | 88.13%
2021-12-31 | 2018 | Air Force Active | QJVF012005 |  | 2019-01-25 | 2019-05-29 | Minot Indoor Firing Range | W9128F | W9128F18C0026 | W9128F18C0026 | QJVF012005,W9128F18C0026 | 24993526 | 24993526 | 2021-02-17 | 2021-12-19 | 0 | 305 | 2021 | 12 | 19 | 20211219 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 26260721.1586 | 26260721.1586 | 0 | 305 | 630 | 48.41%
2021-12-31 | 2019 | Air Force Active | LKTC203101 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL | W912PL19C0028 | W912PL19C0028 | LKTC203101,W912PL19C0028 | 25007200 | 25716568 | 2021-10-02 | 2022-04-22 | 709368 | 202 | 2022 | 04 | 22 | 20220422 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 25697177.0897 | 26390213.8185 | 693036.7288 | 202 | 737 | 27.41%
2022-01-12 | 2017 | Navy Active | N61064402 |  | 2018-04-20 | 2018-12-26 | NOVA GROUP INC | N62742 | N6274219C1320 AWD | N6274219C1320 | N61064402,N6274219C1320 AWD | 25137000 | 26399000 | 2021-07-13 | 2021-12-27 | 1262000 | 167 | 2021 | 12 | 27 | 20211227 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 25830558.4193 | 27063504.2975 | 1232945.8782 | 167 | 930 | 17.96%
2021-12-31 | 2017 | Air Force Active | DHAF152900 |  | 2018-04-01 | 2019-09-06 | Amana Contracting & Steel Building Co. WLL, Abu Dhabi UAE | W912ER | W912ER19C0015 | W912ER19C0015 | DHAF152900,W912ER19C0015 | 25152460 | 25528019 | 2021-10-15 | 2021-11-16 | 375559 | 32 | 2021 | 11 | 16 | 20211116 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 27040848.783 | 27426769.883 | 385921.0999 | 32 | 770 | 4.156%
2021-12-31 | 2019 | Army Active | 63054 |  | 2019-07-26 | 2019-09-27 | Benard Associates, Inc | W912DS | W912DS19C0033 | W912DS19C0033 | 63054,W912DS19C0033 | 25164000 | 30295000 | 2021-11-03 | 2022-11-30 | 5131000 | 392 | 2022 | 11 | 30 | 20221130 | 2019 | 2023 | 1.1519 | 2021 | 1.1227 | 28985596.1586 | 34746024.9385 | 5760428.7799 | 392 | 768 | 51.04%
2022-01-12 | 2017 | Navy Active | N3379A223 |  | 2017-10-13 | 2018-06-28 | J/V P. & C. DEVELOPMENT S.A. -ERGOTEM S.A. | N62470 | N6247018C4015 AWD | N6247018C4015 | N3379A223,N6247018C4015 AWD | 25219000 | 23024000 | 2020-10-05 | 2022-07-31 | -2195000 | 664 | 2022 | 07 | 31 | 20220731 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 25234392.2092 | 23089926.1215 | -2144466.0877 | 664 | 830 | 80%
2021-12-31 | 2018 | Air Force Reserve | SXHT103001 |  | 2018-03-01 | 2018-05-25 | Ashford Leebcor Enterpises, LLC | W912QR | W912QR18C0018 | W912QR18C0018 | SXHT103001,W912QR18C0018 | 25242688 | 22626925 | 2020-07-19 | 2022-02-05 | -2615763 | 566 | 2022 | 02 | 05 | 20220205 | 2018 | 2022 | 1.1227 | 2020 | 1.0993 | 28339252.8623 | 25463861.7533 | -2875391.1091 | 566 | 786 | 72.01%
2021-12-31 | 2019 | Army Active | 62866 |  | 2019-07-12 | 2019-09-30 | MVL USA Inc | W912ER | W912ER19C0018 | W912ER19C0018 | 62866,W912ER19C0018 | 25397000 | 25452000 | 2021-05-02 | 2022-01-05 | 55000 | 248 | 2022 | 01 | 05 | 20220105 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 25412500.85 | 25466234.6245 | 53733.7744 | 248 | 580 | 42.76%
2022-01-12 | 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N62473 | N6247315D2427 0002 | N6247315D2427 | N60495420,N6247315D2427 0002 | 25541000 | 28487000 | 2017-11-24 | 2019-10-31 | 2946000 | 706 | 2019 | 10 | 31 | 20191031 | 2015 | 2020 | 1.1519 | 2018 | 1.1227 | 29419850.2419 | 32727241.235 | 3307390.9931 | 706 | 800 | 88.25%
2022-02-02 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278 | W91278-12-D-0037/39179628 | W9127812D0037 | AM00048,W91278-12-D-0037/39179628 | 25629526 | 27304618 | 2020-06-10 | 2021-10-15 | 1675092 | 492 | 2021 | 10 | 15 | 20211015 | 2016 | 2022 | 1.2319 | 2019 | 1.2082 | 31573965.3584 | 33597855.6425 | 2023890.2841 | 492 | 1349 | 36.47%
2022-01-12 | 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N40080 | N4008015C0167 AWD | N4008015C0167 | N61151287,N4008015C0167 AWD | 25679000 | 29521000 | 2017-07-17 | 2019-10-31 | 3842000 | 836 | 2019 | 10 | 31 | 20191031 | 2015 | 2020 | 1.0507 | 2018 | 1.0276 | 26980949.3319 | 30928954.4816 | 3948005.1497 | 836 | 684 | 122.2%
2022-01-12 | 2018 | Navy Active | N60191160 |  | 2019-08-28 | 2020-02-14 | SYNCON, LLC | N40085 | N4008520C8503 AWD | N4008520C8503 | N60191160,N4008520C8503 AWD | 25795000 | 24567000 | 2022-03-01 | 2022-07-04 | -1228000 | 125 | 2022 | 07 | 04 | 20220704 | 2020 | 2022 | 0.97698 | 2021 | 0.9382 | 25201140.197 | 24049032.9735 | -1152107.2234 | 125 | 746 | 16.76%
2022-01-06 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278 | W91278-11-D-0066 | W9127811D0066 | 69382,W91278-11-D-0066 | 25816000 | 28305680 | 2015-05-13 | 2015-09-21 | 2489680 | 131 | 2015 | 09 | 21 | 20150921 | 2013 | 2015 | 1.0507 | 2014 | 1.0006 | 27124895.3601 | 29616094.9158 | 2491199.5557 | 131 | 593 | 22.09%
2022-01-06 | 2013 | Special Operations Command | 83702 |  | 2013-07-01 | 2013-09-18 | WG Yates & Sons Construction Co | W91278 | W91278-12-D-0040 | W9127812D0040 | 83702,W91278-12-D-0040 | 25870100 | 29269603 | 2015-06-28 | 2016-09-30 | 3399503 | 460 | 2016 | 09 | 30 | 20160930 | 2013 | 2016 | 1.0507 | 2015 | 1.0006 | 27181738.2807 | 30583316.1394 | 3401577.8587 | 460 | 648 | 70.99%
2022-01-06 | 2008 | Special Operations Command | 53530 |  | 2007-10-31 | 2008-03-20 | B.L. Harbert International, LLC | W912QR | W912QR-08-C-0009 | W912QR08C0009 |  | 25906995 | 26435895 | 2009-12-09 | 2010-01-29 | 528900 | 51 | 2010 | 01 | 29 | 20100129 | 2008 | 2010 | 1.0006 | 2009 | 0.95701 | 25922807.1213 | 26428970.7818 | 506163.6605 | 51 | 629 | 8.108%
2022-01-13 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB | W912GB-07-C-0007-NA | W912GB07C0007NA |  | 25929000 | 28027000 | 2012-05-15 | 2012-07-16 | 2098000 | 62 | 2012 | 07 | 16 | 20120716 | 2008 | 2012 | 1.0993 | 2010 | 1.0507 | 28502588.3719 | 30706958.9353 | 2204370.5634 | 62 | 1355 | 4.576%
2021-12-31 | 2019 | Air Force Active | XLWU203006 |  | 2020-07-24 | 2020-09-25 | Caddell Constr Co. Montgomery | W912HN | W912HN20D3003 | W912HN20D3003 | XLWU203006,W912HN20D3003 | 25994000 | 25994000 | 2022-09-16 | 2022-09-16 | 0 | 0 | 2022 | 09 | 16 | 20220916 | 2020 | 2022 | 1.0751 | 2021 | 1.0276 | 27945569.6686 | 27945569.6686 | 0 | 0 | 721 | 0%
2022-01-13 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A | W9128A-16-C-0004 | W9128A16C0004 | 80412,W9128A-16-C-0004 | 26084000 | 27183000 | 2017-12-08 | 2019-03-29 | 1099000 | 476 | 2019 | 03 | 29 | 20190329 | 2016 | 2019 | 1.2319 | 2018 | 1.2082 | 32133848.7652 | 33461689.518 | 1327840.7528 | 476 | 570 | 83.51%
2022-01-13 | 2017 | Defense Health Agency | 80906 |  | 2017-05-23 | 2017-09-28 | Whiting Turner Contracting Co | N40080 | N40080-17-C-0039 | N4008017C0039 | 80906,N40080-17-C-0039 | 26338000 | 31518000 | 2019-05-10 | 2021-08-31 | 5180000 | 844 | 2021 | 08 | 31 | 20210831 | 2017 | 2021 | 1.1519 | 2019 | 1.1227 | 30337888.715 | 36153328.4109 | 5815439.6959 | 844 | 589 | 143.3%
2021-12-31 | 2019 | Air Force Active | FTFA093965 |  | 2018-11-12 | 2019-03-21 | Whitesell-Green | W91278 | W9127819C0012 | W9127819C0012 | FTFA093965,W9127819C0012 | 26376465 | 26387419 | 2021-04-21 | 2021-04-21 | 10954 | 0 | 2021 | 04 | 21 | 20210421 | 2019 | 2021 | 1.1227 | 2020 | 1.0276 | 29612112.2778 | 29623368.5111 | 11256.2333 | 0 | 762 | 0%
2021-12-31 | 2017 | Air Force Active | AWUB095000 |  | 2016-12-02 | 2019-07-17 | Consolidated Communication Facility | N69450 | N6945013D1771 | N6945013D1771 | AWUB095000,N6945013D1771 | 26418933 | 26418933 | 2022-01-02 | 2022-03-31 | 0 | 88 | 2022 | 03 | 31 | 20220331 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 25810708.8346 | 25810708.8346 | 0 | 88 | 900 | 9.778%
2021-12-31 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N62742 | N6274216C1309 | N6274216C1309 | AJJY133028,N6274216C1309 | 26463336 | 29311091 | 2018-11-08 | 2021-09-19 | 2847755 | 1046 | 2021 | 09 | 19 | 20210919 | 2016 | 2021 | 1.0507 | 2019 | 1.0006 | 27805051.9011 | 30654545.005 | 2849493.1038 | 1046 | 769 | 136%
2021-12-31 | 2018 | Army Active | 90351 |  | 2020-09-18 | 2021-03-19 | AMG | W912PL | W912PL21C0007 | W912PL21C0007 | 90351,W912PL21C0007 | 26473000 | 26518000 | 2023-02-10 | 2023-02-10 | 45000 | 0 | 2023 | 02 | 10 | 20230210 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 25863531.0888 | 25905750.0017 | 42218.9129 | 0 | 693 | 0%
2021-12-31 | 2016 | Air Force Active | LXEZ164289 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV | W912HV16D0009 | W912HV16D0009 | LXEZ164289,W912HV16D0009 | 26546290 | 26546290 | 2021-01-14 | 2021-01-14 | 0 | 0 | 2021 | 01 | 14 | 20210114 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 25935133.7856 | 25935133.7856 | 0 | 0 | 898 | 0%
2022-01-12 | 2019 | Marine Corps Active | M670011522F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011522F,N4008520C0044 AWD | 26607000 | 26859000 | 2019-10-25 | 2025-01-11 | 252000 | 1905 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0276 | 2023 | 0.97698 | 27341117.3912 | 27587315.7758 | 246198.3846 | 1905 | -273 | -697.8%
2021-12-31 | 2018 | Air Force Active | XQPZ164001 |  | 2020-04-16 | 2020-08-21 | Bryan Construction | W9128F | W9128F20C0038 | W9128F20C0038 | XQPZ164001,W9128F20C0038 | 26744525 | 26827768 | 2023-08-13 | 2023-10-20 | 83243 | 68 | 2023 | 10 | 20 | 20231020 | 2020 | 2024 | 1.0006 | 2022 | 0.97698 | 26760848.3008 | 26842174.8569 | 81326.5561 | 68 | 1087 | 6.256%
2022-02-02 | 2013 | DoD Education Activity | PA00028 |  | 2016-06-21 | 2017-07-18 | Gilbane Japan GK | W912HV | W912HV-17-C-0007/32174203 | W912HV17C0007 | PA00028,W912HV-17-C-0007/32174203 | 26840313 | 28001030 | 2019-07-19 | 2021-02-25 | 1160717 | 587 | 2021 | 02 | 25 | 20210225 | 2017 | 2021 | 0.97698 | 2019 | 0.95701 | 26222387.7047 | 27333207.8325 | 1110820.1278 | 587 | 731 | 80.3%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1611 |  | 2017-11-29 | 2017-11-30 | NOVA Group, Inc | N62473 | N62473-18-C-2202 | N6247318C2202 | DESC1611,N62473-18-C-2202 | 26868000 | 26926198 | 2020-03-10 | 2020-03-10 | 58198 | 0 | 2020 | 03 | 10 | 20200310 | 2018 | 2020 | 0.97698 | 2019 | 0.9382 | 26249437.2868 | 26304038.5377 | 54601.251 | 0 | 831 | 0%
2021-12-30 | 2017 | DLA Defense Energy Support Center | DESC1705 |  | 2017-05-29 | 2017-05-30 | Black Construction/Mace Internation | N62742 | N62742-17-C-1313 | N6274217C1313 | DESC1705,N62742-17-C-1313 | 26978100 | 28361127 | 2019-06-29 | 2020-01-31 | 1383027 | 216 | 2020 | 01 | 31 | 20200131 | 2017 | 2020 | 1.0276 | 2019 | 0.97698 | 27722456.4623 | 29073643.0226 | 1351186.5603 | 216 | 760 | 28.42%
2022-01-12 | 2019 | Army National Guard | 020143 |  | 2018-10-02 | 2019-07-19 | TDX Quality, LLC | W91ZRU | W91ZRU-16-2-2001 | W91ZRU1622001 | 020143,W91ZRU-16-2-2001 | 27000000 | 22489000 | 2021-04-23 | 2021-10-30 | -4511000 | 190 | 2021 | 10 | 30 | 20211030 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 28368925.2682 | 23855172.0164 | -4513753.2517 | 190 | 644 | 29.5%
2022-01-12 | 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N40080 | N4008016C0151 AWD | N4008016C0151 | M00264677,N4008016C0151 AWD | 27064000 | 27404000 | 2018-01-05 | 2018-10-23 | 340000 | 291 | 2018 | 10 | 23 | 20181023 | 2016 | 2019 | 1.0507 | 2018 | 1.0276 | 28436170.1281 | 28785551.1148 | 349380.9867 | 291 | 645 | 45.12%
2022-01-12 | 2019 | Navy Active | N69232586 |  | 2019-02-08 | 2019-09-26 | SOLPAC CONSTRUCTION INC | N62473 | N6247318D5855 N6247319F5449 | N6247318D5855 | N69232586,N6247318D5855 N6247319F5449 | 27152000 | 26967000 | 2020-02-15 | 2021-07-01 | -185000 | 502 | 2021 | 07 | 01 | 20210701 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 26526898.9583 | 26349851.7335 | -177047.2248 | 502 | 142 | 353.5%
2022-01-12 | 2019 | Marine Corps Active | N41557270 |  | 2019-01-25 | 2019-09-12 | GILBANE SMCC ECC LLC | N62742 | N6274219D1331 N6274219F9926 | N6274219D1331 | N41557270,N6274219D1331 N6274219F9926 | 27191000 | 25408000 | 2022-03-25 | 2022-03-25 | -1783000 | 0 | 2022 | 03 | 25 | 20220325 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 27941230.6154 | 26157142.376 | -1784088.2394 | 0 | 925 | 0%
2021-12-31 | 2015 | Air Force Active | PAYZ15001H |  | 2017-03-08 | 2017-09-22 | Cimolai S.p.A | N62470 | N6247017C5002 | N6247017C5002 | PAYZ15001H,N6247017C5002 | 27192353 | 37466344 | 2020-08-30 | 2022-12-22 | 10273991 | 844 | 2022 | 12 | 22 | 20221222 | 2017 | 2023 | 0.97698 | 2020 | 0.95701 | 26566322.9401 | 36398655.8818 | 9832332.9418 | 844 | 1073 | 78.66%
2022-02-02 | 2016 | DoD Education Activity | AM00035 |  | 2016-03-14 | 2017-03-29 | POETTKER CONSTRUCTION COMPANY | W912HN | W912HN-17-C-0005/37035966 | W912HN17C0005 | AM00035,W912HN-17-C-0005/37035966 | 27223000 | 27209938 | 2019-04-26 | 2019-08-15 | -13062 | 111 | 2019 | 08 | 15 | 20190815 | 2017 | 2019 | 1.0507 | 2018 | 1.0006 | 28603231.5769 | 28590161.6046 | -13069.9723 | 111 | 758 | 14.64%
2022-01-06 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278 | W91278-11-D-0062 | W9127811D0062 | 76375,W91278-11-D-0062 | 27358000 | 29794432 | 2016-07-23 | 2017-08-28 | 2436432 | 401 | 2017 | 08 | 28 | 20170828 | 2014 | 2017 | 1.2581 | 2016 | 1.2319 | 34418025.6377 | 37419556.7454 | 3001531.1078 | 401 | 663 | 60.48%
2021-12-31 | 2021 | Air Force Active | LRCT190002 |  | 2021-06-23 | 2021-09-16 | Relyant Global LLC | W912GB | W912GB21F0202 | W912GB21F0202 | LRCT190002,W912GB21F0202 | 27388762 | 27388762 | 2024-11-05 | 2024-11-05 | 0 | 0 | 2024 | 11 | 05 | 20241105 | 2021 | 2025 | 1.2319 | 2023 | 1.0993 | 33741233.5522 | 33741233.5522 | 0 | 0 | 1146 | 0%
2022-01-12 | 2019 | Navy Active | N60201427 |  | 2018-07-30 | 2019-02-22 | Archer Western Federal JV | N69450 | N6945019F0855 | N6945019F0855 | N60201427,N6945019F0855 | 27496000 | 26493000 | 2021-02-05 | 2021-06-04 | -1003000 | 119 | 2021 | 06 | 04 | 20210604 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 28890072.9323 | 27886460.7595 | -1003612.1728 | 119 | 714 | 16.67%
2021-12-31 | 2020 | Air Force Active | RKMF203007 |  | 2020-03-13 | 2020-06-19 | Record Steel and Construction, Inc., dba RsCI | W912PL | W912PL20C0018 | W912PL20C0018 | RKMF203007,W912PL20C0018 | 27554000 | 27554000 | 2022-07-24 | 2022-07-24 | 0 | 0 | 2022 | 07 | 24 | 20220724 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 27570817.3573 | 27570817.3573 | 0 | 0 | 765 | 0%
2022-01-12 | 2020 | Marine Corps Active | M670011203F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | M670011203F,N4008520D0034 N4008520F6501 | 27688000 | 28664000 | 2024-09-30 | 2025-09-27 | 976000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 1.0751 | 2023 | 1.0276 | 29766751.2881 | 30769680.2382 | 1002928.95 | 362 | 1476 | 24.53%
2022-02-02 | 2015 | DoD Education Activity | PA00023 |  | 2016-06-13 | 2016-11-22 | NES PACIFIC LIMITED LIABILITY CO. | W912HV | W912HV-17-C-0002/37064811 | W912HV17C0002 | PA00023,W912HV-17-C-0002/37064811 | 27722277 | 30649314 | 2019-05-28 | 2021-01-21 | 2927037 | 604 | 2021 | 01 | 21 | 20210121 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 27739197.0637 | 30598846.9881 | 2859649.9244 | 604 | 917 | 65.87%
2022-02-28 | 2021 | Defense Information Systems Agency | 01DISA21 |  | 2021-04-16 | 2021-09-13 | The Korte Company | W912PL | W912PL21C0013 | W912PL21C0013 | 01DISA21,W912PL21C0013 | 27737733 | 27737733 | 2023-09-13 | 2023-09-13 | 0 | 0 | 2023 | 09 | 13 | 20230913 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 28503048.6007 | 28503048.6007 | 0 | 0 | 730 | 0%
2022-01-12 | 2021 | Marine Corps Active | N61159311 |  | 2020-09-14 | 2021-03-15 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274219D1332 N6274221F9927 | N6274219D1332 | N61159311,N6274219D1332 N6274221F9927 | 27795000 | 28047000 | 2023-08-23 | 2023-08-23 | 252000 | 0 | 2023 | 08 | 23 | 20230823 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 29204232.5122 | 29456386.3183 | 252153.8061 | 0 | 891 | 0%
2022-01-13 | 2018 | Defense Health Agency | 14021 |  | 2018-06-12 | 2019-12-18 | Soltek Pacific Construction Co. | N62473 | N6247318D5855 | N6247318D5855 | 14021,N6247318D5855 | 27799000 | 28065000 | 2022-05-10 | 2022-05-10 | 266000 | 0 | 2022 | 05 | 10 | 20220510 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 28566006.0269 | 28832168.3778 | 266162.3509 | 0 | 874 | 0%
2022-01-06 | 2008 | Special Operations Command | 0P-926 |  | 2008-05-27 | 2009-09-25 | Contrack Watts, Inc | W912ER | W912ER-09-C-0051 | W912ER09C0051 | 0P-926,W912ER-09-C-0051 | 27841952 | 15889227 | 2011-12-13 | 2012-12-27 | -11952725 | 380 | 2012 | 12 | 27 | 20121227 | 2009 | 2013 | 0.97698 | 2011 | 0.9382 | 27200966.6877 | 15986943.225 | -11214023.4627 | 380 | 809 | 46.97%
2022-02-02 | 2016 | DoD Education Activity | AM00110 |  | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278 | W91278-12-D-0037/41084584 | W9127812D0037 | AM00110,W91278-12-D-0037/41084584 | 27895686 | 37522745 | 2020-05-28 | 2022-09-01 | 9627059 | 826 | 2022 | 09 | 01 | 20220901 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 27912711.9025 | 37318134.0209 | 9405422.1184 | 826 | 1157 | 71.39%
2022-01-12 | 2020 | Marine Corps Active | M670011506F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | M670011506F,N4008520D0034 N4008520F6501 | 28045000 | 30423000 | 2024-09-30 | 2025-09-27 | 2378000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 0.97698 | 2023 | 0.95701 | 27399340.0591 | 29675114.6569 | 2275774.5978 | 362 | 1476 | 24.53%
2022-01-06 | 2012 | Special Operations Command | CZQZ083012 |  | 2012-05-07 | 2012-08-31 | Hensel Phelps Construction Co | W912PP | W912PP-12-C-0027 | W912PP12C0027 | CZQZ083012,W912PP-12-C-0027 | 28160000 | 29398390 | 2014-09-04 | 2014-10-02 | 1238390 | 28 | 2014 | 10 | 02 | 20141002 | 2012 | 2015 | 0.97698 | 2014 | 0.97698 | 27511692.4965 | 28721571.9308 | 1209879.4343 | 28 | 734 | 3.815%
2022-01-12 | 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N62470 | N6247017C5005 AWD | N6247017C5005 | N62995655,N6247017C5005 AWD | 28340000 | 51111000 | 2019-04-23 | 2021-11-30 | 22771000 | 952 | 2021 | 11 | 30 | 20211130 | 2017 | 2022 | 1.0507 | 2020 | 1.0276 | 29776864.5222 | 53176142.3106 | 23399277.7884 | 952 | 882 | 107.9%
2021-12-31 | 2018 | Air Force Active | ASVF183100F |  | 2020-03-11 | 2020-04-10 | American International Contractors, Inc (Pkg 2, Aprons) | W912ER | W912ER20C0009 | W912ER20C0009 | ASVF183100F,W912ER20C0009 | 28401350 | 28167704 | 2023-03-21 | 2023-11-17 | -233646 | 241 | 2023 | 11 | 17 | 20231117 | 2020 | 2024 | 1.1227 | 2022 | 1.0276 | 31885393.4764 | 31645300.9175 | -240092.5589 | 241 | 1075 | 22.42%
2022-01-12 | 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N40085 | N4008516C5506 AWD | N4008516C5506 | M00146194,N4008516C5506 AWD | 28561000 | 27767000 | 2019-01-29 | 2019-01-29 | -794000 | 0 | 2019 | 01 | 29 | 20190129 | 2016 | 2019 | 1.0751 | 2018 | 1.0507 | 30705294.1181 | 29871037.575 | -834256.5431 | 0 | 881 | 0%
2022-01-06 | 2010 | Special Operations Command | 63831 |  | 2010-01-06 | 2010-08-03 | Federal Contracting dba Bryan Construction | W9128F | W9128F-10-C-0061 | W9128F10C0061 | 63831,W9128F-10-C-0061 | 28586634 | 33108929 | 2012-05-01 | 2012-08-03 | 4522295 | 94 | 2012 | 08 | 03 | 20120803 | 2010 | 2012 | 1.0507 | 2011 | 1.0006 | 30036003.0968 | 34561058.2424 | 4525055.1456 | 94 | 637 | 14.76%
2022-01-13 | 2019 | Defense Health Agency | 89838 |  | 2019-07-09 | 2019-09-30 | DeMaria Building Co | N40085 | N4008519C9124 | N4008519C9124 | 89838,N4008519C9124 | 28729000 | 28301000 | 2021-10-30 | 2022-12-30 | -428000 | 426 | 2022 | 12 | 30 | 20221230 | 2019 | 2023 | 1.0006 | 2021 | 0.97698 | 28746534.5088 | 28328388.0462 | -418146.4627 | 426 | 761 | 55.98%
2022-02-02 | 2015 | DoD Education Activity | EU00064 |  | 2017-06-29 | 2017-09-21 | Joint Venture WMV Brussels American School | W912GB | W912GB-17-C-0018/44739768 | W912GB17C0018 | EU00064,W912GB-17-C-0018/44739768 | 28765482 | 29107109 | 2020-10-24 | 2023-03-31 | 341627 | 888 | 2023 | 03 | 31 | 20230331 | 2017 | 2023 | 1.0507 | 2020 | 1.0006 | 30223918.8578 | 30565754.367 | 341835.5092 | 888 | 1129 | 78.65%
2021-11-30 | 2018 | Missile Defense Agency | 674 |  | 2018-04-17 | 2018-07-20 | CP03-Watterson Construction Company | W911KB | W911KB18C0030 | W911KB18C0030 | 674,W911KB18C0030 | 28807000 | 32124438 | 2020-11-01 | 2021-03-29 | 3317438 | 148 | 2021 | 03 | 29 | 20210329 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 29601817.8934 | 32842880.8952 | 3241063.0019 | 148 | 835 | 17.72%
2021-12-31 | 2018 | Missile Defense Agency | 674 |  | 2018-04-17 | 2018-07-20 | CP03-Watterson Construction Company | W911KB | W911KB-18-C-0030 | W911KB18C0030 | 674,W911KB-18-C-0030 | 28807000 | 32124438 | 2020-11-01 | 2021-03-29 | 3317438 | 148 | 2021 | 03 | 29 | 20210329 | 2018 | 2021 | 1.0006 | 2020 | 0.97698 | 28824582.1155 | 32065645.1173 | 3241063.0019 | 148 | 835 | 17.72%
2022-01-06 | 2011 | Special Operations Command | 76511 |  | 2011-04-30 | 2011-09-30 | Archer Western Contractors, LLC | W912HN | W912HN-11-C-0014 | W912HN11C0014 | 76511,W912HN-11-C-0014 | 28900000 | 30484390 | 2013-05-11 | 2013-10-31 | 1584390 | 173 | 2013 | 10 | 31 | 20131031 | 2011 | 2014 | 1.0993 | 2013 | 1.0507 | 31768475.6045 | 33433195.6602 | 1664720.0558 | 173 | 589 | 29.37%
2021-12-31 | 2019 | Army Reserve | 77268 |  | 2018-11-20 | 2019-02-28 | Straub Construction, Inc. | W912QR | W912QR19C0012 | W912QR19C0012 | 77268,W912QR19C0012 | 28937000 | 30632000 | 2020-11-21 | 2022-02-09 | 1695000 | 445 | 2022 | 02 | 09 | 20220209 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 28954661.4599 | 30576796.844 | 1622135.384 | 445 | 632 | 70.41%
2022-01-12 | 2017 | Navy Active | N00620240 |  | 2016-06-14 | 2017-08-09 | BETHEL-WEBCOR JV-1 | N44255 | N4425517D4032 N4425517F4132 | N4425517D4032 | N00620240,N4425517D4032 N4425517F4132 | 28966000 | 29771000 | 2020-03-26 | 2021-01-19 | 805000 | 299 | 2021 | 01 | 19 | 20210119 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 28983679.1598 | 29770146.2216 | 786467.0618 | 299 | 960 | 31.15%
2022-01-12 | 2017 | Navy Active | N61755652 |  | 2017-06-12 | 2018-05-23 | APTIM FEDERAL SERVICES, LLC | N62742 | N6274218C1318 AWD | N6274218C1318 | N61755652,N6274218C1318 AWD | 28975000 | 29381000 | 2020-04-03 | 2021-08-15 | 406000 | 499 | 2021 | 08 | 15 | 20210815 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 28307929.3354 | 28696476.218 | 388546.8825 | 499 | 681 | 73.27%
2022-01-12 | 2017 | Army National Guard | 200101 |  | 2018-06-12 | 2018-11-27 | The Law Company Inc. | A-0136 | A-013650 | A013650 | 200101,A-013650 | 29000000 | 28834954 | 2020-12-23 | 2022-02-12 | -165046 | 416 | 2022 | 02 | 12 | 20220212 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 28332353.7783 | 28174402.7715 | -157951.0068 | 416 | 757 | 54.95%
2022-01-12 | 2020 | Army National Guard | 160024 |  | 2020-08-25 | 2020-08-31 | IMCO Construction | W912J7 | W912J7-19-2-2001 | W912J71922001 | 160024,W912J7-19-2-2001 | 29000000 | 30185000 | 2022-09-02 | 2022-03-16 | 1185000 | -170 | 2022 | 03 | 16 | 20220316 | 2020 | 2022 | 1.0993 | 2021 | 1.0507 | 31878401.1256 | 33123481.7346 | 1245080.609 | -170 | 732 | -23.22%
2021-09-30 | 2017 | Air National Guard | FJRP159062 |  | 2018-09-19 | 2019-03-29 | Cleveland Construction Inc | W91242 | W9124219C5004 | W9124219C5004 | FJRP159062,W9124219C5004 | 29161433 | 28170000 | 2020-10-28 | 2020-10-28 | -991433 | 0 | 2020 | 10 | 28 | 20201028 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 29966030.1029 | 28997422.1545 | -968607.9484 | 0 | 579 | 0%
2022-01-06 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN | W912HN-11-D-0002 | W912HN11D0002 | 76364,W912HN-11-D-0002 | 29232386 | 33465310 | 2014-08-26 | 2016-04-21 | 4232924 | 604 | 2016 | 04 | 21 | 20160421 | 2013 | 2016 | 1.0006 | 2015 | 1.0006 | 29250227.7463 | 33485735.2767 | 4235507.5303 | 604 | 670 | 90.15%
2022-01-12 | 2020 | Marine Corps Active | M670011518F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011518F,N4008520C0044 AWD | 29242000 | 30232000 | 2024-09-30 | 2025-09-27 | 990000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 1.0276 | 2023 | 0.97698 | 30048820.0381 | 31016027.9774 | 967207.9393 | 362 | 1529 | 23.68%
2022-01-12 | 2019 | Marine Corps Active | M67004947 |  | 2019-08-07 | 2020-01-31 | THE HASKELL COMPANY | N40085 | N4008520C8504 AWD | N4008520C8504 | M67004947,N4008520C8504 AWD | 29418000 | 28448000 | 2022-05-04 | 2022-07-27 | -970000 | 84 | 2022 | 07 | 27 | 20220727 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 30229676.0783 | 29259084.0468 | -970592.0315 | 84 | 824 | 10.19%
2022-01-13 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 | N4008016C0172 | N4008016C0172 | 80306,N4008016C0172 | 29435000 | 30582000 | 2017-12-10 | 2018-08-31 | 1147000 | 264 | 2018 | 08 | 31 | 20180831 | 2016 | 2018 | 1.0006 | 2017 | 0.97698 | 29452965.4101 | 30573558.8509 | 1120593.4408 | 264 | 465 | 56.77%
2021-12-31 | 2012 | Air Force Active | TYFR063017 |  | 2012-03-01 | 2012-05-24 | LBB (EBC AWD) | W912GB | W912GB11C0013 | W912GB11C0013 | TYFR063017,W912GB11C0013 | 29541693 | 29662433 | 2017-01-18 | 2026-06-18 | 120740 | 3438 | 2026 | 06 | 18 | 20260618 | 2012 | 2026 | 1.0507 | 2019 | 1.0006 | 31039484.4819 | 31160298.1746 | 120813.6927 | 3438 | 1700 | 202.2%
2021-12-30 | 2018 | Air National Guard | PSXE999132 |  | 2018-06-08 | 2019-08-05 | Messer Construction Company | W912L7 | W912L719C7001 | W912L719C7001 | PSXE999132,W912L719C7001 | 29613217 | 30218917 | 2021-08-22 | 2021-08-22 | 605700 | 0 | 2021 | 08 | 22 | 20210822 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 31114634.8157 | 31720704.4997 | 606069.684 | 0 | 748 | 0%
2021-08-31 | 2018 | Army Active | 70677 |  | 2018-02-26 | 2018-09-14 | ACC Construction Co. | W912HN | W912HN18C3002 | W912HN18C3002 | 70677,W912HN18C3002 | 29857000 | 33153000 | 2020-12-16 | 2021-08-31 | 3296000 | 258 | 2021 | 08 | 31 | 20210831 | 2018 | 2021 | 1.0507 | 2020 | 1.0276 | 31370777.8419 | 34757718.2306 | 3386940.3887 | 258 | 824 | 31.31%
2022-01-06 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278 | W91278-12-D-0037 | W9127812D0037 | FTFA113004,W91278-12-D-0037 | 29942300 | 32051388 | 2016-12-25 | 2017-05-26 | 2109088 | 152 | 2017 | 05 | 26 | 20170526 | 2013 | 2017 | 0.97698 | 2015 | 0.9382 | 29252959.8806 | 31231702.1604 | 1978742.2798 | 152 | 1192 | 12.75%
2022-01-12 | 2020 | Army National Guard | 500110 |  | 2020-09-22 | 2020-09-29 | Dew Construction | 40766 | 40766 | 40766 | 500110,40766 | 30000000 | 28775000 | 2022-09-02 | 2022-09-02 | -1225000 | 0 | 2022 | 09 | 02 | 20220902 | 2020 | 2022 | 0.95701 | 2021 | 0.9382 | 28710360.7792 | 27561068.15 | -1149292.6292 | 0 | 703 | 0%
2022-01-06 | 2017 | Special Operations Command | 69552 |  | 2017-03-02 | 2019-01-15 | ACC Construction Co., Inc. | W912PM | W912PM19C0008 | W912PM19C0008 | 69552,W912PM19C0008 | 30006388 | 31202082 | 2020-11-08 | 2022-02-08 | 1195694 | 457 | 2022 | 02 | 08 | 20220208 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 29315572.4285 | 30437370.2252 | 1121797.7968 | 457 | 663 | 68.93%
2022-01-13 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB | W912GB-09-C-0038 | W912GB09C0038 | 66588,W912GB-09-C-0038 | 30080000 | 31830000 | 2016-05-30 | 2017-05-03 | 1750000 | 338 | 2017 | 05 | 03 | 20170503 | 2013 | 2017 | 1.0507 | 2015 | 1.0006 | 31605084.1506 | 33356152.2487 | 1751068.0981 | 338 | 1169 | 28.91%
2021-12-31 | 2017 | Air Force Active | VDYD101053 |  | 2020-02-24 | 2020-07-29 | River City Construction, LLC/East Peoria IL | W912QR | W912QR20C0028 | W912QR20C0028 | VDYD101053,W912QR20C0028 | 30100000 | 30100000 | 2023-03-08 | 2023-10-12 | 0 | 218 | 2023 | 10 | 12 | 20231012 | 2020 | 2024 | 0.97698 | 2022 | 0.95701 | 29407029.2665 | 29407029.2665 | 0 | 218 | 952 | 22.9%
2022-01-06 | 2018 | Special Operations Command | FTEV153008 |  | 2019-06-27 | 2020-02-27 | RC Construction Co, Inc | W91278 | W9127820C0009 | W9127820C0009 | FTEV153008,W9127820C0009 | 30127950 | 29857715 | 2023-03-18 | 2023-03-18 | -270235 | 0 | 2023 | 03 | 18 | 20230318 | 2020 | 2023 | 1.0751 | 2022 | 1.0276 | 32389887.1161 | 32112196.0251 | -277691.091 | 0 | 1115 | 0%
2022-01-12 | 2017 | Marine Corps Active | M00263403 |  | 2017-01-27 | 2018-07-31 | KORTE CONSTRUCTION COMPANY | N40085 | N4008518C0640 AWD | N4008518C0640 | M00263403,N4008518C0640 AWD | 30382000 | 29633000 | 2021-02-28 | 2022-01-02 | -749000 | 308 | 2022 | 01 | 02 | 20220102 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 31220273.9347 | 30470816.7887 | -749457.146 | 308 | 943 | 32.66%
2022-01-12 | 2017 | Navy Active | N32446371 |  | 2017-09-19 | 2018-03-30 | ENGINEERED CONSTRUCTION SERVICES,INC | N40085 | N4008518C8719 AWD | N4008518C8719 | N32446371,N4008518C8719 AWD | 30414000 | 30767000 | 2021-09-14 | 2021-09-14 | 353000 | 0 | 2021 | 09 | 14 | 20210914 | 2018 | 2021 | 1.2082 | 2020 | 1.1743 | 36746996.0464 | 37161530.4761 | 414534.4297 | 0 | 1264 | 0%
2021-12-31 | 2018 | Army Active | 88380 |  | 2019-06-18 | 2019-09-05 | M.W. Builders | W9126G | W9126G19C0119 | W9126G19C0119 | 88380,W9126G19C0119 | 30477000 | 36023000 | 2021-08-15 | 2022-02-05 | 5546000 | 174 | 2022 | 02 | 05 | 20220205 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 31317895.0927 | 36736213.5084 | 5418318.4157 | 174 | 710 | 24.51%
2020-12-09 | 2016 | National Security Agency | 31066 |  | 2015-04-15 | 2016-06-06 | Hensel-Phelps | W912DR | W912DR-15-D-0032 DO 0002 | W912DR15D0032 | 31066,W912DR-15-D-0032 DO 0002 | 30538350 | 33305344 | 2018-08-08 | 2018-12-18 | 2766994 | 132 | 2018 | 12 | 18 | 20181218 | 2016 | 2019 | 1.0006 | 2018 | 0.97698 | 30556988.8307 | 33260280.3104 | 2703291.4797 | 132 | 793 | 16.65%
2021-11-16 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113 | 230113-D | 230113D | 230113,230113-D | 30615000 | 32795000 | 2017-08-03 | 2021-03-31 | 2180000 | 1336 | 2021 | 03 | 31 | 20210331 | 2015 | 2021 | 1.0751 | 2018 | 1.0276 | 32913503.7087 | 35153652.3881 | 2240148.6794 | 1336 | 779 | 171.5%
2022-01-06 | 2013 | Special Operations Command | 69287 |  | 2013-06-03 | 2013-09-20 | Archer Western Contractors, LLC | W91278 | W91278-11-D-0073 | W9127811D0073 | 69287,W91278-11-D-0073 | 30907435 | 33877211 | 2015-07-26 | 2016-05-25 | 2969776 | 304 | 2016 | 05 | 25 | 20160525 | 2013 | 2016 | 1.0507 | 2015 | 1.0006 | 32474470.8795 | 35446059.4578 | 2971588.5784 | 304 | 674 | 45.1%
2022-01-12 | 2019 | Marine Corps Active | M00146254F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520C0055 AWD | N4008520C0055 | M00146254F,N4008520C0055 AWD | 30990000 | 30904000 | 2025-08-12 | 2025-08-12 | -86000 | 0 | 2025 | 08 | 12 | 20250812 | 2020 | 2025 | 1.0006 | 2023 | 0.95701 | 31008914.4916 | 30926611.4574 | -82303.0342 | 0 | 1826 | 0%
2022-01-12 | 2019 | Navy Active | N00213720 |  | 2019-04-17 | 2019-09-26 | THE HASKELL COMPANY | N69450 | N6945019D0909 N6945019F0874 | N6945019D0909 | N00213720,N6945019D0909 N6945019F0874 | 30995000 | 29632000 | 2021-12-13 | 2023-06-29 | -1363000 | 563 | 2023 | 06 | 29 | 20230629 | 2019 | 2023 | 1.2082 | 2021 | 1.1743 | 37448975.5526 | 35848379.4401 | -1600596.1126 | 563 | 809 | 69.59%
2022-01-12 | 2017 | Army National Guard | 150035 |  | 2017-02-02 | 2017-09-28 | Alutiiq General Contractors LLC | W912J6 | W912J6-17-C-0001 | W912J617C0001 | 150035,W912J6-17-C-0001 | 31000000 | 28565000 | 2019-06-30 | 2021-12-30 | -2435000 | 914 | 2021 | 12 | 30 | 20211230 | 2017 | 2022 | 1.2826 | 2020 | 1.2581 | 39759482.0663 | 36696104.1722 | -3063377.8941 | 914 | 640 | 142.8%
2022-01-12 | 2018 | Army National Guard | 530129 |  | 2018-09-05 | 2018-09-11 | Pease Construction | 2016-0 | 2016-0008 G (1-1) | 20160008 | 530129,2016-0008 G (1-1) | 31000000 | 31823000 | 2020-09-01 | 2021-09-01 | 823000 | 365 | 2021 | 09 | 01 | 20210901 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 31855325.2575 | 32659377.9182 | 804052.6607 | 365 | 721 | 50.62%
2022-01-12 | 2018 | Navy Active | N69212995 |  | 2018-12-19 | 2019-01-31 | AECOM CONSTRUCTION, INC. | N40085 | N4008519D9066 N4008519F4710 | N4008519D9066 | N69212995,N4008519D9066 N4008519F4710 | 31074000 | 29801000 | 2021-06-25 | 2021-12-08 | -1273000 | 166 | 2021 | 12 | 08 | 20211208 | 2019 | 2022 | 1.0507 | 2021 | 1.0006 | 32649480.8808 | 31375703.9158 | -1273776.9651 | 166 | 876 | 18.95%
2022-01-12 | 2015 | Navy Active | N68469275 |  | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N40080 | N4008018C0005 AWD | N4008018C0005 | N68469275,N4008018C0005 AWD | 31151000 | 44069000 | 2019-11-15 | 2022-01-20 | 12918000 | 797 | 2022 | 01 | 20 | 20220120 | 2018 | 2022 | 1.1227 | 2020 | 1.0993 | 34972347.8702 | 49172526.6888 | 14200178.8186 | 797 | 743 | 107.3%
2021-12-31 | 2020 | Air Force Reserve | UHHZ073005 |  | 2020-11-15 | 2021-01-29 | ACC Construction Company, Inc. | W912QR | W912QR19C0009 | W912QR19C0009 | UHHZ073005,W912QR19C0009 | 31229066 | 31229066 | 2023-04-11 | 2023-04-11 | 0 | 0 | 2023 | 04 | 11 | 20230411 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 33573672.3701 | 33573672.3701 | 0 | 0 | 802 | 0%
2021-12-31 | 2019 | Air Force Active | FTFA143913 |  | 2019-03-26 | 2019-04-25 | Korte Construction | W91278 | W9127819C0013 | W9127819C0013 | FTFA143913,W9127819C0013 | 31295038 | 31286284 | 2020-04-24 | 2020-04-26 | -8754 | 2 | 2020 | 04 | 26 | 20200426 | 2019 | 2020 | 1.0507 | 2020 | 1.0006 | 32881725.7143 | 32872966.3714 | -8759.3429 | 2 | 365 | 0.5479%
2021-12-30 | 2020 | Air National Guard | TUMR189004 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N69450 | N6945021C0031 | N6945021C0031 | TUMR189004,N6945021C0031 | 31741307 | 27230000 | 2024-02-28 | 2024-02-28 | -4511307 | 0 | 2024 | 02 | 28 | 20240228 | 2021 | 2024 | 1.0006 | 2023 | 0.9382 | 31760680.0456 | 27528180.5491 | -4232499.4966 | 0 | 923 | 0%
2022-01-12 | 2016 | Navy Active | N68436983 |  | 2016-04-15 | 2016-09-21 | NOVA GROUP INC | N44255 | N4425516C7005 AWD | N4425516C7005 | N68436983,N4425516C7005 AWD | 31744000 | 35122000 | 2018-02-13 | 2019-04-21 | 3378000 | 432 | 2019 | 04 | 21 | 20190421 | 2016 | 2019 | 1.0507 | 2018 | 1.0006 | 33353450.5079 | 36733512.2424 | 3380061.7345 | 432 | 510 | 84.71%
2022-01-12 | 2018 | Army National Guard | 290109 |  | 2018-09-19 | 2018-09-20 | KCI Construction Company | T1818- | T1818-01 | T181801 | 290109,T1818-01 | 32000000 | 24564000 | 2020-11-18 | 2021-06-30 | -7436000 | 224 | 2021 | 06 | 30 | 20210630 | 2018 | 2021 | 1.0751 | 2020 | 1.0507 | 34402486.3197 | 26589474.1607 | -7813012.159 | 224 | 790 | 28.35%
2022-01-12 | 2019 | Army National Guard | 380116 |  | 2019-05-31 | 2019-06-05 | Gast Construction | AGND 1 | AGND 19-17 | AGND | 380116,AGND 19-17 | 32000000 | 28758000 | 2021-06-30 | 2021-06-30 | -3242000 | 0 | 2021 | 06 | 30 | 20210630 | 2019 | 2021 | 0.95701 | 2020 | 0.9382 | 30624384.8312 | 27582746.7055 | -3041638.1257 | 0 | 756 | 0%
2022-01-12 | 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N44255 | N4425516C7004 AWD | N4425516C7004 | N68436993,N4425516C7004 AWD | 32047000 | 32209000 | 2019-08-07 | 2019-08-07 | 162000 | 0 | 2019 | 08 | 07 | 20190807 | 2016 | 2019 | 1.0006 | 2018 | 0.97698 | 32066559.6228 | 32224830.0129 | 158270.3901 | 0 | 1072 | 0%
2022-01-31 | 2014 | DLA Defense Energy Support Center | DESC1502 A |  | 2014-06-17 | 2014-10-21 | NOVA Group Inc. | W912BV | W912BV-15-C-0001 | W912BV15C0001 | DESC1502 A,W912BV-15-C-0001 | 32060100 | 32532000 | 2017-05-23 | 2021-08-16 | 471900 | 1546 | 2021 | 08 | 16 | 20210816 | 2015 | 2021 | 1.0276 | 2018 | 1.0006 | 32944674.6222 | 33416862.6425 | 472188.0203 | 1546 | 945 | 163.6%
2021-12-31 | 2018 | Air Force Reserve | UHHZ073003 |  | 2019-06-28 | 2019-09-24 | ACC Construction Company, Inc. | W912QR | W912QR19C0042 | W912QR19C0042 | UHHZ073003,W912QR19C0042 | 32093710 | 28917160 | 2021-11-26 | 2022-07-30 | -3176550 | 246 | 2022 | 07 | 30 | 20220730 | 2019 | 2022 | 1.0006 | 2021 | 0.9382 | 32113298.1319 | 29133065.0695 | -2980233.0624 | 246 | 794 | 30.98%
2022-02-02 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278 | W91278-12-D-0039/30132665 | W9127812D0039 | AM00031,W91278-12-D-0039/30132665 | 32124000 | 33068283 | 2017-02-10 | 2017-10-31 | 944283 | 263 | 2017 | 10 | 31 | 20171031 | 2015 | 2018 | 1.0006 | 2017 | 0.95701 | 32143606.6192 | 33047296.8061 | 903690.1869 | 263 | 827 | 31.8%
2021-12-31 | 2018 | Air Force Active | ASVF183100A |  | 2019-01-11 | 2020-04-10 | American International Contractors, (Pkg 2, Aprons) | W912ER | W912ER20C0009 | W912ER20C0009 | ASVF183100A,W912ER20C0009 | 32474636 | 32474636 | 2023-03-28 | 2023-03-28 | 0 | 0 | 2023 | 03 | 28 | 20230328 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 34121130.4368 | 34121130.4368 | 0 | 0 | 1082 | 0%
2022-01-12 | 2017 | Marine Corps Active | M67865249 |  | 2017-09-19 | 2017-12-18 | R A BURCH CONSTRUCTION CO INC | N62473 | N6247316D1884 N6247318F4138 | N6247316D1884 | M67865249,N6247316D1884 N6247318F4138 | 32536000 | 34614000 | 2019-09-24 | 2020-10-01 | 2078000 | 373 | 2020 | 10 | 01 | 20201001 | 2018 | 2021 | 1.0006 | 2020 | 0.97698 | 32555858.08 | 34586017.7748 | 2030159.6949 | 373 | 645 | 57.83%
2021-12-30 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2014-12-12 | 2015-04-07 | Nippo Corporation | W912HV | W912HV-15-C-0005 | W912HV15C0005 | DESC1401,W912HV-15-C-0005 | 32623000 | 33122640 | 2017-08-23 | 2018-11-15 | 499640 | 449 | 2018 | 11 | 15 | 20181115 | 2015 | 2019 | 0.97698 | 2017 | 0.95701 | 31871944.0452 | 32350105.5339 | 478161.4887 | 449 | 869 | 51.67%
2021-12-30 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV | W912HV-15-C-005 | W912HV15C005 | DESC1401,W912HV-15-C-005 | 32623000 | 42122640 | 2017-08-23 | 2021-09-30 | 9499640 | 1499 | 2021 | 09 | 30 | 20210930 | 2015 | 2021 | 1.0276 | 2018 | 1.0006 | 33523105.6734 | 43028543.7006 | 9505438.0271 | 1499 | 869 | 172.5%
2022-01-06 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM | W912PM-17-C-0001 | W912PM17C0001 | 80773,W912PM-17-C-0001 | 32661077 | 33207816 | 2019-01-31 | 2019-06-06 | 546739 | 126 | 2019 | 06 | 06 | 20190606 | 2017 | 2019 | 1.0276 | 2018 | 1.0006 | 33562233.2612 | 34109305.9588 | 547072.6977 | 126 | 801 | 15.73%
2022-01-06 | 2010 | Special Operations Command | 63019 |  | 2009-09-24 | 2010-04-09 | Hensel Phelps Construction Co. | W912PP | W912PP-10-C-0015 | W912PP10C0015 | 63019,W912PP-10-C-0015 | 32766000 | 35162304 | 2012-12-24 | 2013-03-15 | 2396304 | 81 | 2013 | 03 | 15 | 20130315 | 2010 | 2013 | 1.0507 | 2012 | 1.0276 | 34427266.8643 | 36889687.6171 | 2462420.7528 | 81 | 990 | 8.182%
2022-01-12 | 2018 | Navy Active | N00246988 |  | 2018-06-06 | 2018-08-30 | RQ CONSTRUCTION, LLC | N62473 | N6247317D0820 N6247318F5040 | N6247317D0820 | N00246988,N6247317D0820 N6247318F5040 | 32923000 | 32930000 | 2021-03-22 | 2021-10-29 | 7000 | 221 | 2021 | 10 | 29 | 20211029 | 2018 | 2022 | 0.97698 | 2020 | 0.95701 | 32165037.3601 | 32171736.4443 | 6699.0842 | 221 | 935 | 23.64%
2022-01-12 | 2014 | Navy Active | N00128714 |  | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N40085 | N4008518C8707 AWD | N4008518C8707 | N00128714,N4008518C8707 AWD | 32940000 | 31764000 | 2020-08-14 | 2020-10-23 | -1176000 | 70 | 2020 | 10 | 23 | 20201023 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 33848852.064 | 32672134.3021 | -1176717.7619 | 70 | 746 | 9.383%
2021-12-31 | 2018 | Army Active | 86816 |  | 2019-03-21 | 2019-09-10 | The Robins & Morton Group | W91278 | W9127819C0024 | W9127819C0024 | 86816,W9127819C0024 | 32995000 | 34056000 | 2021-10-10 | 2022-04-14 | 1061000 | 186 | 2022 | 04 | 14 | 20220414 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 33015138.2268 | 34051711.584 | 1036573.3572 | 186 | 761 | 24.44%
2021-12-31 | 2019 | Air Force Active | MSET153504 |  | 2018-10-15 | 2018-11-14 | KVF35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153504,DIOCB2076 | 33031258 | 33031258 | 2023-01-21 | 2023-01-21 | 0 | 0 | 2023 | 01 | 21 | 20230121 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 33942627.976 | 33942627.976 | 0 | 0 | 1529 | 0%
2021-12-31 | 2021 | Army Reserve | 82197 |  | 2021-08-04 | 2021-09-30 | Sauer Construction, LLC | W912QR | W912QR21C0049 | W912QR21C0049 | 82197,W912QR21C0049 | 33126000 | 33126000 | 2023-10-20 | 2023-10-20 | 0 | 0 | 2023 | 10 | 20 | 20231020 | 2021 | 2024 | 1.0276 | 2023 | 0.95701 | 34039984.0155 | 34039984.0155 | 0 | 0 | 750 | 0%
2021-12-31 | 2016 | Air Force Active | LXEZ154288 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV | W912HV16D0009 | W912HV16D0009 | LXEZ154288,W912HV16D0009 | 33322662 | 33322662 | 2021-01-14 | 2021-01-14 | 0 | 0 | 2021 | 01 | 14 | 20210114 | 2018 | 2021 | 1.0507 | 2020 | 1.0006 | 35012152.1487 | 35012152.1487 | 0 | 0 | 898 | 0%
2022-01-12 | 2019 | Marine Corps Active | M670011509F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011509F,N4008520C0044 AWD | 33391000 | 40681000 | 2017-05-30 | 2025-01-11 | 7290000 | 2783 | 2025 | 01 | 11 | 20250111 | 2020 | 2025 | 1.0751 | 2023 | 1.0276 | 35897919.3969 | 43389058.7881 | 7491139.3912 | 2783 | -1151 | -241.8%
2022-05-03 | 2018 | DLA Defense Energy Support Center | DESC1805 |  | 2018-05-21 | 2018-12-27 | TOA CORPORATION | W912HV | W912HV19C0003 / 51379145 | W912HV19C0003 | DESC1805,W912HV19C0003 / 51379145 | 33455000 | 33455000 | 2021-04-01 | 2022-02-28 | 0 | 333 | 2022 | 02 | 28 | 20220228 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 34378061.4997 | 34378061.4997 | 0 | 333 | 826 | 40.31%
2022-02-02 | 2016 | DoD Education Activity | EU00068 |  | 2017-09-05 | 2018-04-20 | Staatliches Hochbauamt Amberg | W912GB | W912GB-12-C-0036/57200363 | W912GB12C0036 | EU00068,W912GB-12-C-0036/57200363 | 33667431 | 37180306 | 2021-03-16 | 2022-03-30 | 3512875 | 379 | 2022 | 03 | 30 | 20220330 | 2018 | 2022 | 1.0507 | 2020 | 1.0006 | 35374401.2596 | 38889420.314 | 3515019.0544 | 379 | 1061 | 35.72%
2022-01-06 | 2016 | Special Operations Command | AFSOC103002 |  | 2018-04-09 | 2018-09-28 | NIPPO CORPORATION | W912HV | W912HV-16-D-0008 | W912HV16D0008 | AFSOC103002,W912HV-16-D-0008 | 33751828 | 34992358 | 2020-10-21 | 2021-02-17 | 1240530 | 119 | 2021 | 02 | 17 | 20210217 | 2018 | 2021 | 1.0006 | 2020 | 0.97698 | 33772428.1506 | 34984398.3172 | 1211970.1666 | 119 | 754 | 15.78%
2022-01-12 | 2019 | Marine Corps Active | M00146130F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520C0055 AWD | N4008520C0055 | M00146130F,N4008520C0055 AWD | 33831000 | 33952000 | 2025-08-12 | 2025-08-12 | 121000 | 0 | 2025 | 08 | 12 | 20250812 | 2020 | 2025 | 1.0993 | 2023 | 1.0276 | 37188903.051 | 37313241.5786 | 124338.5276 | 0 | 1826 | 0%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB | W912GB-10-C-0031, P00085 | W912GB10C0031, | 76007,W912GB-10-C-0031, P00085 | 33888000 | 34523000 | 2021-03-31 | 2021-12-30 | 635000 | 274 | 2021 | 12 | 30 | 20211230 | 2013 | 2022 | 0.97698 | 2018 | 0.95701 | 33107820.8566 | 33715523.4931 | 607702.6365 | 274 | 2773 | 9.881%
2022-01-12 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274214C1304 AWD | N6274214C1304 | N62813320,N6274214C1304 AWD | 33970000 | 36725000 | 2017-08-03 | 2020-10-06 | 2755000 | 1160 | 2020 | 10 | 06 | 20201006 | 2014 | 2021 | 1.2581 | 2018 | 1.2319 | 42736323.2295 | 46130310.093 | 3393986.8635 | 1160 | 1130 | 102.7%
2022-01-12 | 2020 | Army National Guard | 011801 |  | 2021-04-22 | 2021-06-10 | Carmon Construction, Inc. | AC-21- | AC-21-C-0004-S | AC21C0004S | 011801,AC-21-C-0004-S | 34000000 | 34880000 | 2022-10-21 | 2023-08-27 | 880000 | 310 | 2023 | 08 | 27 | 20230827 | 2021 | 2023 | 1.0507 | 2022 | 1.0006 | 35723831.8192 | 36604368.9199 | 880537.1008 | 310 | 498 | 62.25%
2021-12-31 | 2020 | Army Active | 76673 |  | 2020-06-29 | 2020-11-10 | Turner Construction Co, Inc | W91278 | W9127821C0006 | W9127821C0006 | 76673,W9127821C0006 | 34050000 | 34762000 | 2022-12-25 | 2022-12-25 | 712000 | 0 | 2022 | 12 | 25 | 20221225 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 34070782.1374 | 34752174.6999 | 681392.5625 | 0 | 775 | 0%
2022-01-06 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co | W91278 | W91278-12-D-0038 | W9127812D0038 | NVZR143703,W91278-12-D-0038 | 34157000 | 38234191 | 2019-01-26 | 2019-11-19 | 4077191 | 297 | 2019 | 11 | 19 | 20191119 | 2016 | 2020 | 1.0276 | 2018 | 1.0006 | 35099430.4781 | 39179109.9581 | 4079679.48 | 297 | 858 | 34.62%
2021-12-31 | 2019 | National Security Agency | 32100 |  | 2019-03-18 | 2020-01-30 | Hensel-Phelps | W912DR | W912DR-20-C-0004 | W912DR20C0004 | 32100,W912DR-20-C-0004 | 34227105 | 35707039 | 2022-11-17 | 2022-11-17 | 1479934 | 0 | 2022 | 11 | 17 | 20221117 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 35171469.7548 | 36617332.2947 | 1445862.5399 | 0 | 1022 | 0%
2021-12-31 | 2018 | Air Force Active | CRWU093002 |  | 2018-02-01 | 2018-12-18 | Mortenson | W9128F | W9128F18R00040030 | W9128F18R00040030 | CRWU093002,W9128F18R00040030 | 34249000 | 34971796 | 2021-04-22 | 2022-01-15 | 722796 | 268 | 2022 | 01 | 15 | 20220115 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 35193968.8628 | 35900124.4483 | 706155.5856 | 268 | 856 | 31.31%
2022-01-12 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N40085 | N4008515C8739 AWD | N4008515C8739 | N32414547,N4008515C8739 AWD | 34317000 | 58233000 | 2016-11-23 | 2021-11-19 | 23916000 | 1822 | 2021 | 11 | 19 | 20211119 | 2015 | 2022 | 0.97698 | 2019 | 0.95701 | 33526944.2969 | 56414843.9102 | 22887899.6132 | 1822 | 555 | 328.3%
2021-12-31 | 2020 | Air Force Active | FSPM173504 |  | 2020-01-31 | 2020-08-06 | Korte Construction Company | W912PL | W912PL20C0030 | W912PL20C0030 | FSPM173504,W912PL20C0030 | 34420210 | 34420210 | 2020-08-06 | 2023-08-09 | 0 | 1098 | 2023 | 08 | 09 | 20230809 | 2020 | 2023 | 1.0006 | 2022 | 0.9382 | 34441218.092 | 34441218.092 | 0 | 1098 | 0 | #DIV/0!
2022-01-12 | 2018 | Marine Corps Active | M67865210 |  | 2018-05-16 | 2018-08-30 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318D5853 N6247318F4873 | N6247318D5853 | M67865210,N6247318D5853 N6247318F4873 | 34513000 | 39683000 | 2020-05-20 | 2021-02-26 | 5170000 | 282 | 2021 | 02 | 26 | 20210226 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 33718431.9294 | 38666184.1037 | 4947752.1743 | 282 | 629 | 44.83%
2022-01-12 | 2018 | Marine Corps Active | M00318877 |  | 2020-05-20 | 2020-09-23 | NIKING CORP. | N62742 | N6274220C1304 AWD | N6274220C1304 | M00318877,N6274220C1304 AWD | 34513000 | 18250000 | 2022-01-07 | 2022-02-11 | -16263000 | 35 | 2022 | 02 | 11 | 20220211 | 2020 | 2022 | 1.0006 | 2021 | 0.9382 | 34534064.7257 | 19276149.5997 | -15257915.1259 | 35 | 471 | 7.431%
2022-01-12 | 2016 | Navy Active | N62688610 |  | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N40085 | N4008517C0307 AWD | N4008517C0307 | N62688610,N4008517C0307 AWD | 34675000 | 37844000 | 2019-10-25 | 2020-12-30 | 3169000 | 432 | 2020 | 12 | 30 | 20201230 | 2017 | 2021 | 1.2319 | 2019 | 1.2082 | 42717420.8685 | 46546290.1547 | 3828869.2862 | 432 | 785 | 55.03%
2022-01-12 | 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N40085 | N4008516C3013 AWD | N4008516C3013 | N32446308,N4008516C3013 AWD | 34722000 | 34943000 | 2018-10-25 | 2018-10-25 | 221000 | 0 | 2018 | 10 | 25 | 20181025 | 2016 | 2019 | 1.0507 | 2018 | 1.0006 | 36482437.8949 | 36703572.7804 | 221134.8855 | 0 | 917 | 0%
2022-01-06 | 2017 | Special Operations Command | 76514 |  | 2017-03-02 | 2018-04-05 | RQ Construction, LLC | W912PM | W912PM18C0011 | W912PM18C0011 | 76514,W912PM18C0011 | 34937000 | 36225167 | 2020-03-23 | 2021-10-29 | 1288167 | 585 | 2021 | 10 | 29 | 20211029 | 2018 | 2022 | 1.0276 | 2020 | 0.97698 | 35900951.5653 | 37159462.0194 | 1258510.4541 | 585 | 718 | 81.48%
2022-01-13 | 2017 | Defense Health Agency | 14019 |  | 2017-06-23 | 2018-06-29 | RQ-DPRI | N40085 | N40085-18-C-0637 | N4008518C0637 | 14019,N40085-18-C-0637 | 35000000 | 31558000 | 2020-07-13 | 2021-10-07 | -3442000 | 451 | 2021 | 10 | 07 | 20211007 | 2018 | 2022 | 1.1519 | 2020 | 1.1227 | 40315365.8222 | 36451129.6382 | -3864236.184 | 451 | 745 | 60.54%
2022-01-12 | 2020 | Army National Guard | 310103 |  | 2020-08-26 | 2020-08-31 | Sampson Construction Company, Inc. | W91243 | W91243-19-2-2001 | W912431922001 | 310103,W91243-19-2-2001 | 35000000 | 27225000 | 2022-10-28 | 2022-10-28 | -7775000 | 0 | 2022 | 10 | 28 | 20221028 | 2020 | 2023 | 1.1743 | 2022 | 1.0507 | 41101147.4244 | 32931947.6481 | -8169199.7763 | 0 | 788 | 0%
2022-01-12 | 2018 | Navy Active | N62688495 |  | 2017-07-10 | 2018-09-28 | WHITING-TURNER CONTRACTING CO | N40085 | N4008518C1148 AWD | N4008518C1148 | N62688495,N4008518C1148 AWD | 35158000 | 34046000 | 2021-02-04 | 2022-09-04 | -1112000 | 577 | 2022 | 09 | 04 | 20220904 | 2018 | 2022 | 1.0751 | 2020 | 1.0276 | 37797581.6884 | 36654900.3437 | -1142681.3447 | 577 | 860 | 67.09%
2021-12-31 | 2020 | Air Force Active | NKAK123007 |  | 2020-05-15 | 2020-08-31 | The Ross Group Construction | W9127S | W9127S20C6006 | W9127S20C6006 | NKAK123007,W9127S20C6006 | 35396600 | 35396600 | 2020-08-31 | 2023-10-15 | 0 | 1140 | 2023 | 10 | 15 | 20231015 | 2020 | 2024 | 1.0006 | 2022 | 0.95701 | 35418204.0237 | 35418204.0237 | 0 | 1140 | 0 | #DIV/0!
2022-01-12 | 2020 | Marine Corps Active | M670011495 |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N40085 | N4008520C0145 AWD | N4008520C0145 | M670011495,N4008520C0145 AWD | 35517314 | 37448000 | 2023-03-05 | 2023-03-19 | 1930686 | 14 | 2023 | 03 | 19 | 20230319 | 2020 | 2023 | 1.0276 | 2022 | 1.0006 | 36497277.0885 | 38429141.4668 | 1931864.3783 | 14 | 934 | 1.499%
2022-01-12 | 2017 | Marine Corps Active | M67865198 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318C4605 AWD | N6247318C4605 | M67865198,N6247318C4605 AWD | 35632000 | 39482000 | 2020-01-14 | 2020-06-26 | 3850000 | 164 | 2020 | 06 | 26 | 20200626 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 35653747.6981 | 39415111.9066 | 3761364.2085 | 164 | 720 | 22.78%
2022-01-13 | 2017 | Defense Health Agency | 71509 |  | 2017-06-30 | 2018-12-26 | KBE BLDG CORP | N40085 | N4008519C9070 | N4008519C9070 | 71509,N4008519C9070 | 35912000 | 32464000 | 2021-01-24 | 2021-07-14 | -3448000 | 171 | 2021 | 07 | 14 | 20210714 | 2019 | 2021 | 1.0751 | 2020 | 1.0276 | 38608190.2723 | 35065056.0308 | -3543134.2415 | 171 | 760 | 22.5%
2022-01-12 | 2019 | Marine Corps Active | M00681079 |  | 2019-07-24 | 2019-12-12 | ORION CONSTRUCTION CORPORATION | N62473 | N6247320C0612 AWD | N6247320C0612 | M00681079,N6247320C0612 AWD | 35918000 | 34747000 | 2022-05-30 | 2022-05-30 | -1171000 | 0 | 2022 | 05 | 30 | 20220530 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 35939922.2559 | 34819261.1734 | -1120661.0824 | 0 | 900 | 0%
2022-02-02 | 2014 | DoD Education Activity | AM00046 | 246 | 2013-02-06 | 2016-03-16 | J&J Contractors & Engineers, Inc. | W912WJ | W912WJ-17-C-0004/57439943 | W912WJ17C0004 | AM00046,W912WJ-17-C-0004/57439943 | 35970000 | 37442688 | 2019-09-09 | 2019-08-20 | 1472688 | -20 | 2019 | 08 | 20 | 20190820 | 2016 | 2019 | 1.0276 | 2018 | 0.97698 | 36962453.2101 | 38401236.5695 | 1438783.3593 | -20 | 1272 | -1.572%
2022-01-12 | 2018 | Army National Guard | 100040 |  | 2018-09-07 | 2018-09-13 | Harkins Builders, Inc. | 09-201 | 09-2016 | 92016 | 100040,09-2016 | 36000000 | 36000000 | 2020-12-31 | 2020-12-31 | 0 | 0 | 2020 | 12 | 31 | 20201231 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 36993280.9442 | 36993280.9442 | 0 | 0 | 840 | 0%
2022-01-12 | 2020 | Navy Active | N476091919 |  | 2021-02-03 | 2021-05-20 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247321D1206 N6247321F4741 | N6247321D1206 | N476091919,N6247321D1206 N6247321F4741 | 36044616 | 45821000 | 2024-02-05 | 2024-02-05 | 9776384 | 0 | 2024 | 02 | 05 | 20240205 | 2021 | 2024 | 0.97698 | 2023 | 0.9382 | 35214786.6316 | 44386971.18 | 9172184.5484 | 0 | 991 | 0%
2022-01-06 | 2015 | Special Operations Command | 69302 |  | 2015-11-12 | 2017-04-03 | Sauer Incorporated | W91278 | W91278-12-D-0039 | W9127812D0039 | 69302,W91278-12-D-0039 | 36061000 | 39828403 | 2019-05-07 | 2020-12-11 | 3767403 | 584 | 2020 | 12 | 11 | 20201211 | 2017 | 2021 | 1.0507 | 2019 | 1.0006 | 37889326.448 | 41659028.8514 | 3769702.4034 | 584 | 764 | 76.44%
2022-01-12 | 2021 | Marine Corps Active | N61159804 |  | 2020-02-24 | 2021-03-22 | CORE TECH-HDCC-KAJIMA LLC | N62742 | N6274221C1335 AWD | N6274221C1335 | N61159804,N6274221C1335 AWD | 36105000 | 36105000 | 2024-03-12 | 2024-03-12 | 0 | 0 | 2024 | 03 | 12 | 20240312 | 2021 | 2024 | 1.0276 | 2023 | 0.97698 | 37101178.0137 | 37101178.0137 | 0 | 0 | 1086 | 0%
2021-12-30 | 2017 | DLA Defense Distribution Center | DDCX1701A |  | 2017-12-08 | 2018-04-12 | Carouthers Construction | W9126G | W9126G-18-C-0018 | W9126G18C0018 | DDCX1701A,W9126G-18-C-0018 | 36159560 | 36510784 | 2020-06-25 | 2021-05-24 | 351224 | 333 | 2021 | 05 | 24 | 20210524 | 2018 | 2021 | 1.0993 | 2020 | 1.0276 | 39748584.7657 | 40109499.4353 | 360914.6696 | 333 | 805 | 41.37%
2021-12-31 | 2019 | Air Force Active | MSET153508 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153508,DIOCB2076 | 36198139 | 36198139 | 2024-01-21 | 2024-01-21 | 0 | 0 | 2024 | 01 | 21 | 20240121 | 2019 | 2024 | 1.0276 | 2022 | 1.0006 | 37196886.8246 | 37196886.8246 | 0 | 0 | 1894 | 0%
2022-01-06 | 2015 | Special Operations Command | CZQZ063029 |  | 2016-12-13 | 2018-10-05 | Federal Contracting, Inc. | W912PP | W912PP19C0001 | W912PP19C0001 | CZQZ063029,W912PP19C0001 | 36206044 | 38176680 | 2021-05-16 | 2022-02-22 | 1970636 | 282 | 2022 | 02 | 22 | 20220222 | 2019 | 2022 | 1.1519 | 2021 | 1.1227 | 41704568.8239 | 43916946.2024 | 2212377.3785 | 282 | 954 | 29.56%
2022-01-12 | 2019 | Navy Active | N002450888 |  | 2019-01-02 | 2019-03-28 | HELIX ELECTRIC, INC. | N62473 | N6247316D3201 0010 | N6247316D3201 | N002450888,N6247316D3201 0010 | 36336000 | 48661000 | 2021-08-18 | 2022-07-07 | 12325000 | 323 | 2022 | 07 | 07 | 20220707 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 37338551.5664 | 49671074.0288 | 12332522.4624 | 323 | 874 | 36.96%
2022-01-31 | 2018 | DoD Education Activity | EU00117 |  | 2019-05-01 | 2019-09-27 | ICM SPA | N62470 | N6247019C5007 | N6247019C5007 | EU00117,N6247019C5007 | 36391000 | 39826000 | 2022-01-27 | 2022-12-02 | 3435000 | 309 | 2022 | 12 | 02 | 20221202 | 2019 | 2023 | 0.97698 | 2021 | 0.9382 | 35553196.081 | 38775906.4331 | 3222710.3522 | 309 | 853 | 36.23%
2022-01-12 | 2019 | Navy Active | N61755640 |  | 2019-02-20 | 2019-06-25 | GILBANE FEDERAL | N62742 | N6274219C1310 AWD | N6274219C1310 | N61755640,N6274219C1310 AWD | 36419000 | 36147000 | 2022-10-07 | 2022-12-24 | -272000 | 78 | 2022 | 12 | 24 | 20221224 | 2019 | 2023 | 0.97698 | 2021 | 0.95701 | 35580551.457 | 35320244.1859 | -260307.2711 | 78 | 1200 | 6.5%
2022-01-06 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F | W9128F-14-C-0024 | W9128F14C0024 | 76367,W9128F-14-C-0024 | 36441000 | 33300649 | 2016-07-20 | 2018-01-30 | -3140351 | 559 | 2018 | 01 | 30 | 20180130 | 2014 | 2018 | 1.0006 | 2016 | 0.95701 | 36463241.4646 | 33457887.7918 | -3005353.6728 | 559 | 734 | 76.16%
2021-12-30 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | 1234 | 1234 | 1234 | DESC1606,1234 | 36443425 | 39151158 | 2018-07-01 | 2018-08-20 | 2707733 | 50 | 2018 | 08 | 20 | 20180820 | 2016 | 2018 | 1.0276 | 2017 | 1.0006 | 37448940.5443 | 40158326.1869 | 2709385.6426 | 50 | 958 | 5.219%
2021-12-30 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR | W912QR-15-C-0026 | W912QR15C0026 | DESC1301,W912QR-15-C-0026 | 36448000 | 37081000 | 2017-03-30 | 2021-04-25 | 633000 | 1487 | 2021 | 04 | 25 | 20210425 | 2015 | 2021 | 1.0276 | 2018 | 1.0006 | 37453641.7738 | 38087028.1201 | 633386.3463 | 1487 | 580 | 256.4%
2022-01-12 | 2020 | Marine Corps Active | M670011519F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | M670011519F,N4008520D0034 N4008520F6501 | 36463000 | 37513000 | 2024-09-30 | 2025-09-27 | 1050000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 0.97698 | 2023 | 0.95701 | 35623538.4765 | 36628401.1038 | 1004862.6273 | 362 | 1476 | 24.53%
2021-12-31 | 2020 | Army Active | 87807 |  | 2020-04-10 | 2021-07-02 | M.W. Builders | W9126G | W9126G21C0014 | W9126G21C0014 | 87807,W9126G21C0014 | 36514000 | 36525000 | 2023-07-20 | 2023-07-20 | 11000 | 0 | 2023 | 07 | 20 | 20230720 | 2021 | 2023 | 1.0751 | 2022 | 1.0507 | 39255387.0462 | 39266944.7565 | 11557.7103 | 0 | 748 | 0%
2021-12-30 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | N69450 | N69450-16-C-1604 | N6945016C1604 | DESC1606,N69450-16-C-1604 | 36565000 | 57832172 | 2017-11-05 | 2019-12-22 | 21267172 | 777 | 2019 | 12 | 22 | 20191222 | 2016 | 2020 | 1.0751 | 2018 | 1.0276 | 39310216.0088 | 61164173.4723 | 21853957.4635 | 777 | 720 | 107.9%
2022-01-12 | 2021 | Marine Corps Active | N61159802 |  | 2021-04-08 | 2021-08-16 | CADDELL-NAN A JOINT VENTURE | N62742 | N6274219D1329 N6274221F9933 | N6274219D1329 | N61159802,N6274219D1329 N6274221F9933 | 36571666 | 41359000 | 2023-12-07 | 2023-12-07 | 4787334 | 0 | 2023 | 12 | 07 | 20231207 | 2021 | 2024 | 0.97698 | 2023 | 0.95701 | 35729702.7371 | 40311238.9474 | 4581536.2104 | 0 | 843 | 0%
2021-12-31 | 2020 | Air Force Active | RKMF163007 |  | 2020-07-23 | 2020-09-30 | KORTE | W912PL | W912PL20C0021 | W912PL20C0021 | RKMF163007,W912PL20C0021 | 36685652 | 37557368 | 2022-12-28 | 2023-05-07 | 871716 | 130 | 2023 | 05 | 07 | 20230507 | 2020 | 2023 | 0.97698 | 2022 | 0.95701 | 35841064.5191 | 36675307.2143 | 834242.6952 | 130 | 819 | 15.87%
2022-01-12 | 2019 | Marine Corps Active | M00263404 |  | 2019-02-14 | 2019-07-10 | R. C. CONSTRUCTION | N40085 | N4008519C9017 AWD | N4008519C9017 | M00263404,N4008519C9017 AWD | 36938000 | 36163000 | 2021-08-17 | 2021-11-04 | -775000 | 79 | 2021 | 11 | 04 | 20211104 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 36087602.8919 | 35360499.3917 | -727103.5001 | 79 | 769 | 10.27%
2022-01-12 | 2017 | Army National Guard | 490601 |  | 2017-09-21 | 2017-09-26 | Jacobsen Construction Company | 187507 | 1875077 | 1875077 | 490601,1875077 | 37000000 | 37610000 | 2019-04-03 | 2021-05-27 | 610000 | 785 | 2021 | 05 | 27 | 20210527 | 2017 | 2021 | 1.0507 | 2019 | 1.0006 | 38875934.6267 | 39486306.9352 | 610372.3085 | 785 | 554 | 141.7%
2021-08-31 | 2019 | Army Active | 94610 |  | 2019-11-07 | 2020-01-10 | SLSCO, Ltd | W9126G | W9126G19D0021 | W9126G19D0021 | 94610,W9126G19D0021 | 37106000 | 47319000 | 2021-07-20 | 2021-08-29 | 10213000 | 40 | 2021 | 08 | 29 | 20210829 | 2020 | 2021 | 0.97698 | 2021 | 0.95701 | 36251735.1482 | 46025698.9695 | 9773963.8213 | 40 | 557 | 7.181%
2021-12-31 | 2020 | Army Active | 69347 |  | 2020-02-06 | 2020-05-20 | B.L. Harbert Internationl | W912QR | W912QR20C0022 | W912QR20C0022 | 69347,W912QR20C0022 | 37142000 | 39788000 | 2022-07-11 | 2022-10-08 | 2646000 | 89 | 2022 | 10 | 08 | 20221008 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 38166790.0231 | 40751873.0609 | 2585083.0378 | 89 | 782 | 11.38%
2022-01-12 | 2018 | Marine Corps Active | M670011320 |  | 2018-08-09 | 2018-09-28 | SAUER, INC. | N40085 | N4008518C0610 AWD | N4008518C0610 | M670011320,N4008518C0610 AWD | 37174000 | 36007000 | 2020-10-23 | 2021-11-05 | -1167000 | 378 | 2021 | 11 | 05 | 20211105 | 2018 | 2022 | 1.0276 | 2020 | 0.95701 | 38199672.9395 | 37082839.9052 | -1116833.0343 | 378 | 756 | 50%
2022-01-12 | 2018 | Navy Active | N61151163 |  | 2018-02-12 | 2018-09-29 | JOHN C. GRIMBERG CO., INC. | N40080 | N4008018C0008 AWD | N4008018C0008 | N61151163,N4008018C0008 AWD | 37296000 | 35903000 | 2021-08-14 | 2021-08-14 | -1393000 | 0 | 2021 | 08 | 14 | 20210814 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 38325039.0582 | 36931188.8521 | -1393850.2061 | 0 | 1050 | 0%
2021-12-31 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G | W9126G-14-D-0050 | W9126G14D0050 | 68530,W9126G-14-D-0050 | 37657000 | 55028000 | 2018-12-17 | 2022-05-20 | 17371000 | 1250 | 2022 | 05 | 20 | 20220520 | 2015 | 2022 | 1.0006 | 2019 | 0.97698 | 37679983.6402 | 54651063.5534 | 16971079.9132 | 1250 | 1181 | 105.8%
2022-01-12 | 2017 | Navy Active | N00128714 | N00128714A | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N40085 | N4008518C8707 AWD | N4008518C8707 | N00128714,N4008518C8707 AWD | 37695000 | 35814000 | 2020-08-14 | 2020-10-23 | -1881000 | 70 | 2020 | 10 | 23 | 20201023 | 2018 | 2021 | 0.97698 | 2020 | 0.95701 | 36827175.0233 | 35027035.4024 | -1800139.6209 | 70 | 746 | 9.383%
2022-01-12 | 2018 | Marine Corps Active | M62974539 |  | 2018-05-02 | 2018-07-03 | WHITING-TURNER CONTRACTING CO | N62473 | N6247317D0822 N6247318F4783 | N6247317D0822 | M62974539,N6247317D0822 N6247318F4783 | 37962000 | 37974000 | 2020-06-28 | 2022-04-04 | 12000 | 645 | 2022 | 04 | 04 | 20220404 | 2018 | 2022 | 1.1227 | 2020 | 1.0993 | 42618865.2001 | 42632056.2626 | 13191.0625 | 645 | 726 | 88.84%
2021-12-31 | 2020 | Army Active | 77728 |  | 2020-02-07 | 2020-06-26 | Walsh Federal, LLC | W912DW | W912DW20C0007 | W912DW20C0007 | 77728,W912DW20C0007 | 38027000 | 39097000 | 2022-12-31 | 2023-01-11 | 1070000 | 11 | 2023 | 01 | 11 | 20230111 | 2020 | 2023 | 1.0006 | 2022 | 0.95701 | 38050209.4667 | 39074212.3344 | 1024002.8678 | 11 | 918 | 1.198%
2022-01-12 | 2017 | Navy Active | N68436400 |  | 2017-08-10 | 2018-09-29 | CUSTOM MECHANICAL SYSTEMS CORP(CMS) | N44255 | N4425517D4034 N4425518F4438 | N4425517D4034 | N68436400,N4425517D4034 N4425518F4438 | 38496000 | 39961000 | 2021-06-30 | 2022-03-19 | 1465000 | 262 | 2022 | 03 | 19 | 20220319 | 2018 | 2022 | 0.97698 | 2020 | 0.9382 | 37609734.1742 | 38984194.3389 | 1374460.1648 | 262 | 1005 | 26.07%
2022-01-06 | 2015 | Special Operations Command | 79437 |  | 2016-06-27 | 2016-09-28 | SAUER Incorporated, d/b/a Sauer Southeast | W91278 | W91278-12-D-0039 | W9127812D0039 | 79437,W91278-12-D-0039 | 38659000 | 53691548 | 2019-02-11 | 2022-02-13 | 15032548 | 1098 | 2022 | 02 | 13 | 20220213 | 2016 | 2022 | 1.1914 | 2019 | 1.1519 | 46056810.1206 | 63372315.0309 | 17315504.9103 | 1098 | 866 | 126.8%
2022-01-12 | 2017 | Marine Corps Active | M67865203 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318C4605 AWD | N6247318C4605 | M67865203,N6247318C4605 AWD | 38707000 | 41830000 | 2020-01-14 | 2020-06-26 | 3123000 | 164 | 2020 | 06 | 26 | 20200626 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 38730624.4991 | 41781725.9077 | 3051101.4086 | 164 | 720 | 22.78%
2022-01-13 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 | N6945013C1756 | N6945013C1756 | 71317,N6945013C1756 | 38744000 | 46104000 | 2016-12-30 | 2019-02-15 | 7360000 | 777 | 2019 | 02 | 15 | 20190215 | 2013 | 2019 | 0.97698 | 2016 | 0.95701 | 37852024.6479 | 44895633.159 | 7043608.5112 | 777 | 1295 | 60%
2022-01-12 | 2016 | Navy Active | N47608975 |  | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N40080 | N4008018C0311 AWD | N4008018C0311 | N47608975,N4008018C0311 AWD | 38795000 | 38693000 | 2020-02-02 | 2020-07-23 | -102000 | 172 | 2020 | 07 | 23 | 20200723 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 38818678.2091 | 38719026.4821 | -99651.7271 | 172 | 660 | 26.06%
2022-01-12 | 2018 | Army National Guard | 270132 |  | 2018-08-31 | 2018-09-06 | Stahl Construction Company | Swift | Swift #147206 | Swift | 270132,Swift #147206 | 39000000 | 40487000 | 2020-02-14 | 2020-08-04 | 1487000 | 172 | 2020 | 08 | 04 | 20200804 | 2018 | 2020 | 1.0507 | 2019 | 1.0006 | 40977336.4985 | 42465244.0767 | 1487907.5782 | 172 | 526 | 32.7%
2021-12-31 | 2018 | Air Force Active | MSET153514 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET153514,DIOCB2076 | 39101561 | 39101561 | 2021-10-05 | 2021-10-05 | 0 | 0 | 2021 | 10 | 05 | 20211005 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 39125426.3161 | 39125426.3161 | 0 | 0 | 1056 | 0%
2022-01-13 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G- | W912G-09-D-0004-0008 | W912G09D00040008 | 72481,W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12 | 8163000 | 60 | 2013 | 10 | 12 | 20131012 | 2011 | 2014 | 1.0276 | 2013 | 1.0006 | 40430573.2986 | 48598555.5186 | 8167982.2199 | 60 | 748 | 8.021%
2022-01-12 | 2020 | Navy Active | N62995130 |  | 2020-07-06 | 2020-09-29 | WOLFF & MULLER GOVERNMENT SERVICES | N62470 | N6247020C0013 AWD | N6247020C0013 | N62995130,N6247020C0013 AWD | 39712368 | 45589000 | 2025-06-05 | 2025-06-05 | 5876632 | 0 | 2025 | 06 | 05 | 20250605 | 2020 | 2025 | 1.0751 | 2023 | 1.0276 | 42693881.1514 | 48732656.112 | 6038774.9606 | 0 | 1710 | 0%
2022-01-12 | 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N69450 | N6945014C1756 AWD | N6945014C1756 | N42237099,N6945014C1756 AWD | 39730000 | 41372000 | 2018-06-20 | 2019-03-27 | 1642000 | 280 | 2019 | 03 | 27 | 20190327 | 2014 | 2019 | 0.97698 | 2017 | 0.95701 | 38815324.6763 | 40386738.423 | 1571413.7467 | 280 | 1400 | 20%
2022-01-12 | 2018 | Navy Active | N68469275 | N68469275A | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N40080 | N4008018C0005 AWD | N4008018C0005 | N68469275,N4008018C0005 AWD | 39776000 | 37882000 | 2019-11-15 | 2022-01-20 | -1894000 | 797 | 2022 | 01 | 20 | 20220120 | 2018 | 2022 | 1.0006 | 2020 | 0.97698 | 39800276.9544 | 37949881.1594 | -1850395.795 | 797 | 743 | 107.3%
2022-01-12 | 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N62473 | N6247317C3403 AWD | N6247317C3403 | M006811220,N6247317C3403 AWD | 39860000 | 43124000 | 2019-03-30 | 2019-03-30 | 3264000 | 0 | 2019 | 03 | 30 | 20190330 | 2017 | 2019 | 1.0507 | 2018 | 1.0276 | 41880939.3033 | 45234996.7756 | 3354057.4723 | 0 | 850 | 0%
2022-01-12 | 2019 | Navy Active | N68469001 |  | 2019-06-07 | 2019-09-16 | ENVIRONMENTAL CHEMICAL CORPORATION | N62470 | N6247019D8025 N6247019F9101 | N6247019D8025 | N68469001,N6247019D8025 N6247019F9101 | 40000000 | 102049000 | 2024-09-15 | 2024-09-15 | 62049000 | 0 | 2024 | 09 | 15 | 20240915 | 2019 | 2024 | 1.2581 | 2022 | 1.2319 | 50322429.4725 | 126762898.0368 | 76440468.5644 | 0 | 1826 | 0%
2020-12-09 | 2015 | National Security Agency | 27532 |  | 2015-04-15 | 2016-04-05 | Hensel-Phelps | W912DR | W912DR-15-D-0032 | W912DR15D0032 | 27532,W912DR-15-D-0032 | 40081050 | 45544834 | 2018-10-25 | 2019-04-03 | 5463784 | 160 | 2019 | 04 | 03 | 20190403 | 2016 | 2019 | 1.0006 | 2018 | 0.97698 | 40105513.1392 | 45443508.3549 | 5337995.2157 | 160 | 933 | 17.15%
2022-01-13 | 2016 | Defense Health Agency | 81422 |  | 2017-11-27 | 2018-09-24 | United Excel Corportation (now StructSure Projects) | W9126G | W9126G-18-C-0077 | W9126G18C0077 | 81422,W9126G-18-C-0077 | 40138000 | 48168000 | 2021-04-01 | 2023-06-19 | 8030000 | 809 | 2023 | 06 | 19 | 20230619 | 2018 | 2023 | 1.0276 | 2021 | 0.97698 | 41245453.0706 | 49090584.134 | 7845131.0635 | 809 | 920 | 87.93%
2021-12-31 | 2018 | Army Active | 77779 |  | 2018-06-22 | 2019-06-06 | S.B. Ballard Construction Company | W91236 | W9123619C0014 | W9123619C0014 | 77779,W9123619C0014 | 40458000 | 40771000 | 2021-02-15 | 2022-01-14 | 313000 | 333 | 2022 | 01 | 14 | 20220114 | 2019 | 2022 | 1.1914 | 2021 | 1.1519 | 48200067.8719 | 48560602.4291 | 360534.5572 | 333 | 620 | 53.71%
2022-01-12 | 2017 | Navy Active | N60201154 |  | 2017-02-23 | 2017-06-29 | HENSEL PHELPS CONSTRUCTION CO | N69450 | N6945014D1269 N6945017F0700 | N6945014D1269 | N60201154,N6945014D1269 N6945017F0700 | 40518000 | 40483000 | 2019-09-26 | 2019-12-27 | -35000 | 92 | 2019 | 12 | 27 | 20191227 | 2017 | 2020 | 1.0006 | 2019 | 0.97698 | 40542729.828 | 40508535.6079 | -34194.2201 | 92 | 819 | 11.23%
2022-01-12 | 2019 | Marine Corps Active | M00146142F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520C0055 AWD | N4008520C0055 | M00146142F,N4008520C0055 AWD | 40771000 | 41147000 | 2025-08-12 | 2025-08-12 | 376000 | 0 | 2025 | 08 | 12 | 20250812 | 2020 | 2025 | 0.97698 | 2023 | 0.95701 | 39832358.4792 | 40192195.001 | 359836.5218 | 0 | 1826 | 0%
2022-01-12 | 2018 | Navy Active | N41557H280 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N62742 | N6274219C1309 AWD | N6274219C1309 | N41557H280,N6274219C1309 AWD | 40850000 | 39044000 | 2022-07-05 | 2023-03-13 | -1806000 | 251 | 2023 | 03 | 13 | 20230313 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 41977097.9603 | 40212676.2044 | -1764421.756 | 251 | 1020 | 24.61%
2022-01-12 | 2019 | Marine Corps Active | M00146162F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008520C0055 AWD | N4008520C0055 | M00146162F,N4008520C0055 AWD | 41270000 | 45089000 | 2025-08-12 | 2025-08-12 | 3819000 | 0 | 2025 | 08 | 12 | 20250812 | 2020 | 2025 | 1.0507 | 2023 | 1.0006 | 43362427.6229 | 47183758.5181 | 3821330.8952 | 0 | 1826 | 0%
2022-01-06 | 2011 | Special Operations Command | 66362 |  | 2011-04-08 | 2012-05-30 | Archer Western Contractors, LLC | W912HN | W912HN-12-C-0009 | W912HN12C0009 | 66362,W912HN-12-C-0009 | 41446000 | 44338384 | 2014-01-31 | 2014-12-30 | 2892384 | 333 | 2014 | 12 | 30 | 20141230 | 2012 | 2015 | 0.97698 | 2014 | 0.95701 | 40491818.4378 | 43259864.7096 | 2768046.2717 | 333 | 611 | 54.5%
2021-12-31 | 2016 | Air Force Active | KNMD043004 |  | 2018-02-01 | 2018-09-29 | Nordic PCL Construction | W9128A | W9128A18C0009 | W9128A18C0009 | KNMD043004,W9128A18C0009 | 41476374 | 44043580 | 2020-10-22 | 2021-10-29 | 2567206 | 372 | 2021 | 10 | 29 | 20211029 | 2018 | 2022 | 1.0751 | 2020 | 1.0006 | 44590324.6602 | 47159097.5333 | 2568772.8731 | 372 | 754 | 49.34%
2022-02-02 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB | W912GB-12-C-0006/44599966 | W912GB12C0006 | EU00034,W912GB-12-C-0006/44599966 | 41569129 | 43920418 | 2018-12-24 | 2019-06-13 | 2351289 | 171 | 2019 | 06 | 13 | 20190613 | 2016 | 2019 | 0.97698 | 2018 | 0.95701 | 40612112.7271 | 42862324.5766 | 2250211.8495 | 171 | 885 | 19.32%
2022-01-12 | 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N62473 | N6247315C1604 AWD | N6247315C1604 | N00245800,N6247315C1604 AWD | 41838000 | 45470000 | 2019-04-10 | 2019-04-10 | 3632000 | 0 | 2019 | 04 | 10 | 20190410 | 2015 | 2019 | 1.2826 | 2017 | 1.2581 | 53659910.0223 | 58229186.6184 | 4569276.5961 | 0 | 1301 | 0%
2021-12-31 | 2021 | Air Force Active | AJJY203001 |  | 2020-09-16 | 2021-02-25 | Granite-Obayashi, a Joint Venture | N62742 | N6274221C1338 | N6274221C1338 | AJJY203001,N6274221C1338 | 41944700 | 42937637 | 2023-03-25 | 2023-07-05 | 992937 | 102 | 2023 | 07 | 05 | 20230705 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 43102001.9784 | 44072079.3013 | 970077.3229 | 102 | 758 | 13.46%
2021-12-31 | 2016 | Army Active | 86824 |  | 2019-04-08 | 2019-04-18 | Staatliches Hochbauamt Amberg | W912GB | W912GB-15-C-0007 | W912GB15C0007 | 86824,W912GB-15-C-0007 | 42195000 | 44125000 | 2023-06-03 | 2023-06-03 | 1930000 | 0 | 2023 | 06 | 03 | 20230603 | 2019 | 2023 | 1.0006 | 2021 | 0.97698 | 42220753.3712 | 44106320.364 | 1885566.9928 | 0 | 1507 | 0%
2022-01-06 | 2016 | Special Operations Command | 76513 |  | 2016-11-07 | 2017-08-02 | Caddell Construction CO. | W912PM | W912PM17C0004 | W912PM17C0004 | 76513,W912PM17C0004 | 42661500 | 45640993 | 2019-12-18 | 2021-04-22 | 2979493 | 491 | 2021 | 04 | 22 | 20210422 | 2017 | 2021 | 1.1914 | 2019 | 1.0006 | 50825230.9931 | 53806542.5021 | 2981311.509 | 491 | 868 | 56.57%
2022-01-12 | 2021 | Marine Corps Active | M006811130 |  | 2020-07-23 | 2021-02-18 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247321D1206 N6247321F4378 | N6247321D1206 | M006811130,N6247321D1206 N6247321F4378 | 42661879 | 48134000 | 2023-05-13 | 2023-05-22 | 5472121 | 9 | 2023 | 05 | 22 | 20230522 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 41679705.1268 | 46813638.4587 | 5133933.3319 | 9 | 814 | 1.106%
2022-01-06 | 2020 | Special Operations Command | PQWY083008 |  | 2019-12-13 | 2020-05-28 | Jabez-Absher Small Business Joint Venture | W912DW | W912DW20C0005 | W912DW20C0005 | PQWY083008,W912DW20C0005 | 42743158 | 44684710 | 2022-06-16 | 2022-11-22 | 1941552 | 159 | 2022 | 11 | 22 | 20221122 | 2020 | 2023 | 1.0006 | 2022 | 0.97698 | 42769245.9349 | 44666098.9743 | 1896853.0394 | 159 | 749 | 21.23%
2022-01-31 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-08-25 | Hensel Phelps Constuction co | N62742 | N62742-15-C-1308 | N6274215C1308 | DESC1551,N62742-15-C-1308 | 42823800 | 46800984 | 2017-09-23 | 2018-01-31 | 3977184 | 130 | 2018 | 01 | 31 | 20180131 | 2015 | 2018 | 1.0507 | 2017 | 0.97698 | 44995006.737 | 48880626.8794 | 3885620.1424 | 130 | 760 | 17.11%
2022-02-02 | 2014 | DoD Education Activity | EU00040 |  | 2016-10-21 | 2017-05-09 | LBB Kaiserslautern | W912GB | W912GB-12-C-0025/52029339 | W912GB12C0025 | EU00040,W912GB-12-C-0025/52029339 | 43000974 | 49730554 | 2020-01-12 | 2021-03-26 | 6729580 | 439 | 2021 | 03 | 26 | 20210326 | 2017 | 2021 | 1.0507 | 2019 | 1.0006 | 45181163.6246 | 51914850.9684 | 6733687.3438 | 439 | 978 | 44.89%
2022-01-12 | 2016 | Marine Corps Active | M62974602 |  | 2017-03-31 | 2017-07-27 | STRAUB CONSTRUCTION, INC. | N62473 | N6247316D1887 N6247317F4044 | N6247316D1887 | M62974602,N6247316D1887 N6247317F4044 | 43119000 | 40940000 | 2019-06-30 | 2020-06-22 | -2179000 | 358 | 2020 | 06 | 22 | 20200622 | 2017 | 2020 | 0.97698 | 2019 | 0.97698 | 42126302.1575 | 39997467.7133 | -2128834.4442 | 358 | 703 | 50.92%
2021-12-31 | 2017 | Army Active | 81428 |  | 2019-03-21 | 2019-06-03 | Daebo E & C | W912UM | W912UM19C0015 | W912UM19C0015 | 81428,W912UM19C0015 | 43171000 | 50468000 | 2021-07-14 | 2021-12-31 | 7297000 | 170 | 2021 | 12 | 31 | 20211231 | 2019 | 2022 | 0.95701 | 2021 | 0.9382 | 41315166.1734 | 48161197.4513 | 6846031.278 | 170 | 772 | 22.02%
2022-01-12 | 2018 | Navy Active | N41557250 |  | 2018-01-24 | 2018-09-24 | BLACK CONSTRUCTION CORP. | N62742 | N6274218C1300 AWD | N6274218C1300 | N41557250,N6274218C1300 AWD | 43203000 | 41238000 | 2021-01-21 | 2021-07-27 | -1965000 | 187 | 2021 | 07 | 27 | 20210727 | 2018 | 2021 | 1.1914 | 2020 | 1.1519 | 51470352.7676 | 49206932.9436 | -2263419.824 | 187 | 850 | 22%
2021-12-31 | 2018 | Army Active | 86991 |  | 2019-03-28 | 2020-01-27 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB | W912GB-17-C-0002 | W912GB17C0002 | 86991,W912GB-17-C-0002 | 43508000 | 43874000 | 2022-06-22 | 2023-03-19 | 366000 | 270 | 2023 | 03 | 19 | 20230319 | 2020 | 2023 | 1.0507 | 2022 | 1.0276 | 45713896.3173 | 46089994.6736 | 376098.3563 | 270 | 877 | 30.79%
2022-01-12 | 2019 | Navy Active | N324461074 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N40085 | N4008520C8500 AWD | N4008520C8500 | N324461074,N4008520C8500 AWD | 43523000 | 45838000 | 2021-01-27 | 2022-03-20 | 2315000 | 417 | 2022 | 03 | 20 | 20220320 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 44723849.0705 | 46985552.4841 | 2261703.4137 | 417 | 433 | 96.3%
2021-08-31 | 2019 | Army Active | 94612 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G | W9126G19D0021 | W9126G19D0021 | 94612,W9126G19D0021 | 43620000 | 66268000 | 2021-01-24 | 2021-09-02 | 22648000 | 221 | 2021 | 09 | 02 | 20210902 | 2020 | 2021 | 1.1519 | 2021 | 1.0507 | 50244464.4904 | 74040739.2857 | 23796274.7953 | 221 | 373 | 59.25%
2022-01-12 | 2020 | Navy Active | N68436447 |  | 2020-01-10 | 2020-06-08 | N4425520C1002 AWD | N44255 | N4425520C1002 AWD | N4425520C1002 | N68436447,N4425520C1002 AWD | 43771888 | 50919000 | 2023-08-02 | 2023-08-02 | 7147112 | 0 | 2023 | 08 | 02 | 20230802 | 2020 | 2023 | 1.2319 | 2022 | 1.2082 | 53924215.1955 | 62559544.2021 | 8635329.0066 | 0 | 1150 | 0%
2021-12-31 | 2020 | Air Force Active | TDKA143002 |  | 2020-10-06 | 2021-04-27 | JE Dunn | W9128F | W9128F21C0019 | W9128F21C0019 | TDKA143002,W9128F21C0019 | 43789430 | 43789430 | 2023-09-11 | 2023-09-11 | 0 | 0 | 2023 | 09 | 11 | 20230911 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 44997630.1772 | 44997630.1772 | 0 | 0 | 867 | 0%
2022-01-12 | 2020 | Marine Corps Active | M670011533F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N40085 | N4008520D0034 N4008520F6501 | N4008520D0034 | M670011533F,N4008520D0034 N4008520F6501 | 43802000 | 45033000 | 2024-09-30 | 2025-09-27 | 1231000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 1.0006 | 2023 | 0.97698 | 43828734.1904 | 45031393.7594 | 1202659.569 | 362 | 1476 | 24.53%
2021-12-31 | 2019 | Army Active | 52203 |  | 2020-02-27 | 2020-09-29 | Kiewit Infrastructure West Co. | W9128A | W9128A20C0006 | W9128A20C0006 | 52203,W9128A20C0006 | 44925000 | 45597000 | 2022-08-03 | 2022-08-03 | 672000 | 0 | 2022 | 08 | 03 | 20220803 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 44952419.6042 | 45595531.6857 | 643112.0815 | 0 | 673 | 0%
2021-12-31 | 2019 | Army Active | 33584 |  | 2020-10-13 | 2021-03-26 | SGS, LLC | W9126G | W9126G21C0005 | W9126G21C0005 | 33584,W9126G21C0005 | 44927000 | 44928000 | 2023-12-11 | 2023-12-11 | 1000 | 0 | 2023 | 12 | 11 | 20231211 | 2021 | 2024 | 1.1227 | 2023 | 1.0507 | 50438273.9804 | 50439324.6814 | 1050.7009 | 0 | 990 | 0%
2022-01-06 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction, LLC | W912DW | W912DW-15-C-0006 | W912DW15C0006 | 69445,W912DW-15-C-0006 | 45104149 | 49614197 | 2017-05-25 | 2018-05-18 | 4510048 | 358 | 2018 | 05 | 18 | 20180518 | 2015 | 2018 | 1.0276 | 2017 | 0.95701 | 46348623.7697 | 50664793.9434 | 4316170.1737 | 358 | 749 | 47.8%
2022-01-06 | 2021 | Special Operations Command | 86022 |  | 2021-03-10 | 2021-08-10 | Harper | W912PL | W912PL21C0017 | W912PL21C0017 | 86022,W912PL21C0017 | 45167317 | 45167317 | 2023-11-07 | 2023-11-07 | 0 | 0 | 2023 | 11 | 07 | 20231107 | 2021 | 2024 | 1.0006 | 2023 | 0.9382 | 45194884.5004 | 45194884.5004 | 0 | 0 | 819 | 0%
2021-11-30 | 2021 | Missile Defense Agency | 680 |  | 2020-09-28 | 2021-03-17 | Davis Constructors & Engineers, Inc | W911KB | W911KB21C0012 | W911KB21C0012 | 680,W911KB21C0012 | 45487063 | 45647063 | 2023-01-31 | 2023-07-23 | 160000 | 173 | 2023 | 07 | 23 | 20230723 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 46742102.8024 | 46898419.2371 | 156316.4346 | 173 | 685 | 25.26%
2021-12-31 | 2021 | Missile Defense Agency | 680 |  | 2020-09-28 | 2021-03-17 | Davis Constructors & Engineers, Inc | W911KB | W911KB-21-C-0012 | W911KB21C0012 | 680,W911KB-21-C-0012 | 45487063 | 45647063 | 2023-01-31 | 2023-07-23 | 160000 | 173 | 2023 | 07 | 23 | 20230723 | 2021 | 2023 | 1.0507 | 2022 | 1.0276 | 47793299.6635 | 47957714.2455 | 164414.582 | 173 | 685 | 25.26%
2022-01-13 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-13 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G | W9126G-08-D-0056-CV01 | W9126G08D0056CV01 | 71325,W9126G-08-D-0056-CV01 | 45536000 | 47478000 | 2016-10-23 | 2018-06-01 | 1942000 | 586 | 2018 | 06 | 01 | 20180601 | 2013 | 2018 | 1.2082 | 2016 | 1.1914 | 55017794.8303 | 57331417.1499 | 2313622.3196 | 586 | 1136 | 51.58%
2022-01-12 | 2016 | Navy Active | N32443614 |  | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N40085 | N4008518C1116 AWD | N4008518C1116 | N32443614,N4008518C1116 AWD | 45614000 | 43914000 | 2021-04-15 | 2021-06-30 | -1700000 | 76 | 2021 | 06 | 30 | 20210630 | 2018 | 2021 | 1.0276 | 2020 | 0.95701 | 46872542.1386 | 45245621.6945 | -1626920.4442 | 76 | 1217 | 6.245%
2021-12-31 | 2018 | Air Force Active | FTFA053017 |  | 2019-05-20 | 2019-09-30 | Dormitories Replace Dorm 19 | W91278 | W9127819C0034 | W9127819C0034 | FTFA053017,W9127819C0034 | 45719464 | 45719464 | 2021-11-05 | 2022-05-04 | 0 | 180 | 2022 | 05 | 04 | 20220504 | 2019 | 2022 | 1.0006 | 2021 | 0.9382 | 45747368.4988 | 45747368.4988 | 0 | 180 | 767 | 23.47%
2021-12-31 | 2019 | Army Active | 35782 |  | 2019-08-09 | 2019-09-26 | P & R JV | W912QR | W912QR19C0039 | W912QR19C0039 | 35782,W912QR19C0039 | 45794000 | 46183000 | 2022-02-05 | 2022-10-14 | 389000 | 251 | 2022 | 10 | 14 | 20221014 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 47057508.5434 | 47437552.8751 | 380044.3317 | 251 | 863 | 29.08%
2022-01-12 | 2017 | Navy Active | N00620256 |  | 2018-04-05 | 2019-01-30 | RQ CONSTRUCTION, LLC | N44255 | N4425519C0003 AWD | N4425519C0003 | N00620256,N4425519C0003 AWD | 45981000 | 47543000 | 2021-07-19 | 2021-10-29 | 1562000 | 102 | 2021 | 10 | 29 | 20211029 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 47249668.086 | 48775707.2792 | 1526039.1932 | 102 | 901 | 11.32%
2022-01-12 | 2019 | Marine Corps Active | M006811901 |  | 2018-11-27 | 2019-05-02 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318D5853 N6247319F4561 | N6247318D5853 | M006811901,N6247318D5853 N6247319F4561 | 46146000 | 46788000 | 2022-06-09 | 2022-12-09 | 642000 | 183 | 2022 | 12 | 09 | 20221209 | 2019 | 2023 | 1.2826 | 2021 | 1.2581 | 59185195.4656 | 59992870.4586 | 807674.993 | 183 | 1134 | 16.14%
2021-12-31 | 2020 | Army Active | 77303 |  | 2020-02-28 | 2020-06-19 | TEPA EC | W9128F | W9128F20C0029 | W9128F20C0029 | 77303,W9128F20C0029 | 46209000 | 46745000 | 2022-06-12 | 2022-07-28 | 536000 | 46 | 2022 | 07 | 28 | 20220728 | 2020 | 2022 | 1.0276 | 2021 | 1.0006 | 47483958.8654 | 48020286.0085 | 536327.1432 | 46 | 723 | 6.362%
2021-12-31 | 2017 | Air Force Active | MUHJ133000 |  | 2020-11-03 | 2021-05-11 | Source Selection Sensitive | W91236 | W9123621C2005 | W9123621C2005 | MUHJ133000,W9123621C2005 | 46375000 | 46375000 | 2023-08-03 | 2023-08-03 | 0 | 0 | 2023 | 08 | 03 | 20230803 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 47654538.9942 | 47654538.9942 | 0 | 0 | 814 | 0%
2021-12-31 | 2019 | Air Force Reserve | YTPM099001B |  | 2019-07-26 | 2021-06-17 | Ciambro AZ JV | W912QR | W912QR21C0025 | W912QR21C0025 | YTPM099001B,W912QR21C0025 | 46421000 | 46421000 | 2023-09-29 | 2023-09-29 | 0 | 0 | 2023 | 09 | 29 | 20230929 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 49906181.7953 | 49906181.7953 | 0 | 0 | 834 | 0%
2021-12-31 | 2019 | Air Force Active | VLSB193001 |  | 2020-08-11 | 2020-12-30 | B.L. Harbert International, L.L.C. | N69450 | N6945021C0004 | N6945021C0004 | VLSB193001,N6945021C0004 | 46487791 | 46487791 | 2022-12-30 | 2022-12-30 | 0 | 0 | 2022 | 12 | 30 | 20221230 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 47770442.0261 | 47770442.0261 | 0 | 0 | 730 | 0%
2022-01-06 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV | W912HV-15-C-0004 | W912HV15C0004 | 78024,W912HV-15-C-0004 | 46555863 | 63212524 | 2017-12-12 | 2018-06-18 | 16656661 | 188 | 2018 | 06 | 18 | 20180618 | 2015 | 2018 | 1.1227 | 2017 | 1.0276 | 52266952.4649 | 69383189.6861 | 17116237.2213 | 188 | 917 | 20.5%
2022-01-31 | 2016 | DLA Defense Supply Center Philadelphia | DSCP1501 |  | 2016-03-11 | 2016-09-16 | Daniel J. keating Company | N40085 | N40085-16-C-3037 | N4008516C3037 | DSCP1501,N40085-16-C-3037 | 46845550 | 57854412 | 2019-03-30 | 2020-01-02 | 11008862 | 278 | 2020 | 01 | 02 | 20200102 | 2016 | 2020 | 1.0276 | 2018 | 1.0006 | 48138072.0038 | 59153653.1722 | 11015581.1684 | 278 | 925 | 30.05%
2022-02-02 | 2016 | DoD Education Activity | EU00051 | 51 | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB | W912GB-12-C-0030/54892650 | W912GB12C0030 | EU00051,W912GB-12-C-0030/54892650 | 46915286 | 53161479 | 2021-01-23 | 2022-05-30 | 6246193 | 492 | 2022 | 05 | 30 | 20220530 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 48209732.0994 | 54459737.4119 | 6250005.3125 | 492 | 1283 | 38.35%
2022-01-12 | 2017 | Navy Active | N47608265 |  | 2018-04-10 | 2019-01-30 | B.L. HARBERT INTERNATIONAL, L.L.C. | N40080 | N4008019C2015 AWD | N4008019C2015 | N47608265,N4008019C2015 AWD | 46919000 | 51371000 | 2020-09-28 | 2021-08-27 | 4452000 | 333 | 2021 | 08 | 27 | 20210827 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 48213548.5729 | 52563053.3667 | 4349504.7938 | 333 | 607 | 54.86%
2022-01-12 | 2020 | Navy Active | N32443653 |  | 2020-04-16 | 2020-09-04 | MEB GENERAL CONTRACTORS, INC. | N40085 | N4008520C0063 AWD | N4008520C0063 | N32443653,N4008520C0063 AWD | 46986935 | 49652000 | 2023-06-17 | 2023-07-13 | 2665065 | 26 | 2023 | 07 | 13 | 20230713 | 2020 | 2023 | 1.0751 | 2022 | 1.0276 | 50514605.892 | 53253203.0664 | 2738597.1744 | 26 | 1016 | 2.559%
2021-12-31 | 2017 | Air Force Active | FJXT133000 |  | 2020-03-01 | 2020-03-31 | Aircraft Maintenance Hangar | W912BU | W912BU20C0015 | W912BU20C0015 | FJXT133000,W912BU20C0015 | 47042000 | 47042000 | 2021-12-31 | 2022-01-23 | 0 | 23 | 2022 | 01 | 23 | 20220123 | 2020 | 2022 | 1.0751 | 2021 | 1.0276 | 50573805.0454 | 50573805.0454 | 0 | 23 | 640 | 3.594%
2021-12-31 | 2020 | Army Active | 73391 |  | 2020-06-12 | 2020-09-29 | Purcell Construction | W91236 | W9123620C2027 | W9123620C2027 | 73391,W9123620C2027 | 47269000 | 46831000 | 2022-11-03 | 2022-11-03 | -438000 | 0 | 2022 | 11 | 03 | 20221103 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 49665582.5371 | 49227315.2074 | -438267.3297 | 0 | 765 | 0%
2022-01-12 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | CONTRACK WATTS, INC | N62742 | N6274217C1325 AWD | N6274217C1325 | N61755535,N6274217C1325 AWD | 47314000 | 44985000 | 2020-01-03 | 2020-01-03 | -2329000 | 0 | 2020 | 01 | 03 | 20200103 | 2017 | 2020 | 0.97698 | 2019 | 0.95701 | 46224723.6782 | 43995842.6697 | -2228881.0085 | 0 | 865 | 0%
2022-01-12 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274215C1301 AWD | N6274215C1301 | M00318907,N6274215C1301 AWD | 47645000 | 40860000 | 2020-09-18 | 2021-12-20 | -6785000 | 458 | 2021 | 12 | 20 | 20211220 | 2015 | 2022 | 1.0507 | 2019 | 1.0006 | 50060646.0889 | 43271504.92 | -6789141.1689 | 458 | 1984 | 23.08%
2022-01-12 | 2019 | Navy Active | N00245440 |  | 2019-05-01 | 2019-06-14 | MANSON CONSTRUCTION CO | N62473 | N6247319C1208 AWD | N6247319C1208 | N00245440,N6247319C1208 AWD | 47724000 | 102132000 | 2021-10-27 | 2021-10-31 | 54408000 | 4 | 2021 | 10 | 31 | 20211031 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 47753127.9508 | 100908531.5499 | 53155403.599 | 4 | 866 | 0.4619%
2022-01-12 | 2016 | Marine Corps Active | M670011280 |  | 2016-12-16 | 2017-05-30 | CADDELL CONSTRUCTION CO. (DE), LLC | N40085 | N4008517C8325 AWD | N4008517C8325 | M670011280,N4008517C8325 AWD | 47882000 | 51796000 | 2019-06-24 | 2022-08-10 | 3914000 | 1143 | 2022 | 08 | 10 | 20220810 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 47911224.3848 | 51735115.1672 | 3823890.7824 | 1143 | 755 | 151.4%
2022-02-02 | 2017 | DoD Education Activity | AM00047 |  | 2018-01-03 | 2019-02-27 | Dobco, Inc. | W912BU | W912BU-19-C-0017/53356011 | W912BU19C0017 | AM00047,W912BU-19-C-0017/53356011 | 47962590 | 49780896 | 2021-12-24 | 2022-02-25 | 1818306 | 63 | 2022 | 02 | 25 | 20220225 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 49285932.4079 | 51105348.196 | 1819415.7881 | 63 | 1031 | 6.111%
2022-02-02 | 2017 | DoD Education Activity | EU00039 |  | 2019-03-19 | 2019-09-16 | LBB Kaiserslautern | W912GB | W912GB-15-C-0013/47316927 | W912GB15C0013 | EU00039,W912GB-15-C-0013/47316927 | 48012330 | 48330200 | 2023-05-02 | 2025-05-01 | 317870 | 730 | 2025 | 05 | 01 | 20250501 | 2019 | 2025 | 1.0006 | 2022 | 0.95701 | 48041633.9307 | 48345839.3434 | 304205.4127 | 730 | 1324 | 55.14%
2022-01-12 | 2020 | Marine Corps Active | M670011527F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011527F,N4008520C0044 AWD | 48103000 | 48584000 | 2025-05-27 | 2026-01-22 | 481000 | 240 | 2026 | 01 | 22 | 20260122 | 2020 | 2026 | 1.1227 | 2023 | 1.0507 | 54003879.4774 | 54509266.6275 | 505387.1501 | 240 | 1768 | 13.57%
2022-02-02 | 2016 | DoD Education Activity | AM00033 |  | 2016-07-25 | 2017-03-01 | DOBCO, Inc. | W912DS | W912DS-17-C-0005/44966911 | W912DS17C0005 | AM00033,W912DS-17-C-0005/44966911 | 48535000 | 50878598 | 2020-03-05 | 2020-01-06 | 2343598 | -59 | 2020 | 01 | 06 | 20200106 | 2017 | 2020 | 1.0006 | 2019 | 0.95701 | 48564622.938 | 50807474.4081 | 2242851.4701 | -59 | 1100 | -5.364%
2022-01-12 | 2020 | Marine Corps Active | M67001728F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M67001728F,N4008520C0044 AWD | 48575000 | 49432000 | 2024-10-12 | 2025-02-18 | 857000 | 129 | 2025 | 02 | 18 | 20250218 | 2020 | 2025 | 1.2826 | 2023 | 1.2581 | 62300543.2701 | 63378701.3215 | 1078158.0514 | 129 | 1541 | 8.371%
2021-12-31 | 2017 | Air Force Active | EVKP174535 |  | 2020-06-12 | 2021-06-25 | Nishimatsu Construction Co. | W912HV | W912HV21C0001 | W912HV21C0001 | EVKP174535,W912HV21C0001 | 49607160 | 49607160 | 2023-09-01 | 2023-09-01 | 0 | 0 | 2023 | 09 | 01 | 20230901 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 50975877.9646 | 50975877.9646 | 0 | 0 | 798 | 0%
2021-12-31 | 2016 | Army Reserve | 85813 |  | 2017-06-28 | 2017-09-28 | Hensel Phelps Construction Co. | W912QR | W912QR-17-C-0043 | W912QR17C0043 | 85813,W912QR-17-C-0043 | 49643000 | 52023000 | 2019-10-04 | 2022-06-01 | 2380000 | 971 | 2022 | 06 | 01 | 20220601 | 2017 | 2022 | 1.1914 | 2020 | 1.1227 | 59142715.1457 | 61814673.9249 | 2671958.7792 | 971 | 736 | 131.9%
2021-12-31 | 2020 | Air Force Active | AJJY073105P3 |  | 2020-01-17 | 2020-09-16 | Core Tech-Hawaiian Dredging | N62742 | N6274220C1324 | N6274220C1324 | AJJY073105P3,N6274220C1324 | 49677730 | 49677730 | 2023-07-16 | 2023-07-16 | 0 | 0 | 2023 | 07 | 16 | 20230716 | 2020 | 2023 | 1.0276 | 2022 | 0.97698 | 51048395.0712 | 51048395.0712 | 0 | 0 | 1033 | 0%
2022-01-06 | 2018 | Special Operations Command | 80771 |  | 2017-11-16 | 2018-09-27 | MEB General Contractors, Inc | W91236 | W9123618C0025 | W9123618C0025 | 80771,W9123618C0025 | 50257000 | 51308106 | 2020-12-26 | 2021-12-31 | 1051106 | 370 | 2021 | 12 | 31 | 20211231 | 2018 | 2022 | 1.0993 | 2020 | 1.0507 | 55245269.1506 | 56349667.2085 | 1104398.0579 | 370 | 821 | 45.07%
2022-01-12 | 2018 | Navy Active | N00216450 |  | 2018-05-25 | 2018-09-05 | URS GROUP, INC. | N62470 | N6247013D6022 N6247018F4121 | N6247013D6022 | N00216450,N6247013D6022 N6247018F4121 | 50430000 | 49912000 | 2021-09-04 | 2022-07-08 | -518000 | 307 | 2022 | 07 | 08 | 20220708 | 2018 | 2022 | 1.0006 | 2020 | 0.9382 | 50460779.5357 | 49974792.9382 | -485986.5975 | 307 | 1095 | 28.04%
2022-01-12 | 2020 | Navy Active | N62813033 |  | 2020-04-22 | 2020-08-10 | HDR ENGINEERING, INC.DBA HONOLULU HDR HAWAII PACIFIC | N62478 | N6247820C4016 AWD | N6247820C4016 | N62813033,N6247820C4016 AWD | 50430000 | 35936000 | 2022-09-09 | 2022-09-09 | -14494000 | 0 | 2022 | 09 | 09 | 20220909 | 2020 | 2022 | 1.0993 | 2021 | 1.0507 | 55435440.3022 | 40206580.9379 | -15228859.3643 | 0 | 760 | 0%
2022-01-12 | 2020 | Navy Active | N61755491 |  | 2020-03-02 | 2020-08-07 | BLACK CONSTRUCTION-TUTOR PERINI JV | N62742 | N6274219D1328 N6274220F9924 | N6274219D1328 | N61755491,N6274219D1328 N6274220F9924 | 50514009 | 54163000 | 2022-12-20 | 2022-12-20 | 3648991 | 0 | 2022 | 12 | 20 | 20221220 | 2020 | 2023 | 1.1227 | 2022 | 1.0507 | 56710651.1851 | 60544649.4437 | 3833998.2586 | 0 | 865 | 0%
2022-01-12 | 2014 | Marine Corps Active | M00318863 |  | 2015-07-14 | 2016-09-19 | CONTRACK WATTS, INC | N62742 | N6274216C1325 AWD | N6274216C1325 | M00318863,N6274216C1325 AWD | 50583000 | 50006000 | 2019-04-17 | 2020-03-07 | -577000 | 325 | 2020 | 03 | 07 | 20200307 | 2016 | 2020 | 1.2082 | 2018 | 1.1914 | 61115713.1918 | 60428298.1154 | -687415.0764 | 325 | 940 | 34.57%
2022-01-12 | 2020 | Navy Active | N476091918 |  | 2020-11-23 | 2021-03-03 | SOLPAC CONSTRUCTION INC | N62473 | N6247318D5855 N6247321F4428 | N6247318D5855 | N476091918,N6247318D5855 N6247321F4428 | 50924000 | 58919000 | 2023-05-03 | 2023-05-03 | 7995000 | 0 | 2023 | 05 | 03 | 20230503 | 2021 | 2023 | 1.1743 | 2022 | 1.0507 | 59800995.184 | 68201349.1662 | 8400353.9822 | 0 | 791 | 0%
2022-02-02 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB | W912GB-12-C-0022 | W912GB12C0022 | EU00072,W912GB-12-C-0022 | 50967096 | 52793178 | 2019-04-19 | 2018-07-26 | 1826082 | -267 | 2018 | 07 | 26 | 20180726 | 2016 | 2018 | 1.0276 | 2017 | 1.0006 | 52373336.1456 | 54200532.6797 | 1827196.5341 | -267 | 1093 | -24.43%
2022-01-12 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | NAN INC. DBAOCEAN HOUSE BUILDERS | N62742 | N6274215C1305 AWD | N6274215C1305 | M00318861,N6274215C1305 AWD | 51071000 | 52377000 | 2018-08-11 | 2021-02-03 | 1306000 | 907 | 2021 | 02 | 03 | 20210203 | 2015 | 2021 | 1.0507 | 2018 | 1.0006 | 53660347.4952 | 54967144.6016 | 1306797.1064 | 907 | 1075 | 84.37%
2022-01-12 | 2020 | Marine Corps Active | M670011338F |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N40085 | N4008520C0145 AWD | N4008520C0145 | M670011338F,N4008520C0145 AWD | 51246000 | 52469000 | 2025-05-27 | 2026-01-22 | 1223000 | 240 | 2026 | 01 | 22 | 20260122 | 2020 | 2026 | 1.0993 | 2023 | 1.0507 | 56332432.5545 | 57617439.7991 | 1285007.2446 | 240 | 1748 | 13.73%
2021-12-31 | 2017 | Air Force Active | FXSB982839 |  | 2016-10-20 | 2020-04-01 | ADD/ALTER AWACS ALERT HANGAR | W911KB | W911KB20C008 | W911KB20C008 | FXSB982839,W911KB20C008 | 51446741 | 51446741 | 2022-03-17 | 2022-03-17 | 0 | 0 | 2022 | 03 | 17 | 20220317 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 52866215.0966 | 52866215.0966 | 0 | 0 | 715 | 0%
2022-01-06 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278 | W91278-11-D-0073 | W9127811D0073 | 76376,W91278-11-D-0073 | 51696668 | 61769562 | 2017-05-14 | 2018-01-19 | 10072894 | 250 | 2018 | 01 | 19 | 20180119 | 2015 | 2018 | 1.0993 | 2017 | 1.0276 | 56827831.7021 | 67178648.3038 | 10350816.6018 | 250 | 894 | 27.96%
2022-01-12 | 2021 | Navy Active | N62863313 |  | 2021-07-22 | 2021-12-16 | ACCIONA CMS JV, LLC | N62470 | N6247021D0011 N6247022F9000 | N6247021D0011 | N62863313,N6247021D0011 N6247022F9000 | 51758888.76 | 58177000 | 2024-09-09 | 2024-09-09 | 6418111.24 | 0 | 2024 | 09 | 09 | 20240909 | 2022 | 2024 | 1.0276 | 2023 | 0.97698 | 53186975.3684 | 59457327.0318 | 6270351.6635 | 0 | 998 | 0%
2022-01-13 | 2015 | Defense Health Agency | 81430 |  | 2016-06-20 | 2018-01-18 | JE Dunn Construction Company | W9127S | W9127S-13-D-6001 TO W91236-18-F-0014 | W9127S13D6001 | 81430,W9127S-13-D-6001 TO W91236-18-F-0014 | 52181000 | 56349000 | 2021-03-18 | 2022-08-12 | 4168000 | 512 | 2022 | 08 | 12 | 20220812 | 2018 | 2022 | 1.0751 | 2020 | 1.0276 | 56098629.3328 | 60381629.1932 | 4282999.8604 | 512 | 1155 | 44.33%
2022-01-12 | 2020 | Navy Active | N69212169 |  | 2020-11-09 | 2021-03-25 | SAUER, INC. | N40085 | N4008521C0028 AWD | N4008521C0028 | N69212169,N4008521C0028 AWD | 52191740 | 58176000 | 2023-06-25 | 2023-10-21 | 5984260 | 118 | 2023 | 10 | 21 | 20231021 | 2021 | 2024 | 1.0006 | 2023 | 0.95701 | 52223594.7992 | 57950603.5858 | 5727008.7866 | 118 | 822 | 14.36%
2022-01-12 | 2018 | Navy Active | N00213211 |  | 2019-05-03 | 2021-05-13 | KORTE CONSTRUCTION COMPANY | N69450 | N6945021C0019 AWD | N6945021C0019 | N00213211,N6945021C0019 AWD | 52266000 | 51919000 | 2023-12-29 | 2023-12-29 | -347000 | 0 | 2023 | 12 | 29 | 20231229 | 2021 | 2024 | 1.0006 | 2023 | 0.95701 | 52297900.1232 | 51965816.9502 | -332083.173 | 0 | 960 | 0%
2022-01-12 | 2020 | Navy Active | N476091922 |  | 2021-02-03 | 2021-06-10 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247321D1206 N6247321F4825 | N6247321D1206 | N476091922,N6247321D1206 N6247321F4825 | 52301995 | 73261000 | 2024-01-23 | 2024-01-23 | 20959005 | 0 | 2024 | 01 | 23 | 20240123 | 2021 | 2024 | 1.0751 | 2023 | 1.0276 | 56228708.3588 | 77765996.1443 | 21537287.7855 | 0 | 957 | 0%
2021-12-31 | 2018 | Air Force Active | PTFL163019 |  | 2018-10-29 | 2019-07-11 | Walsh Federal LLC | W912DS | W912DS19C0011 | W912DS19C0011 | PTFL163019,W912DS19C0011 | 52324000 | 52696600 | 2021-07-23 | 2021-09-13 | 372600 | 52 | 2021 | 09 | 13 | 20210913 | 2019 | 2021 | 0.97698 | 2020 | 0.9382 | 51119382.0379 | 51468954.6368 | 349572.5989 | 52 | 743 | 6.999%
2022-02-02 | 2015 | DoD Education Activity | PA00022 |  | 2018-09-21 | 2019-07-29 | Nippo Corporation | W912HV | W912HV19C0007/36943919 | W912HV19C0007 | PA00022,W912HV19C0007/36943919 | 52447552 | 50699295 | 2022-08-05 | 2022-08-05 | -1748257 | 0 | 2022 | 08 | 05 | 20220805 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 53894639.6104 | 52186631.4787 | -1708008.1317 | 0 | 1103 | 0%
2021-12-31 | 2017 | Air Force Reserve | VKAG159021 |  | 2017-05-19 | 2017-09-27 | Walbridge Aldinger LLC | W912QR | W912QR17C0031 | W912QR17C0031 | VKAG159021,W912QR17C0031 | 52493799 | 58903514 | 2020-09-09 | 2021-08-31 | 6409715 | 356 | 2021 | 08 | 31 | 20210831 | 2017 | 2021 | 1.0276 | 2019 | 1.0006 | 53942162.6177 | 60355789.7345 | 6413627.1168 | 356 | 1078 | 33.02%
2022-01-31 | 2014 | DoD Education Activity | AM00021 |  | 2016-11-07 | 2017-11-20 | John C. Grimberg CO., Inc. | N40080 | N4008018C0006 | N4008018C0006 | AM00021,N4008018C0006 | 52553000 | 52182000 | 2020-01-09 | 2020-10-13 | -371000 | 278 | 2020 | 10 | 13 | 20201013 | 2018 | 2021 | 1.0276 | 2020 | 1.0006 | 54002997.0406 | 53631770.6038 | -371226.4368 | 278 | 780 | 35.64%
2022-01-12 | 2018 | Navy Active | N63042282 |  | 2018-01-23 | 2018-09-19 | R A BURCH CONSTRUCTION CO INC | N62473 | N6247318C2201 AWD | N6247318C2201 | N63042282,N6247318C2201 AWD | 52594000 | 49645000 | 2021-02-24 | 2022-02-25 | -2949000 | 366 | 2022 | 02 | 25 | 20220225 | 2018 | 2022 | 1.2581 | 2020 | 1.1914 | 66166446.3919 | 62653123.9302 | -3513322.4617 | 366 | 889 | 41.17%
2021-12-31 | 2018 | Air Force Active | LXEZ184546 |  | 2019-11-27 | 2020-05-18 | Kyowa Exeo Corporation | W912HV | W912HV20B00010004 | W912HV20B00010004 | LXEZ184546,W912HV20B00010004 | 52649852 | 52649852 | 2022-12-30 | 2022-12-30 | 0 | 0 | 2022 | 12 | 30 | 20221230 | 2020 | 2023 | 1.0006 | 2022 | 0.9382 | 52681986.4041 | 52681986.4041 | 0 | 0 | 956 | 0%
2022-01-12 | 2019 | Marine Corps Active | M00146235 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N40085 | N4008520C8501 AWD | N4008520C8501 | M00146235,N4008520C8501 AWD | 53073000 | 60955000 | 2022-07-14 | 2022-12-30 | 7882000 | 169 | 2022 | 12 | 30 | 20221230 | 2020 | 2023 | 1.1519 | 2022 | 1.0993 | 61133068.8652 | 69797398.4401 | 8664329.5749 | 169 | 934 | 18.09%
2021-12-31 | 2008 | Army Active | 66253 |  | 2008-02-15 | 2008-03-31 | Staatliches Hochbauamt Nurnberg II | W912GB | W912GB-06-C-0038 | W912GB06C0038 |  | 53186000 | 55561000 | 2010-10-09 | 2022-07-29 | 2375000 | 4311 | 2022 | 07 | 29 | 20220729 | 2008 | 2022 | 1.1227 | 2015 | 1.0993 | 59710420.013 | 62321151.1396 | 2610731.1267 | 4311 | 922 | 467.6%
2022-01-12 | 2019 | Navy Active | N002461018 |  | 2019-04-03 | 2019-07-25 | BALDI BROS INC201 CALIFORNIA AVENUE | N62473 | N6247319C1211 AWD | N6247319C1211 | N002461018,N6247319C1211 AWD | 53283000 | 61863000 | 2021-05-28 | 2022-07-25 | 8580000 | 423 | 2022 | 07 | 25 | 20220725 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 53315520.8408 | 61697989.6483 | 8382468.8075 | 423 | 673 | 62.85%
2022-01-12 | 2020 | Navy Active | N476091916 |  | 2020-05-15 | 2020-09-03 | SOLPAC CONSTRUCTION INC | N62473 | N6247318D5855 N6247320F5296 | N6247318D5855 | N476091916,N6247318D5855 N6247320F5296 | 53426000 | 61905000 | 2022-09-19 | 2022-09-19 | 8479000 | 0 | 2022 | 09 | 19 | 20220919 | 2020 | 2022 | 1.1743 | 2021 | 1.1227 | 62739140.0656 | 72258273.8845 | 9519133.8189 | 0 | 746 | 0%
2022-01-12 | 2020 | Marine Corps Active | M006811090 |  | 2020-04-16 | 2020-09-24 | DPR-RQ CONSTRUCTION, LLC | N62473 | N6247320C0055 AWD | N6247320C0055 | M006811090,N6247320C0055 AWD | 53546419 | 80806000 | 2024-01-07 | 2024-01-07 | 27259581 | 0 | 2024 | 01 | 07 | 20240107 | 2020 | 2024 | 1.0276 | 2022 | 0.97698 | 55023825.6007 | 81655828.7987 | 26632003.198 | 0 | 1200 | 0%
2022-01-12 | 2018 | Navy Active | N41557260 |  | 2018-01-24 | 2018-09-21 | BLACK CONSTRUCTION CORP. | N62742 | N6274218C1300 AWD | N6274218C1300 | N41557260,N6274218C1300 AWD | 53554000 | 50302000 | 2020-12-28 | 2021-07-27 | -3252000 | 211 | 2021 | 07 | 27 | 20210727 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 53586686.2434 | 50474483.1349 | -3112203.1085 | 211 | 829 | 25.45%
2022-01-12 | 2020 | Marine Corps Active | M006812000 |  | 2020-05-28 | 2020-12-17 | WHITING-TURNER CONTRACTING CO | N62473 | N6247318D5858 N6247321F4212 | N6247318D5858 | M006812000,N6247318D5858 N6247321F4212 | 53611262.49 | 62002000 | 2025-02-14 | 2025-02-14 | 8390737.51 | 0 | 2025 | 02 | 14 | 20250214 | 2021 | 2025 | 1.0006 | 2023 | 0.95701 | 53643983.6831 | 61674020.3869 | 8030036.7039 | 0 | 1520 | 0%
2022-01-12 | 2020 | Navy Active | N47609810 |  | 2020-04-15 | 2020-06-26 | BALDI BROS INC201 CALIFORNIA AVENUE | N62473 | N6247319D2438 N6247320F4817 | N6247319D2438 | N47609810,N6247319D2438 N6247320F4817 | 53866451 | 57165000 | 2022-04-10 | 2022-04-10 | 3298549 | 0 | 2022 | 04 | 10 | 20220410 | 2020 | 2022 | 1.0006 | 2021 | 0.97698 | 53899327.9453 | 57121936.815 | 3222608.8698 | 0 | 653 | 0%
2022-01-12 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274215C1301 AWD | N6274215C1301 | M00318908,N6274215C1301 AWD | 53999000 | 50582000 | 2020-09-18 | 2021-12-20 | -3417000 | 458 | 2021 | 12 | 20 | 20211220 | 2015 | 2022 | 0.97698 | 2019 | 0.95701 | 52755819.713 | 49485709.6202 | -3270110.0928 | 458 | 1984 | 23.08%
2021-12-30 | 2015 | DLA Defense Energy Support Center | DESC1508 |  | 2016-03-31 | 2017-03-30 | CB&I Federal Services, LLC | N62473 | N62473-15-R-0001-0008 | N6247315R00010008 | DESC1508,N62473-15-R-0001-0008 | 54095271 | 58620122 | 2020-03-30 | 2020-08-25 | 4524851 | 148 | 2020 | 08 | 25 | 20200825 | 2017 | 2020 | 1.0993 | 2019 | 1.0276 | 59464508.5495 | 64114205.3349 | 4649696.7854 | 148 | 1096 | 13.5%
2022-05-02 | 2021 | DLA Defense Energy Support Center | DESC2002 |  | 2021-01-04 | 2021-05-21 | Garco | N44255 | N4425521R20000014 | N4425521R20000014 | DESC2002,N4425521R20000014 | 54249000 | 54387326 | 2024-01-20 | 2024-01-21 | 138326 | 1 | 2024 | 01 | 21 | 20240121 | 2021 | 2024 | 1.0276 | 2023 | 0.97698 | 55745791.6096 | 55880933.0292 | 135141.4196 | 1 | 974 | 0.1027%
2022-01-12 | 2020 | Marine Corps Active | M67001883F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M67001883F,N4008520C0044 AWD | 54587000 | 58083000 | 2024-09-30 | 2025-09-27 | 3496000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 1.1227 | 2023 | 1.0507 | 61283283.1431 | 64956533.6148 | 3673250.4718 | 362 | 1529 | 23.68%
2022-01-13 | 2016 | Defense Health Agency | 86953 |  | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR | W912QR-17-C-0009 | W912QR17C0009 | 86953,W912QR-17-C-0009 | 54817000 | 56042000 | 2021-06-23 | 2022-05-31 | 1225000 | 342 | 2022 | 05 | 31 | 20220531 | 2017 | 2022 | 1.1743 | 2020 | 1.1519 | 64372617.0961 | 65783654.8999 | 1411037.8038 | 342 | 1553 | 22.02%
2021-12-31 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan Construction, Inc. | W9128A | W9128A-16-C-0006 | W9128A16C0006 | 59779,W9128A-16-C-0006 | 54844000 | 57844000 | 2020-06-10 | 2022-02-20 | 3000000 | 620 | 2022 | 02 | 20 | 20220220 | 2016 | 2022 | 1.0507 | 2019 | 1.0276 | 57624642.1262 | 60707415.5382 | 3082773.412 | 620 | 1413 | 43.88%
2021-12-31 | 2019 | Army Active | 81429 |  | 2019-07-22 | 2019-10-30 | Daebo Engineering & Construction Co., Ltd. | W912UM | W912UM20C0001 | W912UM20C0001 | 81429,W912UM20C0001 | 54939000 | 55670000 | 2022-09-05 | 2022-10-24 | 731000 | 49 | 2022 | 10 | 24 | 20221024 | 2020 | 2023 | 1.0006 | 2022 | 0.95701 | 54972531.5667 | 55672107.3577 | 699575.791 | 49 | 1041 | 4.707%
2022-01-12 | 2020 | Marine Corps Active | M670011312F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011312F,N4008520C0044 AWD | 55017000 | 58510000 | 2024-09-30 | 2025-09-27 | 3493000 | 362 | 2025 | 09 | 27 | 20250927 | 2020 | 2025 | 1.0507 | 2023 | 1.0006 | 57806413.3881 | 61301545.3119 | 3495131.9238 | 362 | 1529 | 23.68%
2021-12-31 | 2018 | Air Force Active | MSET143006 |  | 2018-06-08 | 2021-04-26 | KVF 35 | DIOCB2 | DIOCB2076 | DIOCB2076 | MSET143006,DIOCB2076 | 55113676 | 55113676 | 2023-03-29 | 2023-03-29 | 0 | 0 | 2023 | 03 | 29 | 20230329 | 2021 | 2023 | 1.0006 | 2022 | 0.95701 | 55147314.1788 | 55147314.1788 | 0 | 0 | 702 | 0%
2022-01-12 | 2018 | Marine Corps Active | M67399192 |  | 2017-10-17 | 2018-09-29 | CDM CONSTRUCTORS INC | N62473 | N6247318C4602 AWD | N6247318C4602 | M67399192,N6247318C4602 AWD | 55390000 | 53775000 | 2021-09-28 | 2022-05-10 | -1615000 | 224 | 2022 | 05 | 10 | 20220510 | 2018 | 2022 | 1.0276 | 2020 | 1.0006 | 56918273.0973 | 55302287.3953 | -1615985.702 | 224 | 1095 | 20.46%
2022-01-12 | 2021 | Navy Active | N00245443 |  | 2021-03-05 | 2021-04-30 | MANSON CONSTRUCTION CO | N62473 | N6247321D1406 N6247321F4668 | N6247321D1406 | N00245443,N6247321D1406 N6247321F4668 | 55500000 | 62125000 | 2023-09-17 | 2023-09-17 | 6625000 | 0 | 2023 | 09 | 17 | 20230917 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 59666812.2108 | 66295855.725 | 6629043.5143 | 0 | 870 | 0%
2021-12-31 | 2016 | Air Force Active | MPLS083737S3 |  | 2017-11-29 | 2019-01-16 | Caddell Construction - DCF 3 | W9126G | W9126G19C0001 | W9126G19C0001 | MPLS083737S3,W9126G19C0001 | 55663720 | 55663720 | 2021-08-03 | 2022-06-22 | 0 | 323 | 2022 | 06 | 22 | 20220622 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 57199545.3434 | 57199545.3434 | 0 | 323 | 930 | 34.73%
2021-12-30 | 2020 | Air National Guard | QMSN199056 |  | 2020-07-24 | 2021-03-24 | Thompson Builders Corporation | W50S8X | W50S8X21C0001 | W50S8X21C0001 | QMSN199056,W50S8X21C0001 | 55702065 | 54219500 | 2022-10-17 | 2022-10-17 | -1482565 | 0 | 2022 | 10 | 17 | 20221017 | 2021 | 2023 | 0.97698 | 2022 | 0.9382 | 54419676.2677 | 53028736.654 | -1390939.6138 | 0 | 572 | 0%
2022-01-12 | 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N40085 | N4008517C8315 AWD | N4008517C8315 | M00146193,N4008517C8315 AWD | 55798000 | 56191000 | 2021-11-23 | 2021-12-23 | 393000 | 30 | 2021 | 12 | 23 | 20211223 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 55832055.8503 | 56216008.0929 | 383952.2426 | 30 | 1797 | 1.669%
2021-08-31 | 2019 | Army Active | 94609 |  | 2019-10-11 | 2019-11-19 | CJW Joint Venture | W9126G | W9126G19D0024 | W9126G19D0024 | 94609,W9126G19D0024 | 55842000 | 121858000 | 2021-03-03 | 2021-05-21 | 66016000 | 79 | 2021 | 05 | 21 | 20210521 | 2020 | 2021 | 1.0993 | 2021 | 1.0507 | 61384609.5053 | 130747682.4869 | 69363072.9816 | 79 | 470 | 16.81%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 72662-02 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB | W912GB-10-C-0031, P00102 | W912GB10C0031, | 76007,W912GB-10-C-0031, P00102 | 56039000 | 56985000 | 2021-01-30 | 2022-02-28 | 946000 | 394 | 2022 | 02 | 28 | 20220228 | 2013 | 2022 | 1.0993 | 2018 | 1.0751 | 61601162.782 | 62618186.2838 | 1017023.5018 | 394 | 2713 | 14.52%
2022-02-02 | 2019 | DoD Education Activity | AM00029 |  | 2020-06-29 | 2020-09-30 | A&K Construction Inc | W912QR | W912QR-20-C-0054/33717697 | W912QR20C0054 | AM00029,W912QR-20-C-0054/33717697 | 56070000 | 57548931 | 2023-09-09 | 2024-01-07 | 1478931 | 120 | 2024 | 01 | 07 | 20240107 | 2020 | 2024 | 1.0276 | 2022 | 1.0006 | 57617035.0707 | 59096868.724 | 1479833.6534 | 120 | 1074 | 11.17%
2021-12-31 | 2020 | Army Active | 88410 |  | 2020-10-29 | 2021-06-15 | Zodiac-Poettker | W912HN | W912HN21C3005 | W912HN21C3005 | 88410,W912HN21C3005 | 56295000 | 56295000 | 2023-08-01 | 2023-08-01 | 0 | 0 | 2023 | 08 | 01 | 20230801 | 2021 | 2023 | 1.0276 | 2022 | 0.97698 | 57848243.0766 | 57848243.0766 | 0 | 0 | 777 | 0%
2022-02-02 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB | W912GB-12-C-0041/50728702 | W912GB12C0041 | EU00049,W912GB-12-C-0041/50728702 | 56357984 | 57356183 | 2021-07-23 | 2021-08-23 | 998199 | 31 | 2021 | 08 | 23 | 20210823 | 2016 | 2021 | 1.2082 | 2019 | 1.1914 | 68093201.0006 | 69282415.9778 | 1189214.9773 | 31 | 1876 | 1.652%
2022-01-13 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G | W9126G-13-C-0004 | W9126G13C0004 | 72481,W9126G-13-C-0004 | 56858000 | 254981000 | 2016-11-26 | 2020-02-29 | 198123000 | 1190 | 2020 | 02 | 29 | 20200229 | 2013 | 2020 | 1.0751 | 2017 | 1.0276 | 61126767.724 | 264716206.6272 | 203589438.9033 | 1190 | 1397 | 85.18%
2022-01-12 | 2021 | Navy Active | N62813044 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N62478 | N6247820D4015 N6247821F4087 | N6247820D4015 | N62813044,N6247820D4015 N6247821F4087 | 58566450 | 39107000 | 2023-11-12 | 2023-11-12 | -19459450 | 0 | 2023 | 11 | 12 | 20231112 | 2021 | 2024 | 0.97698 | 2023 | 0.95701 | 57218116.5842 | 38595188.9153 | -18622927.6689 | 0 | 926 | 0%
2022-01-12 | 2021 | Navy Active | N628131006 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N62478 | N6247820D4015 N6247821F4087 | N6247820D4015 | N628131006,N6247820D4015 N6247821F4087 | 58566450 | 30327000 | 2023-11-12 | 2023-11-12 | -28239450 | 0 | 2023 | 11 | 12 | 20231112 | 2021 | 2024 | 1.0751 | 2023 | 1.0276 | 62963484.2162 | 33944875.6729 | -29018608.5434 | 0 | 926 | 0%
2021-08-31 | 2014 | Army Active | 81987 |  | 2017-06-08 | 2017-09-28 | CONTRACK WATTS-UEJO KOGYO JV | W912HV | W912HV-17-D-0013 | W912HV17D0013 | 81987,W912HV-17-D-0013 | 58908000 | 65889000 | 2019-11-22 | 2021-03-19 | 6981000 | 483 | 2021 | 03 | 19 | 20210319 | 2017 | 2021 | 1.0276 | 2019 | 0.97698 | 60533338.7184 | 67353620.1573 | 6820281.4388 | 483 | 785 | 61.53%
2022-01-12 | 2018 | Navy Active | N62813013 |  | 2018-12-14 | 2019-07-26 | NAN INC. DBAOCEAN HOUSE BUILDERS | N62742 | N6274219C1317 AWD | N6274219C1317 | N62813013,N6274219C1317 AWD | 59383000 | 64476000 | 2021-04-26 | 2021-09-25 | 5093000 | 152 | 2021 | 09 | 25 | 20210925 | 2019 | 2021 | 1.0276 | 2020 | 1.0006 | 61021444.5087 | 66117552.9793 | 5096108.4707 | 152 | 640 | 23.75%
2021-12-31 | 2017 | Air Force Active | FTFA043000 |  | 2018-06-07 | 2019-03-15 | Hensel Phelps | W91278 | W9127819C00006 | W9127819C00006 | FTFA043000,W9127819C00006 | 59456363 | 59676833 | 2020-11-11 | 2020-11-11 | 220470 | 0 | 2020 | 11 | 11 | 20201111 | 2019 | 2021 | 1.0276 | 2020 | 0.97698 | 61096831.6773 | 61312225.9544 | 215394.2772 | 0 | 607 | 0%
2021-08-31 | 2016 | Army Active | 75661 |  | 2017-11-30 | 2018-12-14 | Harper Construction | W912BV | W912BV19C0003 | W912BV19C0003 | 75661,W912BV19C0003 | 59467000 | 59467000 | 2020-12-26 | 2020-12-26 | 0 | 0 | 2020 | 12 | 26 | 20201226 | 2019 | 2021 | 0.97698 | 2020 | 0.95701 | 58097933.8668 | 58097933.8668 | 0 | 0 | 743 | 0%
2022-02-02 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV | W912HV-17-C-0004/37880445 | W912HV17C0004 | PA00017,W912HV-17-C-0004/37880445 | 61521811 | 88578226 | 2020-11-17 | 2023-01-22 | 27056415 | 796 | 2023 | 01 | 22 | 20230122 | 2017 | 2023 | 1.0276 | 2020 | 0.97698 | 63219267.7367 | 89652782.2799 | 26433514.5432 | 796 | 1425 | 55.86%
2022-01-12 | 2017 | Navy Active | N00246991 |  | 2016-11-23 | 2017-03-30 | RQ-DPR JV | N62473 | N6247317C0808 AWD | N6247317C0808 | N00246991,N6247317C0808 AWD | 61541000 | 76133000 | 2019-04-23 | 2021-04-30 | 14592000 | 738 | 2021 | 04 | 30 | 20210430 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 61578561.0431 | 75834619.8822 | 14256058.8391 | 738 | 754 | 97.88%
2022-01-12 | 2020 | Marine Corps Active | M00264719 |  | 2020-10-26 | 2021-03-22 | CLARK CONSTRUCTION GROUP, LLC. | N40080 | N4008021C0005 AWD | N4008021C0005 | M00264719,N4008021C0005 AWD | 61810155 | 70319000 | 2023-07-05 | 2023-07-05 | 8508845 | 0 | 2023 | 07 | 05 | 20230705 | 2021 | 2023 | 1.0006 | 2022 | 0.97698 | 61847880.3197 | 70160832.2778 | 8312951.9581 | 0 | 835 | 0%
2021-08-31 | 2015 | Army Active | 77305 |  | 2016-05-23 | 2017-09-11 | Straub Construction, INC | W9128F | W9128F-17-C-0032 | W9128F17C0032 | 77305,W9128F-17-C-0032 | 61936000 | 62889000 | 2019-06-02 | 2021-03-25 | 953000 | 662 | 2021 | 03 | 25 | 20210325 | 2017 | 2021 | 1.1227 | 2019 | 1.0993 | 69533797.8777 | 70581388.094 | 1047590.2163 | 662 | 629 | 105.2%
2021-12-31 | 2021 | Army Active | 55516 |  | 2021-02-12 | 2021-05-28 | ACC | W912HN | W912HN21C3004 | W912HN21C3004 | 55516,W912HN21C3004 | 62212000 | 62212000 | 2023-07-05 | 2023-07-05 | 0 | 0 | 2023 | 07 | 05 | 20230705 | 2021 | 2023 | 1.2082 | 2022 | 1.1519 | 75166177.3538 | 75166177.3538 | 0 | 0 | 768 | 0%
2022-01-12 | 2017 | Marine Corps Active | M62974612 |  | 2017-07-12 | 2019-06-13 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247316D1881 N6247319F4705 | N6247316D1881 | M62974612,N6247316D1881 N6247319F4705 | 62293000 | 62148000 | 2022-06-06 | 2023-05-17 | -145000 | 345 | 2023 | 05 | 17 | 20230517 | 2019 | 2023 | 1.0993 | 2021 | 1.0507 | 68475904.873 | 68323553.2373 | -152351.6357 | 345 | 1089 | 31.68%
2022-01-12 | 2018 | Marine Corps Active | M006811310 |  | 2018-04-12 | 2018-09-27 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247317D0817 | N6247317D0817 | M006811310,N6247317D0817 | 62328000 | 46121000 | 2020-10-10 | 2022-01-15 | -16207000 | 462 | 2022 | 01 | 15 | 20220115 | 2018 | 2022 | 1.2082 | 2020 | 1.1743 | 75306331.6098 | 56274151.7153 | -19032179.8945 | 462 | 744 | 62.1%
2022-01-12 | 2018 | Navy Active | N32446293 |  | 2018-08-31 | 2019-09-25 | METHUEN CONSTRUCTION CO., INC | N40085 | N4008519C9261 AWD | N4008519C9261 | N32446293,N4008519C9261 AWD | 62457000 | 62817000 | 2022-08-09 | 2022-08-09 | 360000 | 0 | 2022 | 08 | 09 | 20220809 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 62495120.1162 | 62839644.4456 | 344524.3294 | 0 | 1049 | 0%
2022-01-12 | 2019 | Marine Corps Active | M00318946 |  | 2018-11-20 | 2019-05-31 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274219C1303 AWD | N6274219C1303 | M00318946,N6274219C1303 AWD | 62559000 | 62483000 | 2021-09-07 | 2022-08-27 | -76000 | 354 | 2022 | 08 | 27 | 20220827 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 62597182.3711 | 62524449.4571 | -72732.914 | 354 | 830 | 42.65%
2021-12-31 | 2018 | Air Force Active | PAF160600 |  | 2019-05-07 | 2019-09-26 | Nova Nacap JV | N62742 | N6274219C1316 | N6274219C1316 | PAF160600,N6274219C1316 | 62585000 | 62595227 | 2022-10-25 | 2022-11-05 | 10227 | 11 | 2022 | 11 | 05 | 20221105 | 2019 | 2023 | 1.0751 | 2021 | 1.0276 | 67283737.6975 | 67294246.8721 | 10509.1746 | 11 | 1125 | 0.9778%
2022-01-31 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N69450 | N6945016C1612 | N6945016C1612 | AM00103,N6945016C1612 | 63028574 | 70507000 | 2018-11-26 | 2021-10-09 | 7478426 | 1048 | 2021 | 10 | 09 | 20211009 | 2016 | 2022 | 1.0276 | 2019 | 1.0006 | 64767604.0416 | 72250594.4374 | 7482990.3958 | 1048 | 878 | 119.4%
2022-01-06 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-03-23 | 2019-08-02 | NIPPO CORPORATION | W912HV | W912HV-17-D-0015 | W912HV17D0015 | AFSOC103022,W912HV-17-D-0015 | 63052343 | 67048014 | 2021-12-26 | 2021-12-26 | 3995671 | 0 | 2021 | 12 | 26 | 20211226 | 2019 | 2022 | 1.0993 | 2021 | 1.0507 | 69310616.6228 | 73508871.8819 | 4198255.2591 | 0 | 877 | 0%
2022-01-12 | 2018 | Navy Active | N00213741 |  | 2019-05-15 | 2019-09-27 | KORTE CONSTRUCTION COMPANY | N69450 | N6945019C0903 AWD | N6945019C0903 | N00213741,N6945019C0903 AWD | 63582000 | 61720000 | 2022-01-17 | 2022-08-25 | -1862000 | 220 | 2022 | 08 | 25 | 20220825 | 2019 | 2022 | 1.0507 | 2021 | 1.0276 | 66805666.9037 | 64892292.206 | -1913374.6977 | 220 | 843 | 26.1%
2021-12-31 | 2020 | Army Active | 60276 |  | 2020-02-13 | 2021-04-30 | M. A. Mortenson Company | W91236 | W9123621C2024 | W9123621C2024 | 60276,W9123621C2024 | 63845000 | 64004000 | 2024-05-31 | 2024-05-31 | 159000 | 0 | 2024 | 05 | 31 | 20240531 | 2021 | 2024 | 1.1519 | 2023 | 1.0507 | 73540986.5977 | 73708048.0465 | 167061.4488 | 0 | 1127 | 0%
2022-01-12 | 2019 | Navy Active | N62813169 |  | 2018-10-15 | 2019-03-29 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N62742 | N62742-19-C-1319 | N6274219C1319 | N62813169,N62742-19-C-1319 | 64705000 | 69905000 | 2022-01-24 | 2022-08-03 | 5200000 | 191 | 2022 | 08 | 03 | 20220803 | 2019 | 2022 | 1.1227 | 2021 | 1.0751 | 72642475.97 | 78232879.9969 | 5590404.027 | 191 | 1032 | 18.51%
2022-01-12 | 2019 | Marine Corps Active | M670011387F |  | 2019-10-09 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N40085 | N4008520C8505 AWD | N4008520C8505 | M670011387F,N4008520C8505 AWD | 64921000 | 66857000 | 2025-03-06 | 2025-03-06 | 1936000 | 0 | 2025 | 03 | 06 | 20250306 | 2020 | 2025 | 1.0006 | 2023 | 0.97698 | 64960623.9983 | 66852052.8575 | 1891428.8591 | 0 | 1686 | 0%
2022-02-28 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR | W912QR-13-0032 | W912QR130032 | VDYDS97032,W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11 | 0 | 72 | 2016 | 03 | 11 | 20160311 | 2013 | 2016 | 1.0276 | 2015 | 1.0006 | 67814849.5176 | 67814849.5176 | 0 | 72 | 821 | 8.77%
2022-01-12 | 2019 | Marine Corps Active | M670011505F |  | 2020-01-23 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N40085 | N4008520C8505 AWD | N4008520C8505 | M670011505F,N4008520C8505 AWD | 66036000 | 64520000 | 2019-10-25 | 2025-03-06 | -1516000 | 1959 | 2025 | 03 | 06 | 20250306 | 2020 | 2025 | 1.0006 | 2023 | 0.9382 | 66076304.5294 | 64653996.2634 | -1422308.2661 | 1959 | -273 | -717.6%
2022-01-12 | 2019 | Navy Active | N60514160 |  | 2018-12-10 | 2019-09-19 | RQ CONSTRUCTION, LLC | N69450 | N6945019C0501 AWD | N6945019C0501 | N60514160,N6945019C0501 AWD | 66357000 | 62810000 | 2022-03-18 | 2022-05-26 | -3547000 | 69 | 2022 | 05 | 26 | 20220526 | 2019 | 2022 | 1.0751 | 2021 | 1.0006 | 71338930.7724 | 67789765.8902 | -3549164.8823 | 69 | 911 | 7.574%
2022-01-13 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 | N4008013C0151 | N4008013C0151 | 77154,N4008013C0151 | 66430000 | 74182000 | 2016-12-06 | 2022-07-31 | 7752000 | 2063 | 2022 | 07 | 31 | 20220731 | 2013 | 2022 | 1.0006 | 2018 | 1.0006 | 66470545.0041 | 74227276.3735 | 7756731.3694 | 2063 | 1499 | 137.6%
2022-01-12 | 2019 | Navy Active | N32414106 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N40085 | N4008519C9057 AWD | N4008519C9057 | N32414106,N4008519C9057 AWD | 66625000 | 66732000 | 2022-02-13 | 2022-07-15 | 107000 | 152 | 2022 | 07 | 15 | 20220715 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 71627051.5954 | 71737003.8471 | 109952.2517 | 152 | 977 | 15.56%
2022-01-12 | 2020 | Navy Active | N00129898 |  | 2020-04-07 | 2020-09-29 | WEEKS MARINE, INC | N40085 | N4008520C0074 AWD | N4008520C0074 | N00129898,N4008520C0074 AWD | 67325000 | 76026000 | 2022-10-26 | 2022-11-12 | 8701000 | 17 | 2022 | 11 | 12 | 20221112 | 2020 | 2023 | 1.0507 | 2022 | 1.0276 | 70738440.5066 | 79679510.9926 | 8941070.486 | 17 | 757 | 2.246%
2022-01-13 | 2017 | Defense Health Agency | 72738 |  | 2017-01-19 | 2017-09-13 | JE Dunn Construction Company | W912-B | W912-BV-17-C-0014 | W912BV17C0014 | 72738,W912-BV-17-C-0014 | 67487000 | 67762000 | 2020-10-31 | 2021-09-30 | 275000 | 334 | 2021 | 09 | 30 | 20210930 | 2017 | 2021 | 1.0006 | 2019 | 0.95701 | 67528190.1353 | 67791368.4425 | 263178.3071 | 334 | 1144 | 29.2%
2022-01-12 | 2020 | Marine Corps Active | M67001695F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M67001695F,N4008520C0044 AWD | 67658000 | 69263000 | 2024-10-12 | 2025-02-18 | 1605000 | 129 | 2025 | 02 | 18 | 20250218 | 2020 | 2025 | 1.1743 | 2023 | 1.1519 | 79452040.9269 | 81300788.4167 | 1848747.4898 | 129 | 1541 | 8.371%
2021-12-31 | 2019 | Army Active | 77301 |  | 2019-04-03 | 2019-08-09 | Federal/Bryan | W9128F | W9128F19C0029 | W9128F19C0029 | 77301,W9128F19C0029 | 69147000 | 70917000 | 2021-05-04 | 2021-10-15 | 1770000 | 164 | 2021 | 10 | 15 | 20211015 | 2019 | 2022 | 1.2319 | 2021 | 1.1914 | 85184758.4944 | 87293466.7878 | 2108708.2934 | 164 | 634 | 25.87%
2021-12-31 | 2019 | Air Force Active | WWYK193001 |  | 2018-08-31 | 2019-08-29 | Korte | W912BV | W912BV19C0015 | W912BV19C0015 | WWYK193001,W912BV19C0015 | 69771792 | 69771792 | 2022-03-19 | 2022-03-19 | 0 | 0 | 2022 | 03 | 19 | 20220319 | 2019 | 2022 | 1.0276 | 2021 | 0.97698 | 71696875.0955 | 71696875.0955 | 0 | 0 | 933 | 0%
2022-01-12 | 2020 | Navy Active | N002461024 |  | 2019-10-16 | 2020-06-11 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247320C0553 AWD | N6247320C0553 | N002461024,N6247320C0553 AWD | 69801056 | 74980000 | 2023-01-01 | 2023-01-01 | 5178944 | 0 | 2023 | 01 | 01 | 20230101 | 2020 | 2023 | 1.1743 | 2022 | 1.1227 | 81968671.2296 | 87782925.3841 | 5814254.1545 | 0 | 934 | 0%
2021-12-31 | 2019 | Air Force Active | WWYK193014 |  | 2018-10-01 | 2019-09-27 | Korte Const Co | W912BV | W912BV19C0017 | W912BV19C0017 | WWYK193014,W912BV19C0017 | 71921672 | 71921672 | 2022-03-20 | 2022-03-20 | 0 | 0 | 2022 | 03 | 20 | 20220320 | 2019 | 2022 | 0.97698 | 2021 | #VALUE! | 70265870.877 | #VALUE! | #VALUE! | 0 | 905 | 0%
2022-01-12 | 2017 | Marine Corps Active | M00318923 |  | 2017-04-07 | 2017-08-21 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N62742 | N6274217C1307 AWD | N6274217C1307 | M00318923,N6274217C1307 AWD | 72494000 | 71484000 | 2020-03-08 | 2021-04-05 | -1010000 | 393 | 2021 | 04 | 05 | 20210405 | 2017 | 2021 | 1.0006 | 2019 | 0.97698 | 72538246.1166 | 71551498.6229 | -986747.4937 | 393 | 930 | 42.26%
2022-02-02 | 2017 | DoD Education Activity | PA00032 |  | 2017-06-22 | 2017-12-22 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV | W912HV18C0002/37880684 | W912HV18C0002 | PA00032,W912HV18C0002/37880684 | 72844929 | 80209599 | 2021-02-15 | 2021-03-10 | 7364670 | 23 | 2021 | 03 | 10 | 20210310 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 72889389.3032 | 79937467.0606 | 7048077.7573 | 23 | 1151 | 1.998%
2022-01-12 | 2017 | Navy Active | N68436834 |  | 2019-03-18 | 2020-02-03 | MANSON CONSTRUCTION CO | N44255 | N4425520C2002 AWD | N4425520C2002 | N68436834,N4425520C2002 AWD | 73000000 | 101304000 | 2022-07-04 | 2022-07-04 | 28304000 | 0 | 2022 | 07 | 04 | 20220704 | 2020 | 2022 | 1.0276 | 2021 | 0.97698 | 75014153.0258 | 102666530.3135 | 27652377.2877 | 0 | 882 | 0%
2022-01-12 | 2018 | Navy Active | N32443257 |  | 2017-11-03 | 2018-09-17 | RQ CONSTRUCTION, LLC | N40085 | N4008518C1107 AWD | N4008518C1107 | N32443257,N4008518C1107 AWD | 73055000 | 71370000 | 2021-06-18 | 2021-11-02 | -1685000 | 137 | 2021 | 11 | 02 | 20211102 | 2018 | 2022 | 1.2319 | 2020 | 1.1914 | 89999168.8983 | 87991726.2574 | -2007442.6409 | 137 | 1005 | 13.63%
2022-01-12 | 2018 | Navy Active | N62813704 |  | 2018-09-21 | 2019-03-12 | KIEWIT INFRASTRUCTURE WEST CO. | N62478 | N62478-19-C-1515 | N6247819C1515 | N62813704,N62478-19-C-1515 | 73199000 | 71082000 | 2021-06-19 | 2021-07-21 | -2117000 | 32 | 2021 | 07 | 21 | 20210721 | 2019 | 2021 | 1.0507 | 2020 | 1.0006 | 76910257.8039 | 74791965.7103 | -2118292.0935 | 32 | 830 | 3.855%
2022-01-13 | 2016 | Defense Health Agency | 80412 | 80412-01 | 2016-10-21 | 2018-02-08 | Hensel-Phelps Const. Co. | W9128A | W9128A-18-C-0001 | W9128A18C0001 | 80412,W9128A-18-C-0001 | 74987000 | 73999000 | 2020-05-21 | 2020-11-20 | -988000 | 183 | 2020 | 11 | 20 | 20201120 | 2018 | 2021 | 1.1914 | 2020 | 1.1743 | 89336558.6414 | 88176331.9655 | -1160226.6759 | 183 | 833 | 21.97%
2022-01-12 | 2018 | Marine Corps Active | N41557601 |  | 2017-06-30 | 2018-05-16 | HENSEL PHELPS CONSTRUCTION CO. | N62742 | N6274218C1316 AWD | N6274218C1316 | N41557601,N6274218C1316 AWD | 75233000 | 72008000 | 2020-10-02 | 2021-10-22 | -3225000 | 385 | 2021 | 10 | 22 | 20211022 | 2018 | 2022 | 1.0276 | 2020 | 0.97698 | 77308764.0355 | 74158010.8998 | -3150753.1357 | 385 | 870 | 44.25%
2022-01-12 | 2019 | Navy Active | N60201426 |  | 2019-05-31 | 2019-09-13 | ARCHER WESTERN CONSTRUCTION, LLC | N69450 | N6945014D1267 N6945019F0708 | N6945014D1267 | N60201426,N6945014D1267 N6945019F0708 | 76123000 | 73246000 | 2021-04-02 | 2022-06-27 | -2877000 | 451 | 2022 | 06 | 27 | 20220627 | 2019 | 2022 | 0.97698 | 2021 | 0.95701 | 74370474.7127 | 71617151.114 | -2753323.5987 | 451 | 567 | 79.54%
2021-12-31 | 2020 | Army Active | 88077 |  | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR | W912DR20C0007 | W912DR20C0007 | 88077,W912DR20C0007 | 76399000 | 80793000 | 2023-04-01 | 2023-04-29 | 4394000 | 28 | 2023 | 04 | 29 | 20230429 | 2020 | 2023 | 1.1519 | 2022 | 1.0993 | 88001532.3843 | 92831659.7825 | 4830127.3981 | 28 | 1118 | 2.504%
2021-12-31 | 2021 | Army Active | 88077 | 96217 | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR | W912DR20C0007 | W912DR20C0007 | 88077,W912DR20C0007 | 76399000 | 80793000 | 2023-04-29 | 2023-04-29 | 4394000 | 0 | 2023 | 04 | 29 | 20230429 | 2020 | 2023 | 1.0993 | 2022 | 1.0751 | 83981998.8825 | 88705890.2853 | 4723891.4028 | 0 | 1146 | 0%
2021-12-31 | 2021 | Army Active | 76897 |  | 2021-02-10 | 2021-09-21 | Hensel Phelps Construction Co. | W9128A | W9128A21C0007 | W9128A21C0007 | 76897,W9128A21C0007 | 76594000 | 78551000 | 2024-10-12 | 2024-10-12 | 1957000 | 0 | 2024 | 10 | 12 | 20241012 | 2021 | 2025 | 1.0006 | 2023 | 0.95701 | 76640748.5179 | 78513621.0527 | 1872872.5348 | 0 | 1117 | 0%
2021-12-31 | 2018 | Army Active | 61147 |  | 2018-06-20 | 2019-11-15 | Walsh Federal JV | W912DW | W912DW20C0002 | W912DW20C0002 | 61147,W912DW20C0002 | 77308000 | 79376000 | 2022-08-22 | 2022-10-23 | 2068000 | 62 | 2022 | 10 | 23 | 20221023 | 2020 | 2023 | 1.0751 | 2022 | 1.0276 | 83112106.6377 | 85237165.1097 | 2125058.472 | 62 | 1011 | 6.133%
2022-02-02 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB | W912GB-11-C-0029/27243529 | W912GB11C0029 | EU00031,W912GB-11-C-0029/27243529 | 77816984 | 90293144 | 2019-05-08 | 2019-10-31 | 12476160 | 176 | 2019 | 10 | 31 | 20191031 | 2017 | 2020 | 0.97698 | 2019 | 0.95701 | 76025459.3328 | 87965294.4908 | 11939835.158 | 176 | 901 | 19.53%
2022-01-12 | 2017 | Marine Corps Active | M60169464 |  | 2017-02-23 | 2017-06-29 | THE HASKELL COMPANY | N40085 | N4008517C8327 AWD | N4008517C8327 | M60169464,N4008517C8327 AWD | 78310000 | 79679000 | 2020-07-13 | 2021-08-21 | 1369000 | 404 | 2021 | 08 | 21 | 20210821 | 2017 | 2021 | 1.1519 | 2019 | 1.1227 | 90202751.3582 | 91739688.9922 | 1536937.6339 | 404 | 1110 | 36.4%
2022-01-12 | 2017 | Navy Active | N41557H279 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N62742 | N6274219C1309 AWD | N6274219C1309 | N41557H279,N6274219C1309 AWD | 78787000 | 75634000 | 2022-07-05 | 2023-03-13 | -3153000 | 251 | 2023 | 03 | 13 | 20230313 | 2019 | 2023 | 1.0993 | 2021 | 1.0507 | 86607020.327 | 83294160.2762 | -3312860.0508 | 251 | 1020 | 24.61%
2022-01-12 | 2018 | Marine Corps Active | M67865198 | M67865198A | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318C4605 AWD | N6247318C4605 | M67865198,N6247318C4605 AWD | 79399000 | 81408000 | 2020-01-14 | 2020-06-26 | 2009000 | 164 | 2020 | 06 | 26 | 20200626 | 2018 | 2020 | 1.0006 | 2019 | 0.97698 | 79447460.5265 | 81410208.759 | 1962748.2324 | 164 | 720 | 22.78%
2022-01-13 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 | N6274216C1312 | N6274216C1312 | 78150,N6274216C1312 | 79722000 | 83356000 | 2018-12-21 | 2020-08-31 | 3634000 | 619 | 2020 | 08 | 31 | 20200831 | 2016 | 2020 | 1.2319 | 2018 | 1.2082 | 98212493.9143 | 102603188.4508 | 4390694.5365 | 619 | 865 | 71.56%
2022-01-12 | 2020 | Marine Corps Active | M67001707F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M67001707F,N4008520C0044 AWD | 79978000 | 81776000 | 2024-10-12 | 2025-02-18 | 1798000 | 129 | 2025 | 02 | 18 | 20250218 | 2020 | 2025 | 1.1743 | 2023 | 1.1227 | 93919644.8203 | 95938208.6375 | 2018563.8172 | 129 | 1541 | 8.371%
2022-01-12 | 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N44255 | N4425512C3008 P00004 | N4425512C3008 | N68436990,N4425512C3008 P00004 | 80735000 | 82357000 | 2017-09-30 | 2017-09-30 | 1622000 | 0 | 2017 | 09 | 30 | 20170930 | 2015 | 2017 | 0.97698 | 2016 | 0.9382 | 78876295.9412 | 80398053.2021 | 1521757.2609 | 0 | 996 | 0%
2021-12-31 | 2017 | Air Force Active | FTQW183001 |  | 2018-01-30 | 2018-06-05 | Watterson Construction Company | W911KB | W911KB18C0026 | W911KB18C0026 | FTQW183001,W911KB18C0026 | 82125000 | 84396009 | 2020-05-06 | 2021-03-03 | 2271009 | 301 | 2021 | 03 | 03 | 20210303 | 2018 | 2021 | 1.0507 | 2020 | 1.0276 | 86288814.3573 | 88622483.0785 | 2333668.7212 | 301 | 701 | 42.94%
2022-01-12 | 2019 | Navy Active | N41557H282 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N62742 | N6274219C1309 AWD | N6274219C1309 | N41557H282,N6274219C1309 AWD | 83378000 | 79846000 | 2022-07-05 | 2023-03-13 | -3532000 | 251 | 2023 | 03 | 13 | 20230313 | 2019 | 2023 | 1.1914 | 2021 | 1.1519 | 99333265.5847 | 95264869.2394 | -4068396.3453 | 251 | 1020 | 24.61%
2021-11-30 | 2018 | Missile Defense Agency | 674 |  | 2018-09-23 | 2018-12-20 | CP04-NEESER CONSTRUCTION, INC | W911KB | W911KB19C0006 | W911KB19C0006 | 674,W911KB19C0006 | 83991000 | 99641635 | 2021-09-30 | 2022-08-09 | 15650635 | 313 | 2022 | 08 | 09 | 20220809 | 2019 | 2022 | 1.0006 | 2021 | 0.95701 | 84042263.216 | 99020109.1251 | 14977845.9091 | 313 | 1015 | 30.84%
2021-12-31 | 2018 | Missile Defense Agency | 674 |  | 2018-09-23 | 2018-12-20 | CP04-NEESER CONSTRUCTION, INC | W911KB | W911KB-19-C-0006 | W911KB19C0006 | 674,W911KB-19-C-0006 | 83991000 | 99641635 | 2021-09-30 | 2022-08-09 | 15650635 | 313 | 2022 | 08 | 09 | 20220809 | 2019 | 2022 | 1.0993 | 2021 | 1.0507 | 92327544.4462 | 108771681.2875 | 16444136.8413 | 313 | 1015 | 30.84%
2021-12-31 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan | W912HV | W912HV-14-C-0007 | W912HV14C0007 | 62783,W912HV-14-C-0007 | 84367000 | 86073000 | 2021-06-09 | 2022-08-11 | 1706000 | 428 | 2022 | 08 | 11 | 20220811 | 2014 | 2022 | 0.97698 | 2018 | 0.95701 | 82424679.0075 | 84057341.5238 | 1632662.5163 | 428 | 2456 | 17.43%
2021-11-30 | 2016 | Army Active | 71057 |  | 2014-08-28 | 2018-07-19 | Kiewit/Manson MOTCO, AJV | W91238 | W9123818C0015 | W9123818C0015 | 71057,W9123818C0015 | 87549000 | 98782000 | 2020-08-01 | 2021-04-23 | 11233000 | 265 | 2021 | 04 | 23 | 20210423 | 2018 | 2021 | 1.0276 | 2020 | 0.97698 | 89964576.483 | 100938967.1724 | 10974390.6894 | 265 | 744 | 35.62%
2022-02-02 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB | W912GB-12-C-0024/52029300 | W912GB12C0024 | EU00037,W912GB-12-C-0024/52029300 | 89535967 | 97631490 | 2021-03-29 | 2021-06-28 | 8095523 | 91 | 2021 | 06 | 28 | 20210628 | 2018 | 2021 | 1.0006 | 2020 | 0.95701 | 89590614.541 | 97338127.4085 | 7747512.8676 | 91 | 1207 | 7.539%
2021-12-31 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N62742 | N6274210D1307JQ01 | N6274210D1307JQ01 | AJJY123010,N6274210D1307JQ01 | 89918305 | 92491623 | 2017-04-16 | 2020-07-14 | 2573318 | 1185 | 2020 | 07 | 14 | 20200714 | 2015 | 2020 | 1.0751 | 2018 | 1.0507 | 96669164.3017 | 99372951.9326 | 2703787.6309 | 1185 | 786 | 150.8%
2022-01-12 | 2020 | Army National Guard | 361811 |  | 2020-09-17 | 2020-09-30 | Suffolk Construction Co., Inc. | 46086C | 46086C | 46086C | 361811,46086C | 91000000 | 68602000 | 2022-09-16 | 2024-04-12 | -22398000 | 574 | 2024 | 04 | 12 | 20240412 | 2020 | 2024 | 1.0507 | 2022 | 1.0276 | 95613785.1631 | 72597798.8689 | -23015986.2941 | 574 | 716 | 80.17%
2021-12-31 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N62742 | N6274210D13070002 | N6274210D13070002 | AJJY133027,N6274210D13070002 | 96616619 | 102900955 | 2017-03-08 | 2021-07-17 | 6284336 | 1592 | 2021 | 07 | 17 | 20210717 | 2015 | 2021 | 1.0006 | 2018 | 0.97698 | 96675588.1587 | 102815244.3936 | 6139656.235 | 1592 | 811 | 196.3%
2021-12-31 | 2015 | Air Force Active | WWYK153005 |  | 2015-03-05 | 2017-03-30 | Walsh Federal Alberici JV | W912BV | W912BV17C0004 | W912BV17C0004 | WWYK153005,W912BV17C0004 | 97939000 | 98825383 | 2019-04-30 | 2019-08-19 | 886383 | 111 | 2019 | 08 | 19 | 20190819 | 2017 | 2019 | 1.0006 | 2018 | 0.97698 | 97998776.263 | 98864752.7023 | 865976.4393 | 111 | 761 | 14.59%
2021-12-31 | 2016 | Air Force Active | MPLS083737R5 |  | 2017-11-29 | 2019-01-16 | Cadell Construction Co | W9126G | W9126G19C0001 | W9126G19C0001 | MPLS083737R5,W9126G19C0001 | 98410381 | 98410381 | 2021-08-03 | 2022-10-03 | 0 | 426 | 2022 | 10 | 03 | 20221003 | 2019 | 2023 | 1.0507 | 2021 | 1.0006 | 103399879.4148 | 103399879.4148 | 0 | 426 | 930 | 45.81%
2021-12-31 | 2020 | Air Force Active | KRSM1065068 |  | 2020-06-27 | 2020-07-27 | GBSD Mission Integration Facility | W91238 | W9123820C0012 | W9123820C0012 | KRSM1065068,W9123820C0012 | 100809955 | 100809955 | 2023-04-13 | 2023-04-04 | 0 | -9 | 2023 | 04 | 04 | 20230404 | 2020 | 2023 | 1.0006 | 2022 | 0.9382 | 100871483.5268 | 100871483.5268 | 0 | -9 | 990 | -0.9091%
2022-01-12 | 2021 | Marine Corps Active | M670011800A |  | 2020-07-10 | 2021-03-02 | ARCHER WESTERN FEDERAL JV | N40085 | N4008521C0017 | N4008521C0017 | M670011800A,N4008521C0017 | 102629610 | 20000 | 2026-07-23 | 2027-03-20 | -102609610 | 240 | 2027 | 03 | 20 | 20270320 | 2021 | 2027 | 1.0751 | 2024 | 1.0276 | 110334804.8132 | 4894078.9713 | -105440725.8419 | 240 | 1969 | 12.19%
2021-12-31 | 2017 | Air Force Active | MPLS083737R6 |  | 2019-01-22 | 2019-09-26 | ATC 6 | W9126G | W9126G19C0023 | W9126G19C0023 | MPLS083737R6,W9126G19C0023 | 103001487 | 103001487 | 2022-04-13 | 2022-10-27 | 0 | 197 | 2022 | 10 | 27 | 20221027 | 2019 | 2023 | 1.1914 | 2021 | 1.1519 | 122711915.179 | 122711915.179 | 0 | 197 | 930 | 21.18%
2022-01-06 | 2019 | Special Operations Command | 80775 |  | 2020-03-05 | 2020-09-29 | Balfour Beatty Construction, LLC | W91236 | W9123620C2025 | W9123620C2025 | 80775,W9123620C2025 | 104543631 | 104914693 | 2023-01-11 | 2023-01-11 | 371062 | 0 | 2023 | 01 | 11 | 20230111 | 2020 | 2023 | 1.0507 | 2022 | 1.0006 | 109844090.9297 | 110215379.4043 | 371288.4746 | 0 | 834 | 0%
2021-08-31 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS | W912DS-11-C-0023 | W912DS11C0023 | 59044,W912DS-11-C-0023 | 105270000 | 127708000 | 2016-01-29 | 2021-07-30 | 22438000 | 2009 | 2021 | 07 | 30 | 20210730 | 2011 | 2021 | 1.0006 | 2016 | 0.97698 | 105334250.6786 | 127255676.6813 | 21921426.0027 | 2009 | 1582 | 127%
2022-01-12 | 2019 | Navy Active | N63042284 |  | 2018-11-09 | 2019-09-16 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247319C2455 AWD | N6247319C2455 | N63042284,N6247319C2455 AWD | 107641000 | 103221000 | 2021-11-17 | 2022-02-28 | -4420000 | 103 | 2022 | 02 | 28 | 20220228 | 2019 | 2022 | 1.0276 | 2021 | 1.0006 | 110610937.6144 | 106188239.9038 | -4422697.7106 | 103 | 793 | 12.99%
2022-01-12 | 2019 | Navy Active | N61065224 |  | 2018-12-10 | 2019-07-15 | MANSON/CONNOLLY SEAL BEACH JV | N62473 | N6247319C2450 AWD | N6247319C2450 | N61065224,N6247319C2450 AWD | 111089000 | 113495000 | 2022-06-30 | 2024-06-18 | 2406000 | 719 | 2024 | 06 | 18 | 20240618 | 2019 | 2024 | 1.0276 | 2022 | 0.97698 | 114154071.856 | 116504680.2419 | 2350608.3859 | 719 | 1081 | 66.51%
2022-01-12 | 2020 | Navy Active | N476091903 |  | 2020-05-22 | 2020-09-17 | HARPER CONSTRUCTION COMPANY, INC | N62473 | N6247318D5853 N6247320F5462 | N6247318D5853 | N476091903,N6247318D5853 N6247320F5462 | 111944000 | 124945000 | 2022-11-04 | 2022-11-04 | 13001000 | 0 | 2022 | 11 | 04 | 20221104 | 2020 | 2023 | 1.1914 | 2022 | 1.0276 | 133365672.9907 | 146725385.3672 | 13359712.3766 | 0 | 778 | 0%
2021-12-31 | 2020 | Army Active | 88725 |  | 2020-12-02 | 2021-04-02 | J. KOKOLAKIS CONTRACTING | W912HN | W912HN21C3003 | W912HN21C3003 | 88725,W912HN21C3003 | 112377000 | 112360000 | 2024-04-25 | 2024-04-25 | -17000 | 0 | 2024 | 04 | 25 | 20240425 | 2021 | 2024 | 1.0751 | 2023 | 1.0006 | 120814006.411 | 120796996.0352 | -17010.3758 | 0 | 1119 | 0%
2021-12-31 | 2017 | Missile Defense Agency | 657 |  | 2016-12-14 | 2017-04-28 | UNIT-ASRC Construction, LLC | W911KB | W911KB-17-C-0002 | W911KB17C0002 | 657,W911KB-17-C-0002 | 112949720 | 119078184 | 2019-08-23 | 2020-06-01 | 6128464 | 283 | 2020 | 06 | 01 | 20200601 | 2017 | 2020 | 1.1914 | 2019 | 1.1519 | 134563848.1911 | 141623027.2793 | 7059179.0882 | 283 | 847 | 33.41%
2020-12-09 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR | W912DR-10-C-0033 | W912DR10C0033 | 17872,W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12 | 15855000 | 542 | 2015 | 10 | 12 | 20151012 | 2010 | 2016 | 1.1743 | 2013 | 1.1519 | 132959863.281 | 151222723.9984 | 18262860.7175 | 542 | 1327 | 40.84%
2022-01-12 | 2020 | Navy Active | N476091911 |  | 2021-01-19 | 2021-06-24 | WEBCOR CONSTRUCTION LP | N62473 | N6247321D1214 N6247321F4923 | N6247321D1214 | N476091911,N6247321D1214 N6247321F4923 | 113295655 | 145640000 | 2024-01-22 | 2024-01-22 | 32344345 | 0 | 2024 | 01 | 22 | 20240122 | 2021 | 2024 | 1.0276 | 2023 | 1.0006 | 116421610.9772 | 148785697.0821 | 32364086.1049 | 0 | 942 | 0%
2022-01-12 | 2016 | Navy Active | N62688913 |  | 2017-03-23 | 2018-04-23 | WHITING-TURNER CONTRACTING CO | N40085 | N4008518C1134 AWD | N4008518C1134 | N62688913,N4008518C1134 AWD | 114000000 | 110529000 | 2020-11-01 | 2021-05-09 | -3471000 | 189 | 2021 | 05 | 09 | 20210509 | 2018 | 2021 | 1.0751 | 2020 | 1.0006 | 122558857.514 | 119085739.0177 | -3473118.4963 | 189 | 923 | 20.48%
2020-12-09 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR | W912DR-12-C-0019 | W912DR12C0019 | 23051,W912DR-12-C-0019 | 116975000 | 132008057 | 2015-05-03 | 2015-07-28 | 15033057 | 86 | 2015 | 07 | 28 | 20150728 | 2012 | 2015 | 1.0006 | 2014 | 0.97698 | 117046394.7291 | 131733356.4288 | 14686961.6998 | 86 | 949 | 9.062%
2021-12-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB | W912GB-13-R-0003 | W912GB13R0003 | 630,W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-05-12 | -3910000 | 256 | 2016 | 05 | 12 | 20160512 | 2013 | 2016 | 1.0276 | 2015 | 0.97698 | 121564031.5473 | 117744048.6759 | -3819982.8715 | 256 | 782 | 32.74%
2021-12-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB | W912GB-13-R-0003 | W912GB13R0003 | 630,W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-05-12 | -51400000 | 256 | 2016 | 05 | 12 | 20160512 | 2013 | 2016 | 1.0276 | 2015 | 0.97698 | 121564031.5473 | 71347376.9195 | -50216654.6278 | 256 | 782 | 32.74%
2022-01-12 | 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N40080 | N4008016C0156 AWD | N4008016C0156 | N61152621,N4008016C0156 AWD | 120181000 | 139973000 | 2019-09-08 | 2020-05-22 | 19792000 | 257 | 2020 | 05 | 22 | 20200522 | 2016 | 2020 | 0.97698 | 2018 | 0.95701 | 117414158.946 | 136355340.9641 | 18941182.0181 | 257 | 1256 | 20.46%
2021-12-31 | 2020 | Air Force Active | GLEN203001 |  | 2021-06-10 | 2021-09-01 | Hensel Phelps | W9128F | W9128F21C0041 | W9128F21C0041 | GLEN203001,W9128F21C0041 | 121968000 | 121968000 | 2025-03-14 | 2025-03-14 | 0 | 0 | 2025 | 03 | 14 | 20250314 | 2021 | 2025 | 1.0006 | 2023 | 0.95701 | 122042442.1655 | 122042442.1655 | 0 | 0 | 1290 | 0%
2022-01-12 | 2020 | Navy Active | N41557735A |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N62742 | N6274221C1346 AWD | N6274221C1346 | N41557735A,N6274221C1346 AWD | 122137577.15 | 85174000 | 2024-10-25 | 2024-10-25 | -36963577.15 | 0 | 2024 | 10 | 25 | 20241025 | 2021 | 2025 | 1.0276 | 2023 | 0.97698 | 125507491.8155 | 89394900.6181 | -36112591.1975 | 0 | 1123 | 0%
2021-05-31 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR | W912DR-13-C-0038 | W912DR13C0038 | 26170,W912DR-13-C-0038 | 123058382 | 171004789 | 2015-10-11 | 2020-12-31 | 47946407 | 1908 | 2020 | 12 | 31 | 20201231 | 2010 | 2021 | 1.1519 | 2016 | 1.1227 | 141746962.5092 | 195575039.4483 | 53828076.9391 | 1908 | 1843 | 103.5%
2021-12-31 | 2018 | Air Force Active | XDAT1051930 |  | 2018-10-26 | 2019-12-30 | Walsh Federal | N62473 | N6247320C0613 | N6247320C0613 | XDAT1051930,N6247320C0613 | 123643850 | 124327472 | 2022-06-17 | 2022-06-17 | 683622 | 0 | 2022 | 06 | 17 | 20220617 | 2020 | 2022 | 1.0006 | 2021 | 0.95701 | 123719315.0068 | 124373549.482 | 654234.4752 | 0 | 900 | 0%
2022-01-12 | 2016 | Marine Corps Active | N41557715 |  | 2016-04-06 | 2017-08-24 | BLACK CONSTRUCTION CORP. | N62742 | N6274217C1319 AWD | N6274217C1319 | N41557715,N6274217C1319 AWD | 123661000 | 100681000 | 2020-11-26 | 2021-11-08 | -22980000 | 347 | 2021 | 11 | 08 | 20211108 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 123736475.4742 | 101285527.5491 | -22450947.925 | 347 | 1190 | 29.16%
2020-12-09 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR | W912DR-11-C-0036 | W912DR11C0036 | 17866,W912DR-11-C-0036 | 125900000 | 131089216 | 2014-11-30 | 2015-10-31 | 5189216 | 335 | 2015 | 10 | 31 | 20151031 | 2011 | 2016 | 1.0006 | 2014 | 0.97698 | 125976842.0294 | 131046590.4275 | 5069748.3981 | 335 | 1171 | 28.61%
2021-11-30 | 2019 | Missile Defense Agency | 659 |  | 2018-10-10 | 2019-03-08 | CP03-UNIT-ASRC Construction LLC | W911KB | W911KB19C0001 | W911KB19C0001 | 659,W911KB19C0001 | 128657500 | 133332011 | 2021-06-30 | 2022-06-10 | 4674511 | 345 | 2022 | 06 | 10 | 20220610 | 2019 | 2022 | 1.0751 | 2021 | 1.0276 | 138316808.865 | 143120294.94 | 4803486.075 | 345 | 845 | 40.83%
2021-12-31 | 2019 | Missile Defense Agency | 659 |  | 2018-10-10 | 2019-03-08 | CP03-UNIT-ASRC Construction LLC | W911KB | W911KB-19-C-0001 | W911KB19C0001 | 659,W911KB-19-C-0001 | 128657500 | 133332011 | 2021-06-30 | 2022-06-10 | 4674511 | 345 | 2022 | 06 | 10 | 20220610 | 2019 | 2022 | 0.97698 | 2021 | 0.9382 | 125695510.5599 | 130081127.7334 | 4385617.1735 | 345 | 845 | 40.83%
2021-08-31 | 2019 | Army Active | 94611 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G | W9126G19D0021 | W9126G19D0021 | 94611,W9126G19D0021 | 130750000 | 178637000 | 2021-01-25 | 2021-09-02 | 47887000 | 220 | 2021 | 09 | 02 | 20210902 | 2020 | 2021 | 0.97698 | 2021 | 0.95701 | 127739836.4317 | 173568271.3195 | 45828434.8879 | 220 | 374 | 58.82%
2022-01-12 | 2020 | Marine Corps Active | M670011512F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M670011512F,N4008520C0044 AWD | 135347000 | 137453000 | 2025-05-27 | 2026-01-22 | 2106000 | 240 | 2026 | 01 | 22 | 20260122 | 2020 | 2026 | 1.0993 | 2023 | 1.0276 | 148780895.074 | 150945002.0092 | 2164106.9352 | 240 | 1768 | 13.57%
2021-12-31 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB | W912GB-16-C-0005 | W912GB16C0005 | 640,W912GB-16-C-0005 | 141906057 | 171152000 | 2018-11-09 | 2022-10-25 | 29245943 | 1446 | 2022 | 10 | 25 | 20221025 | 2016 | 2023 | 1.0276 | 2020 | 1.0006 | 145821406.5081 | 175085199.5288 | 29263793.0207 | 1446 | 1003 | 144.2%
2021-12-31 | 2016 | Air Force Active | GHLN153001 |  | 2017-09-19 | 2018-12-07 | Construction Contract | W9128F | W9128F19C0005 | W9128F19C0005 | GHLN153001,W9128F19C0005 | 154671056 | 154671056 | 2022-04-20 | 2022-11-05 | 0 | 199 | 2022 | 11 | 05 | 20221105 | 2019 | 2023 | 0.97698 | 2021 | 0.95701 | 151110175.0987 | 151110175.0987 | 0 | 199 | 1230 | 16.18%
2022-01-13 | 2009 | Defense Health Agency | 70354 |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL | W912PL-12-C-0005 | W912PL12C0005 | 70354,W912PL-12-C-0005 | 162257000 | 213468000 | 2015-03-16 | 2018-03-01 | 51211000 | 1081 | 2018 | 03 | 01 | 20180301 | 2012 | 2018 | 1.0993 | 2015 | 1.0507 | 178361852.8081 | 232169298.4343 | 53807445.6262 | 1081 | 1041 | 103.8%
2022-01-12 | 2019 | Navy Active | N32446310 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N40085 | N4008520C8500 AWD | N4008520C8500 | N32446310,N4008520C8500 AWD | 177914000 | 138795000 | 2021-01-27 | 2022-03-20 | -39119000 | 417 | 2022 | 03 | 20 | 20220320 | 2020 | 2022 | 1.0751 | 2021 | 1.0006 | 191271373.4715 | 152128497.5116 | -39142875.9599 | 417 | 433 | 96.3%
2021-12-31 | 2019 | Army Active | 78804 |  | 2020-06-03 | 2020-12-04 | DOBCO GROUP, INC. | W912DS | W912DS21C0002 | W912DS21C0002 | 78804,W912DS21C0002 | 186676000 | 187624000 | 2025-01-04 | 2025-02-11 | 948000 | 38 | 2025 | 02 | 11 | 20250211 | 2021 | 2025 | 1.1914 | 2023 | 1.1519 | 222398434.6745 | 223490405.1545 | 1091970.48 | 38 | 1492 | 2.547%
2021-12-31 | 2019 | Army Active | 88724 |  | 2019-05-31 | 2020-06-19 | Gilbane Federal | W912HN | W912HN20C3006 | W912HN20C3006 | 88724,W912HN20C3006 | 193807000 | 195853000 | 2022-07-07 | 2022-11-04 | 2046000 | 120 | 2022 | 11 | 04 | 20221104 | 2020 | 2023 | 1.0993 | 2022 | 1.0507 | 213043354.7223 | 215193088.8371 | 2149734.1148 | 120 | 748 | 16.04%
2022-01-13 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR | W912DR-15-C-0015 | W912DR15C0015 | 77000,W912DR-15-C-0015 | 206445000 | 218443000 | 2019-02-19 | 2022-02-01 | 11998000 | 1078 | 2022 | 02 | 01 | 20220201 | 2015 | 2022 | 0.97698 | 2019 | 0.95701 | 201692164.6817 | 213174394.9693 | 11482230.2876 | 1078 | 1293 | 83.37%
2022-01-12 | 2020 | Navy Active | N476091904 |  | 2021-02-11 | 2021-06-25 | RQ CONSTRUCTION, LLC | N62473 | N6247321D1211 N6247321F4921 | N6247321D1211 | N476091904,N6247321D1211 N6247321F4921 | 217657842 | 236454000 | 2025-08-29 | 2025-08-29 | 18796158 | 0 | 2025 | 08 | 29 | 20250829 | 2021 | 2025 | 1.0276 | 2023 | 1.0006 | 223663269.4118 | 242470899.4922 | 18807630.0804 | 0 | 1526 | 0%
2021-12-31 | 2018 | Air Force Active | AJXF173021 |  | 2018-11-12 | 2018-12-12 | Clark Construction Group, LLC | N40080 | N4008019C0008 | N4008019C0008 | AJXF173021,N4008019C0008 | 220000000 | 220000000 | 2022-05-25 | 2022-05-25 | 0 | 0 | 2022 | 05 | 25 | 20220525 | 2019 | 2022 | 1.0006 | 2021 | 0.97698 | 220134275.1904 | 220134275.1904 | 0 | 0 | 1260 | 0%
2022-01-12 | 2020 | Marine Corps Active | M67001378F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N40085 | N4008520C0044 AWD | N4008520C0044 | M67001378F,N4008520C0044 AWD | 223502000 | 227567000 | 2024-10-12 | 2025-02-18 | 4065000 | 129 | 2025 | 02 | 18 | 20250218 | 2020 | 2025 | 1.0006 | 2023 | 0.97698 | 223638412.6073 | 227609827.0248 | 3971414.4175 | 129 | 1541 | 8.371%
2021-08-31 | 2019 | Army Active | 94607 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL | W912PL20C0002 | W912PL20C0002 | 94607,W912PL20C0002 | 245241000 | 404677000 | 2021-06-08 | 2021-06-29 | 159436000 | 21 | 2021 | 06 | 29 | 20210629 | 2020 | 2021 | 1.0276 | 2021 | 0.97698 | 252007478.1124 | 407772897.3195 | 155765419.207 | 21 | 580 | 3.621%
2022-01-13 | 2018 | Defense Health Agency | 72481 | 91301 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G | W9126G-13-C-0004 | W9126G13C0004 | 72481,W9126G-13-C-0004 | 251330000 | 206136000 | 2016-11-26 | 2020-02-29 | -45194000 | 1190 | 2020 | 02 | 29 | 20200229 | 2013 | 2020 | 1.0993 | 2017 | 1.0507 | 276275812.2377 | 228790434.1426 | -47485378.0952 | 1190 | 1397 | 85.18%
2021-08-31 | 2019 | Army Active | 94608 |  | 2019-10-22 | 2019-12-02 | Fisher Sand & Gravel CO. | W912PL | W912PL20C0004 | W912PL20C0004 | 94608,W912PL20C0004 | 268073000 | 419850000 | 2021-01-08 | 2021-04-27 | 151777000 | 109 | 2021 | 04 | 27 | 20210427 | 2020 | 2021 | 1.0507 | 2021 | 1.0006 | 281664551.9782 | 433534187.8217 | 151869635.8435 | 109 | 403 | 27.05%
2021-12-31 | 2015 | Army Active | 70668 |  | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A | W9128A17C0005 | W9128A17C0005 | 70668,W9128A17C0005 | 284440000 | 334907000 | 2021-11-07 | 2022-03-11 | 50467000 | 124 | 2022 | 03 | 11 | 20220311 | 2017 | 2022 | 0.97698 | 2020 | 0.95701 | 277891541.6797 | 326189067.5946 | 48297525.9149 | 124 | 1501 | 8.261%
2021-12-31 | 2018 | Army Active | 70668 | 58857 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A | W9128A17C0005 | W9128A17C0005 | 70668,W9128A17C0005 | 284440000 | 334907000 | 2021-11-07 | 2022-03-11 | 50467000 | 124 | 2022 | 03 | 11 | 20220311 | 2017 | 2022 | 1.0507 | 2020 | 1.0276 | 298861374.1954 | 350720816.1236 | 51859441.9281 | 124 | 1501 | 8.261%
2021-12-31 | 2017 | Army Active | 70668 | 76593 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A | W9128A17C0005 | W9128A17C0005 | 70668,W9128A17C0005 | 284440000 | 334907000 | 2021-11-07 | 2022-03-11 | 50467000 | 124 | 2022 | 03 | 11 | 20220311 | 2017 | 2022 | 1.0276 | 2020 | 0.97698 | 292288023.105 | 341593157.5234 | 49305134.4183 | 124 | 1501 | 8.261%
2021-12-31 | 2019 | Army Active | 70668 | 76595 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A | W9128A17C0005 | W9128A17C0005 | 70668,W9128A17C0005 | 284440000 | 334907000 | 2021-11-07 | 2022-03-11 | 50467000 | 124 | 2022 | 03 | 11 | 20220311 | 2017 | 2022 | 1.0276 | 2020 | 1.0006 | 292288023.105 | 342785825.2234 | 50497802.1183 | 124 | 1501 | 8.261%
2022-01-13 | 2018 | Defense Health Agency | 91884 |  | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ | W912DQ-19-C-4011 | W912DQ19C4011 | 91884,W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25 | 5301000 | 12 | 2023 | 10 | 25 | 20231025 | 2019 | 2024 | 1.0507 | 2022 | 1.0006 | 311952057.1553 | 317256292.577 | 5304235.4217 | 12 | 1527 | 0.7859%
2022-01-13 | 2021 | Defense Health Agency | 91884 | 77168 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ | W912DQ-19-C-4011 | W912DQ19C4011 | 91884,W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25 | 5301000 | 12 | 2023 | 10 | 25 | 20231025 | 2019 | 2024 | 1.0507 | 2022 | 1.0276 | 311952057.1553 | 317399317.7743 | 5447260.619 | 12 | 1527 | 0.7859%
2022-01-13 | 2020 | Defense Health Agency | 91884 | 94335 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ | W912DQ-19-C-4011 | W912DQ19C4011 | 91884,W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25 | 5301000 | 12 | 2023 | 10 | 25 | 20231025 | 2019 | 2024 | 1.1914 | 2022 | 1.1519 | 353713776.0421 | 359819826.1627 | 6106050.1207 | 12 | 1527 | 0.7859%
2021-12-31 | 2019 | National Geospatial-Intelligence Agency | NGA-016B |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ | W912DQ-17-R-7000 | W912DQ17R7000 | NGA-016B,W912DQ-17-R-7000 | 315507977 | 345771897 | 2023-10-19 | 2024-06-20 | 30263920 | 245 | 2024 | 06 | 20 | 20240620 | 2019 | 2024 | 1.0507 | 2022 | 1.0276 | 331504526.7045 | 362603462.6777 | 31098935.9732 | 245 | 1675 | 14.63%
2021-12-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ | W912DQ-17-R-7000 | W912DQ17R7000 | NGA-016A,W912DQ-17-R-7000 | 319965869 | 336914829 | 2023-10-19 | 2024-06-20 | 16948960 | 245 | 2024 | 06 | 20 | 20240620 | 2019 | 2024 | 1.0507 | 2022 | 1.0276 | 336188438.0009 | 353605039.084 | 17416601.0831 | 245 | 1675 | 14.63%
2021-12-31 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM | W912UM17C0044 | W912UM17C0044 | 86689,W912UM17C0044 | 382205000 | 389665000 | 2020-11-12 | 2021-12-30 | 7460000 | 413 | 2021 | 12 | 30 | 20211230 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 382438275.6779 | 389726529.4429 | 7288253.765 | 413 | 1169 | 35.33%
2021-12-31 | 2020 | Army Active | 86689 | 91327 | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM | W912UM17C0044 | W912UM17C0044 | 86689,W912UM17C0044 | 382205000 | 389665000 | 2020-11-12 | 2021-12-30 | 7460000 | 413 | 2021 | 12 | 30 | 20211230 | 2017 | 2022 | 1.0006 | 2020 | 0.97698 | 382438275.6779 | 389726529.4429 | 7288253.765 | 413 | 1169 | 35.33%
2021-12-31 | 2018 | Army Active | 86689 | 91380 | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM | W912UM17C0044 | W912UM17C0044 | 86689,W912UM17C0044 | 382205000 | 389665000 | 2020-11-12 | 2021-12-30 | 7460000 | 413 | 2021 | 12 | 30 | 20211230 | 2017 | 2022 | 0.95701 | 2020 | 0.9382 | 365774781.3878 | 372773738.9503 | 6998957.5625 | 413 | 1169 | 35.33%
2021-12-31 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2019-02-26 | Yojin Const and Engr Co., Ltd. | W912UM | W912UM19C0007 | W912UM19C0007 | 86689,W912UM19C0007 | 382205000 | 389665000 | 2022-07-25 | 2023-02-05 | 7460000 | 195 | 2023 | 02 | 05 | 20230205 | 2019 | 2023 | 1.0751 | 2021 | 1.0507 | 410900071.3697 | 418738300.3512 | 7838228.9815 | 195 | 1245 | 15.66%
2021-12-31 | 2019 | Army Active | 86689 | 86877 | 2018-10-10 | 2019-02-26 | Yojin | W912UM | W912UM19C0007 | W912UM19C0007 | 86689,W912UM19C0007 | 382205000 | 389665000 | 2022-07-25 | 2023-02-05 | 7460000 | 195 | 2023 | 02 | 05 | 20230205 | 2019 | 2023 | 1.0276 | 2021 | 0.97698 | 392750470.6471 | 400038724.4122 | 7288253.765 | 195 | 1245 | 15.66%
2021-12-31 | 2018 | Army Active | 86689 | 91380 | 2018-07-27 | 2019-02-26 | Yojin Const and Engr Co., Ltd. | W912UM | W912UM19C0007 | W912UM19C0007 | 86689,W912UM19C0007 | 382205000 | 389665000 | 2022-07-25 | 2023-02-05 | 7460000 | 195 | 2023 | 02 | 05 | 20230205 | 2019 | 2023 | 1.0276 | 2021 | 1.0006 | 392750470.6471 | 400215023.7967 | 7464553.1496 | 195 | 1245 | 15.66%
2022-01-12 | 2020 | Navy Active | N476091900 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N62470 | N6247019D8025 N6247320F5226 | N6247019D8025 | N476091900,N6247019D8025 N6247320F5226 | 437309406 | 483621000 | 2023-11-30 | 2023-11-30 | 46311594 | 0 | 2023 | 11 | 30 | 20231130 | 2020 | 2024 | 1.0751 | 2022 | 1.0006 | 470141589.2938 | 516481449.1943 | 46339859.9005 | 0 | 1176 | 0%
2020-12-09 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR | W912DR-13-C-0005 | W912DR13C0005 | 24649,W912DR-13-C-0005 | 564589000 | 608357051 | 2015-09-15 | 2016-02-08 | 43768051 | 146 | 2016 | 02 | 08 | 20160208 | 2013 | 2016 | 1.1914 | 2015 | 1.1227 | 672629099.801 | 721766254.4725 | 49137154.6715 | 146 | 931 | 15.68%
2022-01-13 | 2018 | Defense Health Agency | 80906 | 81420 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080 | N40080-20-C0001 | N4008020C0001 | 80906,N40080-20-C0001 | 570000000 | 155650000 | 2026-03-01 | 2027-05-13 | -414350000 | 438 | 2027 | 05 | 13 | 20270513 | 2020 | 2027 | 1.0993 | 2024 | 1.0507 | 626575470.3995 | 191217537.6268 | -435357932.7727 | 438 | 2301 | 19.04%
2022-01-13 | 2020 | Defense Health Agency | 80906 | 85667 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080 | N40080-20-C0001 | N4008020C0001 | 80906,N40080-20-C0001 | 570000000 | 155650000 | 2026-03-01 | 2027-05-13 | -414350000 | 438 | 2027 | 05 | 13 | 20270513 | 2020 | 2027 | 1.0751 | 2024 | 1.0276 | 612794287.5701 | 187011899.8132 | -425782387.7569 | 438 | 2301 | 19.04%
2021-12-31 | 2016 | National Security Agency | 30583 |  | 2015-09-30 | 2016-06-17 | Clark Construction | W912DR | W912DR-16-C-0013 | W912DR16C0013 | 30583,W912DR-16-C-0013 | 616311000 | 711463223 | 2020-09-10 | 2022-02-01 | 95152223 | 509 | 2022 | 02 | 01 | 20220201 | 2016 | 2022 | 1.0006 | 2019 | 0.97698 | 616687160.3493 | 709648761.8952 | 92961601.5459 | 509 | 1546 | 32.92%
2021-12-31 | 2019 | National Security Agency | 35168 |  | 2018-10-04 | 2019-03-28 | Hensel-Phelps | W912DR | W912DR-19-C-0013 | W912DR19C0013 | 35168,W912DR-19-C-0013 | 650261000 | 675303918 | 2023-04-30 | 2023-05-09 | 25042918 | 9 | 2023 | 05 | 09 | 20230509 | 2019 | 2023 | 1.0507 | 2021 | 1.0006 | 683229841.2519 | 708288043.9909 | 25058202.739 | 9 | 1494 | 0.6024%
2022-01-13 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2015-08-19 | 2015-08-31 | FRG: Ed. Zublin AG / Gilbane Germany GmbH | W912GB | W912GB-10-C-0031 | W912GB10C0031 | 76007,W912GB-10-C-0031 | 913702000 | 913702000 | 2025-12-30 | 2027-09-30 | 0 | 639 | 2027 | 09 | 30 | 20270930 | 2015 | 2027 | 1.0276 | 2021 | 1.0006 | 938912077.37 | 938912077.37 | 0 | 639 | 3774 | 16.93%
2022-01-31 | 2020 | DLA Defense Energy Support Center | DESC20S1 |  | 2020-08-10 | 2021-04-14 | Rockford Corporation | W912WJ | W912WJ21C0009 | W912WJ21C0009 | DESC20S1,W912WJ21C0009 | 1162500000 | 1162500000 | 2022-08-15 | 2023-05-25 | 0 | 283 | 2023 | 05 | 25 | 20230525 | 2021 | 2023 | 1.0751 | 2022 | 1.0006 | 1249777823.3338 | 1249777823.3338 | 0 | 283 | 488 | 57.99%
[12 empty] | 39282690659.89 | 41154407792
2021-09-13 | 2021 | Marine Corps Active | M006811090A | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Marine Corps Active | M626131005 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2018 | Marine Corps Active | M626131006 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2017 | Marine Corps Active | M626131701 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2016 | Marine Corps Active | M62613604 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2015 | Marine Corps Active | M67400213 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2017 | Marine Corps Active | M67400807 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-10-14 | 2019 | Marine Corps Active | N41557735 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2021 | Marine Corps Active | N61159312 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Marine Corps Reserve | M68479102 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Marine Corps Reserve | M68479811 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Marine Corps Reserve | N83447091 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-10-14 | 2020 | Marine Corps Reserve | N83447181 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2020-12-09 | 2018 | National Security Agency | 34490 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-12-13 | 2018 | Navy Active | N00213211 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2021 | Navy Active | N00213211A | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2021 | Navy Active | N00246762 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-12-13 | 2019 | Navy Active | N32443256 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-10-14 | 2020 | Navy Active | N41557735A | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091901 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091902 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091907 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091908 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091914 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091917 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091920 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N476091921 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2019 | Navy Active | N60042117 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2018 | Navy Active | N61066604 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2019 | Navy Active | N62588312 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2020 | Navy Active | N628632001 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-12-13 | 2019 | Navy Active | N62863811 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2019 | Navy Active | N63005955U | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2021 | Navy Active | N63005964 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2016 | Navy Active | N63005976 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2019 | Navy Active | N66691144 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-12 | 2017 | Navy Active | N68469760 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2021-10-14 | 2019 | Navy Reserve | N00206493 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-07 | 2022 | Washington Headquarters Services | 90570 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-07 | 2020 | Washington Headquarters Services | 91531 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-07 | 2022 | Washington Headquarters Services | 95677 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2022-01-07 | 2022 | Washington Headquarters Services | 95696 | [14 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
Overrun (Underrun) Days = DAYS([Current Contract Completion Date],[Original Contract Completion Date])
Original Duration = DAYS([Original Contract Completion Date],[Contract Award Date])
Note on K1: Franklin, Paul B Jr CIV USN (USA): Cleaning steps: 1. Remove spaces within contract numbers 2. replace "/" with spaces 3. remove "-" instances 4. split on first space
Note on J89: Franklin, Paul B Jr CIV USN (USA): "/50815967" removed
Note on J142: Franklin, Paul B Jr CIV USN (USA): "/57804120" removed
Note on J419: Franklin, Paul B Jr CIV USN (USA): Removed "AWD"
Note on J420: Franklin, Paul B Jr CIV USN (USA): Removed "AWD"
Note on J1118: Franklin, Paul B Jr CIV USN (USA): Removed "/48719947" because separating contracts by project causes outliers.
Note on J1228: Franklin, Paul B Jr CIV USN (USA): Removed "P00002" because the expenses are broken into projects in accordance with 10 US Code 2851 section C2G, creating a large outlier

## Inflation Indices
Award Year | Index
2007 | 1.3029
2008 | 1.2826
2009 | 1.2581
2010 | 1.2319
2011 | 1.2082
2012 | 1.1914
2013 | 1.1743
2014 | 1.1519
2015 | 1.1227
2016 | 1.0993
2017 | 1.0751
2018 | 1.0507
2019 | 1.0276
2020 | 1.0006
2021 | 0.97698
2022 | 0.95701
2023 | 0.9382

## MilCon Contracts Analysis
Original Contract Amount | (Multiple Items) |  |  |  | Remove contracts with no contract number. Must filter out contracts with no starting amount (zero or blank) or blank current obligation amounts. Subset to contracts that should have ended before the reporting period (Jan 2022) since don't want to make incomplete contracts look like underruning contracts | [5 empty] | Schedule Analysis
Current Contract Obligation Amount | (Multiple Items)
|  |  | Original Contract Amount |  | 1.856% |  | Row Labels | Sum of Original Contract Amount | Sum of Current Contract Obligation Amount |  | Original Contract Amount | (Multiple Items) | Must filter out contracts with no starting amount or current obligation amount. Subset to contracts that should have ended before the reporting period (Jan 2022) since don't want to make incomplete contracts look like underruning contracts
Row Labels | Sum of Original Contract Amount (CY23$) | Sum of Final Contract Obligations (CY23$) | Sum of Original Contract Amount (CY23$) | Percent over/under budget | 5.793% | MILCON contracts end up exceeding their original contracted amounts by 5.79% on average. | 785
1234 | 40060624.8462 | 42971648.2053 | 40060624.8462 | 7.267% | 0% | Total original contract amount | 210054 | 15000000 | 16511000 |  | Row Labels | Max of Schedule % Overrun | Max of Price Overrun | Schedule Overrun % | Price Overrun %
92016 | 37825233.6909 | 37825233.6909 | 37825233.6909 | 0% | 17049515778.1934 | Total current contract amount | 1234 |  |  |  | 020143 | 29.5% | -15.88% | 29.5% | -15.88%
151541 | 2466218.7296 | 2095992.9032 | 2466218.7296 | -15.01% |  |  | DESC1606 | 36443425 | 39151158 | 7.43% | 080220 | 63.71% | 8.491% | 63.71% | 8.491%
188046 | 1690171.4495 | 1308323.6512 | 1690171.4495 | -22.59% |  |  | 40766 |  |  |  | 0P-926 | 46.97% | -41.23% | 46.97% | -41.23%
413180 | 3109046.8622 | 3106434.2686 | 3109046.8622 | -0.08403% |  |  | 500110 | 30000000 | 28775000 | -4.083% | 100040 | 0% | 0% | 0% | 0%
1875077 | 39777874.8072 | 40404705.401 | 39777874.8072 | 1.576% |  |  | 92016 |  |  |  | 1391 | 119.7% | -0.3708% | 119.7% | -0.3708%
20160008 | 32571729.0116 | 33395231.3229 | 32571729.0116 | 2.528% |  |  | 100040 | 36000000 | 36000000 | 0% | 14019 | 60.54% | -9.365% | 60.54% | -9.365%
42190131 | 7114783.1096 | 6962464.4677 | 7114783.1096 | -2.141% |  |  | 151541 |  |  |  | 14022 | 51.88% | 1.513% | 51.88% | 1.513%
140033D002 | 3063971.4379 | 3063971.4379 | 3063971.4379 | 0% |  |  | 270127 | 2400000 | 2030000 | -15.42% | 150035 | 142.8% | -7.311% | 142.8% | -7.311%
179997D002 | 6197402.1493 | 6066322.1945 | 6197402.1493 | -2.115% |  |  | 187596 |  |  |  | 15DISA02 | 156.4% | 37.74% | 156.4% | 37.74%
230113D | 34370595.809 | 36661123.8492 | 34370595.809 | 6.664% |  |  | 270203 | 11200000 | 12435000 | 11.03% | 160174 | 79.66% | -18.55% | 79.66% | -18.55%
230135D | 18387266.3775 | 19878175.7868 | 18387266.3775 | 8.108% |  |  | 188046 |  |  |  | 160193 | 21.13% | -7.892% | 21.13% | -7.892%
410818D002 | 11303502.5107 | 11081728.5691 | 11303502.5107 | -1.962% |  |  | 270233 | 1730000 | 1331000 | -23.06% | 171510 | 99.75% | -8.462% | 99.75% | -8.462%
411104A0001 | 3001831.0253 | 3001831.0253 | 3001831.0253 | 0% |  |  | 413180 |  |  |  | 17781 | 67.3% | 0% | 67.3% | 0%
411305C001 | 3001831.0253 | 2981314.4933 | 3001831.0253 | -0.6835% |  |  | ULYB049040 | 3025568 | 3022957 | -0.0863% | 17782 | 127.4% | 0% | 127.4% | 0%
8425A033 | 3001831.0253 | 2986199.3819 | 3001831.0253 | -0.5207% |  |  | 1875077 |  |  |  | 17866 | 28.61% | 3.929% | 28.61% | 3.929%
AGND | 32882916.3949 | 29638937.6669 | 32882916.3949 | -9.865% |  |  | 490601 | 37000000 | 37610000 | 1.649% | 17872 | 40.84% | 13.35% | 40.84% | 13.35%
C85148014 | 8930957.9548 | 7096839.1983 | 8930957.9548 | -20.54% |  |  | 2018586 |  |  |  | 18052 | 67.78% | 8.877% | 67.78% | 8.877%
DACA8701D0014 | 8220.7291 | 8220.7291 | 8220.7291 | 0% |  |  | 531201 | 11400000 | 10861000 | -4.728% | 18053 | 137.5% | 2.162% | 137.5% | 2.162%
DIOCB2076 | 64116018.7773 | 64116018.7773 | 64116018.7773 | 0% |  |  | 2271555 |  |  |  | 18054 | 332.9% | 3.214% | 332.9% | 3.214%
FA282318F4602 | 315790.2677 | 315790.2677 | 315790.2677 | 0% |  |  | 491201 | 12000000 | 13043000 | 8.692% | 190005 | 0% | -0.5207% | 0% | -0.5207%
FA282318F4654 | 13886.0636 | 13886.0636 | 13886.0636 | 0% |  |  | 3534532 |  |  |  | 190130 | 99.59% | -20.54% | 99.59% | -20.54%
FA571018P0325 | 2311542.0589 | 2459632.3895 | 2311542.0589 | 6.407% |  |  | TWLR159061 | 1205000 | 1205000 | 0% | 200129 | 0% | -7.892% | 0% | -7.892%
HQ003413F0027 | 16063823.3209 | 16063823.3209 | 16063823.3209 | 0% |  |  | 9752002 |  |  |  | 200151 | 88.16% | -0.8621% | 88.16% | -0.8621%
HQ003417D0006 | 1246253.1912 | 1246253.1912 | 1246253.1912 | 0% |  |  | 050220 | 2150000 | 1618000 | -24.74% | 20489 | 59% | 1.412% | 59% | 1.412%
HQ003418C0042 | 22818071.1733 | 22818071.1733 | 22818071.1733 | 0% |  |  | 10119102 |  |  |  | 21120 | 52.35% | 13.63% | 52.35% | 13.63%
M9001600004 | 19963317.7813 | 18666526.7784 | 19963317.7813 | -6.496% |  |  | XHEA189054 | 4329586 | 3350722 | -22.61% | 21372 | 69.95% | -5.342% | 69.95% | -5.342%
MWHL103001 | 36757179.6426 | 38254435.7273 | 36757179.6426 | 4.073% |  |  | 20160008 |  |  |  | 230113 | 171.5% | 6.664% | 171.5% | 6.664%
N3319116D1010 | 6553673.6439 | 13078877.366 | 6553673.6439 | 99.57% |  |  | 530129 | 31000000 | 31823000 | 2.655% | 230135 | 64.89% | 8.108% | 64.89% | 8.108%
N3319116D1035 | 3356415.8074 | 3572389.5447 | 3356415.8074 | 6.435% |  |  | 42190131 |  |  |  | 23051 | 429.7% | 11.86% | 429.7% | 11.86%
N3319119C0805 | 3501003.0049 | 3361918.1674 | 3501003.0049 | -3.973% |  |  | LKLW099101 | 6923749 | 6767841 | -2.252% | 23994 | 55.33% | 7.645% | 55.33% | 7.645%
N3943015D1634 | 10948581.9038 | 11142571.0737 | 10948581.9038 | 1.772% |  |  | 12345Brennan |  |  |  | 240149 | 7.173% | -6.496% | 7.173% | -6.496%
N4008010D0498 | 6207447.5796 | 6127968.7155 | 6207447.5796 | -1.28% |  |  | 270220 | 2000000 | 4144000 | 107.2% | 24649 | 15.68% | 7.411% | 15.68% | 7.411%
N4008013C0151 | 21945664.0876 | 25217047.5963 | 21945664.0876 | 14.91% |  |  | 140033D002 |  |  |  | 250065 | 103.3% | 1.713% | 103.3% | 1.713%
N4008015C0167 | 28829088.0215 | 32865881.0171 | 28829088.0215 | 14% |  |  | 411301 | 2850000 | 2850000 | 0% | 25047 | 111% | 10.06% | 111% | 10.06%
N4008016C0151 | 29750243.0367 | 30107481.3548 | 29750243.0367 | 1.201% |  |  | 179997D002 |  |  |  | 260222 | 98.27% | 45.79% | 98.27% | 45.79%
N4008016C0156 | 132109590.5405 | 152905063.463 | 132109590.5405 | 15.74% |  |  | 411300 | 6031000 | 5900000 | -2.172% | 260269 | 0% | -2.028% | 0% | -2.028%
N4008016C0161 | 18883103.8522 | 20551413.1023 | 18883103.8522 | 8.835% |  |  | 219995C001 |  |  |  | 260274 | 73.26% | -3.124% | 73.26% | -3.124%
N4008016C0172 | 32356577.1425 | 33589691.2615 | 32356577.1425 | 3.811% |  |  | 411508 | 9300000 | 7792000 | -16.22% | 26170 | 103.5% | 34.77% | 103.5% | 34.77%
N4008017C0014 | 11700070.5818 | 12960924.9073 | 11700070.5818 | 10.78% |  |  | 219995C003 |  |  |  | 26542 | 68.18% | 7.933% | 68.18% | 7.933%
N4008017C0024 | 1351372.6657 | 1406862.5872 | 1351372.6657 | 4.106% |  |  | 411510 | 15735000 | 8333000 | -47.04% | 270127 | 1.562% | -15.01% | 1.562% | -15.01%
N4008017C0030 | 23503348.6226 | 20895322.316 | 23503348.6226 | -11.1% |  |  | 230113D |  |  |  | 270132 | 32.7% | 3.729% | 32.7% | 3.729%
N4008017C0039 | 28315396.3965 | 33638318.488 | 28315396.3965 | 18.8% |  |  | 230113 | 30615000 | 32795000 | 7.121% | 270233 | -65.36% | -22.59% | -65.36% | -22.59%
N4008017D0009 | 11746193.4339 | 11746193.4339 | 11746193.4339 | 0% |  |  | 230135D |  |  |  | 27532 | 17.15% | 13.03% | 17.15% | 13.03%
N4008017D0012 | 2824229.1113 | 2748187.3671 | 2824229.1113 | -2.692% |  |  | 230135 | 17500000 | 18990000 | 8.514% | 290109 | 28.35% | -22.13% | 28.35% | -22.13%
N4008018C0006 | 55217486.2821 | 54846259.8453 | 55217486.2821 | -0.6723% |  |  | 230139D |  |  |  | 290186 | 29.46% | -16.81% | 29.46% | -16.81%
N4008018C0008 | 39186942.1038 | 37793091.8977 | 39186942.1038 | -3.557% |  |  | 230139 | 3200000 | 2908000 | -9.125% | 300031 | 0% | 31.16% | 0% | 31.16%
N4008018C0034 | 24208149.5622 | 22906355.5075 | 24208149.5622 | -5.378% |  |  | 410818D002 |  |  |  | 30439 | 75.1% | 0% | 75.1% | 0%
N4008018C0311 | 43015696.314 | 42808819.7632 | 43015696.314 | -0.4809% |  |  | 410818 | 11000000 | 10773000 | -2.064% | 31066 | 16.65% | 8.661% | 16.65% | 8.661%
N4008018C2018 | 1566441.693 | 1566441.693 | 1566441.693 | 0% |  |  | 411104A0001 |  |  |  | 31067 | 30.05% | 1.439% | 30.05% | 1.439%
N4008019C2015 | 48213548.5729 | 52668265.8144 | 48213548.5729 | 9.24% |  |  | 411104 | 3000000 | 3000000 | 0% | 31934 | 12.47% | 7.579% | 12.47% | 7.579%
N4008019D0015 | 14532193.8643 | 14160967.4275 | 14532193.8643 | -2.555% |  |  | 411305C001 |  |  |  | 32122 | 126.4% | 37.71% | 126.4% | 37.71%
N4008019D0018 | 3041855.439 | 3043809.3944 | 3041855.439 | 0.06424% |  |  | 411503 | 3000000 | 2979000 | -0.7% | 33003 | 142.3% | 11.59% | 142.3% | 11.59%
N40084USACE01 | 9299699.7929 | 9299699.7929 | 9299699.7929 | 0% |  |  | 46086C |  |  |  | 33005 | 133.3% | 4.311% | 133.3% | 4.311%
N40084USACE02 | 9149671.4869 | 9149671.4869 | 9149671.4869 | 0% |  |  | 361811 | 91000000 | 68602000 | -24.61% | 33017 | 44.08% | 25.46% | 44.08% | 25.46%
N4008510D0261 | 8767.0724 | 8714.4368 | 8767.0724 | -0.6004% |  |  | 8425A033 |  |  |  | 33019 | 133.3% | 4.82% | 133.3% | 4.82%
N4008510D5330 | 11598.3219 | 14304.2925 | 11598.3219 | 23.33% |  |  | 190005 | 3000000 | 2984000 | -0.5333% | 350200 | 20.14% | 21.77% | 20.14% | 21.77%
N4008510D5331 | 36404775.3375 | 44987051.8425 | 36404775.3375 | 23.57% |  |  | A013650 |  |  |  | 36977 | 40.64% | 4.287% | 40.64% | 4.287%
N4008510D5333 | 137284.2251 | 140121.0157 | 137284.2251 | 2.066% |  |  | 200101 | 29000000 | 28834954 | -0.5691% | 371301 | 37.34% | 7.371% | 37.34% | 7.371%
N4008514D1322 | 10113.552 | 10545.8156 | 10113.552 | 4.274% |  |  | AC20C0014S |  |  |  | 380116 | 0% | -9.865% | 0% | -9.865%
N4008514D7742 | 7160255.045 | 7541487.5852 | 7160255.045 | 5.324% |  |  | 010908 | 12000000 | 11894000 | -0.8833% | 410818 | 4.117% | -1.962% | 4.117% | -1.962%
N4008515C8739 | 38526726.6496 | 63102596.2902 | 38526726.6496 | 63.79% |  |  | AC21C0004S |  |  |  | 411104 | 156.9% | 0% | 156.9% | 0%
N4008515C9610 | 2232994.1226 | 2198917.2111 | 2232994.1226 | -1.526% |  |  | 011801 | 34000000 | 34880000 | 2.588% | 411300 | 29.52% | -2.115% | 29.52% | -2.115%
N4008516C3013 | 38168339.4442 | 38400544.3511 | 38168339.4442 | 0.6084% |  |  | AGND |  |  |  | 411301 | 213.3% | 0% | 213.3% | 0%
N4008516C3037 | 51495214.9603 | 63062236.5664 | 51495214.9603 | 22.46% |  |  | 380116 | 32000000 | 28758000 | -10.13% | 411503 | 125.4% | -0.6835% | 125.4% | -0.6835%
N4008516C5505 | 9664651.8171 | 9664651.8171 | 9664651.8171 | 0% |  |  | C85148014 |  |  |  | 43010 | 45.75% | 48.9% | 45.75% | 48.9%
N4008516C5506 | 31395828.0879 | 30561571.5448 | 31395828.0879 | -2.657% |  |  | 190130 | 8500000 | 6667000 | -21.56% | 43055 | 61.53% | 11.55% | 61.53% | 11.55%
N4008516D5524 | 2082489.2549 | 2016723.4221 | 2082489.2549 | -3.158% |  |  | CTR054747 |  |  |  | 440064 | 64.59% | 2.844% | 64.59% | 2.844%
N4008516D6300 | 6073385.042 | 6815305.8432 | 6073385.042 | 12.22% |  |  | 040037 | 18100000 | 17120000 | -5.414% | 460115 | 0% | -12.83% | 0% | -12.83%
N4008516D6303 | 2593129.9097 | 2556107.3271 | 2593129.9097 | -1.428% |  |  | DACA8701D0014 |  |  |  | 465001 | 0% | 19.3% | 0% | 19.3%
N4008517C0307 | 50357714.4282 | 53614150.7424 | 50357714.4282 | 6.467% |  |  | 86711 | 8000 | 8000 | 0% | 470035 | 51.96% | -4.256% | 51.96% | -4.256%
N4008517C5056 | 20347995.5804 | 21165958.1257 | 20347995.5804 | 4.02% |  |  | DIOCB2076 |  |  |  | 47942 | 18.87% | 3.877% | 18.87% | 3.877%
N4008517C8315 | 59987185.3646 | 60380425.2289 | 59987185.3646 | 0.6555% |  |  | MSET143006 | 55113676 | 55113676 | 0% | 490601 | 141.7% | 1.576% | 141.7% | 1.576%
N4008517C8327 | 84189334.4906 | 85596106.7576 | 84189334.4906 | 1.671% |  |  | MSET153501 | 23292923 | 23292923 | 0% | 511503 | 52.99% | 12.69% | 52.99% | 12.69%
N4008517D0358 | 2805371.4987 | 2735495.3014 | 2805371.4987 | -2.491% |  |  | MSET153503 | 22219318 | 22219318 | 0% | 52332 | 4.576% | 7.772% | 4.576% | 7.772%
N4008517D0362 | 7260.3435 | 7244.9296 | 7260.3435 | -0.2123% |  |  | MSET153504 | 33031258 | 33031258 | 0% | 530041 | 94.39% | 8.195% | 94.39% | 8.195%
N4008517D5038 | 2167189.7087 | 2205212.9016 | 2167189.7087 | 1.754% |  |  | MSET153505 | 11543865 | 11543865 | 0% | 530129 | 50.62% | 2.528% | 50.62% | 2.528%
N4008517D5048 | 1024433.4125 | 864129.195 | 1024433.4125 | -15.65% |  |  | MSET153506 | 16724478 | 16724478 | 0% | 53530 | 8.108% | 2.003% | 8.108% | 2.003%
N4008517D5049 | 3553410.1529 | 3555411.3736 | 3553410.1529 | 0.05632% |  |  | MSET153508 | 36198139 | 36198139 | 0% | 53542 | 2.6% | 1.895% | 2.6% | 1.895%
N4008518C0610 | 39058756.5896 | 37891044.3207 | 39058756.5896 | -2.99% |  |  | MSET153509 | 6211718 | 6211718 | 0% | 53712A | 0.335% | 3.194% | 0.335% | 3.194%
N4008518C0614 | 149694.413 | 152834.3283 | 149694.413 | 2.098% |  |  | MSET153513 | 22251003 | 22251003 | 0% | 55112 | 70.54% | 4.204% | 70.54% | 4.204%
N4008518C0637 | 36774532.755 | 33330431.9586 | 36774532.755 | -9.365% |  |  | MSET153514 | 39101561 | 39101561 | 0% | 57442 | 19.1% | 4.282% | 19.1% | 4.282%
N4008518C1107 | 76758956.8691 | 75072928.4432 | 76758956.8691 | -2.197% |  |  | F9K3CE1084MW01 |  |  |  | 58395 | 50% | -2.346% | 50% | -2.346%
N4008518C1116 | 50683711.7439 | 48942649.7492 | 50683711.7439 | -3.435% |  |  | XHEA189054 | 4329586 | 3350722 | -22.61% | 59044 | 127% | 19.39% | 127% | 19.39%
N4008518C1134 | 119779906.6878 | 116306788.1915 | 119779906.6878 | -2.9% |  |  | FA282318F4602 |  |  |  | 59990 | 116.9% | 8.292% | 116.9% | 8.292%
N4008518C1137 | 52072.7384 | 50857.9974 | 52072.7384 | -2.333% |  |  | FTFA033003 | 300552 | 300552 | 0% | 60272 | 59.15% | 2.045% | 59.15% | 2.045%
N4008518C6101 | 6589.9963 | 6577.9889 | 6589.9963 | -0.1822% |  |  | FA282318F4654 |  |  |  | 60743 | 62.41% | 6.779% | 62.41% | 6.779%
N4008518C6118 | 7808.8094 | 7558.0771 | 7808.8094 | -3.211% |  |  | FTFA033003 | 13216 | 13216 | 0% | 60815 | 24.26% | 18.32% | 24.26% | 18.32%
N4008518C8707 | 74216260.6043 | 71157394.7895 | 74216260.6043 | -4.122% |  |  | FA557521C0007 |  |  |  | 60821 | 35.45% | 2.929% | 35.45% | 2.929%
N4008518C8719 | 31956018.2632 | 32309233.7138 | 31956018.2632 | 1.105% |  |  | QUUG064001 | 1336116 | 1336116 | 0% | 60833 | 16.52% | 1.232% | 16.52% | 1.232%
N4008518D1125 | 21184.9222 | 20918.2072 | 21184.9222 | -1.259% |  |  | FA571018P0325 |  |  |  | 61064 | 48.28% | 2.432% | 48.28% | 2.432%
N4008518R1123 | 2703453.508 | 3035656.1414 | 2703453.508 | 12.29% |  |  | ASVF164000 | 2200000 | 2348000 | 6.727% | 61065 | 45.98% | 10.4% | 45.98% | 10.4%
N4008519C9017 | 37957161.4311 | 37200003.7008 | 37957161.4311 | -1.995% |  |  | HQ003413C0133 |  |  |  | 61772 | 133.3% | 4.583% | 133.3% | 4.583%
N4008519C9021 | 22394293.6561 | 22798540.2341 | 22394293.6561 | 1.805% |  |  | 80001 | 9669575 |  |  | 61874 | 83.49% | 31.57% | 83.49% | 31.57%
N4008519C9053 | 3336588.4229 | 3621762.3703 | 3336588.4229 | 8.547% |  |  | HQ003413F0027 |  |  |  | 630 | 32.74% | -22.35% | 32.74% | -22.35%
N4008519C9070 | 36902852.9242 | 33452748.4657 | 36902852.9242 | -9.349% |  |  | 80001A | 13679273 | 13679273 | 0% | 63019 | 8.182% | 7.073% | 8.182% | 7.073%
N4008519C9126 | 23940818.3178 | 24556193.6779 | 23940818.3178 | 2.57% |  |  | HQ003417D0006 |  |  |  | 63027 | 49.81% | 2.624% | 49.81% | 2.624%
N4008519D9066 | 31931367.0017 | 30687674.3686 | 31931367.0017 | -3.895% |  |  | 91474A | 1186116 | 1186116 | 0% | 63035 | 61.2% | 49.32% | 61.2% | 49.32%
N4008520D0034 | 33592401.8039 | #VALUE! | 33592401.8039 |  |  |  | HQ003418C0042 |  |  |  | 63049 | 16.09% | 4.396% | 16.09% | 4.396%
N4008520D0036 | 11665.1154 | 11916.1986 | 11665.1154 | 2.152% |  |  | 80007 | 21716999 | 21716999 | 0% | 63051 | 1.402% | 4.427% | 1.402% | 4.427%
N4019216D2704 | 2946165.4241 | 2526909.6909 | 2946165.4241 | -14.23% |  |  | HQ003419C0043 |  |  |  | 63052 | 12.23% | 14.06% | 12.23% | 14.06%
N4019218C1300 | 22533328.0676 | 22533328.0676 | 22533328.0676 | 0% |  |  | 80011 | 15100000 |  |  | 634 | 18.22% | 16.88% | 18.22% | 16.88%
N4425512C3008 | 90638904.2182 | 92421896.1708 | 90638904.2182 | 1.967% |  |  | LA21C116 |  |  |  | 63711 | 64.3% | 32.63% | 64.3% | 32.63%
N4425516C7002 | 21922446.6775 | 24720577.3445 | 21922446.6775 | 12.76% |  |  | 220304 | 16500000 | 17876000 | 8.339% | 63831 | 14.76% | 15.52% | 14.76% | 15.52%
N4425516C7004 | 35227831.7542 | 35398045.3058 | 35227831.7542 | 0.4832% |  |  | M9001600004 |  |  |  | 63850 | 48.13% | 20.27% | 48.13% | 20.27%
N4425516C7005 | 34894757.4252 | 38444025.1865 | 34894757.4252 | 10.17% |  |  | 240149 | 19000000 | 17704000 | -6.821% | 64156 | 53.28% | 23.16% | 53.28% | 23.16%
N4425517C8002 | 18566591.8357 | 18959131.6501 | 18566591.8357 | 2.114% |  |  | MDISAB21C0012 |  |  |  | 64484 | 29.38% | 16.18% | 29.38% | 16.18%
N4425517D4007 | 10549037.396 | 10965211.8066 | 10549037.396 | 3.945% |  |  | 180202 | 12000000 | 13716000 | 14.3% | 64669 | 57.12% | 13.04% | 57.12% | 13.04%
N4425517D4014 | 7310283.351 | 7259252.2236 | 7310283.351 | -0.6981% |  |  | MWHL103001 |  |  |  | 65052 | 3.44% | 2.2% | 3.44% | 2.2%
N4425517D4032 | 44446978.223 | 46138716.4238 | 44446978.223 | 3.806% |  |  | 18052 | 7566000 | 8257000 | 9.133% | 65266 | 17.83% | 1.591% | 17.83% | 1.591%
N4425519C0003 | 47249668.086 | 48775707.2792 | 47249668.086 | 3.23% |  |  | 18053 | 16095000 | 16448000 | 2.193% | 65272 | 47.17% | 2.854% | 47.17% | 2.854%
N6247011D1010 | 16543.7909 | 17739.2773 | 16543.7909 | 7.226% |  |  | 18054 | 7085000 | 7316000 | 3.26% | 653 | 103.6% | 16.99% | 103.6% | 16.99%
N6247016C6003 | 10149423.3653 | 9454771.7564 | 10149423.3653 | -6.844% |  |  | N3319116D1010 |  |  |  | 65392 | 41.73% | 2.316% | 41.73% | 2.316%
N6247017C5003 | 22121873.7813 | 23122484.1231 | 22121873.7813 | 4.523% |  |  | N62995737 | 6096000 | 12446000 | 104.2% | 65394 | 13.4% | 1.848% | 13.4% | 1.848%
N6247017C5005 | 55873938.094 | 77843338.758 | 55873938.094 | 39.32% |  |  | N3319116D1035 |  |  |  | 65395 | 53.99% | 1.551% | 53.99% | 1.551%
N6247018R4005 | 14536530.2989 | 14536530.2989 | 14536530.2989 | 0% |  |  | CADJ170001 | 3194454 | 3410296 | 6.757% | 65396 | 17.31% | 6.947% | 17.31% | 6.947%
N6247019C5006 | 10420801.7238 | 3979587.6389 | 10420801.7238 | -61.81% |  |  | CADJ170002 | 4911856 | 5442283 | 10.8% | 65397 | 13.4% | 0.1277% | 13.4% | 0.1277%
N6247019C5009 | 16160925.8169 | 16389064.9749 | 16160925.8169 | 1.412% |  |  | N3319119C0805 |  |  |  | 65678 | 2.419% | 4.819% | 2.419% | 4.819%
N6247019D5002 | 11627193.719 | 12165508.4408 | 11627193.719 | 4.63% |  |  | N63005985 | 3407000 | 3268000 | -4.08% | 65699 | 52.44% | 8.442% | 52.44% | 8.442%
N62473 | 21543379.6278 | 22937235.2356 | 21543379.6278 | 6.47% |  |  | N3319119D0801 |  |  |  | 657 | 33.41% | 4.857% | 33.41% | 4.857%
N6247309D1655 | 34254.2385 | 32997.7898 | 34254.2385 | -3.668% |  |  | N62863605 | 7127000 | 9126000 | 28.05% | 65731 | 53.28% | 327.7% | 53.28% | 327.7%
N6247310D5406 | 23110.1981 | 23785.3469 | 23110.1981 | 2.921% |  |  | N3943015D1634 |  |  |  | 659 | 11.58% | 10.51% | 11.58% | 10.51%
N6247310D5411 | 21390407.1553 | 25448364.5566 | 21390407.1553 | 18.97% |  |  | DESC1404 | 9960000 | 10140442 | 1.812% | 66227 | 68.55% | 4.728% | 68.55% | 4.728%
N6247314D0039 | 17557304.2337 | 16230268.9517 | 17557304.2337 | -7.558% |  |  | N4008010D0498 |  |  |  | 66315 | 57.11% | 21.94% | 57.11% | 21.94%
N6247314D0061 | 39047.8971 | 37383.1994 | 39047.8971 | -4.263% |  |  | 80306 | 5286000 | 5217000 | -1.305% | 66362 | 54.5% | 6.747% | 54.5% | 6.747%
N6247314D0068 | 15707880.6699 | 18990944.9347 | 15707880.6699 | 20.9% |  |  | N4008013C0151 |  |  |  | 66443 | 24.96% | 6.05% | 24.96% | 6.05%
N6247315C1604 | 46970340.9262 | 50875023.1235 | 46970340.9262 | 8.313% |  |  | 71408 | 18688000 | 21664000 | 15.92% | 66444 | 25.71% | 1.941% | 25.71% | 1.941%
N6247315C1609 | 55848.4292 | 54783.0272 | 55848.4292 | -1.908% |  |  | 77154 | 66430000 | 74182000 | 11.67% | 66588 | 28.91% | 5.562% | 28.91% | 5.562%
N6247315D2403 | 8131092.9637 | 8261102.4947 | 8131092.9637 | 1.599% |  |  | N4008015C0167 |  |  |  | 66597 | 31.95% | 2.761% | 31.95% | 2.761%
N6247315D2404 | 12097849.3299 | 11484377.4209 | 12097849.3299 | -5.071% |  |  | N61151287 | 25679000 | 29521000 | 14.96% | 66813 | 35% | 4.992% | 35% | 4.992%
N6247315D2405 | 13952.5646 | 13665.659 | 13952.5646 | -2.056% |  |  | N4008016C0151 |  |  |  | 67039 | 13.39% | 3.284% | 13.39% | 3.284%
N6247315D2426 | 34272.9234 | 41240.5019 | 34272.9234 | 20.33% |  |  | M00264677 | 27064000 | 27404000 | 1.256% | 674 | 17.72% | 7.085% | 17.72% | 7.085%
N6247315D2427 | 28674159.3192 | 31769524.2762 | 28674159.3192 | 10.79% |  |  | N4008016C0156 |  |  |  | 67567 | 144.8% | 4.443% | 144.8% | 4.443%
N6247315D2428 | 103378.3571 | 101118.2994 | 103378.3571 | -2.186% |  |  | N61152621 | 120181000 | 139973000 | 16.47% | 68526 | 26.19% | 14.63% | 26.19% | 14.63%
N6247315R00010008 | 58156619.3919 | 62806316.1772 | 58156619.3919 | 7.995% |  |  | N4008016C0161 |  |  |  | 69251 | 39.17% | 0.5833% | 39.17% | 0.5833%
N6247316C0601 | 14233156.475 | 16493214.188 | 14233156.475 | 15.88% |  |  | DESC1507 | 17178089 | 18765895 | 9.243% | 69257 | 35.65% | 14.09% | 35.65% | 14.09%
N6247316D1861 | 10029399.8399 | 11750614.9949 | 10029399.8399 | 17.16% |  |  | N4008016C0172 |  |  |  | 69261 | 12.45% | 3.924% | 12.45% | 3.924%
N6247316D1862 | 2716721.3416 | 2649476.4817 | 2716721.3416 | -2.475% |  |  | 80306 | 29435000 | 30582000 | 3.897% | 69275 | 9.791% | 4.575% | 9.791% | 4.575%
N6247316D1884 | 34185605.6491 | 36264873.9393 | 34185605.6491 | 6.082% |  |  | N4008017C0014 |  |  |  | 69277 | 30.41% | 3.32% | 30.41% | 3.32%
N6247316D1887 | 66252348.1595 | 64076265.5228 | 66252348.1595 | -3.285% |  |  | M00264635 | 10883000 | 12110000 | 11.27% | 69278 | 25% | 2.008% | 25% | 2.008%
N6247317C0808 | 66161356.5813 | 81155966.4574 | 66161356.5813 | 22.66% |  |  | N4008017C0024 |  |  |  | 69287 | 58.72% | 27.45% | 58.72% | 27.45%
N6247317C0815 | 3163953.6637 | 2994790.813 | 3163953.6637 | -5.347% |  |  | M67029007 | 1257000 | 1311000 | 4.296% | 69302 | 76.44% | 9.986% | 76.44% | 9.986%
N6247317C0830 | 39882.1573 | 38271.922 | 39882.1573 | -4.037% |  |  | N4008017C0030 |  |  |  | 69366 | 52.85% | 22.17% | 52.85% | 22.17%
N6247317C3403 | 42852597.022 | 46282084.8767 | 42852597.022 | 8.003% |  |  | N61151190 | 21862000 | 19324000 | -11.61% | 69382 | 22.09% | 9.46% | 22.09% | 9.46%
N6247317D0818 | 15600.8886 | 15539.3391 | 15600.8886 | -0.3945% |  |  | N4008017C0039 |  |  |  | 69445 | 47.8% | 9.575% | 47.8% | 9.575%
N6247317D0819 | 49567.5323 | 48323.1195 | 49567.5323 | -2.511% |  |  | 80906 | 26338000 | 31518000 | 19.67% | 69446 | 21.45% | 6.858% | 21.45% | 6.858%
N6247317D0820 | 34592226.9112 | 34599231.1836 | 34592226.9112 | 0.02025% |  |  | N4008017D0009 |  |  |  | 69447 | 0.2924% | 3.096% | 0.2924% | 3.096%
N6247317D0821 | 71171.5249 | 107497.9302 | 71171.5249 | 51.04% |  |  | AJXF093000 | 11179388 | 11179388 | 0% | 69449 | 16.87% | 20.98% | 16.87% | 20.98%
N6247317D4628 | 15089148.2607 | 15357817.1327 | 15089148.2607 | 1.781% |  |  | N4008017D0012 |  |  |  | 69458 | 102.7% | 15.41% | 102.7% | 15.41%
N6247317D4635 | 22347024.4637 | 22031832.2061 | 22347024.4637 | -1.41% |  |  | N47608421 | 2627000 | 2553000 | -2.817% | 69493 | 27.99% | 14.34% | 27.99% | 14.34%
N6247318C1017 | 93449.3412 | 90751.6958 | 93449.3412 | -2.887% |  |  | N4008018C0005 |  |  |  | 69558 | 20.56% | 12.64% | 20.56% | 12.64%
N6247318C2202 | 28230232.7446 | 28290036.4936 | 28230232.7446 | 0.2118% |  |  | N68469275 | 70927000 | 81951000 | 15.54% | 69559 | 42.97% | 12.67% | 42.97% | 12.67%
N6247318C2205 | 16469737.1696 | 16314642.5666 | 16469737.1696 | -0.9417% |  |  | N4008018C0006 |  |  |  | 69560 | 60.44% | 19.07% | 60.44% | 19.07%
N6247318C4605 | 161532660.4769 | 170762484.0725 | 161532660.4769 | 5.714% |  |  | AM00021 | 52553000 | 52182000 | -0.706% | 69573 | 54.55% | 9.071% | 54.55% | 9.071%
N6247318D0820 | 99921.659 | 95684.0742 | 99921.659 | -4.241% |  |  | N4008018C0008 |  |  |  | 69758 | 171.3% | 20.8% | 171.3% | 20.8%
N6247318D5817 | 3385912.7975 | 3324875.5667 | 3385912.7975 | -1.803% |  |  | N61151163 | 37296000 | 35903000 | -3.735% | 69759 | 16.28% | 0.6241% | 16.28% | 0.6241%
N6247318D5850 | 24788136.4788 | 24319554.9201 | 24788136.4788 | -1.89% |  |  | N4008018C0034 |  |  |  | 70354 | 103.8% | 29.53% | 103.8% | 29.53%
N6247318D5853 | 76201198.5431 | 84022763.7178 | 76201198.5431 | 10.26% |  |  | M00264588 | 23040000 | 21739000 | -5.647% | 70677 | 31.31% | 10.51% | 31.31% | 10.51%
N6247318D5855 | 43126972.443 | 42008290.0809 | 43126972.443 | -2.594% |  |  | N4008018C0311 |  |  |  | 71057 | 35.62% | 12.22% | 35.62% | 12.22%
N6247318D5860 | 1927760.9737 | 2229945.2969 | 1927760.9737 | 15.68% |  |  | N47608975 | 40940000 | 40736000 | -0.4983% | 71224 | 40.33% | 26.09% | 40.33% | 26.09%
N6247318D5862 | 23635623.75 | 22725068.3389 | 23635623.75 | -3.852% |  |  | N4008018C2018 |  |  |  | 71317 | 60% | 17.78% | 60% | 17.78%
N6247319C1208 | 49040759.4384 | 102196163.0375 | 49040759.4384 | 108.4% |  |  | AJXF173021 | 1490854 | 1490854 | 0% | 71325 | 51.58% | 3.992% | 51.58% | 3.992%
N6247319C2425 | 4961210.0111 | 7140539.3355 | 4961210.0111 | 43.93% |  |  | N4008019C0008 |  |  |  | 71408 | 53.44% | 14.91% | 53.44% | 14.91%
N6247319C5826 | 11671380.1379 | 12727024.0485 | 11671380.1379 | 9.045% |  |  | AJXF173021 | 220000000 | 220000000 | 0% | 71503 | 102.9% | -75.3% | 102.9% | -75.3%
N6247319D2428 | 13918721.9553 | 13893706.6967 | 13918721.9553 | -0.1797% |  |  | N4008019C0023 |  |  |  | 71509 | 22.5% | -9.349% | 22.5% | -9.349%
N6247319D2430 | 3417768.1228 | 3534839.5328 | 3417768.1228 | 3.425% |  |  | M00264542 | 21419000 | 20882000 | -2.507% | 71725 | 29.37% | 3.63% | 29.37% | 3.63%
N6247813D4007 | 3154707.6343 | 3010761.6061 | 3154707.6343 | -4.563% |  |  | N4008019C2015 |  |  |  | 72419 | 74.15% | 8.655% | 74.15% | 8.655%
N6247814D4001 | 9365654.3997 | 10047974.9148 | 9365654.3997 | 7.285% |  |  | N47608265 | 46919000 | 51371000 | 9.489% | 72481 | 127.3% | 39.16% | 127.3% | 39.16%
N6247819C1515 | 75218643.6622 | 73100351.5686 | 75218643.6622 | -2.816% |  |  | N4008019D0015 |  |  |  | 72738 | 29.2% | 0.3895% | 29.2% | 0.3895%
N6274210D13070002 | 108468749.3085 | 115071707.025 | 108468749.3085 | 6.087% |  |  | M00264724 | 14142000 | 13771000 | -2.623% | 72742 | 24.1% | 0% | 24.1% | 0%
N6274210D1307JQ01 | 100948741.3681 | 103652528.999 | 100948741.3681 | 2.678% |  |  | N4008019D0018 |  |  |  | 72754 | 113.3% | 38.61% | 113.3% | 38.61%
N6274214C1300 | 20411093.782 | 18837180.0329 | 20411093.782 | -7.711% |  |  | M00264733 | 3040000 | 3042000 | 0.06579% | 72808 | 174.3% | 6.47% | 174.3% | 6.47%
N6274214C1304 | 39128942.1995 | 42023623.2777 | 39128942.1995 | 7.398% |  |  | N4008020C0001 |  |  |  | 73018 | 23.35% | 3.956% | 23.35% | 3.956%
N6274214MP00028 | 10894363.7128 | 10162259.7421 | 10894363.7128 | -6.72% |  |  | 80906 | 1140000000 | 311300000 | -72.69% | 73021 | 15.37% | 2.847% | 15.37% | 2.847%
N6274215C1301 | 114112847.9637 | 103629363.1806 | 114112847.9637 | -9.187% |  |  | N4008021C0005 |  |  |  | 73375 | 25.08% | 0.4877% | 25.08% | 0.4877%
N6274215C1305 | 57335969.2491 | 58708184.6713 | 57335969.2491 | 2.393% |  |  | M00264719 | 61810155 | 70319000 | 13.77% | 74618 | 44.76% | 1.084% | 44.76% | 1.084%
N6274215C1308 | 48077070.7433 | 52352852.5605 | 48077070.7433 | 8.894% |  |  | N4008419D0075 |  |  |  | 74732 | 95.49% | 9.587% | 95.49% | 9.587%
N6274216C1309 | 29089960.0045 | 32016287.8038 | 29089960.0045 | 10.06% |  |  | N610542101 | 1382000 | 2107000 | 52.46% | 74813 | 52.09% | 32.82% | 52.09% | 32.82%
N6274216C1312 | 87634823.9495 | 91453071.1504 | 87634823.9495 | 4.357% |  |  | N4008420D0071 |  |  |  | 74989 | 44.21% | 2.611% | 44.21% | 2.611%
N6274216C1317 | 22863409.1383 | 18288657.2636 | 22863409.1383 | -20.01% |  |  | M626131010U | 0 | 986000 |  | 75660 | 70.32% | 3.731% | 70.32% | 3.731%
N6274216C1325 | 55603626.3495 | 54997371.9095 | 55603626.3495 | -1.09% |  |  | N4008420D0073 |  |  |  | 75661 | 0% | 0% | 0% | 0%
N6274217C1307 | 77936682.6019 | 76898815.5532 | 77936682.6019 | -1.332% |  |  | M626132001 | 18797000 | 17902000 | -4.761% | 75718 | 23.44% | 26.61% | 23.44% | 26.61%
N6274217C1313 | 29003553.6307 | 30424739.9186 | 29003553.6307 | 4.9% |  |  | N4008421C8000 |  |  |  | 76007 | 37.36% | 9.458% | 37.36% | 9.458%
N6274217C1319 | 132945183.1495 | 109951157.4955 | 132945183.1495 | -17.3% |  |  | M67400901U | 3417000 | 3255000 | -4.741% | 76364 | 90.15% | 13.84% | 90.15% | 13.84%
N6274217C1320 | 26658701.6647 | 31729863.9275 | 26658701.6647 | 19.02% |  |  | N40084USACE01 |  |  |  | 76365 | 16.52% | 4.855% | 16.52% | 4.855%
N6274217C1325 | 50866226.1791 | 48472966.4202 | 50866226.1791 | -4.705% |  |  | N61056512 | 9050000 | 9050000 | 0% | 76366 | 11.97% | 14.65% | 11.97% | 14.65%
N6274218C1300 | 101662670.4508 | 96442486.2978 | 101662670.4508 | -5.135% |  |  | N40084USACE02 |  |  |  | 76367 | 76.16% | -8.224% | 76.16% | -8.224%
N6274218C1306 | 9240880.0577 | 12728558.2884 | 9240880.0577 | 37.74% |  |  | M62613603 | 8904000 | 8904000 | 0% | 76371 | 11.97% | 7.625% | 11.97% | 7.625%
N6274218C1314 | 25356334.5309 | 35447946.4062 | 25356334.5309 | 39.8% |  |  | N4008510D0261 |  |  |  | 76373 | 25.41% | 13.72% | 25.41% | 13.72%
N6274218C1316 | 79047383.5074 | 75820415.1552 | 79047383.5074 | -4.082% |  |  | P1410 | 1826 | 1809 | -0.931% | 76375 | 60.48% | 8.499% | 60.48% | 8.499%
N6274218C1318 | 30444059.6165 | 30850307.4152 | 30444059.6165 | 1.334% |  |  | P1469 | 1944 | 1938 | -0.3086% | 76376 | 27.96% | 18.66% | 27.96% | 18.66%
N6274219C1301 | 18498695.6544 | 17274542.5756 | 18498695.6544 | -6.618% |  |  | Q1410 | 1826 | 1809 | -0.931% | 76511 | 29.37% | 5.328% | 29.37% | 5.328%
N6274219C1317 | 61021444.5087 | 66117552.9793 | 61021444.5087 | 8.351% |  |  | Q1469 | 1944 | 1938 | -0.3086% | 76513 | 56.57% | 6.676% | 56.57% | 6.676%
N6274219C1320 | 25830558.4193 | 27063504.2975 | 25830558.4193 | 4.773% |  |  | N4008510D5330 |  |  |  | 76514 | 81.48% | 3.511% | 81.48% | 3.511%
N6274219C1321 | 19212871.4948 | 19860266.386 | 19212871.4948 | 3.37% |  |  | Q1396 | 10331 | 12848 | 24.36% | 76518 | 56.34% | 7.67% | 56.34% | 7.67%
N6274221C1339 | 63746.5711 | 63746.5711 | 63746.5711 | 0% |  |  | N4008510D5331 |  |  |  | 76934 | 15.69% | -72.53% | 15.69% | -72.53%
N6345017C1305 | 9442703.0634 | 9442703.0634 | 9442703.0634 | 0% |  |  | M67001726 | 20159000 | 20079000 | -0.3968% | 77134 | 31.51% | 2.992% | 31.51% | 2.992%
N6945012C0754 | 10495688.7568 | 2592316.3173 | 10495688.7568 | -75.3% |  |  | N60191815 | 11446000 | 19696000 | 72.08% | 77140 | 67.89% | -0.494% | 67.89% | -0.494%
N6945013C1756 | 45497795.8803 | 53588314.235 | 45497795.8803 | 17.78% |  |  | N4008510D5333 |  |  |  | 77186 | 60.59% | 0.4104% | 60.59% | 0.4104%
N6945013D1762 | 16300078.3357 | 16420996.409 | 16300078.3357 | 0.7418% |  |  | 1391 | 30963 | 30840 | -0.3972% | 77301 | 25.87% | 2.434% | 25.87% | 2.434%
N6945014C1756 | 45763699.5462 | 47528977.1255 | 45763699.5462 | 3.857% |  |  | P334 | 29668 | 31020 | 4.557% | 77305 | 105.2% | 1.471% | 105.2% | 1.471%
N6945014D0757 | 11644.4105 | 11470.2479 | 11644.4105 | -1.496% |  |  | Q157 | 19230 | 19583 | 1.836% | 77831 | 4.139% | 3.087% | 4.139% | 3.087%
N6945014D1269 | 43559998.147 | 43524032.4572 | 43559998.147 | -0.08257% |  |  | Q166 | 13588 | 13362 | -1.663% | 78024 | 20.5% | 34.26% | 20.5% | 34.26%
N6945014D1271 | 4647.8611 | 4588.7318 | 4647.8611 | -1.272% |  |  | Q334 | 29668 | 31020 | 4.557% | 78150 | 71.56% | 4.357% | 71.56% | 4.357%
N6945015D1618 | 2568977.8434 | 2548965.6365 | 2568977.8434 | -0.779% |  |  | N4008514D1322 |  |  |  | 78712 | 79.38% | 0.07503% | 79.38% | 0.07503%
N6945016C1604 | 40194266.7985 | 62539704.322 | 40194266.7985 | 55.59% |  |  | P241 | 4921 | 5145 | 4.552% | 79438 | 31.67% | 9.329% | 31.67% | 9.329%
N6945016C1612 | 69284488.4257 | 76969252.7046 | 69284488.4257 | 11.09% |  |  | Q241 | 4921 | 5129 | 4.227% | 79439 | 88.13% | 44.97% | 88.13% | 44.97%
N6945016D0100 | 9347996.5764 | 9030478.8185 | 9347996.5764 | -3.397% |  |  | N4008514D7742 |  |  |  | 79443 | 31.66% | 7.293% | 31.66% | 7.293%
N6945016D0615 | 4426603.0428 | 4810837.414 | 4426603.0428 | 8.68% |  |  | M670011498 | 3135000 | 3313000 | 5.678% | 79456 | 21.46% | 2.951% | 21.46% | 2.951%
N6945016D1110 | 16066714.1673 | 17343315.8044 | 16066714.1673 | 7.946% |  |  | M670011503 | 3833000 | 4036000 | 5.296% | 80001 | 44.98% | -91.55% | 44.98% | -91.55%
N6945016D1111 | 6249804.7809 | 6307082.3975 | 6249804.7809 | 0.9165% |  |  | N4008515C8739 |  |  |  | 80001A | 392.6% | 0% | 392.6% | 0%
N6945016D1112 | 12971873.2353 | 12862441.6554 | 12971873.2353 | -0.8436% |  |  | N32414547 | 34317000 | 58233000 | 69.69% | 80007 | 46.25% | 0% | 46.25% | 0%
N6945016D1113 | 14961981.3266 | 16414867.5429 | 14961981.3266 | 9.711% |  |  | N4008515C9610 |  |  |  | 80233 | 1.247% | 2.446% | 1.247% | 2.446%
N6945017C1613 | 12459075.4362 | 13528797.8102 | 12459075.4362 | 8.586% |  |  | N00129664 | 1989000 | 1958000 | -1.559% | 80306 | 110.9% | 2.991% | 110.9% | 2.991%
N6945017D0507 | 21561758.3009 | 20754071.6669 | 21561758.3009 | -3.746% |  |  | N4008515D0851 |  |  |  | 80412 | 83.51% | 0.1546% | 83.51% | 0.1546%
N6945018C2105 | 3965703.6209 | 3965703.6209 | 3965703.6209 | 0% |  |  | P1482 | 4524 | 5128 | 13.35% | 80690 | 15.11% | 4.123% | 15.11% | 4.123%
N6945018D1318 | 11918100.7154 | 11730986.5815 | 11918100.7154 | -1.57% |  |  | Q1482 | 5152 | 5128 | -0.4658% | 80748 | 5.179% | 0% | 5.179% | 0%
N6945018D1320 | 4634827.1031 | 4484372.5348 | 4634827.1031 | -3.246% |  |  | N4008516C3013 |  |  |  | 80771 | 45.07% | 1.992% | 45.07% | 1.992%
N6945019c1304 | 20895038.1867 | 20895038.1867 | 20895038.1867 | 0% |  |  | N32446308 | 34722000 | 34943000 | 0.6365% | 80773 | 15.73% | 1.636% | 15.73% | 1.636%
N6945019C2105 | 2988124.0475 | 2988124.0475 | 2988124.0475 | 0% |  |  | N4008516C3037 |  |  |  | 80906 | 143.3% | 18.8% | 143.3% | 18.8%
N6945019C5214 | 18944.6702 | 17489.7828 | 18944.6702 | -7.68% |  |  | DSCP1501 | 46845550 | 57854412 | 23.5% | 81236 | 19.3% | 6.095% | 19.3% | 6.095%
N6945019C5648 | 2387094.212 | 2276026.4641 | 2387094.212 | -4.653% |  |  | N4008516C5505 |  |  |  | 81316 | 27.55% | 5.683% | 27.55% | 5.683%
N6945019D0921 | 7604120.2813 | 7604120.2813 | 7604120.2813 | 0% |  |  | M67400606 | 8792000 | 8792000 | 0% | 81428 | 22.02% | 16.07% | 22.02% | 16.07%
N6945019F0855 | 28254645.9123 | 27251033.7395 | 28254645.9123 | -3.552% |  |  | N4008516C5506 |  |  |  | 81436 | 24.36% | 8.438% | 24.36% | 8.438%
N6945019F1275 | 2239625.6355 | 2239625.6355 | 2239625.6355 | 0% |  |  | M00146194 | 28561000 | 27767000 | -2.78% | 81483 | 19.51% | 8.387% | 19.51% | 8.387%
N6945020C2575 | 1764076.0325 | 1918438.5118 | 1764076.0325 | 8.75% |  |  | N4008516D5524 |  |  |  | 81894 | 77.52% | 10.59% | 77.52% | 10.59%
N6945020F0870 | 5060143.5331 | 5060143.5331 | 5060143.5331 | 0% |  |  | M67004971 | 1982000 | 1918000 | -3.229% | 81897 | 24.3% | 4.647% | 24.3% | 4.647%
N9127816C0035 | 3980631.9798 | 3980631.9798 | 3980631.9798 | 0% |  |  | N4008516D6300 |  |  |  | 81987 | 61.53% | 11.33% | 61.53% | 11.33%
NGBID20B0009 | 3001831.0253 | 2444953.7269 | 3001831.0253 | -18.55% |  |  | M67001686 | 3640000 | 3728000 | 2.418% | 82254 | 23.79% | 0.9952% | 23.79% | 0.9952%
PC12318312000 | 15760514.0379 | 17760734.1111 | 15760514.0379 | 12.69% |  |  | M67001729 | 1885000 | 2519000 | 33.63% | 82337 | 18.79% | 1.009% | 18.79% | 1.009%
Swift | 40977336.4985 | 42505364.5197 | 40977336.4985 | 3.729% |  |  | N4008516D6303 |  |  |  | 83011 | -9.375% | 10.64% | -9.375% | 10.64%
T180901 | 12007324.1013 | 9988888.139 | 12007324.1013 | -16.81% |  |  | M00146249 | 1368000 | 1369000 | 0.0731% | 83702 | 70.99% | 12.56% | 70.99% | 12.56%
T181801 | 33622429.9475 | 26181891.446 | 33622429.9475 | -22.13% |  |  | M00146766 | 2468000 | 2431000 | -1.499% | 85711 | 28.77% | 21.34% | 28.77% | 21.34%
USACE | 12064947.5435 | 11388534.9525 | 12064947.5435 | -5.606% |  |  | N4008517C0307 |  |  |  | 85794 | 105.3% | 5.277% | 105.3% | 5.277%
w | 22121873.7813 | 22121873.7813 | 22121873.7813 | 0% |  |  | N62688610 | 46841000 | 50010000 | 6.765% | 86479 | 36.28% | 4.111% | 36.28% | 4.111%
W4126C18C0049 | 4600970.0152 | 4600970.0152 | 4600970.0152 | 0% |  |  | N4008517C5056 |  |  |  | 86689 | 35.33% | 1.817% | 35.33% | 1.817%
W50S8N20C0001 | 3430897.7429 | 3330264.1532 | 3430897.7429 | -2.933% |  |  | N32446285 | 18927000 | 19723000 | 4.206% | 86711 | 66.74% | 1.191% | 66.74% | 1.191%
W50S8Z20C0001 | 12189047.9473 | 11890604.7024 | 12189047.9473 | -2.448% |  |  | N4008517C8315 |  |  |  | 86823 | -15.85% | 2.966% | -15.85% | 2.966%
W911KB14C0011 | 15319839.0124 | 17906474.7382 | 15319839.0124 | 16.88% |  |  | M00146193 | 55798000 | 56191000 | 0.7043% | 86882 | 85.44% | 14.71% | 85.44% | 14.71%
W911KB17C0002 | 121429724.9099 | 127727280.2018 | 121429724.9099 | 5.186% |  |  | N4008517C8325 |  |  |  | 86914 | 226.7% | 2.509% | 226.7% | 2.509%
W911KB17C0021 | 19304301.5511 | 20230683.5522 | 19304301.5511 | 4.799% |  |  | M670011280 | 47882000 | 51796000 | 8.174% | 86943 | 5.474% | 0% | 5.474% | 0%
W911KB17C0029 | 7476714.9285 | 8747348.8389 | 7476714.9285 | 16.99% |  |  | N4008517C8327 |  |  |  | 87208 | 32.46% | 3.648% | 32.46% | 3.648%
W911KB17C0030 | 4395299.2799 | 4438657.5047 | 4395299.2799 | 0.9865% |  |  | M60169464 | 78310000 | 79679000 | 1.748% | 87744 | 0% | -97.64% | 0% | -97.64%
W911KB17D0010 | 6566307.3676 | 6946539.2975 | 6566307.3676 | 5.791% |  |  | N4008517D0358 |  |  |  | 87980 | 76.65% | 1.421% | 76.65% | 1.421%
W911KB17D0012 | 5527412.7278 | 6712135.3724 | 5527412.7278 | 21.43% |  |  | N50092176 | 2670000 | 2602000 | -2.547% | 88028 | 48.65% | 0.5412% | 48.65% | 0.5412%
W911KB17F0055 | 752692.1192 | 752692.1192 | 752692.1192 | 0% |  |  | N4008517D0362 |  |  |  | 88231 | 53.59% | 21.82% | 53.59% | 21.82%
W911KB18C0006 | 20255413.6922 | 21199640.6418 | 20255413.6922 | 4.662% |  |  | P225 | 3455 | 3445 | -0.2894% | 88585 | 53.1% | 7.165% | 53.1% | 7.165%
W911KB18C0015 | 25636683.6053 | 25800040.796 | 25636683.6053 | 0.6372% |  |  | Q225 | 3455 | 3450 | -0.1447% | 88722 | 184.6% | -0.4341% | 184.6% | -0.4341%
W911KB18C0018 | 20016903.529 | 25274677.3699 | 20016903.529 | 26.27% |  |  | N4008517D5038 |  |  |  | 88844 | 44.65% | 0% | 44.65% | 0%
W911KB18C0023 | 5465136.8618 | 5356473.371 | 5465136.8618 | -1.988% |  |  | M68479135 | 2109000 | 2147000 | 1.802% | 89128 | 71.15% | 4.179% | 71.15% | 4.179%
W911KB18C0026 | 86288814.3573 | 88561209.449 | 86288814.3573 | 2.633% |  |  | M68479777 | 17729000 | 25256000 | 42.46% | 89203 | 2.844% | 64.22% | 2.844% | 64.22%
W911KB18C0028 | 39853737.9317 | 41004002.899 | 39853737.9317 | 2.886% |  |  | N4008517D5048 |  |  |  | 89215 | 76.83% | 1.661% | 76.83% | 1.661%
W911KB18C0030 | 60535083.7185 | 67174009.2605 | 60535083.7185 | 10.97% |  |  | N32446385 | 975000 | 819000 | -16% | 89227 | 23.48% | 5.791% | 23.48% | 5.791%
W911KB18R0006 | 14011096.9797 | 15373109.4319 | 14011096.9797 | 9.721% |  |  | N4008517D5049 |  |  |  | 89946 | 42.35% | 4.779% | 42.35% | 4.779%
W911KB19C0013 | 20341084.3564 | 21042142.9807 | 20341084.3564 | 3.447% |  |  | N324461088 | 3458000 | 3460000 | 0.05784% | 90303 | 26.92% | -0.6382% | 26.92% | -0.6382%
W911KB19F0159 | 609024.4864 | 609024.4864 | 609024.4864 | 0% |  |  | N4008518C0610 |  |  |  | 90912 | 13.99% | 30.56% | 13.99% | 30.56%
W911KB20C0002 | 27656869.8466 | 30563294.5331 | 27656869.8466 | 10.51% |  |  | M670011320 | 37174000 | 36007000 | -3.139% | 91311 | 65.25% | 0.2196% | 65.25% | 0.2196%
W911KB21C0033 | 1147790.5465 | 1147790.5465 | 1147790.5465 | 0% |  |  | N4008518C0614 |  |  |  | 91328 | 0% | 0% | 0% | 0%
W911KB21F0085 | 71359.4294 | 71359.4294 | 71359.4294 | 0% |  |  | P1219 | 63726 | 65226 | 2.354% | 91397 | 8.873% | -0.09717% | 8.873% | -0.09717%
W9123616C0025 | 22695223.091 | 23361367.4843 | 22695223.091 | 2.935% |  |  | Q1219 | 64004 | 65183 | 1.842% | 91427 | 41.81% | 1.407% | 41.81% | 1.407%
W9123616R00080005 | 22695223.091 | 23149418.3737 | 22695223.091 | 2.001% |  |  | Q1288 | 14741 | 15200 | 3.114% | 91474A | 0% | 0% | 0% | 0%
W9123618C0008 | 6570201.0641 | 7826807.5557 | 6570201.0641 | 19.13% |  |  | N4008518C0637 |  |  |  | 91528 | 96.92% | 6.414% | 96.92% | 6.414%
W9123618C0025 | 52805076.9334 | 53856824.4673 | 52805076.9334 | 1.992% |  |  | 14019 | 35000000 | 31558000 | -9.834% | 92022 | 153.4% | 2.872% | 153.4% | 2.872%
W9123619C0043 | 5052665.6223 | 5183745.5771 | 5052665.6223 | 2.594% |  |  | N4008518C0640 |  |  |  | 93000 | 46.47% | 0.1501% | 46.47% | 0.1501%
W9123619C0044 | 8559834.174 | 8682909.2461 | 8559834.174 | 1.438% |  |  | M00263403 | 30382000 | 29633000 | -2.465% | 93016 | 69.74% | 2.633% | 69.74% | 2.633%
W9123818C0015 | 91987816.2334 | 103227672.2026 | 91987816.2334 | 12.22% |  |  | N4008518C1103 |  |  |  | 93019 | 10.38% | 1.13% | 10.38% | 1.13%
W9124217C0005 | 16909897.1038 | 18156365.1534 | 16909897.1038 | 7.371% |  |  | P791 | 24701 | 24983 | 1.142% | 93022 | 68.95% | 21.43% | 68.95% | 21.43%
W9124219C5001 | 21455608.6763 | 20899133.2433 | 21455608.6763 | -2.594% |  |  | Q791 | 24701 | 24983 | 1.142% | 94606 | 3.621% | -2.096% | 3.621% | -2.096%
W9124219C5004 | 29966030.1029 | 28973991.99 | 29966030.1029 | -3.311% |  |  | N4008518C1107 |  |  |  | 94607 | 3.621% | 63.48% | 3.621% | 63.48%
W9124219C5007 | 5369148.2787 | 5193488.1314 | 5369148.2787 | -3.272% |  |  | N32443257 | 73055000 | 71370000 | -2.306% | 94608 | 27.05% | 55.28% | 27.05% | 55.28%
W9124V1622001 | 13160244.6057 | 17261479.2337 | 13160244.6057 | 31.16% |  |  | N4008518C1116 |  |  |  | 94609 | 16.81% | 115.4% | 16.81% | 115.4%
W9126G08D0056CV01 | 53473767.1177 | 55608520.7379 | 53473767.1177 | 3.992% |  |  | N32443614 | 48238000 | 46498000 | -3.607% | 94610 | 7.181% | 26.87% | 7.181% | 26.87%
W9126G09D00960002 | 12671877.9028 | 12845816.553 | 12671877.9028 | 1.373% |  |  | N4008518C1134 |  |  |  | 94611 | 58.82% | 35.76% | 58.82% | 35.76%
W9126G11P0208 | 55578.4119 | 55578.4119 | 55578.4119 | 0% |  |  | N62688913 | 114000000 | 110529000 | -3.045% | 94612 | 59.25% | 50.69% | 59.25% | 50.69%
W9126G12C0038 | 4584355.657 | 4620759.5304 | 4584355.657 | 0.7941% |  |  | N4008518C1137 |  |  |  | 94638 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
W9126G12C0051 | 19441813.9207 | 26947383.1692 | 19441813.9207 | 38.61% |  |  | P777 | 24780 | 24173 | -2.45% | 94639 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
W9126G12P0014 | 4821436.4199 | 4821436.4199 | 4821436.4199 | 0% |  |  | Q777 | 24780 | 24173 | -2.45% | A73010 | 124.3% | 2.311% | 124.3% | 2.311%
W9126G13C0004 | 361910869.2124 | 526321426.4121 | 361910869.2124 | 45.43% |  |  | N4008518C1148 |  |  |  | AFSOC103002 | 15.78% | 3.5% | 15.78% | 3.5%
W9126G13C0046 | 1808450.4867 | 752187.9021 | 1808450.4867 | -58.41% |  |  | N62688495 | 35158000 | 34046000 | -3.163% | AFSOC103022 | 24.19% | 5.879% | 24.19% | 5.879%
W9126G14D00500002 | 6822476.261 | 6883342.8599 | 6822476.261 | 0.8921% |  |  | N4008518C6101 |  |  |  | AGGN173001 | 61.99% | 3.172% | 61.99% | 3.172%
W9126G14P0150 | 3777457.6281 | 1822414.5789 | 3777457.6281 | -51.76% |  |  | P1475 | 3136 | 3130 | -0.1913% | AGGN213001 | 0% | 0% | 0% | 0%
W9126G18C0018 | 37992883.5322 | 38344321.8989 | 37992883.5322 | 0.925% |  |  | Q1475 | 3136 | 3130 | -0.1913% | AJJY123010 | 150.8% | 2.678% | 150.8% | 2.678%
W9126G18C0066 | 4078615.0956 | 4078615.0956 | 4078615.0956 | 0% |  |  | N4008518C6118 |  |  |  | AJJY133027 | 196.3% | 6.087% | 196.3% | 6.087%
W9126G19C0019 | 2951241.7464 | 2951241.7464 | 2951241.7464 | 0% |  |  | P1481 | 3716 | 3594 | -3.283% | AJJY133028 | 136% | 10.06% | 136% | 10.06%
W9126G19C0020 | 23451684.9364 | 24064058.4655 | 23451684.9364 | 2.611% |  |  | Q1481 | 3716 | 3594 | -3.283% | AJJY203001 | 0% | 0% | 0% | 0%
W9126G19C0124 | 2470329.0942 | 2535368.7664 | 2470329.0942 | 2.633% |  |  | N4008518C8707 |  |  |  | AJXF093000 | 0% | 0% | 0% | 0%
W9126G19D0021 | 211605072.6371 | 290494069.2886 | 211605072.6371 | 37.28% |  |  | N00128714 | 70635000 | 67578000 | -4.328% | AJXF173021 | 0% | 0% | 0% | 0%
W9126G19D0024 | 55876082.7054 | 120372243.6375 | 55876082.7054 | 115.4% |  |  | N4008518C8719 |  |  |  | ALUA113023 | 63.69% | -1.064% | 63.69% | -1.064%
W9126G20C0004 | 4001440.7568 | 4001440.7568 | 4001440.7568 | 0% |  |  | N32446371 | 30414000 | 30767000 | 1.161% | AM00021 | 35.64% | -0.6723% | 35.64% | -0.6723%
W9127807D0026 | 8670008.7274 | 11499081.7326 | 8670008.7274 | 32.63% |  |  | N4008518D1124 |  |  |  | AM00031 | 31.8% | 2.815% | 31.8% | 2.815%
W9127807D0036 | 18210387.4667 | 18434734.9673 | 18210387.4667 | 1.232% |  |  | P824 | 11130 | 12399 | 11.4% | AM00033 | -5.364% | 4.615% | -5.364% | 4.615%
W9127809C0003 | 11628255.3903 | 11999710.3134 | 11628255.3903 | 3.194% |  |  | P914U | 4626 | 5081 | 9.836% | AM00035 | 14.64% | -0.04689% | 14.64% | -0.04689%
W9127809C0010 | 6592867.2913 | 8271363.1866 | 6592867.2913 | 25.46% |  |  | Q824 | 12500 | 12399 | -0.808% | AM00046 | -1.572% | 3.913% | -1.572% | 3.913%
W9127810518 | 17082675.0671 | 17072905.29 | 17082675.0671 | -0.05719% |  |  | Q914U | 5098 | 5083 | -0.2942% | AM00048 | 36.47% | 3.448% | 36.47% | 3.448%
W9127810C0041 | 3256570.4335 | 3877561.3196 | 3256570.4335 | 19.07% |  |  | N4008518D1125 |  |  |  | AM00103 | 119.4% | 11.09% | 119.4% | 11.09%
W9127810D0058 | 12141733.2116 | 13918415.4393 | 12141733.2116 | 14.63% |  |  | P834 | 10586 | 10666 | 0.7557% | AM00115 | 77.14% | -6.844% | 77.14% | -6.844%
W9127810D0072 | 4966148.5799 | 6007893.3658 | 4966148.5799 | 20.98% |  |  | Q834 | 10586 | 10233 | -3.335% | ASVF164000 | 104.8% | 6.407% | 104.8% | 6.407%
W9127811D0028 | 11891625.5739 | 12582630.944 | 11891625.5739 | 5.811% |  |  | N4008518D1143 |  |  |  | ASVF183100D | 79.3% | -0.3712% | 79.3% | -0.3712%
W9127811D0029 | 23948504.1062 | 25105801.0919 | 23948504.1062 | 4.832% |  |  | P698 | 2846 | 4445 | 56.18% | ASVF183100F | 544.4% | 8.937% | 544.4% | 8.937%
W9127811D0062 | 31512793.6618 | 34191054.2346 | 31512793.6618 | 8.499% |  |  | P900 | 3422 | 0 |  | AWUB105003 | -91.35% | 0% | -91.35% | 0%
W9127811D0066 | 30316206.3402 | 33183988.054 | 30316206.3402 | 9.46% |  |  | Q698 | 2846 | 4299 | 51.05% | AWUB105005 | 140.1% | 0% | 140.1% | 0%
W9127811D0067 | 17743368.4322 | 29244167.7869 | 17743368.4322 | 64.82% |  |  | Q900 | 3422 | 0 |  | BIKF180001 | 0% | 0% | 0% | 0%
W9127811D0068 | 42599481.608 | 47241931.9028 | 42599481.608 | 10.9% |  |  | N4008518D1144 |  |  |  | CADJ170001 | 100.6% | 6.435% | 100.6% | 6.435%
W9127811D0073 | 94333561.6826 | 108496789.008 | 94333561.6826 | 15.01% |  |  | N601911026 | 4218000 | 4419000 | 4.765% | CZQZ083012 | 3.815% | 4.252% | 3.815% | 4.252%
W9127812D0037 | 85085050.384 | 89174173.6059 | 85085050.384 | 4.806% |  |  | N4008518R1123 |  |  |  | CZQZ083013 | -6.922% | 1.973% | -6.922% | 1.973%
W9127812D0038 | 37547260.2499 | 41831168.6493 | 37547260.2499 | 11.41% |  |  | N62688762 | 2573000 | 2905000 | 12.9% | CZQZ083021 | -0.6221% | 0.3337% | -0.6221% | 0.3337%
W9127812D0039 | 74833084.338 | 79719611.865 | 74833084.338 | 6.53% |  |  | N4008519C9017 |  |  |  | CZQZ103006 | 28.6% | 2.317% | 28.6% | 2.317%
W9127812D0040 | 30379736.971 | 34196262.9734 | 30379736.971 | 12.56% |  |  | M00263404 | 36938000 | 36163000 | -2.098% | DCX1305 | 33.11% | 0.6727% | 33.11% | 0.6727%
W9127816C0021 | 17660007.6481 | 18089554.1022 | 17660007.6481 | 2.432% |  |  | N4008519C9021 |  |  |  | DDCX1309 A | 169.3% | 6.276% | 169.3% | 6.276%
W9127816D0015 | 8389012.5613 | 8389012.5613 | 8389012.5613 | 0% |  |  | M00146222 | 21793000 | 22197000 | 1.854% | DDCX1701A | 41.37% | 0.925% | 41.37% | 0.925%
W9127816D0016 | 12937485.0116 | 13116597.2296 | 12937485.0116 | 1.384% |  |  | N4008519C9053 |  |  |  | DDCX1701B | 0% | 0% | 0% | 0%
W9127816D0031 | 7899292.4254 | 7924416.7505 | 7899292.4254 | 0.3181% |  |  | M670011479 | 3247000 | 3532000 | 8.777% | DDPM130007 | 21.65% | 0% | 21.65% | 0%
W9127816D0033 | 42098821.698 | 44175148.7592 | 42098821.698 | 4.932% |  |  | N4008519C9057 |  |  |  | DESC1301 | 256.4% | 1.625% | 256.4% | 1.625%
W9127818C0026 | 8413910.1257 | 8459413.9164 | 8413910.1257 | 0.5408% |  |  | N32414106 | 66625000 | 66732000 | 0.1606% | DESC1353 | 12% | 5.39% | 12% | 5.39%
W9127819C00006 | 61096831.6773 | 61317436.2393 | 61096831.6773 | 0.3611% |  |  | N324141098 | 3142000 | 3125000 | -0.5411% | DESC1401 | 172.5% | 14.36% | 172.5% | 14.36%
W9127819C0012 | 27104221.6684 | 27115182.354 | 27104221.6684 | 0.04044% |  |  | N4008519C9061 |  |  |  | DESC1404 | 4.532% | 1.772% | 4.532% | 1.772%
W9127819C0013 | 32158503.6915 | 32149744.3486 | 32158503.6915 | -0.02724% |  |  | N50092152 | 18501000 | 17819000 | -3.686% | DESC1407 | 24.89% | 3.655% | 24.89% | 3.655%
W9127819C0017 | 13709093.3633 | 13709093.3633 | 13709093.3633 | 0% |  |  | N4008519C9070 |  |  |  | DESC1463 | 10.64% | -2.894% | 10.64% | -2.894%
W9127819C0037 | 13120393.5938 | 13120393.5938 | 13120393.5938 | 0% |  |  | 71509 | 35912000 | 32464000 | -9.601% | DESC1501 | 277.9% | 7.356% | 277.9% | 7.356%
W9127819F0486 | 12710412.475 | 12710412.475 | 12710412.475 | 0% |  |  | N4008519C9124 |  |  |  | DESC1502 | 59.48% | 3.796% | 59.48% | 3.796%
W9127820C0008 | 5295229.9287 | 5548267.1572 | 5295229.9287 | 4.779% |  |  | 89838 | 28729000 | 28301000 | -1.49% | DESC1502 A | 163.6% | 1.378% | 163.6% | 1.378%
W9127820C0010 | 3353172.3328 | 3353172.3328 | 3353172.3328 | 0% |  |  | N4008519C9126 |  |  |  | DESC1502 B | 344.2% | 0% | 344.2% | 0%
W9128A12D0012 | 2712421.0308 | 2780462.534 | 2712421.0308 | 2.509% |  |  | M67004977 | 23298000 | 23913000 | 2.64% | DESC1507 | 77.59% | 6.423% | 77.59% | 6.423%
W9128A16C0004 | 28672972.9297 | 29827693.2582 | 28672972.9297 | 4.027% |  |  | N4008519C9261 |  |  |  | DESC1508 | 13.5% | 7.995% | 13.5% | 7.995%
W9128A18C0001 | 78788911.0772 | 77800308.0595 | 78788911.0772 | -1.255% |  |  | N32446293 | 62457000 | 62817000 | 0.5764% | DESC1513 | 0% | 232.5% | 0% | 232.5%
W9128A18C0009 | 43579264.9778 | 46148037.8509 | 43579264.9778 | 5.894% |  |  | N4008519C9266 |  |  |  | DESC1551 | 17.11% | 8.894% | 17.11% | 8.894%
W9128A18C0016 | 5043364.4921 | 5043364.4921 | 5043364.4921 | 0% |  |  | 14042 | 21895000 | 22225000 | 1.507% | DESC1603 | 0% | 0% | 0% | 0%
W9128F10C0061 | 35216936.5765 | 40680892.5339 | 35216936.5765 | 15.52% |  |  | N4008519D9066 |  |  |  | DESC1605 | 1.344% | 0% | 1.344% | 0%
W9128F12C0011 | 4236037.9397 | 4321103.223 | 4236037.9397 | 2.008% |  |  | N69212995 | 31074000 | 29801000 | -4.097% | DESC1606 | 107.9% | 31.47% | 107.9% | 31.47%
W9128F13C0006 | 1777179.5594 | 1926228.9224 | 1777179.5594 | 8.387% |  |  | N4008519D9070 |  |  |  | DESC1607 | 55.93% | 2.468% | 55.93% | 2.468%
W9128F14C0024 | 41975207.0265 | 38523159.8247 | 41975207.0265 | -8.224% |  |  | P224 | 1828 | 26134 | 1330% | DESC1608 | -20.45% | 0% | -20.45% | 0%
W9128F14C0030 | 17374730.4864 | 18566244.4745 | 17374730.4864 | 6.858% |  |  | P999 | 1828 | 11501 | 529.2% | DESC1609 | 9250% | 2.811%
W9128F15C0032 | 28849193.95 | 29355802.5969 | 28849193.95 | 1.756% |  |  | Q224 | 26797 | 26134 | -2.474% | DESC1611 | 0% | 0.2118% | 0% | 0.2118%
W9128F16C0033 | 9965702.6433 | 10352030.6676 | 9965702.6433 | 3.877% |  |  | Q999 | 10850 | 11501 | 6% | DESC1701 | 22.64% | 2.262% | 22.64% | 2.262%
W9128F16D00550001 | 5556625.0857 | 5556625.0857 | 5556625.0857 | 0% |  |  | N4008519D9089 |  |  |  | DESC1702 | 14.22% | 0.5126% | 14.22% | 0.5126%
W9128F17C0032 | 66586012.2718 | 67565306.6257 | 66586012.2718 | 1.471% |  |  | N32443256 | 23304851 | 25344000 | 8.75% | DESC1705 | 28.42% | 4.9% | 28.42% | 4.9%
W9128F18C0026 | 25683125.8085 | 25683125.8085 | 25683125.8085 | 0% |  |  | N4008519D9164 |  |  |  | DESC1706 | 3.915% | 0% | 3.915% | 0%
W9128F18C0037 | 19903427.828 | 20000487.0311 | 19903427.828 | 0.4877% |  |  | N62688404 | 0 | 1458000 |  | DESC1707 | -2.424% | 0.9865% | -2.424% | 0.9865%
W9128F19C0022 | 6740997.861 | 6814042.4159 | 6740997.861 | 1.084% |  |  | N4008520C0044 |  |  |  | DESC1709 | 0% | 0% | 0% | 0%
W9128F19C0023 | 9384911.7604 | 9384911.7604 | 9384911.7604 | 0% |  |  | M670011199F | 19142000 | 19343000 | 1.05% | DESC1710 | 83.7% | 8.781% | 83.7% | 8.781%
W9128F19C0029 | 71054844.3737 | 72784094.9319 | 71054844.3737 | 2.434% |  |  | M670011300F | 17826000 | 18328000 | 2.816% | DESC18S2 | 58.55% | 8.161% | 58.55% | 8.161%
W9128F19C0032 | 7706461.8657 | 7923052.9797 | 7706461.8657 | 2.811% |  |  | M670011312F | 55017000 | 58510000 | 6.349% | DESC1905 | -20.6% | 4.031% | -20.6% | 4.031%
W9128F20C0006 | 3386065.3966 | 3386065.3966 | 3386065.3966 | 0% |  |  | M670011509F | 33391000 | 40681000 | 21.83% | DESC1909 | 59.16% | 1.438% | 59.16% | 1.438%
W9128F21C0040 | 8004882.7342 | 8004882.7342 | 8004882.7342 | 0% |  |  | M670011512F | 135347000 | 137453000 | 1.556% | DESC1914 | 69.61% | 2.594% | 69.61% | 2.594%
W9129917C0011 | 22547604.5495 | 22663181.6524 | 22547604.5495 | 0.5126% |  |  | M670011518F | 29242000 | 30232000 | 3.386% | DHAF152900 | 4.156% | 1.42% | 4.156% | 1.42%
W912BU16R00370006 | 24910517.8208 | 24910517.8208 | 24910517.8208 | 0% |  |  | M670011520F | 15383000 | 15577000 | 1.261% | DRMS1701 | 31.39% | 0% | 31.39% | 0%
W912BV15C0001 | 35992968.7635 | 36488794.5352 | 35992968.7635 | 1.378% |  |  | M670011522F | 26607000 | 26859000 | 0.9471% | DSCP1501 | 30.05% | 22.46% | 30.05% | 22.46%
W912BV15C0017 | 24661024.3028 | 24855184.6515 | 24661024.3028 | 0.7873% |  |  | M670011524F | 14143000 | 14259000 | 0.8202% | DSCR1501 | 70.46% | 19.13% | 70.46% | 19.13%
W912BV17C0004 | 105292034.6146 | 106223358.0622 | 105292034.6146 | 0.8845% |  |  | M670011525F | 7375000 | 7549000 | 2.359% | DXEB053005 | 76.97% | 4.662% | 76.97% | 4.662%
W912BV17C0005 | 13408369.0431 | 13762941.733 | 13408369.0431 | 2.644% |  |  | M670011527F | 48103000 | 48584000 | 0.9999% | EPPW170003 | 0% | 0% | 0% | 0%
W912BV17C0010 | 11211714.3876 | 11567342.1008 | 11211714.3876 | 3.172% |  |  | M670011529F | 22970805 | 24310000 | 5.83% | EU00031 | 19.53% | 15.32% | 19.53% | 15.32%
W912BV17C0014 | 72553768.5706 | 72836356.1334 | 72553768.5706 | 0.3895% |  |  | M67001378F | 223502000 | 227567000 | 1.819% | EU00034 | 19.32% | 5.406% | 19.32% | 5.406%
W912BV17D0017 | 4625821.61 | 4625821.61 | 4625821.61 | 0% |  |  | M67001695F | 67658000 | 69263000 | 2.372% | EU00037 | 7.539% | 8.611% | 7.539% | 8.611%
W912BV19C0002 | 25560115.9562 | 25560115.9562 | 25560115.9562 | 0% |  |  | M67001707F | 79978000 | 81776000 | 2.248% | EU00040 | 44.89% | 14.96% | 44.89% | 14.96%
W912BV19C0003 | 61107762.1642 | 61107762.1642 | 61107762.1642 | 0% |  |  | M67001728F | 48575000 | 49432000 | 1.764% | EU00049 | 1.652% | 1.656% | 1.652% | 1.656%
W912BV19C0011 | 12588990.251 | 12588990.251 | 12588990.251 | 0% |  |  | M67001883F | 54587000 | 58083000 | 6.404% | EU00072 | -24.43% | 3.933% | -24.43% | 3.933%
W912BV19C0022 | 6356678.7756 | 6875453.943 | 6356678.7756 | 8.161% |  |  | N4008520C0055 |  |  |  | EU00183 | 80.07% | 7.58% | 80.07% | 7.58%
W912DQ17D4016 | 2033602.8608 | 2044609.5746 | 2033602.8608 | 0.5412% |  |  | M00146130F | 33831000 | 33952000 | 0.3577% | FJRP159062 | 0% | -3.311% | 0% | -3.311%
W912DQ19C4000 | 8929766.9835 | 9262970.2273 | 8929766.9835 | 3.731% |  |  | M00146142F | 40771000 | 41147000 | 0.9222% | FJRP159073 | 0% | -2.594% | 0% | -2.594%
W912DQ19C4001 | 230363.326 | 230363.326 | 230363.326 | 0% |  |  | M00146162F | 41270000 | 45089000 | 9.254% | FJRP199080 | 0% | -3.272% | 0% | -3.272%
W912DQ19D4001 | 2666599.0014 | 2670601.4428 | 2666599.0014 | 0.1501% |  |  | M00146246F | 17747042 | 19387000 | 9.241% | FNWZ100071A | 6.591% | 0% | 6.591% | 0%
W912DQ19F4003 | 10877052.1887 | 10823318.4143 | 10877052.1887 | -0.494% |  |  | M00146254F | 30990000 | 30904000 | -0.2775% | FSPM053503C | 9.367% | 0.5389% | 9.367% | 0.5389%
W912DQ20C4000 | 2715656.4676 | 4459561.6915 | 2715656.4676 | 64.22% |  |  | N4008520C0063 |  |  |  | FTEV073010 | 151.4% | 2.432% | 151.4% | 2.432%
W912DR07C0070 | 3461677.4788 | 3461677.4788 | 3461677.4788 | 0% |  |  | N32443653 | 46986935 | 49652000 | 5.672% | FTEV153003 | 96.69% | 4.708% | 96.69% | 4.708%
W912DR08C0016 | 773386.0544 | 774594.2807 | 773386.0544 | 0.1562% |  |  | N4008520C0074 |  |  |  | FTFA033003 | 30.88% | 1.35% | 30.88% | 1.35%
W912DR08C0038 | 1887934.1162 | 1887934.1162 | 1887934.1162 | 0% |  |  | N00129898 | 67325000 | 76026000 | 12.92% | FTFA043000 | 0% | 0.3561% | 0% | 0.3561%
W912DR08C0053 | 3161520.1062 | 3161520.1062 | 3161520.1062 | 0% |  |  | N4008520C0142 |  |  |  | FTFA093965 | 0% | 0.04044% | 0% | 0.04044%
W912DR08C0078 | 888190.8802 | 888190.8802 | 888190.8802 | 0% |  |  | 1362 | 7962 | 7820 | -1.783% | FTFA113004 | 12.75% | 6.734% | 12.75% | 6.734%
W912DR09C0030 | 548514.4812 | 548514.4812 | 548514.4812 | 0% |  |  | P1362 | 7962 | 8206 | 3.065% | FTFA143913 | 0.5479% | -0.02724% | 0.5479% | -0.02724%
W912DR09C0052 | 28071543.2514 | 67835175.5698 | 28071543.2514 | 141.7% |  |  | N4008520C0145 |  |  |  | FTFA163003 | 4.899% | 0.5408% | 4.899% | 0.5408%
W912DR10C0033 | 154340782.658 | 174984915.4914 | 154340782.658 | 13.38% |  |  | M670011338F | 51246000 | 52469000 | 2.387% | FTQW170100 | 0% | 4.511% | 0% | 4.511%
W912DR10C0035 | 5473496.7821 | 5181106.0067 | 5473496.7821 | -5.342% |  |  | M670011495 | 35517314 | 37448000 | 5.436% | FTQW180107 | 25.83% | 26.18% | 25.83% | 26.18%
W912DR10C0079 | 14413664.7199 | 14413664.7199 | 14413664.7199 | 0% |  |  | N4008520C8500 |  |  |  | FTQW180109 | 29.34% | 3.447% | 29.34% | 3.447%
W912DR10F0217 | 346078.2496 | 346078.2496 | 346078.2496 | 0% |  |  | N324461074 | 43523000 | 45838000 | 5.319% | FTQW183001 | 42.94% | 2.595% | 42.94% | 2.595%
W912DR11C0034 | 3866324.3029 | 3866324.3029 | 3866324.3029 | 0% |  |  | N32446310 | 177914000 | 138795000 | -21.99% | GHLN083004 | 121.4% | 0% | 121.4% | 0%
W912DR11C0036 | 152115696.7923 | 158092986.5458 | 152115696.7923 | 3.929% |  |  | N4008520C8501 |  |  |  | GJKZ040009 | 0% | 0% | 0% | 0%
W912DR12C0019 | 139359408.2584 | 156675499.4693 | 139359408.2584 | 12.43% |  |  | M00146199 | 5813000 | 128433000 | 2109% | HAAW179035 | 0% | -2.933% | 0% | -2.933%
W912DR12F0081 | 6600844.2764 | 6600844.2764 | 6600844.2764 | 0% |  |  | M00146235 | 53073000 | 60955000 | 14.85% | KJAQ119006 | 0% | -2.448% | 0% | -2.448%
W912DR13C0005 | 663007306.3771 | 712144461.0486 | 663007306.3771 | 7.411% |  |  | N4008520C8503 |  |  |  | KNMD043004 | 49.34% | 5.894% | 49.34% | 5.894%
W912DR13C0021 | 6168695.0692 | 6789551.7028 | 6168695.0692 | 10.06% |  |  | N60191160 | 25795000 | 24567000 | -4.761% | KNMD179040 | 0% | -8.064% | 0% | -8.064%
W912DR13C0038 | 151600193.0869 | 204305530.8413 | 151600193.0869 | 34.77% |  |  | N4008520C8504 |  |  |  | LBPG150008 | 0% | 0% | 0% | 0%
W912DR15C0025 | 8700706.1088 | 8244515.1961 | 8700706.1088 | -5.243% |  |  | M67004947 | 29418000 | 28448000 | -3.297% | LJYC133003 | 0% | 0% | 0% | 0%
W912DR15C0026 | 27567188.1277 | 29656549.1033 | 27567188.1277 | 7.579% |  |  | N4008520C8505 |  |  |  | LJYC183004 | 0% | 0% | 0% | 0%
W912DR15D0032 | 92233486.4722 | 101091763.304 | 92233486.4722 | 9.604% |  |  | M670011387F | 64921000 | 66857000 | 2.982% | LKLW099101 | 0% | -2.141% | 0% | -2.141%
W912DR16C0049 | 2855259.3491 | 3034457.4445 | 2855259.3491 | 6.276% |  |  | M670011505F | 66036000 | 64520000 | -2.296% | LRCT150007 | 26.67% | 0% | 26.67% | 0%
W912DR17C0022 | 5193700.3566 | 5228638.4553 | 5193700.3566 | 0.6727% |  |  | N4008520D0034 |  |  |  | LXEZ123484 | 0.235% | 2.627% | 0.235% | 2.627%
W912DR17D0012 | 1727649.8599 | 1699280.9346 | 1727649.8599 | -1.642% |  |  | 94638 | 15542000 | 15542000 | 0% | LXEZ154288 | 0% | 0% | 0% | 0%
W912DS11C0023 | 127189987.302 | 151855075.7316 | 127189987.302 | 19.39% |  |  | 94639 | 18842000 | 18842000 | 0% | LXEZ164289 | 0% | 0% | 0% | 0%
W912DS14C0030 | 9948680.4173 | 10680456.8446 | 9948680.4173 | 7.356% |  |  | M670011203F | 27688000 | 28664000 | 3.525% | M00146193 | 1.669% | 0.6555% | 1.669% | 0.6555%
W912DS17C0005 | 52178896.0477 | 54587156.582 | 52178896.0477 | 4.615% |  |  | M670011506F | 28045000 | 30423000 | 8.479% | M00146194 | 0% | -2.657% | 0% | -2.657%
W912DS18B00210013 | 4549351.4832 | 4680180.2848 | 4549351.4832 | 2.876% |  |  | M670011507F | 17318680 | 21230000 | 22.58% | M00146222 | 0% | 1.805% | 0% | 1.805%
W912DS18C0027 | 3319374.3966 | 3467852.964 | 3319374.3966 | 4.473% |  |  | M670011519F | 36463000 | 37513000 | 2.88% | M00146766 | 98.71% | -1.428% | 98.71% | -1.428%
W912DS19B007 | 8215587.0327 | 8276748.3392 | 8215587.0327 | 0.7445% |  |  | M670011533F | 43802000 | 45033000 | 2.81% | M00263404 | 10.27% | -1.995% | 10.27% | -1.995%
W912DS19C0008 | 4300468.9098 | 5239041.4104 | 4300468.9098 | 21.82% |  |  | P1534 | 38218 | 26796 | -29.89% | M00264588 | 49.84% | -5.378% | 49.84% | -5.378%
W912DS19C0011 | 53767678.6702 | 54140506.0835 | 53767678.6702 | 0.6934% |  |  | P997 | 48989 | 0 |  | M00264635 | 247.4% | 10.78% | 247.4% | 10.78%
W912DS20C0005 | 13155992.7541 | 13155992.7541 | 13155992.7541 | 0% |  |  | Q1534 | 26080 | 26796 | 2.745% | M00264677 | 45.12% | 1.201% | 45.12% | 1.201%
W912DW15C0003 | 5034239.7812 | 5743342.9359 | 5034239.7812 | 14.09% |  |  | Q997 | 0 | 0 |  | M00264724 | 28.46% | -2.555% | 28.46% | -2.555%
W912DW15C0006 | 50637154.1593 | 55485806.1787 | 50637154.1593 | 9.575% |  |  | N4008520D0035 |  |  |  | M00264733 | 7.371% | 0.06424% | 7.371% | 0.06424%
W912DW18C0015 | 19963317.7813 | 21599315.6901 | 19963317.7813 | 8.195% |  |  | M670011483 | 11460484 | 12119000 | 5.746% | M00318861 | 84.37% | 2.393% | 84.37% | 2.393%
W912DW19C0002 | 24128867.4959 | 24128867.4959 | 24128867.4959 | 0% |  |  | N4008520D0036 |  |  |  | M00318863 | 34.57% | -1.09% | 34.57% | -1.09%
W912DW19C0008 | 20416620.5257 | 20416620.5257 | 20416620.5257 | 0% |  |  | P1394 | 11658 | 11915 | 2.204% | M00318884 | 128.4% | -7.711% | 128.4% | -7.711%
W912DW19C0015 | 2922469.1946 | 2955489.3359 | 2922469.1946 | 1.13% |  |  | P907 | 44471 | 44471 | 0% | M00318887 | 26.5% | 3.37% | 26.5% | 3.37%
W912DW19C0016 | 3871361.4123 | 3910440.521 | 3871361.4123 | 1.009% |  |  | Q1394 | 11658 | 11912 | 2.179% | M00318902 | 85.91% | 19.02% | 85.91% | 19.02%
W912DW19C0017 | 22927613.4563 | 23851834.3761 | 22927613.4563 | 4.031% |  |  | Q907 | 44471 | 0 |  | M00318907 | 23.08% | -13.03% | 23.08% | -13.03%
W912DW19C008 | 20416620.5257 | 20416620.5257 | 20416620.5257 | 0% |  |  | N4008521C0017 |  |  |  | M00318908 | 23.08% | -5.792% | 23.08% | -5.792%
W912DY12D0053 | 9305201.9586 | 10018904.1139 | 9305201.9586 | 7.67% |  |  | M670011800 | 5850000 | 82095000 | 1303% | M00318923 | 42.26% | -1.332% | 42.26% | -1.332%
W912DY14D0042 | 2555765.9337 | 2555765.9337 | 2555765.9337 | 0% |  |  | M670011800A | 102629610 | 20000 | -99.98% | M006811220 | 0% | 8.003% | 0% | 8.003%
W912DY15D0081 | 1202400.2243 | 1575996.9053 | 1202400.2243 | 31.07% |  |  | M670011801 | 5850000 | 59867000 | 923.4% | M006811599 | 13.74% | 15.68% | 13.74% | 15.68%
W912EP16D0008 | 1365911.2166 | 4541167.831 | 1365911.2166 | 232.5% |  |  | N4008521C0018 |  |  |  | M00681334 | 9.51% | 1.781% | 9.51% | 1.781%
W912ER09C0035 | 8352690.4562 | 8545748.1109 | 8352690.4562 | 2.311% |  |  | P1395 | 13438 | 15727 | 17.03% | M006815001 | 56.58% | -1.552% | 56.58% | -1.552%
W912ER09C0051 | 35026866.6474 | 20585269.4119 | 35026866.6474 | -41.23% |  |  | Q1395 | 15417 | 15683 | 1.725% | M006815002 | -2.695% | 3.425% | -2.695% | 3.425%
W912ER09C0055 | 12552930.0319 | 13593807.362 | 12552930.0319 | 8.292% |  |  | N4008521C0028 |  |  |  | M00681574 | 12.06% | -1.31% | 12.06% | -1.31%
W912ER11D00090012 | 27243941.1551 | 29542874.8027 | 27243941.1551 | 8.438% |  |  | N69212169 | 52191740 | 58176000 | 11.47% | M00681970 | 111.3% | 18.97% | 111.3% | 18.97%
W912ER12C0011 | 33190458.5611 | 35090267.1895 | 33190458.5611 | 5.724% |  |  | N4008521C0035 |  |  |  | M60169464 | 36.4% | 1.671% | 36.4% | 1.671%
W912ER18C0029 | 15916007.2694 | 17108003.3506 | 15916007.2694 | 7.489% |  |  | M00146990 | 22677000 | 21604000 | -4.732% | M62204930 | 2.013% | -1.89% | 2.013% | -1.89%
W912ER19C0008 | 10843544.4969 | 10803747.3097 | 10843544.4969 | -0.367% |  |  | N4008521C0077 |  |  |  | M62613603 | 43.49% | 0% | 43.49% | 0%
W912ER19C0015 | 25846444.9783 | 26213357.7525 | 25846444.9783 | 1.42% |  |  | N32446381 | 0 | 68582000 |  | M62974602 | 50.92% | -4.83% | 50.92% | -4.83%
W912ER19C0016 | 14273713.5896 | 14121784.7619 | 14273713.5896 | -1.064% |  |  | N4008521D0083 |  |  |  | M670011320 | 50% | -2.99% | 50% | -2.99%
W912ER20C0002 | 100061.0342 | 350213.6196 | 100061.0342 | 250% |  |  | N626881035 | 0 | 2907000 |  | M670011479 | 67.8% | 8.547% | 67.8% | 8.547%
W912G09D00040008 | 47537665.5305 | 57123627.4284 | 47537665.5305 | 20.16% |  |  | N626881035A | 0 | 2907000 |  | M670011498 | 180.8% | 5.529% | 180.8% | 5.529%
W912GB07C0007NA | 33255600.3386 | 35840204.491 | 33255600.3386 | 7.772% |  |  | N4019216D2704 |  |  |  | M670011503 | 180.8% | 5.157% | 180.8% | 5.157%
W912GB09C0038 | 35323500.415 | 37288175.988 | 35323500.415 | 5.562% |  |  | N61755680 | 2804000 | 2385000 | -14.94% | M67001686 | 200.4% | 2.26% | 200.4% | 2.26%
W912GB10C0031, | 57839893.929 | 63383977.4661 | 57839893.929 | 9.585% |  |  | N4019217C1305 |  |  |  | M67001726 | 0% | -0.3704% | 0% | -0.3704%
W912GB11C0029 | 83659303.9845 | 96479695.4285 | 83659303.9845 | 15.32% |  |  | N41557635 | 8715000 | 11425000 | 31.1% | M67001729 | 200.4% | 31.44% | 200.4% | 31.44%
W912GB12C0006 | 45695081.6794 | 48165583.2322 | 45695081.6794 | 5.406% |  |  | N4019218C1300 |  |  |  | M67004971 | 0% | -3.158% | 0% | -3.158%
W912GB12C0012 | 21914383.7857 | 21930825.2439 | 21914383.7857 | 0.07503% |  |  | DESC1709 | 21445996 | 21445996 | 0% | M67004972 | 3.84% | -2.799% | 3.84% | -2.799%
W912GB12C0022 | 56127890.8396 | 58335563.9665 | 56127890.8396 | 3.933% |  |  | N4019218D2804 |  |  |  | M67004977 | 3.571% | 2.57% | 3.571% | 2.57%
W912GB12C0024 | 94075524.3198 | 102175988.3557 | 94075524.3198 | 8.611% |  |  | AJJY183017 | 3967372 | 3967372 | 0% | M67029007 | 228.2% | 4.106% | 228.2% | 4.106%
W912GB12C0025 | 46229388.1178 | 53144644.8838 | 46229388.1178 | 14.96% |  |  | N4425512C3008 |  |  |  | M673991232 | 128.9% | 17.16% | 128.9% | 17.16%
W912GB12C0041 | 61951807.6063 | 62977548.052 | 61951807.6063 | 1.656% |  |  | N68436990 | 80735000 | 82357000 | 2.009% | M67399222 | 37.92% | 15.88% | 37.92% | 15.88%
W912GB13R0003 | 277843756.589 | 215748781.7663 | 277843756.589 | -22.35% |  |  | N4425516C7002 |  |  |  | M67400606 | -47.05% | 0% | -47.05% | 0%
W912GB14C0005 | 6435543.2321 | 6435543.2321 | 6435543.2321 | 0% |  |  | N68436431 | 19943000 | 22666000 | 13.65% | M67604132 | 0% | -5.928% | 0% | -5.928%
W912GB15D00500002 | 7630598.3249 | 7630598.3249 | 7630598.3249 | 0% |  |  | N4425516C7004 |  |  |  | M67861650 | 0% | -5.606% | 0% | -5.606%
W912GB15D00560002 | 1629625.3505 | 1629625.3505 | 1629625.3505 | 0% |  |  | N68436993 | 32047000 | 32209000 | 0.5055% | M67865198 | 22.78% | 4.981% | 22.78% | 4.981%
W912GB15D0060 | 2648595.818 | 2648595.818 | 2648595.818 | 0% |  |  | N4425516C7005 |  |  |  | M67865203 | 22.78% | 7.891% | 22.78% | 7.891%
W912GB16C0003 | 2580574.0714 | 2737867.4838 | 2580574.0714 | 6.095% |  |  | N68436983 | 31744000 | 35122000 | 10.64% | M67865210 | 44.83% | 14.27% | 44.83% | 14.27%
W912GB16C0038 | 26195637.2625 | 28599708.4095 | 26195637.2625 | 9.177% |  |  | N4425517C8002 |  |  |  | M67865222 | 23.45% | 9.045% | 23.45% | 9.045%
W912GB17C0005 | 212129.3925 | 212129.3925 | 212129.3925 | 0% |  |  | N68436401 | 17270000 | 17652000 | 2.212% | M67865238 | 0% | 43.93% | 0% | 43.93%
W912GB17C0019 | 16382033.9544 | 19878166.4885 | 16382033.9544 | 21.34% |  |  | N4425517D4007 |  |  |  | M67865249 | 57.83% | 6.082% | 57.83% | 6.082%
W912GB17C0023 | 2610882.5587 | 2808793.8196 | 2610882.5587 | 7.58% |  |  | N68436438 | 10040000 | 10445000 | 4.034% | M68479135 | 74.66% | 1.754% | 74.66% | 1.754%
W912GB17F0444 | 1692976.556 | 1692976.556 | 1692976.556 | 0% |  |  | N4425517D4014 |  |  |  | MAHG063004 | 93.23% | 0% | 93.23% | 0%
W912GB18C0013 | 10716792.3074 | 10716792.3074 | 10716792.3074 | 0% |  |  | N00620258 | 7114000 | 7063000 | -0.7169% | MAHG173002 | 0% | 0% | 0% | 0%
W912GB18F0020 | 2705642.118 | 2705642.118 | 2705642.118 | 0% |  |  | N4425517D4032 |  |  |  | MAHG173003 | 0% | 0% | 0% | 0%
W912GB19F0076 | 3899854.2841 | 3899854.2841 | 3899854.2841 | 0% |  |  | N00620240 | 28966000 | 29771000 | 2.779% | MPLS113003A | 0% | 0% | 0% | 0%
W912HN07D0024 | 4446840.5122 | 5369703.8402 | 4446840.5122 | 20.75% |  |  | N00620253 | 12949000 | 13813000 | 6.672% | MPLS3274JB | 142.9% | 0.8921% | 142.9% | 0.8921%
W912HN07D0042 | 30468500.4053 | 30873015.9965 | 30468500.4053 | 1.328% |  |  | N4425517D4034 |  |  |  | MSET153501 | 0% | 0% | 0% | 0%
W912HN07D0054 | 23724547.0772 | 24659004.399 | 23724547.0772 | 3.939% |  |  | N68436400 | 38496000 | 39961000 | 3.806% | MSET153514 | 0% | 0% | 0% | 0%
W912HN07D0056 | 14429679.9029 | 15111962.5978 | 14429679.9029 | 4.728% |  |  | N4425519C0003 |  |  |  | MXRD153006 | -7.368% | 0% | -7.368% | 0%
W912HN09C0022 | 6097820.3913 | 7214676.1375 | 6097820.3913 | 18.32% |  |  | N00620256 | 45981000 | 47543000 | 3.397% | N00128714 | 9.383% | -4.122% | 9.383% | -4.122%
W912HN09C0046 | 15441285.2583 | 16488029.7355 | 15441285.2583 | 6.779% |  |  | N4425520C1002 |  |  |  | N00129664 | 0% | -1.526% | 0% | -1.526%
W912HN09C0050 | 14816253.0069 | 15991672.3816 | 14816253.0069 | 7.933% |  |  | N68436447 | 43771888 | 50919000 | 16.33% | N00204723 | 40.48% | -3.746% | 40.48% | -3.746%
W912HN10C0024 | 3639160.8365 | 3805668.9255 | 3639160.8365 | 4.575% |  |  | N4425520C2002 |  |  |  | N00206493 | 68.57% | -3.246% | 68.57% | -3.246%
W912HN10C0028 | 3348158.8013 | 3772247.4565 | 3348158.8013 | 12.67% |  |  | N68436834 | 73000000 | 101304000 | 38.77% | N00206500 | 53.3% | 8.586% | 53.3% | 8.586%
W912HN10C0054 | 22974519.2075 | 28015423.3149 | 22974519.2075 | 21.94% |  |  | N4425521R20000014 |  |  |  | N00207674 | 42.52% | 1.54% | 42.52% | 1.54%
W912HN10C0063 | 8206795.7491 | 9277168.9306 | 8206795.7491 | 13.04% |  |  | DESC2002 | 54249000 | 54387326 | 0.255% | N00207711 | 0% | -4.653% | 0% | -4.653%
W912HN10D0033 | 1241712.5769 | 1261467.0776 | 1241712.5769 | 1.591% |  |  | N6247011D1010 |  |  |  | N00213678 | 0% | 0.7418% | 0% | 0.7418%
W912HN10D0049 | 21517733.5871 | 23317303.2419 | 21517733.5871 | 8.363% |  |  | Q183 | 15050 | 16162 | 7.389% | N00213731 | 88.58% | -3.397% | 88.58% | -3.397%
W912HN10D0055 | 19981863.6455 | 23060909.3948 | 19981863.6455 | 15.41% |  |  | N6247013D6022 |  |  |  | N00216485 | 56.49% | 8.68% | 56.49% | 8.68%
W912HN10D0056 | 3017893.0987 | 3060512.1997 | 3017893.0987 | 1.412% |  |  | N00216450 | 50430000 | 49912000 | -1.027% | N00245110 | 0% | -6.131% | 0% | -6.131%
W912HN10D0057 | 18596510.0254 | 18884916.7769 | 18596510.0254 | 1.551% |  |  | N6247016C6001 |  |  |  | N00245312 | 0% | -2.475% | 0% | -2.475%
W912HN10D0058 | 10254216.9871 | 11184354.7424 | 10254216.9871 | 9.071% |  |  | N62863712 | 19252000 | 22395000 | 16.33% | N00245440 | 0.4619% | 108.4% | 0.4619% | 108.4%
W912HN10D0059 | 11490652.3587 | 15118525.3351 | 11490652.3587 | 31.57% |  |  | N6247016C6003 |  |  |  | N00245800 | 0% | 8.313% | 0% | 8.313%
W912HN10D0060 | 12634379.351 | 13004462.8905 | 12634379.351 | 2.929% |  |  | AM00115 | 9233000 | 8557000 | -7.322% | N002461017 | 0% | -5.347% | 0% | -5.347%
W912HN10D0061 | 26590863.4287 | 30403845.5829 | 26590863.4287 | 14.34% |  |  | N6247016D6006 |  |  |  | N00246947 | 97.66% | 27.69% | 97.66% | 27.69%
W912HN10D0063 | 42577766.678 | 48508379.9793 | 42577766.678 | 13.93% |  |  | 14041 | 22911000 | 23032000 | 0.5281% | N00246988 | 23.64% | 0.02025% | 23.64% | 0.02025%
W912HN11C0009 | 11688381.6582 | 11915229.8248 | 11688381.6582 | 1.941% |  |  | N6247017C5002 |  |  |  | N00246991 | 97.88% | 22.66% | 97.88% | 22.66%
W912HN11C0010 | 16175734.3023 | 18792677.2397 | 16175734.3023 | 16.18% |  |  | PAYZ15001H | 27192353 | 37466344 | 37.78% | N00620240 | 31.15% | 2.656% | 31.15% | 2.656%
W912HN11C0011 | 3405475.3612 | 3426728.0432 | 3405475.3612 | 0.6241% |  |  | N6247017C5003 |  |  |  | N00620253 | 35.03% | 6.497% | 35.03% | 6.497%
W912HN11C0014 | 34917741.3606 | 36778319.8454 | 34917741.3606 | 5.328% |  |  | DESC1701 | 20577000 | 21577000 | 4.86% | N00620256 | 11.32% | 3.23% | 11.32% | 3.23%
W912HN11C0016 | 3750247.5815 | 3897398.4882 | 3750247.5815 | 3.924% |  |  | N6247017C5005 |  |  |  | N00620258 | -5.128% | -0.6981% | -5.128% | -0.6981%
W912HN11D0002 | 56399096.1416 | 66909598.9334 | 56399096.1416 | 18.64% |  |  | N62995407 | 23632000 | 22817000 | -3.449% | N32414547 | 328.3% | 63.79% | 328.3% | 63.79%
W912HN11D0003 | 15345916.8904 | 16129672.6436 | 15345916.8904 | 5.107% |  |  | N62995655 | 28340000 | 51111000 | 80.35% | N32443257 | 13.63% | -2.197% | 13.63% | -2.197%
W912HN12C0009 | 49377132.1622 | 52708775.5639 | 49377132.1622 | 6.747% |  |  | N6247017C5006 |  |  |  | N32443614 | 6.245% | -3.435% | 6.245% | -3.435%
W912HN12C0016 | 17609218.7596 | 18558404.8587 | 17609218.7596 | 5.39% |  |  | N62863621 | 21868000 | 23489000 | 7.413% | N324461088 | 60.04% | 0.05632% | 60.04% | 0.05632%
W912HN12D0030 | 1764390.4665 | 1807543.7235 | 1764390.4665 | 2.446% |  |  | N6247018C4004 |  |  |  | N32446285 | 91.47% | 4.02% | 91.47% | 4.02%
W912HN13D0002 | 6733190.1763 | 6931853.0743 | 6733190.1763 | 2.951% |  |  | ASHE143008 | 15453726 | 16235042 | 5.056% | N32446308 | 0% | 0.6084% | 0% | 0.6084%
W912HN16C0017 | 10517673.861 | 11441239.9836 | 10517673.861 | 8.781% |  |  | N6247018C4015 |  |  |  | N32446371 | 0% | 1.105% | 0% | 1.105%
W912HN17C0005 | 29266840.1588 | 29253115.9032 | 29266840.1588 | -0.04689% |  |  | N3379A223 | 25219000 | 23024000 | -8.704% | N32446385 | 0% | -15.65% | 0% | -15.65%
W912HN17C0006 | 9091237.5875 | 9480530.6898 | 9091237.5875 | 4.282% |  |  | N6247018R4005 |  |  |  | N3379A505 | 88.19% | 4.63% | 88.19% | 4.63%
W912HN17C0008 | 4955033.1077 | 5470528.0009 | 4955033.1077 | 10.4% |  |  | BIKF180001 | 14146220 | 14146220 | 0% | N41557230 | 0% | -20.01% | 0% | -20.01%
W912HN18C3002 | 31370777.8419 | 34668789.5284 | 31370777.8419 | 10.51% |  |  | N6247019C5006 |  |  |  | N41557250 | 22% | -4.331% | 22% | -4.331%
W912HN18C3003 | 12876339.9689 | 13405662.8397 | 12876339.9689 | 4.111% |  |  | N66691911 | 10141000 | 3548000 | -65.01% | N41557260 | 25.45% | -5.783% | 25.45% | -5.783%
W912HN19C3000 | 14386275.9228 | 15145387.6085 | 14386275.9228 | 5.277% |  |  | N6247019C5007 |  |  |  | N41557295 | 0% | -6.618% | 0% | -6.618%
W912HN19C3001 | 2932745.106 | 2967766.4679 | 2932745.106 | 1.194% |  |  | EU00117 | 36391000 | 39826000 | 9.439% | N41557601 | 44.25% | -4.082% | 44.25% | -4.082%
W912HN19C3002 | 10319070.2012 | 2834504.8447 | 10319070.2012 | -72.53% |  |  | N6247019C5009 |  |  |  | N41557715 | 29.16% | -17.3% | 29.16% | -17.3%
W912HN19C3003 | 22028471.2112 | 22954646.0864 | 22028471.2112 | 4.204% |  |  | N62588307 | 10833000 | 11195000 | 3.342% | N42237099 | 20% | 3.857% | 20% | 3.857%
W912HN19C3004 | 3495865.0492 | 3641954.1591 | 3495865.0492 | 4.179% |  |  | N62588308 | 4894000 | 4760000 | -2.738% | N42237642 | 134.9% | 9.711% | 134.9% | 9.711%
W912HN19C3006 | 24371116.9686 | 24371116.9686 | 24371116.9686 | 0% |  |  | N6247019D5002 |  |  |  | N42237671 | 15.58% | 0.2955% | 15.58% | 0.2955%
W912HN19C3008 | 4762884.9216 | 4899661.8019 | 4762884.9216 | 2.872% |  |  | N3379A505 | 11315000 | 11866000 | 4.87% | N47608265 | 54.86% | 9.24% | 54.86% | 9.24%
W912HN19C3010 | 7118123.8084 | 7133755.4518 | 7118123.8084 | 0.2196% |  |  | N6247019D8025 |  |  |  | N47608421 | 153.3% | -2.692% | 153.3% | -2.692%
W912HN20C3001 | 5158146.3118 | 5231419.6406 | 5158146.3118 | 1.421% |  |  | N476091900 | 437309406 | 483621000 | 10.59% | N47608975 | 50.15% | -0.4809% | 50.15% | -0.4809%
W912HN20C3002 | 4999049.2675 | 5082092.3734 | 4999049.2675 | 1.661% |  |  | N68469001 | 40000000 | 102049000 | 155.1% | N50092176 | 0% | -2.491% | 0% | -2.491%
W912HN20C3011 | 7038293.144 | 7031454.3 | 7038293.144 | -0.09717% |  |  | N6247020C0009 |  |  |  | N60191815 | 204% | 65.75% | 204% | 65.75%
W912HN20F4009 | 10834168.5122 | 10834168.5122 | 10834168.5122 | 0% |  |  | N62863812 | 4598802.63 | 5169000 | 12.4% | N60201154 | 11.23% | -0.08257% | 11.23% | -0.08257%
W912HP11D0016 | 2616362.5403 | 2703221.008 | 2616362.5403 | 3.32% |  |  | N6247020C0010 |  |  |  | N60201195 | 56.46% | 4.057% | 56.46% | 4.057%
W912HV15C0004 | 52266952.4649 | 70174157.2206 | 52266952.4649 | 34.26% |  |  | BIKF190001 | 19776676 | 19776676 | 0% | N60201424 | 0% | 7.946% | 0% | 7.946%
W912HV15C0005 | 36624920.695 | 37162072.5158 | 36624920.695 | 1.467% |  |  | BIKF190002 | 4671392 | 4671392 | 0% | N60201427 | 16.67% | -3.552% | 16.67% | -3.552%
W912HV15C005 | 36624920.695 | 46606201.3333 | 36624920.695 | 27.25% |  |  | BIKF190003 | 14404448 | 14404448 | 0% | N60495111 | 91.38% | -5.071% | 91.38% | -5.071%
W912HV15D0032 | 3646720.2731 | 3766653.5175 | 3646720.2731 | 3.289% |  |  | N6247020C0013 |  |  |  | N60495393 | 27.47% | -0.9417% | 27.47% | -0.9417%
W912HV16D0008 | 35463077.2665 | 36704364.4138 | 35463077.2665 | 3.5% |  |  | N62995130 | 39712368 | 45589000 | 14.8% | N60495420 | 88.25% | 10.79% | 88.25% | 10.79%
W912HV16D0009 | 98934818.6612 | 99968044.8976 | 98934818.6612 | 1.044% |  |  | N6247021D0011 |  |  |  | N60495426 | 0% | -1.803% | 0% | -1.803%
W912HV17C0002 | 29803601.7264 | 32811399.0062 | 29803601.7264 | 10.09% |  |  | N62863313 | 51758888.76 | 58177000 | 12.4% | N60495440 | 7.067% | 0.3168% | 7.067% | 0.3168%
W912HV17C0007 | 28855421.9 | 30048164.4022 | 28855421.9 | 4.134% |  |  | N62863620 | 23932976.31 | 25766000 | 7.659% | N61054011 | 0% | -6.72% | 0% | -6.72%
W912HV17D0013 | 63330677.0038 | 70504290.7336 | 63330677.0038 | 11.33% |  |  | N62863811 | 18113697.55 | 18131000 | 0.09552% | N61056512 | 0% | 0% | 0% | 0%
W912HV17D0014 | 15890723.4466 | 16131179.7728 | 15890723.4466 | 1.513% |  |  | N6247021D0016 |  |  |  | N61064402 | 17.96% | 4.773% | 17.96% | 4.773%
W912HV17D0015 | 64792028.8553 | 68695710.3848 | 64792028.8553 | 6.025% |  |  | N62863785 | 0 | 0 |  | N61065160 | 15.3% | 4.579% | 15.3% | 4.579%
W912HV18C0002 | 76538235.0728 | 83907400.0386 | 76538235.0728 | 9.628% |  |  | N62473 |  |  |  | N61065202 | 84.46% | -7.558% | 84.46% | -7.558%
W912HV19C0005 | 4224427.1656 | 4378521.1582 | 4224427.1656 | 3.648% |  |  | 72808 | 18703000 | 19971000 | 6.78% | N61065241 | 22.64% | -3.852% | 22.64% | -3.852%
W912HV20C0006 | 2414670.8755 | 2429657.7137 | 2414670.8755 | 0.6207% |  |  | N6247309D1655 |  |  |  | N61151163 | 0% | -3.557% | 0% | -3.557%
W912J31622001 | 9036028.0484 | 11003227.9803 | 9036028.0484 | 21.77% |  |  | P888 | 14869 | 14339 | -3.564% | N61151190 | 60.79% | -11.1% | 60.79% | -11.1%
W912J617C0001 | 33327408.6222 | 30890922.44 | 33327408.6222 | -7.311% |  |  | Q888 | 14869 | 14256 | -4.123% | N61151287 | 122.2% | 14% | 122.2% | 14%
W912J61822021 | 3213264.1278 | 2954142.0712 | 3213264.1278 | -8.064% |  |  | N6247310D5406 |  |  |  | N61152621 | 20.46% | 15.74% | 20.46% | 15.74%
W912J71922002 | 6003662.0506 | 5529827.8581 | 6003662.0506 | -7.892% |  |  | Q418 | 20585 | 21213 | 3.051% | N61755535 | 0% | -4.705% | 0% | -4.705%
W912JC18220001 | 19963317.7813 | 19791212.8025 | 19963317.7813 | -0.8621% |  |  | N6247310D5411 |  |  |  | N61755652 | 73.27% | 1.334% | 73.27% | 1.334%
W912JC1922001 | 3614817.551 | 3329540.0578 | 3614817.551 | -7.892% |  |  | M00681970 | 19459000 | 23408000 | 20.29% | N61755680 | 166.8% | -14.23% | 166.8% | -14.23%
W912JM19C0012 | 2920971.9943 | 3008989.6824 | 2920971.9943 | 3.013% |  |  | N6247314D0039 |  |  |  | N62588307 | 20.72% | 3.254% | 20.72% | 3.254%
W912KZ1922101 | 8494972.6741 | 7686239.3132 | 8494972.6741 | -9.52% |  |  | N61065202 | 15972000 | 14709000 | -7.908% | N62588308 | 20.72% | -2.666% | 20.72% | -2.666%
W912L1922101 | 8004882.7342 | 8004882.7342 | 8004882.7342 | 0% |  |  | N6247314D0061 |  |  |  | N62688610 | 55.03% | 6.467% | 55.03% | 6.467%
W912L61922101 | 8004882.7342 | 8004882.7342 | 8004882.7342 | 0% |  |  | Q889 | 36321 | 34701 | -4.46% | N62688762 | 129.3% | 12.29% | 129.3% | 12.29%
W912l718R0005 | 1606980.2089 | 1538591.7687 | 1606980.2089 | -4.256% |  |  | N6247314D0068 |  |  |  | N62688913 | 20.48% | -2.9% | 20.48% | -2.9%
W912L719C7001 | 30430279.3373 | 31036349.0213 | 30430279.3373 | 1.992% |  |  | M67604132 | 2887000 | 2712000 | -6.062% | N62813013 | 23.75% | 8.351% | 23.75% | 8.351%
W912LC1822001 | 5523324.0591 | 5992317.327 | 5523324.0591 | 8.491% |  |  | N00246947 | 11659000 | 15037000 | 28.97% | N62813036 | 132.7% | 7.285% | 132.7% | 7.285%
W912LD1522001 | 21501553.9498 | 22112970.6765 | 21501553.9498 | 2.844% |  |  | N6247315C1604 |  |  |  | N62813058 | 244.4% | -4.563% | 244.4% | -4.563%
W912MM1722001 | 15413867.0601 | 13435660.4144 | 15413867.0601 | -12.83% |  |  | N00245800 | 41838000 | 45470000 | 8.681% | N62813320 | 102.7% | 7.398% | 102.7% | 7.398%
W912MM2022001 | 3001831.0253 | 3581178.8112 | 3001831.0253 | 19.3% |  |  | N6247315C1609 |  |  |  | N62813704 | 3.855% | -2.816% | 3.855% | -2.816%
W912NS19C6003 | 6219450.1447 | 6303109.1742 | 6219450.1447 | 1.345% |  |  | P893 | 24873 | 24379 | -1.986% | N62995407 | 107.9% | -3.21% | 107.9% | -3.21%
W912PL12C0005 | 193306599.7503 | 250799743.0452 | 193306599.7503 | 29.74% |  |  | Q893 | 24873 | 24376 | -1.998% | N62995655 | 107.9% | 74.78% | 107.9% | 74.78%
W912PL14C0020 | 7541184.9945 | 7684059.5702 | 7541184.9945 | 1.895% |  |  | N6247315D2403 |  |  |  | N62995737 | 163.5% | 99.57% | 163.5% | 99.57%
W912PL17C0042 | 3968696.6237 | 4704666.3984 | 3968696.6237 | 18.54% |  |  | N63042218 | 7386000 | 7509000 | 1.665% | N63005985 | 0% | -3.973% | 0% | -3.973%
W912PL18C0013 | 17046042.4301 | 17069333.8108 | 17046042.4301 | 0.1366% |  |  | Q1126 | 10911 | 11647 | 6.745% | N63042218 | 186.7% | 1.592% | 186.7% | 1.592%
W912PL19C0007 | 4104199.0025 | 4104199.0025 | 4104199.0025 | 0% |  |  | N6247315D2404 |  |  |  | N63042392 | 0% | -0.1797% | 0% | -0.1797%
W912PL19C0017 | 5239687.2093 | 5575767.5438 | 5239687.2093 | 6.414% |  |  | N60495111 | 11253000 | 10656000 | -5.305% | N66691911 | 29.18% | -61.81% | 29.18% | -61.81%
W912PL19C0023 | 22219603.1627 | 22870490.1419 | 22219603.1627 | 2.929% |  |  | N6247315D2405 |  |  |  | N68436401 | 66.14% | 2.114% | 66.14% | 2.114%
W912PL20C0002 | 260632978.1633 | 416078925.6571 | 260632978.1633 | 59.64% |  |  | Q1119 | 12428 | 12167 | -2.1% | N68436431 | 295.9% | 12.76% | 295.9% | 12.76%
W912PL20C0004 | 268236616.1505 | 416519363.0269 | 268236616.1505 | 55.28% |  |  | N6247315D2426 |  |  |  | N68436438 | 52.07% | 3.945% | 52.07% | 3.945%
W912PL20C0019 | 5484345.2833 | 5796001.1748 | 5484345.2833 | 5.683% |  |  | Q776 | 30528 | 37009 | 21.23% | N68436983 | 84.71% | 10.17% | 84.71% | 10.17%
W912PL20C0035 | 5662904.1988 | 5662904.1988 | 5662904.1988 | 0% |  |  | N6247315D2427 |  |  |  | N68436990 | 0% | 1.967% | 0% | 1.967%
W912PL8C0024 | 23550410.7763 | 23677327.5301 | 23550410.7763 | 0.5389% |  |  | N60495420 | 25541000 | 28487000 | 11.53% | N68436993 | 0% | 0.4832% | 0% | 0.4832%
W912PM16F0007 | 865494.6008 | 883100.2723 | 865494.6008 | 2.034% |  |  | N6247315D2428 |  |  |  | N69212995 | 18.95% | -3.895% | 18.95% | -3.895%
W912PM17C0001 | 35113195.4588 | 35687654.6377 | 35113195.4588 | 1.636% |  |  | P920 | 47022 | 45951 | -2.278% | N69232586 | 353.5% | -0.6635% | 353.5% | -0.6635%
W912PM17C0004 | 45864427.1915 | 48926127.7921 | 45864427.1915 | 6.676% |  |  | Q920 | 47022 | 45942 | -2.297% | N69232777 | 63.15% | 8.63% | 63.15% | 8.63%
W912PM18C0011 | 36708338.5961 | 37997291.8182 | 36708338.5961 | 3.511% |  |  | N6247315R00010008 |  |  |  | N83447077 | 79.39% | -1.57% | 79.39% | -1.57%
W912PM18C0013 | 16013860.0982 | 15966087.3862 | 16013860.0982 | -0.2983% |  |  | DESC1508 | 54095271 | 58620122 | 8.365% | N83447084 | 42.82% | -0.779% | 42.82% | -0.779%
W912PM18C0014 | 18883202.4727 | 25080666.7368 | 18883202.4727 | 32.82% |  |  | N6247316C0601 |  |  |  | N83447222 | 0.277% | 8.75% | 0.277% | 8.75%
W912PM18C0015 | 12804928.0291 | 15400589.3033 | 12804928.0291 | 20.27% |  |  | M67399222 | 12948000 | 15099000 | 16.61% | NUEX093016 | 5.96% | 0.1366% | 5.96% | 0.1366%
W912PM18C0016 | 26220241.8543 | 38010296.4278 | 26220241.8543 | 44.97% |  |  | N6247316D1861 |  |  |  | NVZR123709 | 65.74% | 5.811% | 65.74% | 5.811%
W912PM18C0019 | 4332225.9326 | 4791196.8909 | 4332225.9326 | 10.59% |  |  | M673991232 | 9329000 | 11004000 | 17.95% | NVZR143703 | 34.62% | 11.41% | 34.62% | 11.41%
W912PM19C0007 | 16929075.8819 | 18163706.9692 | 16929075.8819 | 7.293% |  |  | N6247316D1862 |  |  |  | NVZR153710 | 0% | 0% | 0% | 0%
W912PM19C0016 | 10045730.9586 | 10104332.7039 | 10045730.9586 | 0.5833% |  |  | N00245312 | 2527000 | 2463000 | -2.533% | NVZR153711 | 0% | 0% | 0% | 0%
W912PM19C0043 | 9915226.8842 | 10013901.6336 | 9915226.8842 | 0.9952% |  |  | N6247316D1881 |  |  |  | NZAS043002 | -20.53% | 0% | -20.53% | 0%
W912PP09C0006 | 7404357.9825 | 7598650.4871 | 7404357.9825 | 2.624% |  |  | M62974612 | 62293000 | 62148000 | -0.2328% | NZAS173001 | 30.32% | 0% | 30.32% | 0%
W912PP09C0034 | 13690619.5174 | 20385685.6264 | 13690619.5174 | 48.9% |  |  | N6247316D1884 |  |  |  | P1219 | 73.42% | 2.242% | 73.42% | 2.242%
W912PP10C0015 | 40365652.8386 | 43220515.0523 | 40365652.8386 | 7.073% |  |  | M67865249 | 32536000 | 34614000 | 6.387% | P1394 | 3.417% | 2.152% | 3.417% | 2.152%
W912PP11C0002 | 11514254.4939 | 17192569.8899 | 11514254.4939 | 49.32% |  |  | N6247316D1887 |  |  |  | P1410 | 77.84% | -0.9132% | 77.84% | -0.9132%
W912PP11C0016 | 28687860.5177 | 29957822.3436 | 28687860.5177 | 4.427% |  |  | M62974602 | 43119000 | 40940000 | -5.053% | P1469 | 65.48% | -0.3008% | 65.48% | -0.3008%
W912PP11C0029 | 23478254.3294 | 24510436.8392 | 23478254.3294 | 4.396% |  |  | N60495440 | 18936000 | 18999000 | 0.3327% | P1475 | 108.4% | -0.1822% | 108.4% | -0.1822%
W912PP12C0002 | 16021081.3302 | 20299757.6799 | 16021081.3302 | 26.71% |  |  | N6247316D3201 |  |  |  | P1481 | 54.46% | -3.211% | 54.46% | -3.211%
W912PP12C0003 | 16218861.7823 | 16471706.6468 | 16218861.7823 | 1.559% |  |  | N002450888 | 36336000 | 48661000 | 33.92% | P225 | 33.16% | -0.2831% | 33.16% | -0.2831%
W912PP12C0023 | 26481463.7365 | 29298584.528 | 26481463.7365 | 10.64% |  |  | N6247317C0808 |  |  |  | P241 | 37.2% | 4.432% | 37.2% | 4.432%
W912PP12C0025 | 11114627.3271 | 11554272.2093 | 11114627.3271 | 3.956% |  |  | N00246991 | 61541000 | 76133000 | 23.71% | P334 | 71.33% | 4.356% | 71.33% | 4.356%
W912PP12C0027 | 33548714.9951 | 34975176.306 | 33548714.9951 | 4.252% |  |  | N6247317C0815 |  |  |  | P771 | 111.4% | 101833%
W912PP12C0033 | 17513001.0806 | 18011583.5134 | 17513001.0806 | 2.847% |  |  | N002461017 | 2943000 | 2782000 | -5.471% | P777 | 22.67% | -2.333% | 22.67% | -2.333%
W912PP14C0014 | 22440669.51 | 22883463.5999 | 22440669.51 | 1.973% |  |  | N6247317C0830 |  |  |  | P834 | 16.22% | 0.7379% | 16.22% | 0.7379%
W912PP14D0025 | 12793424.6001 | 12836114.5792 | 12793424.6001 | 0.3337% |  |  | Q890 | 37097 | 35530 | -4.224% | P888 | 55.48% | -3.402% | 55.48% | -3.402%
W912PP15C003 | 23899773.1426 | 24773351.259 | 23899773.1426 | 3.655% |  |  | N6247317C3403 |  |  |  | P893 | 37.49% | -1.902% | 37.49% | -1.902%
W912PP18C0022 | 6023615.9302 | 6163186.4413 | 6023615.9302 | 2.317% |  |  | M006811220 | 39860000 | 43124000 | 8.189% | P918 | 4.435% | -0.3945% | 4.435% | -0.3945%
W912QG19C0006 | 3209764.1524 | 3122014.6278 | 3209764.1524 | -2.734% |  |  | N6247317D0817 |  |  |  | P920 | 58.43% | -2.177% | 58.43% | -2.177%
W912QR08C0009 | 33227377.5192 | 33892765.8429 | 33227377.5192 | 2.003% |  |  | M006811310 | 62328000 | 46121000 | -26% | P921 | 13.16% | -4.224% | 13.16% | -4.224%
W912QR08C0012 | 19445502.0782 | 19895845.048 | 19445502.0782 | 2.316% |  |  | N6247317D0818 |  |  |  | PA00023 | 65.87% | 10.09% | 65.87% | 10.09%
W912QR09C0023 | 16133433.7919 | 16910847.7339 | 16133433.7919 | 4.819% |  |  | P918 | 15182 | 15119 | -0.415% | PA00028 | 80.3% | 4.134% | 80.3% | 4.134%
W912QR10C0048 | 3554859.377 | 4004166.1324 | 3554859.377 | 12.64% |  |  | Q918 | 15182 | 14821 | -2.378% | PA00032 | 1.998% | 9.628% | 1.998% | 9.628%
W912QR130032 | 77497974.9465 | 77497974.9465 | 77497974.9465 | 0% |  |  | N6247317D0819 |  |  |  | PAF150400 | 26.19% | 39.8% | 26.19% | 39.8%
W912QR14C0016 | 25482974.1386 | 26272004.6888 | 25482974.1386 | 3.096% |  |  | Q966 | 46106 | 44895 | -2.627% | PAYZ15001B | 0% | 0% | 0% | 0%
W912QR14C0019 | 3898949.7108 | 4006610.5642 | 3898949.7108 | 2.761% |  |  | N6247317D0820 |  |  |  | PAYZ16000B | 25.52% | 0.6207% | 25.52% | 0.6207%
W912QR15C0021 | 16673065.4438 | 17387789.998 | 16673065.4438 | 4.287% |  |  | N00246988 | 32923000 | 32930000 | 0.02126% | PDPG120514 | 135.7% | 1.694% | 135.7% | 1.694%
W912QR15C0026 | 40919140.1616 | 41584233.854 | 40919140.1616 | 1.625% |  |  | P200 | 26431 | 30463 | 15.25% | PNQS072140 | 0% | 0% | 0% | 0%
W912QR15D0001 | 5554530.8579 | 5831811.9909 | 5554530.8579 | 4.992% |  |  | Q200 | 26431 | 30670 | 16.04% | PNQS103165 | 0% | 0% | 0% | 0%
W912QR16C0002 | 24997063.5033 | 26210573.5805 | 24997063.5033 | 4.855% |  |  | N6247317D0821 |  |  |  | PSTE139022 | 0% | -2.734% | 0% | -2.734%
W912QR17C0002 | 12874055.4275 | 13472376.0247 | 12874055.4275 | 4.647% |  |  | P771 | 32 | 34250 | 106931% | PSXE999132 | 0% | 1.992% | 0% | 1.992%
W912QR17C0012 | 2367321.0899 | 2357045.1785 | 2367321.0899 | -0.4341% |  |  | Q771 | 32018 | 34171 | 6.724% | PTFL163001 | 0% | 2.876% | 0% | 2.876%
W912QR17C0021 | 20783402.0479 | 20868692.1123 | 20783402.0479 | 0.4104% |  |  | Q919 | 18210 | 18051 | -0.8731% | PTFL163006 | 166.6% | 4.473% | 166.6% | 4.473%
W912QR17C0031 | 56434912.5615 | 63021478.8884 | 56434912.5615 | 11.67% |  |  | Q952 | 16668 | 16762 | 0.564% | PTFL163010 | 10.35% | 0.7445% | 10.35% | 0.7445%
W912QR17C0049 | 2942605.8705 | 2942605.8705 | 2942605.8705 | 0% |  |  | N6247317D0822 |  |  |  | PTFL163019 | 6.999% | 0.6934% | 6.999% | 0.6934%
W912QR18C0003 | 22253845.8215 | 25526842.2494 | 22253845.8215 | 14.71% |  |  | M62974539 | 37962000 | 37974000 | 0.03161% | Q1119 | 0% | -2.056% | 0% | -2.056%
W912QR18C0005 | 10239080.6199 | 11220679.3652 | 10239080.6199 | 9.587% |  |  | P949 | 15467 | 16676 | 7.817% | Q1126 | 68.29% | 6.448% | 68.29% | 6.448%
W912QR18C0015 | 25048710.3109 | 25798167.4568 | 25048710.3109 | 2.992% |  |  | P950 | 18434 | 21058 | 14.23% | Q1219 | 94.63% | 1.754% | 94.63% | 1.754%
W912QR18C0026 | 7386427.5791 | 7714627.7712 | 7386427.5791 | 4.443% |  |  | Q949 | 15467 | 16189 | 4.668% | Q1288 | 94.63% | 2.965% | 94.63% | 2.965%
W912QR18C0031 | 5220092.3895 | 5308546.3437 | 5220092.3895 | 1.694% |  |  | Q950 | 18434 | 20159 | 9.358% | Q1396 | 40.7% | 23.33% | 40.7% | 23.33%
W912QR18C0037 | 1777785.9835 | 1802801.242 | 1777785.9835 | 1.407% |  |  | N6247317D4627 |  |  |  | Q1410 | 77.84% | -0.9132% | 77.84% | -0.9132%
W912QR18C0048 | 2583673.6013 | 2768786.5145 | 2583673.6013 | 7.165% |  |  | M00243312 | 9525039 | 10133000 | 6.383% | Q1469 | 65.48% | -0.3008% | 65.48% | -0.3008%
W912QR19C0009 | 1881519.3725 | 1869512.0484 | 1881519.3725 | -0.6382% |  |  | N6247317D4628 |  |  |  | Q1475 | 108.4% | -0.1822% | 108.4% | -0.1822%
W912QR19C0017 | 9068655.174 | 9366493.8465 | 9068655.174 | 3.284% |  |  | M00681334 | 14684000 | 14959000 | 1.873% | Q1481 | 54.46% | -3.211% | 54.46% | -3.211%
W912QR19C0020 | 10670486.8459 | 10118401.0904 | 10670486.8459 | -5.174% |  |  | N6247317D4635 |  |  |  | Q157 | 199.8% | 1.755% | 199.8% | 1.755%
W912QR19C0021 | 11623130.6236 | 11645346.1199 | 11623130.6236 | 0.1911% |  |  | M006815001 | 9032000 | 8888000 | -1.594% | Q166 | 89.47% | -1.593% | 89.47% | -1.593%
W912QR19C0051 | 21254695.0847 | 22131044.0964 | 21254695.0847 | 4.123% |  |  | M00681574 | 12715000 | 12544000 | -1.345% | Q170 | 38.41% | -1.496% | 38.41% | -1.496%
W912QR20C0009 | 3705260.0956 | 4837577.269 | 3705260.0956 | 30.56% |  |  | N476091924 | 1660000 | 4986000 | 200.4% | Q183 | 43.05% | 7.226% | 43.05% | 7.226%
W912QR20C0011 | 6614034.3591 | 6614034.3591 | 6614034.3591 | 0% |  |  | N6247318C1017 |  |  |  | Q225 | 17.3% | -0.1415% | 17.3% | -0.1415%
W912QR20C0012 | 19763054.8604 | 20349241.4903 | 19763054.8604 | 2.966% |  |  | Q892 | 49562 | 48220 | -2.708% | Q240 | 0% | -7.68% | 0% | -7.68%
W912QR20C0019 | 6109726.7469 | 6331500.6885 | 6109726.7469 | 3.63% |  |  | Q964 | 39378 | 38024 | -3.438% | Q241 | 37.2% | 4.116% | 37.2% | 4.116%
W912SV13R0001 | 24510590.5523 | 24930506.043 | 24510590.5523 | 1.713% |  |  | N6247318C2201 |  |  |  | Q334 | 71.33% | 4.356% | 71.33% | 4.356%
W912UM13C0025 | 26258935.9302 | 28531650.1827 | 26258935.9302 | 8.655% |  |  | N63042282 | 52594000 | 49645000 | -5.607% | Q418 | 63.78% | 2.921% | 63.78% | 2.921%
W912UM17C0044 | 1232700214.1092 | 1255093873.5581 | 1232700214.1092 | 1.817% |  |  | N6247318C2202 |  |  |  | Q771 | 133.5% | 6.404% | 133.5% | 6.404%
W912UM19C0015 | 44362136.9901 | 51491143.3874 | 44362136.9901 | 16.07% |  |  | DESC1611 | 26868000 | 26926198 | 0.2166% | Q776 | 84.62% | 20.33% | 84.62% | 20.33%
W912UM19C0017 | 1261542.8116 | 1261542.8116 | 1261542.8116 | 0% |  |  | N6247318C2205 |  |  |  | Q777 | 22.67% | -2.333% | 22.67% | -2.333%
W912WJ17C0004 | 39540209.9478 | 41087564.6077 | 39540209.9478 | 3.913% |  |  | N60495393 | 15675000 | 15520000 | -0.9888% | Q834 | 0% | -3.256% | 0% | -3.256%
W912WJ19C0011 | 21180708.5229 | 26817869.947 | 21180708.5229 | 26.61% |  |  | N6247318C4602 |  |  |  | Q888 | 55.48% | -3.934% | 55.48% | -3.934%
W912WJ19C0014 | 2411756.3993 | 2411756.3993 | 2411756.3993 | 0% |  |  | M67399192 | 55390000 | 53775000 | -2.916% | Q889 | 33.44% | -4.263% | 33.44% | -4.263%
W91SMC1922001 | 5137955.6867 | 4703200.6029 | 5137955.6867 | -8.462% |  |  | N6247318C4605 |  |  |  | Q890 | 33.44% | -4.037% | 33.44% | -4.037%
W91ZRU1622001 | 27744960.7082 | 23337814.2291 | 27744960.7082 | -15.88% |  |  | M67865198 | 115031000 | 120890000 | 5.093% | Q892 | 7.957% | -2.579% | 7.957% | -2.579%
WH12DR14D0019 | 24595835.3512 | 33869845.3657 | 24595835.3512 | 37.71% |  |  | M67865203 | 38707000 | 41830000 | 8.068% | Q893 | 37.49% | -1.913% | 37.49% | -1.913%
Y18228 | 1260841.123 | 1838193.2902 | 1260841.123 | 45.79% |  |  | N6247318D0820 |  |  |  | Q919 | 87.74% | -0.8346% | 87.74% | -0.8346%
Y20003 | 3001831.0253 | 2908041.1645 | 3001831.0253 | -3.124% |  |  | P921 | 47550 | 45441 | -4.435% | Q920 | 58.43% | -2.195% | 58.43% | -2.195%
Y20410 | 4143527.4253 | 4059507.3417 | 4143527.4253 | -2.028% |  |  | Q921 | 47550 | 45424 | -4.471% | Q921 | 13.16% | -4.258% | 13.16% | -4.258%
Grand Total | 17049515778.1934 | #VALUE! | 17049515778.1934 | #VALUE! |  |  | N6247318D5817 |  |  |  | Q9440 | 220.6% | -1.272% | 220.6% | -1.272%
|  |  | 0 |  |  |  | ACJP183018 | 4749000 | 4749000 | 0% | Q952 | 12.11% | 0.539% | 12.11% | 0.539%
|  |  | 0 |  |  |  | N60495426 | 3295000 | 3234000 | -1.851% | Q964 | 7.957% | -3.275% | 7.957% | -3.275%
|  |  | 0 |  |  |  | XDAT1026962 | 0 | 0 |  | Q966 | 23.02% | -2.511% | 23.02% | -2.511%
|  |  | 0 |  |  |  | N6247318D5850 |  |  |  | QJVF012005 | 48.41% | 0% | 48.41% | 0%
|  |  | 0 |  |  |  | M62204930 | 23592000 | 23136000 | -1.933% | RKMF063004 | 18.4% | 2.929% | 18.4% | 2.929%
|  |  | 0 |  |  |  | N6247318D5853 |  |  |  | RKMF203001 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | M006811901 | 46146000 | 46788000 | 1.391% | RVKQ079104 | 18.38% | 0.1911% | 18.38% | 0.1911%
|  |  | 0 |  |  |  | M67865210 | 34513000 | 39683000 | 14.98% | SGBP1047602 | 1430% | 0% | 1430% | 0%
|  |  | 0 |  |  |  | N476091903 | 111944000 | 124945000 | 11.61% | SMYU073011 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | N61065160 | 19180000 | 20082000 | 4.703% | SXHT013001 | 68.1% | 0.4928% | 68.1% | 0.4928%
|  |  | 0 |  |  |  | N69232777 | 19686000 | 21473000 | 9.078% | SXHT171217 | 28.09% | 0% | 28.09% | 0%
|  |  | 0 |  |  |  | N6247318D5855 |  |  |  | TMKH003003 | 35.52% | -0.2983% | 35.52% | -0.2983%
|  |  | 0 |  |  |  | 14021 | 27799000 | 28065000 | 0.9569% | UHHZ163000 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | 89906 | 15767000 | 15980000 | 1.351% | ULDF123001 | 6.738% | 0% | 6.738% | 0%
|  |  | 0 |  |  |  | N00245110 | 14817000 | 13884000 | -6.297% | ULYB049040 | 45.66% | 0.8688% | 45.66% | 0.8688%
|  |  | 0 |  |  |  | N476091916 | 53426000 | 61905000 | 15.87% | VDYDS97032 | 8.77% | 0% | 8.77% | 0%
|  |  | 0 |  |  |  | N476091918 | 50924000 | 58919000 | 15.7% | VKAG013004R5 | 2477% | 0% | 2477% | 0%
|  |  | 0 |  |  |  | N63042366 | 16347000 | 16549000 | 1.236% | VKAG159021 | 33.02% | 11.67% | 33.02% | 11.67%
|  |  | 0 |  |  |  | N69232586 | 27152000 | 26967000 | -0.6813% | WEAS079054 | 0% | -9.52% | 0% | -9.52%
|  |  | 0 |  |  |  | N6247318D5858 |  |  |  | WWYK093003 | 10.74% | 2.644% | 10.74% | 2.644%
|  |  | 0 |  |  |  | M006812000 | 53611262.49 | 62002000 | 15.65% | WWYK153005 | 14.59% | 0.8845% | 14.59% | 0.8845%
|  |  | 0 |  |  |  | N6247318D5860 |  |  |  | WWYK193003 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | M006811599 | 1876000 | 2178000 | 16.1% | XDQU139458 | 45.39% | 3.013% | 45.39% | 3.013%
|  |  | 0 |  |  |  | N6247318D5862 |  |  |  | XHZG179037 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | N61065241 | 23001000 | 22091000 | -3.956% | XLWU193005 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | N61065243 | 18993300 | 21649000 | 13.98% | XLWU193006 | 0% | -0.05719% | 0% | -0.05719%
|  |  | 0 |  |  |  | N6247319C1208 |  |  |  | YTPM059004 | 48.7% | -5.174% | 48.7% | -5.174%
|  |  | 0 |  |  |  | N00245440 | 47724000 | 102132000 | 114% | YWHG031002R2 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | N6247319C1211 |  |  |  | ZHTV153201 | 0% | 0% | 0% | 0%
|  |  | 0 |  |  |  | N002461018 | 53283000 | 61863000 | 16.1% | Grand Total | #VALUE! | #VALUE!
|  |  | 0 |  |  |  | N6247319C1238
|  |  | 0 |  |  |  | P855 | 96932 | 102065 | 5.295%
|  |  | 0 |  |  |  | Q855 | 96932 | 98243 | 1.352%
|  |  | 0 |  |  |  | N6247319C2425
|  |  | 0 |  |  |  | M67865238 | 4828000 | 7006000 | 45.11%
|  |  | 0 |  |  |  | N6247319C2450
|  |  | 0 |  |  |  | N61065224 | 111089000 | 113495000 | 2.166%
|  |  | 0 |  |  |  | N6247319C2455
|  |  | 0 |  |  |  | N63042284 | 107641000 | 103221000 | -4.106%
|  |  | 0 |  |  |  | N6247319C5826
|  |  | 0 |  |  |  | M67865222 | 11358000 | 12413000 | 9.289%
|  |  | 0 |  |  |  | N6247319D2428
|  |  | 0 |  |  |  | N63042392 | 13545000 | 13520000 | -0.1846%
|  |  | 0 |  |  |  | N6247319D2430
|  |  | 0 |  |  |  | M006815002 | 3326000 | 3443000 | 3.518%
|  |  | 0 |  |  |  | N360423271 | 19465544 | 49122000 | 152.4%
|  |  | 0 |  |  |  | N6247319D2438
|  |  | 0 |  |  |  | N47609810 | 53866451 | 57165000 | 6.124%
|  |  | 0 |  |  |  | N6247319F5135
|  |  | 0 |  |  |  | DESC17U3 | 4384341 | 4883963 | 11.4%
|  |  | 0 |  |  |  | N6247320C0055
|  |  | 0 |  |  |  | M006811090 | 53546419 | 80806000 | 50.91%
|  |  | 0 |  |  |  | M006811090A | 0 | 248000
|  |  | 0 |  |  |  | N6247320C0553
|  |  | 0 |  |  |  | N002461024 | 69801056 | 74980000 | 7.42%
|  |  | 0 |  |  |  | N6247320C0612
|  |  | 0 |  |  |  | M00681079 | 35918000 | 34747000 | -3.26%
|  |  | 0 |  |  |  | N6247320C0613
|  |  | 0 |  |  |  | XDAT1051930 | 123643850 | 124327472 | 0.5529%
|  |  | 0 |  |  |  | N6247321D1206
|  |  | 0 |  |  |  | M006811130 | 42661879 | 48134000 | 12.83%
|  |  | 0 |  |  |  | N476091919 | 36044616 | 45821000 | 27.12%
|  |  | 0 |  |  |  | N476091922 | 52301995 | 73261000 | 40.07%
|  |  | 0 |  |  |  | N6247321D1211
|  |  | 0 |  |  |  | N476091904 | 217657842 | 236454000 | 8.636%
|  |  | 0 |  |  |  | N6247321D1214
|  |  | 0 |  |  |  | N476091911 | 113295655 | 145640000 | 28.55%
|  |  | 0 |  |  |  | N6247321D1220
|  |  | 0 |  |  |  | M67865280 | 0 | 5325000
|  |  | 0 |  |  |  | N6247321D1406
|  |  | 0 |  |  |  | N00245443 | 55500000 | 62125000 | 11.94%
|  |  | 0 |  |  |  | N6247813D4007
|  |  | 0 |  |  |  | N62813058 | 2810000 | 2673000 | -4.875%
|  |  | 0 |  |  |  | N6247814D4001
|  |  | 0 |  |  |  | N62813036 | 8520000 | 9184000 | 7.793%
|  |  | 0 |  |  |  | N6247818C1516
|  |  | 0 |  |  |  | N61064416 | 23932000 | 26696000 | 11.55%
|  |  | 0 |  |  |  | N6247818D4024
|  |  | 0 |  |  |  | N62813216 | 17897000 | 17831000 | -0.3688%
|  |  | 0 |  |  |  | N6247819C1515
|  |  | 0 |  |  |  | N62813704 | 73199000 | 71082000 | -2.892%
|  |  | 0 |  |  |  | N6247819D5029
|  |  | 0 |  |  |  | P463 | 54279 | 61404 | 13.13%
|  |  | 0 |  |  |  | Q463 | 0 | 64930
|  |  | 0 |  |  |  | N6247820C4016
|  |  | 0 |  |  |  | N62813033 | 50430000 | 35936000 | -28.74%
|  |  | 0 |  |  |  | N6247820D4003
|  |  | 0 |  |  |  | KNMD624007 | 8552000 | 8552000 | 0%
|  |  | 0 |  |  |  | N6247820D4015
|  |  | 0 |  |  |  | N62813044 | 58566450 | 39107000 | -33.23%
|  |  | 0 |  |  |  | N628131006 | 58566450 | 30327000 | -48.22%
|  |  | 0 |  |  |  | N6274210D13070002
|  |  | 0 |  |  |  | AJJY133027 | 96616619 | 102900955 | 6.504%
|  |  | 0 |  |  |  | N6274210D1307JQ01
|  |  | 0 |  |  |  | AJJY123010 | 89918305 | 92491623 | 2.862%
|  |  | 0 |  |  |  | N6274214C1300
|  |  | 0 |  |  |  | M00318884 | 17720000 | 16256000 | -8.262%
|  |  | 0 |  |  |  | N6274214C1304
|  |  | 0 |  |  |  | N62813320 | 33970000 | 36725000 | 8.11%
|  |  | 0 |  |  |  | N6274214MP00028
|  |  | 0 |  |  |  | N61054011 | 9458000 | 8792000 | -7.042%
|  |  | 0 |  |  |  | N6274215C1301
|  |  | 0 |  |  |  | M00318907 | 47645000 | 40860000 | -14.24%
|  |  | 0 |  |  |  | M00318908 | 53999000 | 50582000 | -6.328%
|  |  | 0 |  |  |  | N6274215C1305
|  |  | 0 |  |  |  | M00318861 | 51071000 | 52377000 | 2.557%
|  |  | 0 |  |  |  | N6274215C1308
|  |  | 0 |  |  |  | DESC1551 | 42823800 | 46800984 | 9.287%
|  |  | 0 |  |  |  | N6274216C1309
|  |  | 0 |  |  |  | AJJY133028 | 26463336 | 29311091 | 10.76%
|  |  | 0 |  |  |  | N6274216C1312
|  |  | 0 |  |  |  | 78150 | 79722000 | 83356000 | 4.558%
|  |  | 0 |  |  |  | N6274216C1317
|  |  | 0 |  |  |  | N41557230 | 20799000 | 16445000 | -20.93%
|  |  | 0 |  |  |  | N6274216C1325
|  |  | 0 |  |  |  | M00318863 | 50583000 | 50006000 | -1.141%
|  |  | 0 |  |  |  | N6274217C1307
|  |  | 0 |  |  |  | M00318923 | 72494000 | 71484000 | -1.393%
|  |  | 0 |  |  |  | N6274217C1313
|  |  | 0 |  |  |  | DESC1705 | 26978100 | 28361127 | 5.126%
|  |  | 0 |  |  |  | N6274217C1319
|  |  | 0 |  |  |  | N41557715 | 123661000 | 100681000 | -18.58%
|  |  | 0 |  |  |  | N6274217C1320
|  |  | 0 |  |  |  | M00318902 | 24797000 | 29732000 | 19.9%
|  |  | 0 |  |  |  | N6274217C1325
|  |  | 0 |  |  |  | N61755535 | 47314000 | 44985000 | -4.922%
|  |  | 0 |  |  |  | N6274217F0307
|  |  | 0 |  |  |  | 14DISA01 | 1781248 | 1781248 | 0%
|  |  | 0 |  |  |  | N6274218C1300
|  |  | 0 |  |  |  | N41557250 | 43203000 | 41238000 | -4.548%
|  |  | 0 |  |  |  | N41557260 | 53554000 | 50302000 | -6.072%
|  |  | 0 |  |  |  | N6274218C1306
|  |  | 0 |  |  |  | 15DISA02 | 8794967 | 12189000 | 38.59%
|  |  | 0 |  |  |  | N6274218C1314
|  |  | 0 |  |  |  | PAF150400 | 24132780 | 33953429 | 40.69%
|  |  | 0 |  |  |  | N6274218C1316
|  |  | 0 |  |  |  | N41557601 | 75233000 | 72008000 | -4.287%
|  |  | 0 |  |  |  | N6274218C1318
|  |  | 0 |  |  |  | N61755652 | 28975000 | 29381000 | 1.401%
|  |  | 0 |  |  |  | N6274219C1301
|  |  | 0 |  |  |  | N41557295 | 18002000 | 16749000 | -6.96%
|  |  | 0 |  |  |  | N6274219C1303
|  |  | 0 |  |  |  | M00318946 | 62559000 | 62483000 | -0.1215%
|  |  | 0 |  |  |  | N6274219C1309
|  |  | 0 |  |  |  | N41557H279 | 78787000 | 75634000 | -4.002%
|  |  | 0 |  |  |  | N41557H280 | 40850000 | 39044000 | -4.421%
|  |  | 0 |  |  |  | N41557H282 | 83378000 | 79846000 | -4.236%
|  |  | 0 |  |  |  | N6274219C1310
|  |  | 0 |  |  |  | N61755640 | 36419000 | 36147000 | -0.7469%
|  |  | 0 |  |  |  | N6274219C1316
|  |  | 0 |  |  |  | PAF160600 | 62585000 | 62595227 | 0.01634%
|  |  | 0 |  |  |  | N6274219C1317
|  |  | 0 |  |  |  | N62813013 | 59383000 | 64476000 | 8.577%
|  |  | 0 |  |  |  | N6274219C1319
|  |  | 0 |  |  |  | N62813169 | 64705000 | 69905000 | 8.036%
|  |  | 0 |  |  |  | N6274219C1320
|  |  | 0 |  |  |  | N61064402 | 25137000 | 26399000 | 5.02%
|  |  | 0 |  |  |  | N6274219C1321
|  |  | 0 |  |  |  | M00318887 | 18697000 | 19344000 | 3.46%
|  |  | 0 |  |  |  | N6274219D1328
|  |  | 0 |  |  |  | N61755491 | 50514009 | 54163000 | 7.224%
|  |  | 0 |  |  |  | N6274219D1329
|  |  | 0 |  |  |  | N61159802 | 36571666 | 41359000 | 13.09%
|  |  | 0 |  |  |  | N6274219D1330
|  |  | 0 |  |  |  | N41557296 | 17683000 | 17949000 | 1.504%
|  |  | 0 |  |  |  | N6274219D1331
|  |  | 0 |  |  |  | N41557270 | 27191000 | 25408000 | -6.557%
|  |  | 0 |  |  |  | N6274219D1332
|  |  | 0 |  |  |  | N61159311 | 27795000 | 28047000 | 0.9066%
|  |  | 0 |  |  |  | N6274220C1303
|  |  | 0 |  |  |  | PAF180300 | 10310997 | 10421366 | 1.07%
|  |  | 0 |  |  |  | N6274220C1304
|  |  | 0 |  |  |  | M00318877 | 34513000 | 18250000 | -47.12%
|  |  | 0 |  |  |  | N6274220C1324
|  |  | 0 |  |  |  | AJJY073105P3 | 49677730 | 49677730 | 0%
|  |  | 0 |  |  |  | N6274221C1315
|  |  | 0 |  |  |  | N61159803 | 0 | 9380000
|  |  | 0 |  |  |  | N6274221C1335
|  |  | 0 |  |  |  | N61159804 | 36105000 | 36105000 | 0%
|  |  | 0 |  |  |  | N6274221C1338
|  |  | 0 |  |  |  | AJJY203001 | 41944700 | 42937637 | 2.367%
|  |  | 0 |  |  |  | N6274221C1339
|  |  | 0 |  |  |  | AJJY203001 | 66610 | 66610 | 0%
|  |  | 0 |  |  |  | N6274221C1346
|  |  | 0 |  |  |  | N41557735 | 0 | 6003000
|  |  | 0 |  |  |  | N41557735A | 122137577.15 | 85174000 | -30.26%
|  |  | 0 |  |  |  | N6345017C1305
|  |  | 0 |  |  |  | DESC1706 | 8783275 | 8783275 | 0%
|  |  | 0 |  |  |  | N6945012C0754
|  |  | 0 |  |  |  | 71503 | 9548000 | 2026000 | -78.78%
|  |  | 0 |  |  |  | N6945013C1756
|  |  | 0 |  |  |  | 71317 | 38744000 | 46104000 | 19%
|  |  | 0 |  |  |  | N6945013D1762
|  |  | 0 |  |  |  | N00213678 | 14151000 | 14261000 | 0.7773%
|  |  | 0 |  |  |  | N6945013D1771
|  |  | 0 |  |  |  | AWUB095000 | 26418933 | 26418933 | 0%
|  |  | 0 |  |  |  | N6945014C1756
|  |  | 0 |  |  |  | N42237099 | 39730000 | 41372000 | 4.133%
|  |  | 0 |  |  |  | N6945014D0757
|  |  | 0 |  |  |  | Q170 | 10593 | 10431 | -1.529%
|  |  | 0 |  |  |  | N6945014D1267
|  |  | 0 |  |  |  | N60201426 | 76123000 | 73246000 | -3.779%
|  |  | 0 |  |  |  | N6945014D1269
|  |  | 0 |  |  |  | N60201154 | 40518000 | 40483000 | -0.08638%
|  |  | 0 |  |  |  | N6945014D1271
|  |  | 0 |  |  |  | Q9440 | 4140 | 4085 | -1.329%
|  |  | 0 |  |  |  | N6945015D1618
|  |  | 0 |  |  |  | N83447084 | 2500000 | 2480000 | -0.8%
|  |  | 0 |  |  |  | N6945016C1604
|  |  | 0 |  |  |  | DESC1606 | 36565000 | 57832172 | 58.16%
|  |  | 0 |  |  |  | N6945016C1612
|  |  | 0 |  |  |  | AM00103 | 63028574 | 70507000 | 11.87%
|  |  | 0 |  |  |  | N6945016D0100
|  |  | 0 |  |  |  | N00213731 | 9097000 | 8772000 | -3.573%
|  |  | 0 |  |  |  | N6945016D0615
|  |  | 0 |  |  |  | N00216485 | 4213000 | 4597000 | 9.115%
|  |  | 0 |  |  |  | N6945016D1110
|  |  | 0 |  |  |  | N60201424 | 14616000 | 15831000 | 8.313%
|  |  | 0 |  |  |  | N6945016D1111
|  |  | 0 |  |  |  | N00207674 | 3036000 | 3084000 | 1.581%
|  |  | 0 |  |  |  | N42237671 | 2979000 | 2988000 | 0.3021%
|  |  | 0 |  |  |  | N60201421 | 11062000 | 11655000 | 5.361%
|  |  | 0 |  |  |  | N6945016D1112
|  |  | 0 |  |  |  | M67004972 | 8625000 | 8378000 | -2.864%
|  |  | 0 |  |  |  | N60201195 | 3600000 | 3750000 | 4.167%
|  |  | 0 |  |  |  | N6945016D1113
|  |  | 0 |  |  |  | N42237642 | 14240000 | 15692000 | 10.2%
|  |  | 0 |  |  |  | N6945017C1613
|  |  | 0 |  |  |  | N00206500 | 11589000 | 12630000 | 8.983%
|  |  | 0 |  |  |  | N6945017D0507
|  |  | 0 |  |  |  | N00204723 | 20056000 | 19270000 | -3.919%
|  |  | 0 |  |  |  | N62604855 | 21022000 | 21246000 | 1.066%
|  |  | 0 |  |  |  | N6945018C2105
|  |  | 0 |  |  |  | AWUB105003 | 3774341 | 3774341 | 0%
|  |  | 0 |  |  |  | N6945018D1313
|  |  | 0 |  |  |  | N60514343 | 12440000 | 11911000 | -4.252%
|  |  | 0 |  |  |  | N6945018D1317
|  |  | 0 |  |  |  | 89839 | 5634000 | 5634000 | 0%
|  |  | 0 |  |  |  | N6945018D1318
|  |  | 0 |  |  |  | N60508288 | 2466000 | 4583000 | 85.85%
|  |  | 0 |  |  |  | N83447077 | 11343000 | 11156000 | -1.649%
|  |  | 0 |  |  |  | N6945018D1320
|  |  | 0 |  |  |  | N00206493 | 4632000 | 4478000 | -3.325%
|  |  | 0 |  |  |  | N6945018D1323
|  |  | 0 |  |  |  | Q246U | 0 | 6328
|  |  | 0 |  |  |  | N6945019C0501
|  |  | 0 |  |  |  | N60514160 | 66357000 | 62810000 | -5.345%
|  |  | 0 |  |  |  | N6945019C0903
|  |  | 0 |  |  |  | N00213741 | 63582000 | 61720000 | -2.929%
|  |  | 0 |  |  |  | N6945019c1304
|  |  | 0 |  |  |  | DESC1608 | 20334000 | 20334000 | 0%
|  |  | 0 |  |  |  | N6945019C2105
|  |  | 0 |  |  |  | AWUB105005 | 2907892 | 2907892 | 0%
|  |  | 0 |  |  |  | N6945019C5214
|  |  | 0 |  |  |  | Q240 | 18436 | 16982 | -7.887%
|  |  | 0 |  |  |  | N6945019C5648
|  |  | 0 |  |  |  | N00207711 | 2323000 | 2212000 | -4.778%
|  |  | 0 |  |  |  | N6945019D0908
|  |  | 0 |  |  |  | N00206475 | 6796000 | 26130000 | 284.5%
|  |  | 0 |  |  |  | N6945019D0909
|  |  | 0 |  |  |  | N00213720 | 30995000 | 29632000 | -4.397%
|  |  | 0 |  |  |  | N6945019D0910
|  |  | 0 |  |  |  | 89902 | 21895000 | 22895000 | 4.567%
|  |  | 0 |  |  |  | N6945019D0918
|  |  | 0 |  |  |  | M67695009 | 10933245 | 12625000 | 15.47%
|  |  | 0 |  |  |  | N6945019D0919
|  |  | 0 |  |  |  | P945 | 17165 | 18219 | 6.14%
|  |  | 0 |  |  |  | Q945 | 18408 | 18219 | -1.027%
|  |  | 0 |  |  |  | N6945019D0920
|  |  | 0 |  |  |  | 93298 | 3859000 | 3910000 | 1.322%
|  |  | 0 |  |  |  | N6945019D0921
|  |  | 0 |  |  |  | MAHG173002 | 3591891 | 3591891 | 0%
|  |  | 0 |  |  |  | MAHG173003 | 4007591 | 4007591 | 0%
|  |  | 0 |  |  |  | N6945019D0922
|  |  | 0 |  |  |  | N42237643 | 11207000 | 11489000 | 2.516%
|  |  | 0 |  |  |  | N6945019D1085
|  |  | 0 |  |  |  | N60508253 | 10500000 | 16343000 | 55.65%
|  |  | 0 |  |  |  | N6945019F0855
|  |  | 0 |  |  |  | N60201427 | 27496000 | 26493000 | -3.648%
|  |  | 0 |  |  |  | N6945019F1275
[7 empty] | DDPM130007 | 2179491 | 2179491 | 0%
N6945020C2575
[7 empty] | N83447222 | 1763000 | 1921000 | 8.962%
N6945020D0036
[7 empty] | N83447181 | 0 | 1101000
N6945020F0870
[7 empty] | MAHG063004 | 5057057 | 5057057 | 0%
N6945021C0004
[7 empty] | VLSB193001 | 46487791 | 46487791 | 0%
N6945021C0005
[7 empty] | RQLH059034 | 7261649 | 6401000 | -11.85%
[7 empty] | RQLH189009 | 21831459 | 19244906 | -11.85%
N6945021C0019
[7 empty] | N00213211 | 52266000 | 51919000 | -0.6639%
N6945021C0031
[7 empty] | TUMR189003 | 9201235 | 7791000 | -15.33%
[7 empty] | TUMR189004 | 31741307 | 27230000 | -14.21%
N6945021C0038
[7 empty] | DDPM414396 | 11259595 | 11259595 | 0%
[7 empty] | DDPM414415 | 16788096 | 16788096 | 0%
N9127816C0035
[7 empty] | DRMS1701 | 3788549 | 3788549 | 0%
NGB01
[7 empty] | 571863 | 3000000 | 2895000 | -3.5%
NGB2220C0002
[7 empty] | 280408 | 8100000 | 6069000 | -25.07%
NGBID20B0009
[7 empty] | 160174 | 3000000 | 2430000 | -19%
PC12318312000
[7 empty] | 511503 | 15000000 | 16999000 | 13.33%
PLACE
[7 empty] | DESC19S2 | 6193389 | 7190107 | 16.09%
S
[7 empty] | XLWU203006 | 1072907 | 1072907 | 0%
Swift
[7 empty] | 270132 | 39000000 | 40487000 | 3.813%
T180901
[7 empty] | 290186 | 12000000 | 9934000 | -17.22%
T181801
[7 empty] | 290109 | 32000000 | 24564000 | -23.24%
USACE
[7 empty] | M67861650 | 11741000 | 11065000 | -5.758%
w
[7 empty] | DESC1701 | 20577000 | 20577000 | 0%
W4126C18C0049
[7 empty] | FNWZ100071A | 4378953 | 4378953 | 0%
W50S6V21C0001
[7 empty] | TDKA169004 | 8176132 | 7902831 | -3.343%
W50S7020C0002
[7 empty] | XDQU109057 | 20213955 | 20422750 | 1.033%
W50S7G20C0001
[7 empty] | ULYB169010 | 5962100 | 5653014 | -5.184%
W50S8721C5001
[7 empty] | FJRP189050 | 3279911 | 3216900 | -1.921%
W50S8721C5002
[7 empty] | FJRP199040 | 4690132 | 4598700 | -1.949%
W50S8N20C0001
[7 empty] | HAAW179035 | 3428805 | 3325800 | -3.004%
W50S8R20C0003
[7 empty] | PBXP929798 | 10316495 | 10365100 | 0.4711%
W50S8R21C0002
[7 empty] | PBXP169102 | 2279117 | 2160653 | -5.198%
W50S8W22C0001
[7 empty] | DPEZ029038 | 5527675 | 5375875 | -2.746%
W50S8X21C0001
[7 empty] | QMSN199056 | 55702065 | 54219500 | -2.662%
W50S8Z20C0001
[7 empty] | KJAQ119006 | 12181613 | 11876137 | -2.508%
W50S8Z21C0001
[7 empty] | KJAQ159096 | 7873129 | 7697582 | -2.23%
W50S9F21C0001
[7 empty] | XGFG189001 | 10552313 | 9135750 | -13.42%
W901UZ21C0001
[7 empty] | KKGA169022 | 13557321 | 13039500 | -3.819%
W911KB14C0011
[7 empty] | 634 | 13300000 | 15604000 | 17.32%
W911KB17C0002
[7 empty] | 657 | 112949720 | 119078184 | 5.426%
W911KB17C0021
[7 empty] | FTQW170100 | 17956192 | 18837872 | 4.91%
W911KB17C0029
[7 empty] | 653 | 6954581 | 8191098 | 17.78%
W911KB17C0030
[7 empty] | DESC1707 | 4088355 | 4129621 | 1.009%
W911KB17D0010
[7 empty] | 89227 | 6390000 | 6770000 | 5.947%
W911KB17D0012
[7 empty] | 93022 | 5379000 | 6563000 | 22.01%
W911KB17F0055
[7 empty] | FTQW170100 | 37199 | 37199 | 0%
[7 empty] | FTQW180107 | 22546 | 22546 | 0%
[7 empty] | FTQW183001 | 692488 | 692488 | 0%
W911KB18C0006
[7 empty] | DXEB053005 | 19278001 | 20221652 | 4.895%
W911KB18C0015
[7 empty] | 657 | 24399601 | 24558572 | 0.6515%
W911KB18C0018
[7 empty] | FTQW180107 | 19051000 | 24167601 | 26.86%
W911KB18C0023
[7 empty] | 674 | 5201420 | 5098000 | -1.988%
W911KB18C0026
[7 empty] | FTQW183001 | 82125000 | 84396009 | 2.765%
W911KB18C0028
[7 empty] | 674 | 37930620 | 39050000 | 2.951%
W911KB18C0030
[7 empty] | 674 | 57614000 | 64248876 | 11.52%
W911KB18R0006
[7 empty] | 657 | 13335000 | 14660442 | 9.94%
W911KB19C0001
[7 empty] | 659 | 257315000 | 266664022 | 3.633%
W911KB19C0006
[7 empty] | 674 | 167982000 | 199283270 | 18.63%
W911KB19C0013
[7 empty] | FTQW180109 | 19794920 | 20495551 | 3.539%
W911KB19C0030
[7 empty] | FTQW1054329 | 15241345 | 15241345 | 0%
W911KB19F0159
[7 empty] | FTQW170100 | 30099 | 30099 | 0%
[7 empty] | FTQW180107 | 18242 | 18242 | 0%
[7 empty] | FTQW183001 | 560312 | 560312 | 0%
W911KB19R0008
[7 empty] | FTQW1053834 | 9258084 | 9258084 | 0%
W911KB20C0002
[7 empty] | 659 | 27640000 | 30614914 | 10.76%
W911KB20C008
[7 empty] | FXSB982839 | 51446741 | 51446741 | 0%
W911KB21C0012
[7 empty] | 680 | 90974126 | 91294126 | 0.3517%
W911KB21C0033
[7 empty] | FTQW170100 | 1174838 | 1174838 | 0%
W911KB21F0085
[7 empty] | FTQW170100 | 15588 | 15588 | 0%
[7 empty] | FTQW180107 | 26041 | 26041 | 0%
[7 empty] | FTQW183001 | 31412 | 31412 | 0%
W911YN19C0001
[7 empty] | LSGA019179 | 6346208 | 6410955 | 1.02%
W911YN2022003
[7 empty] | 120330 | 3000000 | 3000000 | 0%
W9123616C0025
[7 empty] | DESC1607 | 20646000 | 21280000 | 3.071%
W9123616R00080005
[7 empty] | DESC1607 | 20646000 | 21088000 | 2.141%
W9123618C0008
[7 empty] | DSCR1501 | 6253160 | 7509000 | 20.08%
W9123618C0025
[7 empty] | 80771 | 50257000 | 51308106 | 2.091%
W9123619C0014
[7 empty] | 77779 | 40458000 | 40771000 | 0.7736%
W9123619C0043
[7 empty] | DESC1914 | 4917000 | 5048000 | 2.664%
W9123619C0044
[7 empty] | DESC1909 | 8330000 | 8453000 | 1.477%
W9123620C2025
[7 empty] | 80775 | 104543631 | 104914693 | 0.3549%
W9123620C2027
[7 empty] | 73391 | 47269000 | 46831000 | -0.9266%
W9123621C2005
[7 empty] | MUHJ133000 | 46375000 | 46375000 | 0%
W9123621C2013
[7 empty] | MUHJ179000 | 7644604 | 6748367 | -11.72%
W9123621C2024
[7 empty] | 60276 | 63845000 | 64004000 | 0.249%
W9123818C0015
[7 empty] | 71057 | 87549000 | 98782000 | 12.83%
W9123818C0020
[7 empty] | 77538 | 7970000 | 10413000 | 30.65%
W9123819C0010
[7 empty] | DESC1714 | 19480000 | 20000032 | 2.67%
W9123819C0015
[7 empty] | 76093 | 8916000 | 10402000 | 16.67%
W9123820C0012
[7 empty] | KRSM1065068 | 100809955 | 100809955 | 0%
W9123821C0007
[7 empty] | KRSM113031 | 3892900 | 3892900 | 0%
W9123821C0011
[7 empty] | 74877 | 13438000 | 13438000 | 0%
W9124217C0005
[7 empty] | 371301 | 15729000 | 16942000 | 7.712%
W9124218220019
[7 empty] | 371402 | 1950000 | 4760000 | 144.1%
W9124219C5001
[7 empty] | FJRP159073 | 20879519 | 20323383 | -2.664%
W9124219C5004
[7 empty] | FJRP159062 | 29161433 | 28170000 | -3.4%
W9124219C5007
[7 empty] | FJRP199080 | 5224985 | 5049432 | -3.36%
W912431822001
[7 empty] | 310140 | 9300000 | 8685000 | -6.613%
W912431922001
[7 empty] | 310103 | 35000000 | 27225000 | -22.21%
W9124V1622001
[7 empty] | 300031 | 12806888 | 16905621 | 32%
W9126G08D0056CV01
[7 empty] | 71325 | 45536000 | 47478000 | 4.265%
W9126G09D00960002
[7 empty] | 72481 | 10488000 | 10634000 | 1.392%
W9126G11P0208
[7 empty] | 72481 | 46000 | 46000 | 0%
W9126G12C0038
[7 empty] | 72481 | 3848000 | 3879000 | 0.8056%
W9126G12C0051
[7 empty] | 72754 | 16319000 | 22835000 | 39.93%
W9126G12P0014
[7 empty] | 72481 | 4047000 | 4047000 | 0%
W9126G13C0004
[7 empty] | 72481 | 308188000 | 461117000 | 49.62%
W9126G13C0046
[7 empty] | 72481 | 1540000 | 623000 | -59.55%
W9126G14D0050
[7 empty] | 68530 | 37657000 | 55028000 | 46.13%
W9126G14D00500002
[7 empty] | MPLS3274JB | 6077000 | 6133616 | 0.9316%
W9126G14P0150
[7 empty] | 72481 | 3279420 | 1538000 | -53.1%
W9126G17C0046
[7 empty] | 81234 | 2580000 | 2708000 | 4.961%
W9126G18C0018
[7 empty] | DDCX1701A | 36159560 | 36510784 | 0.9713%
W9126G18C0066
[7 empty] | DDCX1701B | 3881804 | 3881804 | 0%
W9126G18C0077
[7 empty] | 81422 | 40138000 | 48168000 | 20.01%
W9126G19C0001
[7 empty] | MPLS083737R5 | 98410381 | 98410381 | 0%
[7 empty] | MPLS083737S3 | 55663720 | 55663720 | 0%
W9126G19C0019
[7 empty] | MPLS113003A | 2872000 | 2872000 | 0%
W9126G19C0020
[7 empty] | 74989 | 22822000 | 23434000 | 2.682%
W9126G19C0023
[7 empty] | MPLS083737R6 | 103001487 | 103001487 | 0%
W9126G19C0026
[7 empty] | DESC19I1 | 8330000 | 8453000 | 1.477%
W9126G19C0035
[7 empty] | MPLS083737R5 | 5546178 | 5546178 | 0%
W9126G19C0119
[7 empty] | 88380 | 30477000 | 36023000 | 18.2%
W9126G19C0124
[7 empty] | 93016 | 2404000 | 2469000 | 2.704%
W9126G19D0021
[7 empty] | 94610 | 37106000 | 47319000 | 27.52%
[7 empty] | 94611 | 130750000 | 178637000 | 36.62%
[7 empty] | 94612 | 43620000 | 66268000 | 51.92%
W9126G19D0024
[7 empty] | 94609 | 55842000 | 121858000 | 118.2%
W9126G20C0004
[7 empty] | 88844 | 3999000 | 3999000 | 0%
W9126G20C0005
[7 empty] | 75157 | 8315000 | 8403000 | 1.058%
W9126G20C0009
[7 empty] | 67402 | 8996000 | 9321000 | 3.613%
W9126G20C0038
[7 empty] | 91996 | 13350000 | 13141000 | -1.566%
W9126G21C0005
[7 empty] | 33584 | 44927000 | 44928000 | 0.002226%
W9126G21C0014
[7 empty] | 87807 | 36514000 | 36525000 | 0.03013%
W9127807D0026
[7 empty] | 63711 | 7175815 | 9584934 | 33.57%
W9127807D0036
[7 empty] | 60833 | 15072000 | 15260312 | 1.249%
W9127809C0003
[7 empty] | 53712A | 9243000 | 9544521 | 3.262%
W9127809C0010
[7 empty] | 33017 | 5240500 | 6602985 | 26%
W9127809C0017
[7 empty] | 67428 | 0 | 39068176
W9127810518
[7 empty] | XLWU193006 | 16624000 | 16614000 | -0.06015%
W9127810C0041
[7 empty] | 69560 | 2643455 | 3157424 | 19.44%
W9127810D0058
[7 empty] | 68526 | 10815034 | 12431294 | 14.94%
W9127810D0072
[7 empty] | 69449 | 4110280 | 4984696 | 21.27%
W9127811D0028
[7 empty] | NVZR123709 | 9981550 | 10581450 | 6.01%
W9127811D0029
[7 empty] | 61064 | 13951000 | 14300613 | 2.506%
[7 empty] | 79438 | 7193631 | 7896819 | 9.775%
W9127811D0062
[7 empty] | 76375 | 27358000 | 29794432 | 8.906%
W9127811D0066
[7 empty] | 69382 | 25816000 | 28305680 | 9.644%
W9127811D0067
[7 empty] | 69287 | 15404000 | 25866356 | 67.92%
W9127811D0068
[7 empty] | 76366 | 16664200 | 19188822 | 15.15%
[7 empty] | 76371 | 19092800 | 20598546 | 7.886%
W9127811D0073
[7 empty] | 69287 | 30907435 | 33877211 | 9.609%
[7 empty] | 76376 | 51696668 | 61769562 | 19.48%
W9127812D0037
[7 empty] | AM00048 | 45415526 | 47090618 | 3.688%
[7 empty] | AM00110 | 39010686 | 48637745 | 24.68%
[7 empty] | FTFA113004 | 29942300 | 32051388 | 7.044%
W9127812D0038
[7 empty] | NVZR143703 | 34157000 | 38234191 | 11.94%
W9127812D0039
[7 empty] | 69302 | 36061000 | 39828403 | 10.45%
[7 empty] | 79437 | 38659000 | 53691548 | 38.88%
[7 empty] | AM00031 | 32124000 | 33068283 | 2.939%
W9127812D0040
[7 empty] | 83702 | 25870100 | 29269603 | 13.14%
W9127816C0021
[7 empty] | FTEV073010 | 16065430 | 16483443 | 2.602%
W9127816D0015
[7 empty] | ANZY163001 | 19344000 | 20218608 | 4.521%
[7 empty] | NVZR153711 | 8163765 | 8163765 | 0%
W9127816D0016
[7 empty] | FTFA033003 | 12034000 | 12208303 | 1.448%
W9127816D0018
[7 empty] | 92518 | 21993000 | 23127000 | 5.156%
W9127816D0031
[7 empty] | FTFA043000 | 7687194 | 7712303 | 0.3266%
W9127816D0033
[7 empty] | 65699 | 16707000 | 18188000 | 8.865%
[7 empty] | FTEV153003 | 10689719 | 11218212 | 4.944%
[7 empty] | SXHT013001 | 12383350 | 12447196 | 0.5156%
W9127816D0035
[7 empty] | 92422 | 3929000 | 3929000 | 0%
W9127818C0026
[7 empty] | FTFA163003 | 8007902 | 8052184 | 0.553%
W9127819C00006
[7 empty] | FTFA043000 | 59456363 | 59676833 | 0.3708%
W9127819C0012
[7 empty] | FTFA093965 | 26376465 | 26387419 | 0.04153%
W9127819C0013
[7 empty] | FTFA143913 | 31295038 | 31286284 | -0.02797%
W9127819C0017
[7 empty] | PNQS072140 | 13341000 | 13341000 | 0%
W9127819C0019
[7 empty] | 61388 | 18881000 | 18977000 | 0.5084%
W9127819C0024
[7 empty] | 86816 | 32995000 | 34056000 | 3.216%
W9127819C0034
[7 empty] | FTFA053017 | 45719464 | 45719464 | 0%
W9127819C0037
[7 empty] | PNQS103165 | 12768107 | 12768107 | 0%
W9127819F0486
[7 empty] | XLWU193005 | 12369134 | 12369134 | 0%
W9127820C0008
[7 empty] | 89946 | 5292000 | 5551000 | 4.894%
W9127820C0009
[7 empty] | FTEV153008 | 30127950 | 29857715 | -0.897%
W9127820C0010
[7 empty] | NVZR153710 | 3351127 | 3351127 | 0%
W9127820C0027
[7 empty] | DESC19S4 | 13051000 | 13051000 | 0%
W9127820C0033
[7 empty] | FTFA163007 | 0 | 0
W9127821C0006
[7 empty] | 76673 | 34050000 | 34762000 | 2.091%
W9127821C0012
[7 empty] | DESC1513 | 14758000 | 14809000 | 0.3456%
W9127Q21C0015
[7 empty] | LRXQ159097 | 7233035 | 7123500 | -1.514%
W9127S13D6001
[7 empty] | 81430 | 52181000 | 56349000 | 7.988%
W9127S20C6006
[7 empty] | NKAK123007 | 35396600 | 35396600 | 0%
W9128A12D0012
[7 empty] | 86914 | 2523000 | 2591000 | 2.695%
W9128A16C0004
[7 empty] | 80412 | 26084000 | 27183000 | 4.213%
W9128A16C0006
[7 empty] | 59779 | 54844000 | 57844000 | 5.47%
W9128A16D0005
[7 empty] | 93021 | 5827000 | 5827000 | 0%
W9128A16D0011
[7 empty] | 80412 | 1484000 | 1484000 | 0%
W9128A17C0005
[7 empty] | 70668 | 1137760000 | 1339628000 | 17.74%
W9128A18C0001
[7 empty] | 80412 | 74987000 | 73999000 | -1.318%
W9128A18C0009
[7 empty] | KNMD043004 | 41476374 | 44043580 | 6.19%
W9128A18C0016
[7 empty] | 30439 | 4800000 | 4800000 | 0%
W9128A19C0006
[7 empty] | 91742 | 14200000 | 15266000 | 7.507%
W9128A20C0006
[7 empty] | 52203 | 44925000 | 45597000 | 1.496%
W9128A21C0007
[7 empty] | 76897 | 76594000 | 78551000 | 2.555%
W9128F10C0061
[7 empty] | 63831 | 28586634 | 33108929 | 15.82%
W9128F12C0011
[7 empty] | 69278 | 3505997 | 3578435 | 2.066%
W9128F13C0006
[7 empty] | 81483 | 1513371 | 1642769 | 8.55%
W9128F14C0024
[7 empty] | 76367 | 36441000 | 33300649 | -8.618%
W9128F14C0030
[7 empty] | 69446 | 15083965 | 16145285 | 7.036%
W9128F15C0032
[7 empty] | DESC1463 | 8518820 | 8267000 | -2.956%
[7 empty] | DESC1507 | 17178089 | 17906802 | 4.242%
W9128F16C0033
[7 empty] | 47942 | 9065868 | 9433554 | 4.056%
W9128F16D00550001
[7 empty] | GHLN083004 | 5168580 | 5168580 | 0%
W9128F17C0032
[7 empty] | 77305 | 61936000 | 62889000 | 1.539%
W9128F180281
[7 empty] | 77987 | 11396000 | 13579000 | 19.16%
W9128F18C0026
[7 empty] | QJVF012005 | 24993526 | 24993526 | 0%
W9128F18C0037
[7 empty] | 73375 | 18943000 | 19040000 | 0.5121%
W9128F18R00040030
[7 empty] | CRWU093002 | 34249000 | 34971796 | 2.11%
W9128F19C0005
[7 empty] | GHLN153001 | 154671056 | 154671056 | 0%
W9128F19C0016
[7 empty] | 81899 | 8794325 | 9276699 | 5.485%
W9128F19C0018
[7 empty] | 79447 | 12309817 | 13873974 | 12.71%
W9128F19C0022
[7 empty] | 74618 | 6560000 | 6633000 | 1.113%
W9128F19C0023
[7 empty] | SGBP1047602 | 9132924 | 9132924 | 0%
W9128F19C0029
[7 empty] | 77301 | 69147000 | 70917000 | 2.56%
W9128F19C0032
[7 empty] | DESC1609 | 7499541 | 7716000 | 2.886%
W9128F20C0006
[7 empty] | 86943 | 3384000 | 3384000 | 0%
W9128F20C0029
[7 empty] | 77303 | 46209000 | 46745000 | 1.16%
W9128F20C0038
[7 empty] | XQPZ164001 | 26744525 | 26827768 | 0.3113%
W9128F20C0039
[7 empty] | DECS1913 | 22124000 | 22201000 | 0.348%
W9128F20C0048
[7 empty] | CRWU173001 | 4763991 | 4849127 | 1.787%
W9128F21C0013
[7 empty] | XQPZ174006 | 5040100 | 5040100 | 0%
W9128F21C0019
[7 empty] | TDKA143002 | 43789430 | 43789430 | 0%
W9128F21C0039
[7 empty] | XGFG189004 | 21978910 | 19678800 | -10.47%
W9128F21C0040
[7 empty] | XHZG179037 | 8000000 | 8000000 | 0%
W9128F21C0041
[7 empty] | GLEN203001 | 121968000 | 121968000 | 0%
W9129917C0011
[7 empty] | DESC1702 | 20973000 | 21083000 | 0.5245%
W912BU16R00370006
[7 empty] | DESC1605 | 23170900 | 23170900 | 0%
W912BU19C0017
[7 empty] | AM00047 | 47962590 | 49780896 | 3.791%
W912BU20C0015
[7 empty] | FJXT133000 | 47042000 | 47042000 | 0%
W912BU20C0033
[7 empty] | 86204 | 3408000 | 3452000 | 1.291%
W912BV15C0001
[7 empty] | DESC1502 A | 32060100 | 32532000 | 1.472%
W912BV15C0017
[7 empty] | DESC1502 | 4556371 | 4733000 | 3.877%
[7 empty] | DESC1502 B | 17410000 | 17410000 | 0%
W912BV17C0004
[7 empty] | WWYK153005 | 97939000 | 98825383 | 0.905%
W912BV17C0005
[7 empty] | WWYK093003 | 12472000 | 12809463 | 2.706%
W912BV17C0010
[7 empty] | AGGN173001 | 10428748 | 10774827 | 3.319%
W912BV17C0014
[7 empty] | 72738 | 67487000 | 67762000 | 0.4075%
W912BV17D0017
[7 empty] | 91328 | 4623000 | 4623000 | 0%
W912BV19C0002
[7 empty] | WWYK193003 | 24873819 | 24873819 | 0%
W912BV19C0003
[7 empty] | 75661 | 59467000 | 59467000 | 0%
W912BV19C0011
[7 empty] | AGGN213001 | 12250972 | 12250972 | 0%
W912BV19C0015
[7 empty] | WWYK193001 | 69771792 | 69771792 | 0%
W912BV19C0017
[7 empty] | WWYK193014 | 71921672 | 71921672 | 0%
W912BV19C0022
[7 empty] | DESC18S2 | 6186000 | 6717000 | 8.584%
W912BV19C0024
[7 empty] | AGGN123003 | 0 | 0
W912BV20C0005
[7 empty] | AGGN053009 | 183861 | 183861 | 0%
W912DQ17C7002
[7 empty] | NGA-016A-IPO | 3146064 | 3152406 | 0.2016%
W912DQ17D4016
[7 empty] | 88028 | 1979000 | 1990000 | 0.5558%
W912DQ17R7000
[7 empty] | NGA-016A | 319965869 | 336914829 | 5.297%
[7 empty] | NGA-016B | 315507977 | 345771897 | 9.592%
W912DQ18C4051
[7 empty] | PRQE055155 | 0 | 0
W912DQ19C4000
[7 empty] | 75660 | 8690000 | 9023000 | 3.832%
W912DQ19C4001
[7 empty] | YWHG031002R2 | 224178 | 224178 | 0%
W912DQ19C4011
[7 empty] | 91884 | 890697000 | 906600000 | 1.785%
W912DQ19D4001
[7 empty] | 93000 | 2595000 | 2599000 | 0.1541%
W912DQ19F4003
[7 empty] | 77140 | 10585000 | 10530000 | -0.5196%
W912DQ20C4000
[7 empty] | 89203 | 2714000 | 4499000 | 65.77%
W912DR07C0070
[7 empty] | 58395 | 2657000 | 2657000 | 0%
W912DR08C0016
[7 empty] | 58395 | 603000 | 604000 | 0.1658%
W912DR08C0038
[7 empty] | 58395 | 1472000 | 1472000 | 0%
W912DR08C0053
[7 empty] | 58395 | 2465000 | 2465000 | 0%
W912DR08C0078
[7 empty] | 58395 | 706000 | 706000 | 0%
W912DR09C0026
[7 empty] | 58395 | 3200000 | 7149000 | 123.4%
W912DR09C0030
[7 empty] | 65731 | 436000 | 436000 | 0%
W912DR09C0052
[7 empty] | 64156 | 14398000 | 17919000 | 24.45%
[7 empty] | 65731 | 7915345 | 37771000 | 377.2%
W912DR10C0033
[7 empty] | 17872 | 113223000 | 129078000 | 14%
[7 empty] | 21120 | 12060000 | 13760000 | 14.1%
W912DR10C0035
[7 empty] | 21372 | 4443000 | 4201000 | -5.447%
W912DR10C0079
[7 empty] | 17781 | 11700000 | 11700000 | 0%
W912DR10F0217
[7 empty] | 65731 | 280922 | 280922 | 0%
W912DR11C0034
[7 empty] | 17782 | 3200000 | 3200000 | 0%
W912DR11C0036
[7 empty] | 17866 | 125900000 | 131089216 | 4.122%
W912DR12C0019
[7 empty] | 23051 | 116975000 | 132008057 | 12.85%
W912DR12F0081
[7 empty] | 23051 | 5621000 | 5621000 | 0%
W912DR13C0005
[7 empty] | 24649 | 564589000 | 608357051 | 7.752%
W912DR13C0021
[7 empty] | 25047 | 5253000 | 5792000 | 10.26%
W912DR13C0038
[7 empty] | 26170 | 123058382 | 171004789 | 38.96%
W912DR15C0015
[7 empty] | 77000 | 206445000 | 218443000 | 5.812%
W912DR15C0025
[7 empty] | 58395 | 7750000 | 7476000 | -3.535%
W912DR15C0026
[7 empty] | 31934 | 24554985 | 26455691 | 7.741%
W912DR15D0032
[7 empty] | 27532 | 40081050 | 45544834 | 13.63%
[7 empty] | 31066 | 30538350 | 33305344 | 9.061%
[7 empty] | 31067 | 13900000 | 14104547 | 1.472%
W912DR16C0013
[7 empty] | 30583 | 616311000 | 711463223 | 15.44%
W912DR16C0049
[7 empty] | DDCX1309 A | 2597449 | 2768000 | 6.566%
W912DR16D0017
[7 empty] | 87744 | 7232827
W912DR17C0022
[7 empty] | DCX1305 | 4831000 | 4865000 | 0.7038%
W912DR17D0002
[7 empty] | 91474 | 24006000 | 24006000 | 0%
W912DR17D0012
[7 empty] | 58395 | 1607000 | 1580000 | -1.68%
W912DR17D0014
[7 empty] | 420502 | 20000000 | 15725000 | -21.38%
W912DR17D0015
[7 empty] | 80772 | 7745692 | 8571497 | 10.66%
[7 empty] | 88963 | 11774418
W912DR19C0013
[7 empty] | 35168 | 650261000 | 675303918 | 3.851%
W912DR19C0057
[7 empty] | 87645 | 9255000 | 9255000 | 0%
W912DR20C0004
[7 empty] | 32100 | 34227105 | 35707039 | 4.324%
W912DR20C0007
[7 empty] | 88077 | 152798000 | 161586000 | 5.751%
W912DR20C0014
[7 empty] | 87637 | 9711000 | 9711000 | 0%
W912DR20C0015
[7 empty] | 88790 | 20553000 | 20553000 | 0%
W912DR20C0042
[7 empty] | 86409 | 24482000 | 24603000 | 0.4942%
W912DR21C0009
[7 empty] | 92232 | 16690000 | 16690000 | 0%
W912DR21C0016
[7 empty] | 35161 | 21386000 | 21386000 | 0%
W912DR21C0052
[7 empty] | 77000 | 3052000 | 3052000 | 0%
W912DS11C0023
[7 empty] | 59044 | 105270000 | 127708000 | 21.31%
W912DS14C0030
[7 empty] | DESC1501 | 8637000 | 9333465 | 8.064%
W912DS17C0005
[7 empty] | AM00033 | 48535000 | 50878598 | 4.829%
W912DS18B00210013
[7 empty] | PTFL163001 | 4427200 | 4557949 | 2.953%
W912DS18C0027
[7 empty] | PTFL163006 | 3159200 | 3307588 | 4.697%
W912DS19B007
[7 empty] | PTFL163010 | 7994996 | 8056120 | 0.7645%
W912DS19C0008
[7 empty] | 88231 | 4185000 | 5123000 | 22.41%
W912DS19C0011
[7 empty] | PTFL163019 | 52324000 | 52696600 | 0.7121%
W912DS19C0018
[7 empty] | 90722 | 14893000 | 17784000 | 19.41%
W912DS19C0033
[7 empty] | 63054 | 25164000 | 30295000 | 20.39%
W912DS20C0005
[7 empty] | ULDF123001 | 13147968 | 13147968 | 0%
W912DS20C0025
[7 empty] | 87933 | 21732000 | 21702000 | -0.138%
W912DS21C0002
[7 empty] | 78804 | 186676000 | 187624000 | 0.5078%
W912DS22C0002
[7 empty] | 81352 | 0 | 0
W912DW15C0003
[7 empty] | 69257 | 4484160 | 5129236 | 14.39%
W912DW15C0006
[7 empty] | 69445 | 45104149 | 49614197 | 9.999%
W912DW18C0015
[7 empty] | 530041 | 19000000 | 20635000 | 8.605%
W912DW19C0002
[7 empty] | GJKZ040009 | 23481000 | 23481000 | 0%
W912DW19C0008
[7 empty] | NZAS173001 | 19868428 | 19868428 | 0%
W912DW19C0012
[7 empty] | 86518 | 5076000 | 5223000 | 2.896%
W912DW19C0015
[7 empty] | 93019 | 2844000 | 2877000 | 1.16%
W912DW19C0016
[7 empty] | 82337 | 3869000 | 3909000 | 1.034%
W912DW19C0017
[7 empty] | DESC1905 | 22312000 | 23258000 | 4.24%
W912DW19C008
[7 empty] | NZAS043002 | 19868428 | 19868428 | 0%
W912DW20C0001
[7 empty] | 55199 | 21087000 | 21620000 | 2.528%
W912DW20C0002
[7 empty] | 61147 | 77308000 | 79376000 | 2.675%
W912DW20C0005
[7 empty] | PQWY083008 | 42743158 | 44684710 | 4.542%
W912DW20C0007
[7 empty] | 77728 | 38027000 | 39097000 | 2.814%
W912DW20C0015
[7 empty] | GJLK1053425 | 12230000 | 12230000 | 0%
W912DW21C0021
[7 empty] | DESC2104A | 9845000 | 9845000 | 0%
W912DW21C0022
[7 empty] | DESC2104B | 10279000 | 10279000 | 0%
W912DY11D0002
[7 empty] | 673 | 877752 | 1098939 | 25.2%
W912DY12D0053
[7 empty] | 76518 | 8465006 | 9128867 | 7.842%
W912DY14D0042
[7 empty] | 674 | 2432439 | 2432439 | 0%
W912DY15D0081
[7 empty] | 70354 | 1118431 | 1474000 | 31.79%
W912EP16D0008
[7 empty] | DESC1513 | 1300000 | 4390000 | 237.7%
W912ER09C0035
[7 empty] | A73010 | 6639338 | 6799124 | 2.407%
W912ER09C0051
[7 empty] | 0P-926 | 27841952 | 15889227 | -42.93%
W912ER09C0055
[7 empty] | 59990 | 9978000 | 10839492 | 8.634%
W912ER11D00090012
[7 empty] | 81436 | 24784000 | 26972000 | 8.828%
W912ER12C0011
[7 empty] | 33003 | 4574738 | 5123284 | 11.99%
[7 empty] | 33005 | 3603251 | 3763908 | 4.459%
[7 empty] | 33019 | 2930589 | 3076695 | 4.986%
[7 empty] | 61772 | 16750710 | 17544730 | 4.74%
W912ER18C0029
[7 empty] | ASVF183100F | 15147990 | 16339259 | 7.864%
W912ER18D0005
[7 empty] | AEWV171012 | 3705150 | 3769955 | 1.749%
W912ER19C0008
[7 empty] | ASVF183100D | 10434344 | 10393609 | -0.3904%
[7 empty] | ASVF183100F | 118048 | 118048 | 0%
W912ER19C0015
[7 empty] | DHAF152900 | 25152460 | 25528019 | 1.493%
W912ER19C0016
[7 empty] | ALUA113023 | 13890460 | 13734951 | -1.12%
W912ER19C0018
[7 empty] | 62866 | 25397000 | 25452000 | 0.2166%
W912ER20C0002
[7 empty] | ASVF183100F | 100000 | 350000 | 250%
W912ER20C0009
[7 empty] | ASVF183100A | 32474636 | 32474636 | 0%
[7 empty] | ASVF183100B | 9862845 | 9856753 | -0.06177%
[7 empty] | ASVF183100C | 8267668 | 8267668 | 0%
[7 empty] | ASVF183100E | 804821 | 806055 | 0.1533%
[7 empty] | ASVF183100F | 28401350 | 28167704 | -0.8227%
W912G09D00040008
[7 empty] | 72481 | 39345000 | 47508000 | 20.75%
W912GB06C0038
[7 empty] | 66253 | 53186000 | 55561000 | 4.465%
W912GB07C0007NA
[7 empty] | 52332 | 25929000 | 28027000 | 8.091%
W912GB09C0038
[7 empty] | 66588 | 30080000 | 31830000 | 5.818%
W912GB10C0031
[7 empty] | 76007 | 913702000 | 913702000 | 0%
W912GB10C0031,
[7 empty] | 76007 | 126360947 | 132311713 | 4.709%
W912GB11C0013
[7 empty] | TYFR063017 | 29541693 | 29662433 | 0.4087%
W912GB11C0029
[7 empty] | EU00031 | 77816984 | 90497815 | 16.3%
W912GB12C0006
[7 empty] | EU00034 | 41569129 | 44309247 | 6.592%
W912GB12C0012
[7 empty] | 78712 | 20384000 | 20400000 | 0.07849%
W912GB12C0022
[7 empty] | EU00072 | 51059927 | 53113428 | 4.022%
W912GB12C0024
[7 empty] | EU00037 | 89535967 | 97631490 | 9.042%
W912GB12C0025
[7 empty] | EU00040 | 43000974 | 49730554 | 15.65%
W912GB12C0030
[7 empty] | EU00051 | 46915286 | 53161479 | 13.31%
W912GB12C0036
[7 empty] | EU00068 | 33667431 | 37180306 | 10.43%
W912GB12C0041
[7 empty] | EU00049 | 56357984 | 57356183 | 1.771%
W912GB13C0005
[7 empty] | 77986 | 23667000 | 27070000 | 14.38%
W912GB13R0003
[7 empty] | 630 | 236600000 | 181290000 | -23.38%
W912GB14C0005
[7 empty] | DESC1603 | 6125000 | 6125000 | 0%
W912GB15C0007
[7 empty] | 86824 | 42195000 | 44125000 | 4.574%
W912GB15C0013
[7 empty] | EU00039 | 48012330 | 48330200 | 0.6621%
W912GB15C011
[7 empty] | 13DISA01 | 2219820 | 2219820 | 0%
W912GB15D0029
[7 empty] | EEEI150006 | 1451631 | 1451631 | 0%
[7 empty] | EEEI180001 | 1210326 | 1210326 | 0%
W912GB15D00500002
[7 empty] | PAYZ15001B | 7097718 | 7097718 | 0%
W912GB15D00560002
[7 empty] | PAYZ15001B | 1515821 | 1515821 | 0%
W912GB15D0060
[7 empty] | EPPW170003 | 2463632 | 2463632 | 0%
W912GB15D0084
[7 empty] | 86832 | 4004000 | 9904000 | 147.4%
W912GB16C0003
[7 empty] | 81236 | 2579000 | 2740000 | 6.243%
W912GB16C0005
[7 empty] | 640 | 141906057 | 171152000 | 20.61%
W912GB16C0006
[7 empty] | 86094 | 2418000 | 2835000 | 17.25%
W912GB16C0007
[7 empty] | 62380 | 20950000 | 23278000 | 11.11%
W912GB16C0038
[7 empty] | 76007 | 21988000 | 24175000 | 9.946%
W912GB17C0002
[7 empty] | 86991 | 43508000 | 43874000 | 0.8412%
W912GB17C0005
[7 empty] | 72742 | 2103000 | 2103000 | 0%
W912GB17C0018
[7 empty] | EU00064 | 28765482 | 29107109 | 1.188%
W912GB17C0019
[7 empty] | 85711 | 15238000 | 18732000 | 22.93%
W912GB17C0023
[7 empty] | EU00183 | 2609290 | 2811865 | 7.764%
W912GB17D0015
[7 empty] | 86404 | 6121000 | 6783000 | 10.82%
[7 empty] | 91732 | 844000 | 1038000 | 22.99%
W912GB17F0444
[7 empty] | LBPG150008 | 1611283 | 1611283 | 0%
W912GB17F0461
[7 empty] | LBPG150009 | 1978602 | 1978602 | 0%
W912GB18C0002
[7 empty] | 78713 | 0 | 0
W912GB18C0013
[7 empty] | LJYC133003 | 10199660 | 10199660 | 0%
W912GB18C0024
[7 empty] | 93209 | 0 | 0
W912GB18F0020
[7 empty] | LRCT150007 | 2575083 | 2575083 | 0%
[7 empty] | LRCT150009 | 2356785 | 2356785 | 0%
[7 empty] | LRCT150010 | 2021357 | 2021357 | 0%
W912GB18F0021
[7 empty] | LRCT150008 | 1711902 | 1711902 | 0%
W912GB18F0186
[7 empty] | 689 | 3260896 | 0
W912GB19D0039
[7 empty] | 88542 | 11399000 | 11717000 | 2.79%
W912GB19F0076
[7 empty] | LJYC183004 | 3795142 | 3795142 | 0%
W912GB21C0022
[7 empty] | LRCT210001 | 12482193 | 12482193 | 0%
W912GB21D0019
[7 empty] | LRCT190001 | 10852364 | 10852364 | 0%
W912GB21F0202
[7 empty] | LRCT190002 | 27388762 | 27388762 | 0%
[7 empty] | LRCT210002 | 12163401 | 12163401 | 0%
W912HN07D0024
[7 empty] | 65272 | 323348 | 343221 | 6.146%
[7 empty] | 69366 | 3292508 | 4036729 | 22.6%
W912HN07D0042
[7 empty] | 65394 | 16571575 | 16883761 | 1.884%
[7 empty] | 65397 | 7184356 | 7193709 | 0.1302%
W912HN07D0054
[7 empty] | 65272 | 13354750 | 13733299 | 2.835%
[7 empty] | 65396 | 5143000 | 5507227 | 7.082%
W912HN07D0056
[7 empty] | 66227 | 11713000 | 12285692 | 4.889%
W912HN09C0022
[7 empty] | 60815 | 4847000 | 5753585 | 18.7%
W912HN09C0046
[7 empty] | 60743 | 12273879 | 13140227 | 7.058%
W912HN09C0050
[7 empty] | 26542 | 11777057 | 12749904 | 8.261%
W912HN09C0054
[7 empty] | 60636 | 0 | 0
W912HN10C0024
[7 empty] | 69275 | 2954015 | 3091827 | 4.665%
W912HN10C0028
[7 empty] | 69559 | 2717800 | 3068801 | 12.91%
W912HN10C0054
[7 empty] | 66315 | 18649100 | 22880316 | 22.69%
W912HN10C0063
[7 empty] | 64669 | 6661700 | 7560146 | 13.49%
W912HN10D0033
[7 empty] | 65266 | 1007935 | 1024285 | 1.622%
W912HN10D0049
[7 empty] | 60272 | 8290317 | 8465679 | 2.115%
[7 empty] | 76373 | 9771161 | 11158105 | 14.19%
W912HN10D0055
[7 empty] | 69458 | 16772305 | 19445395 | 15.94%
W912HN10D0056
[7 empty] | 20489 | 2620000 | 2657000 | 1.412%
W912HN10D0057
[7 empty] | 65395 | 15391578 | 15637173 | 1.596%
W912HN10D0058
[7 empty] | 69573 | 8487000 | 9279066 | 9.333%
W912HN10D0059
[7 empty] | 61874 | 9327304 | 12372455 | 32.65%
W912HN10D0060
[7 empty] | 60821 | 10605000 | 10926290 | 3.03%
W912HN10D0061
[7 empty] | 69493 | 23085000 | 26553696 | 15.03%
W912HN10D0063
[7 empty] | 23994 | 15315000 | 16526000 | 7.907%
[7 empty] | 43055 | 4773799 | 5344212 | 11.95%
[7 empty] | 69758 | 15649974 | 19104823 | 22.08%
W912HN11C0009
[7 empty] | 66444 | 9674000 | 9864411 | 1.968%
W912HN11C0010
[7 empty] | 64484 | 13388000 | 15616478 | 16.65%
W912HN11C0011
[7 empty] | 69759 | 2818574 | 2836413 | 0.6329%
W912HN11C0014
[7 empty] | 76511 | 28900000 | 30484390 | 5.482%
W912HN11C0016
[7 empty] | 69261 | 3103928 | 3227443 | 3.979%
W912HN11D0002
[7 empty] | 71224 | 18525847 | 23524962 | 26.98%
[7 empty] | 76364 | 29232386 | 33465310 | 14.48%
W912HN11D0003
[7 empty] | 65052 | 3199999 | 3271762 | 2.243%
[7 empty] | 66443 | 9591000 | 10179482 | 6.136%
W912HN12C0009
[7 empty] | 66362 | 41446000 | 44338384 | 6.979%
W912HN12C0016
[7 empty] | DESC1353 | 15685100 | 16568000 | 5.629%
W912HN12D0030
[7 empty] | 80233 | 1531765 | 1570203 | 2.509%
W912HN13D0002
[7 empty] | 79456 | 5997470 | 6178195 | 3.013%
W912HN16C0017
[7 empty] | DESC1710 | 9568000 | 10447000 | 9.187%
W912HN17C0005
[7 empty] | AM00035 | 27223000 | 27209938 | -0.04798%
W912HN17C0006
[7 empty] | 57442 | 8456354 | 8826862 | 4.381%
W912HN17C0008
[7 empty] | 61065 | 4609000 | 5099620 | 10.64%
W912HN18C3002
[7 empty] | 70677 | 29857000 | 33153000 | 11.04%
W912HN18C3003
[7 empty] | 86479 | 12255000 | 12784000 | 4.317%
W912HN19C3000
[7 empty] | 85794 | 14000000 | 14777000 | 5.55%
W912HN19C3001
[7 empty] | 86711 | 2854000 | 2889000 | 1.226%
W912HN19C3002
[7 empty] | 76934 | 10042000 | 2562000 | -74.49%
W912HN19C3003
[7 empty] | 55112 | 21437000 | 22385000 | 4.422%
W912HN19C3004
[7 empty] | 89128 | 3402000 | 3548000 | 4.292%
W912HN19C3006
[7 empty] | VKAG013004R5 | 23716745 | 23716745 | 0%
W912HN19C3008
[7 empty] | 92022 | 4635000 | 4775000 | 3.02%
W912HN19C3010
[7 empty] | 91311 | 6927000 | 6943000 | 0.231%
W912HN20C3001
[7 empty] | 87980 | 5155000 | 5230000 | 1.455%
W912HN20C3002
[7 empty] | 89215 | 4996000 | 5081000 | 1.701%
W912HN20C3004
[7 empty] | 87205 | 6187000 | 10773000 | 74.12%
W912HN20C3006
[7 empty] | 88724 | 193807000 | 195853000 | 1.056%
W912HN20C3007
[7 empty] | QSEU083023 | 23471929 | 23471929 | 0%
W912HN20C3011
[7 empty] | 91397 | 7034000 | 7027000 | -0.09952%
W912HN20D3003
[7 empty] | XLWU203006 | 25994000 | 25994000 | 0%
W912HN20F4009
[7 empty] | UHHZ163000 | 10827560 | 10827560 | 0%
W912HN21C3003
[7 empty] | 88725 | 112377000 | 112360000 | -0.01513%
W912HN21C3004
[7 empty] | 55516 | 62212000 | 62212000 | 0%
W912HN21C3005
[7 empty] | 88410 | 56295000 | 56295000 | 0%
W912HP11D0016
[7 empty] | 69277 | 2196113 | 2270078 | 3.368%
W912HV14C0007
[7 empty] | 62783 | 84367000 | 86073000 | 2.022%
W912HV15C0004
[7 empty] | 78024 | 46555863 | 63212524 | 35.78%
W912HV15C0005
[7 empty] | DESC1401 | 32623000 | 33122640 | 1.532%
W912HV15C005
[7 empty] | DESC1401 | 32623000 | 42122640 | 29.12%
W912HV15D0032
[7 empty] | AFSOC103022 | 3470750 | 3587463 | 3.363%
W912HV16D0008
[7 empty] | AFSOC103002 | 33751828 | 34992358 | 3.675%
W912HV16D0009
[7 empty] | 77831 | 18324000 | 18905000 | 3.171%
[7 empty] | LXEZ123484 | 16739026 | 17190622 | 2.698%
[7 empty] | LXEZ154288 | 33322662 | 33322662 | 0%
[7 empty] | LXEZ164289 | 26546290 | 26546290 | 0%
W912HV17C0002
[7 empty] | PA00023 | 27722277 | 30649314 | 10.56%
W912HV17C0004
[7 empty] | PA00017 | 61521811 | 88578226 | 43.98%
W912HV17C0007
[7 empty] | PA00028 | 26840313 | 28001030 | 4.325%
W912HV17C0008
[7 empty] | DESC1708 | 6804938 | 6817433 | 0.1836%
W912HV17D0013
[7 empty] | 81987 | 58908000 | 65889000 | 11.85%
W912HV17D0014
[7 empty] | 14022 | 14781000 | 15015000 | 1.583%
W912HV17D0015
[7 empty] | AFSOC103022 | 63052343 | 67048014 | 6.337%
W912HV17D001520F004
[7 empty] | ZNRE204308 | 10150068 | 10150068 | 0%
W912HV18C0002
[7 empty] | PA00032 | 72844929 | 80209599 | 10.11%
W912HV19C0003
[7 empty] | DESC1805 | 33455000 | 33455000 | 0%
W912HV19C0004
[7 empty] | 81903 | 16975565 | 17857223 | 5.194%
W912HV19C0005
[7 empty] | 87208 | 4111000 | 4265000 | 3.746%
W912HV19C0007
[7 empty] | PA00022 | 52447552 | 50699295 | -3.333%
W912HV20B00010004
[7 empty] | LXEZ184546 | 52649852 | 52649852 | 0%
W912HV20C0006
[7 empty] | PAYZ16000B | 2413198 | 2428538 | 0.6357%
W912HV21C0001
[7 empty] | EVKP174535 | 49607160 | 49607160 | 0%
W912HV21C0002
[7 empty] | AFSOC103010 | 10759517 | 10759517 | 0%
W912J22022001
[7 empty] | 550148 | 11600000 | 9051000 | -21.97%
W912J31622001
[7 empty] | 350200 | 8600000 | 10566000 | 22.86%
W912J617C0001
[7 empty] | 150035 | 31000000 | 28565000 | -7.855%
W912J61822021
[7 empty] | KNMD179040 | 3126987 | 2868023 | -8.282%
W912J620C0001
[7 empty] | KNMD189008 | 20236741 | 18275318 | -9.692%
W912J71922001
[7 empty] | 160024 | 29000000 | 30185000 | 4.086%
W912J71922002
[7 empty] | 160193 | 6000000 | 5515000 | -8.083%
W912JC18220001
[7 empty] | 200151 | 19000000 | 18828000 | -0.9053%
W912JC1922001
[7 empty] | 200129 | 3700000 | 3408000 | -7.892%
W912JM19C0012
[7 empty] | XDQU139458 | 2842543 | 2930507 | 3.095%
W912KC1722001
[7 empty] | 420595 | 2567000 | 3382000 | 31.75%
W912KN1922001
[7 empty] | 340132 | 15000000 | 13530000 | -9.8%
W912KZ1922101
[7 empty] | WEAS079054 | 8489791 | 7662000 | -9.75%
W912l12022002
[7 empty] | 481315 | 7800000 | 9228000 | 18.31%
W912L1922101
[7 empty] | XHZG179037 | 8000000 | 8000000 | 0%
W912L61922014
[7 empty] | 400602 | 9800000 | 9323000 | -4.867%
W912L61922101
[7 empty] | XHZG179037 | 8000000 | 8000000 | 0%
W912l718R0005
[7 empty] | 470035 | 1606000 | 1536000 | -4.359%
W912L71922001
[7 empty] | 470030 | 11200000 | 12806000 | 14.34%
W912L719C7001
[7 empty] | PSXE999132 | 29613217 | 30218917 | 2.045%
W912LC1822001
[7 empty] | 080220 | 5519955 | 6000000 | 8.697%
W912LD1522001
[7 empty] | 440064 | 20000000 | 20595000 | 2.975%
W912LD1922001
[7 empty] | 440061 | 2900000 | 3515000 | 21.21%
W912LM21C0002
[7 empty] | FMKM119035 | 2439785 | 2352600 | -3.573%
W912LM21R10010002
[7 empty] | FMKM179063 | 6397054 | 6232840 | -2.567%
W912MM1722001
[7 empty] | 460115 | 15000000 | 13023000 | -13.18%
W912MM2022001
[7 empty] | 465001 | 3000000 | 3593000 | 19.77%
W912NS19C6003
[7 empty] | ULYB049040 | 6052456 | 6136064 | 1.381%
W912PL12C0005
[7 empty] | 70354 | 162257000 | 213468000 | 31.56%
W912PL14C0020
[7 empty] | 53542 | 6546920 | 6674183 | 1.944%
W912PL17C0042
[7 empty] | 70354 | 3691544 | 4392000 | 18.97%
W912PL18C0013
[7 empty] | NUEX093016 | 16223496 | 16246162 | 0.1397%
W912PL18C0036
[7 empty] | 77102 | 20265000 | 23382000 | 15.38%
W912PL19C0007
[7 empty] | 80748 | 3994000 | 3994000 | 0%
W912PL19C0017
[7 empty] | 91528 | 5099000 | 5443000 | 6.746%
W912PL19C0023
[7 empty] | RKMF063004 | 21623000 | 22289225 | 3.081%
W912PL19C0024
[7 empty] | RKMF123009 | 5555674 | 5822833 | 4.809%
W912PL19C0028
[7 empty] | LKTC203101 | 25007200 | 25716568 | 2.837%
[7 empty] | LKTC203102 | 24652900 | 25087883 | 1.764%
W912PL19C0035
[7 empty] | FBNV033002 | 0 | 0
W912PL20C0001
[7 empty] | RKMF173010 | 3698666 | 4146204 | 12.1%
W912PL20C0002
[7 empty] | 94606 | 15233000 | 14906000 | -2.147%
[7 empty] | 94607 | 245241000 | 404677000 | 65.01%
W912PL20C0004
[7 empty] | 94608 | 268073000 | 419850000 | 56.62%
W912PL20C0007
[7 empty] | RKMF103011 | 2667515 | 5075675 | 90.28%
W912PL20C0008
[7 empty] | FBNV163001 | 0 | 0
W912PL20C0018
[7 empty] | RKMF203007 | 27554000 | 27554000 | 0%
W912PL20C0019
[7 empty] | 81316 | 5481000 | 5800000 | 5.82%
W912PL20C0021
[7 empty] | RKMF163007 | 36685652 | 37557368 | 2.376%
W912PL20C0030
[7 empty] | FSPM173504 | 34420210 | 34420210 | 0%
W912PL20C0035
[7 empty] | RKMF203001 | 5659450 | 5659450 | 0%
W912PL21C0007
[7 empty] | 90351 | 26473000 | 26518000 | 0.17%
W912PL21C0013
[7 empty] | 01DISA21 | 27737733 | 27737733 | 0%
W912PL21C0017
[7 empty] | 86022 | 45167317 | 45167317 | 0%
W912PL8C0024
[7 empty] | FSPM053503C | 22414000 | 22537509 | 0.551%
W912PM16F0007
[7 empty] | 61064 | 770924 | 786940 | 2.078%
W912PM17C0001
[7 empty] | 80773 | 32661077 | 33207816 | 1.674%
W912PM17C0004
[7 empty] | 76513 | 42661500 | 45640993 | 6.984%
W912PM18C0011
[7 empty] | 76514 | 34937000 | 36225167 | 3.687%
W912PM18C0013
[7 empty] | TMKH003003 | 15241121 | 15194631 | -0.305%
W912PM18C0014
[7 empty] | 74813 | 17972005 | 24165689 | 34.46%
W912PM18C0015
[7 empty] | 63850 | 12187034 | 14781112 | 21.29%
W912PM18C0016
[7 empty] | 79439 | 24955000 | 36737863 | 47.22%
W912PM18C0019
[7 empty] | 81894 | 4123177 | 4581868 | 11.12%
W912PM19C0007
[7 empty] | 79443 | 16474525 | 17708403 | 7.49%
W912PM19C0008
[7 empty] | 69552 | 30006388 | 31202082 | 3.985%
W912PM19C0011
[7 empty] | 79453 | 21039018 | 22062531 | 4.865%
W912PM19C0016
[7 empty] | 69251 | 9776000 | 9834566 | 0.5991%
W912PM19C0020
[7 empty] | 85958 | 11507959 | 12710896 | 10.45%
W912PM19C0027
[7 empty] | 91252 | 3864000 | 4141000 | 7.169%
W912PM19C0042
[7 empty] | 80774 | 17061326 | 17061326 | 0%
W912PM19C0043
[7 empty] | 82254 | 9649000 | 9750000 | 1.047%
W912PM20C0014
[7 empty] | 89057 | 10480000 | 10674000 | 1.851%
W912PM20C0016
[7 empty] | 92594 | 20768000 | 22105601 | 6.441%
W912PM20C0018
[7 empty] | 86021 | 10284300 | 10681863 | 3.866%
W912PM20C0031
[7 empty] | 81165 | 24885638 | 25356619 | 1.893%
W912PP09C0006
[7 empty] | 63027 | 5885533 | 6043246 | 2.68%
W912PP09C0034
[7 empty] | 43010 | 10882320 | 16423555 | 50.92%
W912PP10C0015
[7 empty] | 063054x | 0 | 4616078
[7 empty] | 63019 | 32766000 | 35162304 | 7.313%
W912PP11C0002
[7 empty] | 63035 | 9529882 | 14296126 | 50.01%
W912PP11C0016
[7 empty] | 63051 | 23743780 | 24809756 | 4.489%
W912PP11C0029
[7 empty] | 63049 | 19432000 | 20310963 | 4.523%
W912PP12C0002
[7 empty] | 63052 | 13260000 | 16851420 | 27.08%
W912PP12C0003
[7 empty] | 63052 | 13613730 | 13829042 | 1.582%
W912PP12C0023
[7 empty] | 83011 | 22227916 | 24626857 | 10.79%
W912PP12C0025
[7 empty] | 73018 | 9329356 | 9703739 | 4.013%
W912PP12C0027
[7 empty] | CZQZ083012 | 28160000 | 29398390 | 4.398%
W912PP12C0033
[7 empty] | 73021 | 14700000 | 15132847 | 2.945%
W912PP14C0014
[7 empty] | CZQZ083013 | 19481987 | 19876398 | 2.024%
W912PP14D0025
[7 empty] | CZQZ083021 | 11900000 | 11940630 | 0.3414%
W912PP15C003
[7 empty] | DESC1407 | 21288300 | 22083000 | 3.733%
W912PP18C0022
[7 empty] | CZQZ103006 | 5732950 | 5868773 | 2.369%
W912PP19C0001
[7 empty] | CZQZ063029 | 36206044 | 38176680 | 5.443%
[7 empty] | CZQZ133003 | 16606634 | 16964180 | 2.153%
W912PP19C0019
[7 empty] | KWRD143000 | 0 | 0
W912PP19D0035
[7 empty] | MHMV053107 | 2855784 | 2855784 | 0%
W912PP19D0037
[7 empty] | MHMV083126A | 8427275 | 8427275 | 0%
W912QG19C0006
[7 empty] | PSTE139022 | 3123581 | 3035885 | -2.808%
W912QG21C0004
[7 empty] | PSTE089064 | 4748809 | 4571407 | -3.736%
W912QR08C0009
[7 empty] | 53530 | 25906995 | 26435895 | 2.042%
W912QR08C0012
[7 empty] | 65392 | 15161429 | 15519395 | 2.361%
W912QR09C0023
[7 empty] | 65678 | 12824050 | 13455100 | 4.921%
W912QR10C0048
[7 empty] | 69558 | 2885585 | 3257458 | 12.89%
W912QR130032
[7 empty] | VDYDS97032 | 65994000 | 65994000 | 0%
W912QR14C0016
[7 empty] | 69447 | 22123180 | 22825995 | 3.177%
W912QR14C0019
[7 empty] | 66597 | 3384894 | 3480791 | 2.833%
W912QR15C0021
[7 empty] | 36977 | 14851238 | 15516050 | 4.476%
W912QR15C0026
[7 empty] | DESC1301 | 36448000 | 37081000 | 1.737%
W912QR15D0001
[7 empty] | 66813 | 5405390 | 5682502 | 5.127%
W912QR16C0002
[7 empty] | 76365 | 22740000 | 23868765 | 4.964%
W912QR17C0002
[7 empty] | 81897 | 11975000 | 12544449 | 4.755%
W912QR17C0009
[7 empty] | 86953 | 54817000 | 56042000 | 2.235%
W912QR17C0012
[7 empty] | 88722 | 2202000 | 2192000 | -0.4541%
W912QR17C0021
[7 empty] | 77186 | 19332000 | 19415000 | 0.4293%
W912QR17C0031
[7 empty] | VKAG159021 | 52493799 | 58903514 | 12.21%
W912QR17C0038
[7 empty] | FGWB009002 | 9397411 | 10249989 | 9.072%
W912QR17C0043
[7 empty] | 85813 | 49643000 | 52023000 | 4.794%
W912QR17C0049
[7 empty] | SXHT171217 | 2863596 | 2863596 | 0%
W912QR18C0003
[7 empty] | 86882 | 21180000 | 24451000 | 15.44%
W912QR18C0005
[7 empty] | 74732 | 9745000 | 10726000 | 10.07%
W912QR18C0015
[7 empty] | 77134 | 23840000 | 24589000 | 3.142%
W912QR18C0018
[7 empty] | SXHT103001 | 25242688 | 22626925 | -10.36%
W912QR18C0026
[7 empty] | 67567 | 7030000 | 7358000 | 4.666%
W912QR18C0031
[7 empty] | PDPG120514 | 4968200 | 5056600 | 1.779%
W912QR18C0037
[7 empty] | 91427 | 1692000 | 1717000 | 1.478%
W912QR18C0048
[7 empty] | 88585 | 2459000 | 2644000 | 7.523%
W912QR19B00160005
[7 empty] | ZHTV093301 | 4911384 | 4911384 | 0%
W912QR19C0009
[7 empty] | 90303 | 1831000 | 1819000 | -0.6554%
[7 empty] | UHHZ073005 | 31229066 | 31229066 | 0%
W912QR19C0012
[7 empty] | 77268 | 28937000 | 30632000 | 5.858%
W912QR19C0017
[7 empty] | 67039 | 8825159 | 9122816 | 3.373%
W912QR19C0018
[7 empty] | 88731 | 17399000 | 18625000 | 7.046%
W912QR19C0020
[7 empty] | YTPM059004 | 10383981 | 9832232 | -5.313%
W912QR19C0021
[7 empty] | RVKQ079104 | 11311046 | 11333785 | 0.201%
W912QR19C0026
[7 empty] | CTGB169002 | 9928185 | 9928185 | 0%
W912QR19C0027
[7 empty] | ZHTV093301 | 2173425 | 2173425 | 0%
W912QR19C0039
[7 empty] | 35782 | 45794000 | 46183000 | 0.8495%
W912QR19C0042
[7 empty] | UHHZ073003 | 32093710 | 28917160 | -9.898%
W912QR19C0045
[7 empty] | 77163 | 10304000 | 10389000 | 0.8249%
W912QR19C0046
[7 empty] | 77074 | 18838000 | 19063000 | 1.194%
W912QR19C0051
[7 empty] | 80690 | 20684000 | 21581000 | 4.337%
W912QR20C0009
[7 empty] | 90912 | 3703000 | 4862000 | 31.3%
W912QR20C0011
[7 empty] | ZHTV153201 | 6610000 | 6610000 | 0%
W912QR20C0012
[7 empty] | 86823 | 19751000 | 20351000 | 3.038%
W912QR20C0019
[7 empty] | 71725 | 6106000 | 6333000 | 3.718%
W912QR20C0022
[7 empty] | 69347 | 37142000 | 39788000 | 7.124%
W912QR20C0027
[7 empty] | 62856 | 22344000 | 23010000 | 2.981%
W912QR20C0028
[7 empty] | VDYD101053 | 30100000 | 30100000 | 0%
W912QR20C0035
[7 empty] | 90202 | 20217000 | 20217000 | 0%
W912QR20C0039
[7 empty] | CTGB989003 | 11471000 | 11471000 | 0%
W912QR20C0049
[7 empty] | AJXF223744 | 9992147 | 9992147 | 0%
W912QR20C0050
[7 empty] | SXHT203000 | 20438870 | 20438870 | 0%
W912QR20C0052
[7 empty] | 81802 | 18824000 | 19077000 | 1.344%
W912QR20C0054
[7 empty] | AM00029 | 56070000 | 57548931 | 2.638%
W912QR20C0056
[7 empty] | VKAG159026 | 4628152 | 4628152 | 0%
W912QR20D0024
[7 empty] | 92098 | 4924000 | 4924000 | 0%
W912QR21C0003
[7 empty] | 87438 | 4970375 | 5035427 | 1.309%
W912QR21C0025
[7 empty] | YTPM099001B | 46421000 | 46421000 | 0%
W912QR21C0031
[7 empty] | 90896 | 3962000 | 3962000 | 0%
W912QR21C0033
[7 empty] | AM00182 | 58989 | 58989 | 0%
W912QR21C0043
[7 empty] | QJKL100004 | 10511086 | 10511086 | 0%
W912QR21C0046
[7 empty] | 81564 | 9972000 | 9972000 | 0%
W912QR21C0049
[7 empty] | 82197 | 33126000 | 33126000 | 0%
W912QR21C0054
[7 empty] | 88752 | 7933000 | 7933000 | 0%
W912SV13R0001
[7 empty] | 250065 | 21279000 | 21661000 | 1.795%
W912TF1822001
[7 empty] | 330050 | 5950000 | 6539000 | 9.899%
W912UM13C0025
[7 empty] | 72419 | 22361000 | 24475000 | 9.454%
W912UM17C0044
[7 empty] | 86689 | 1146615000 | 1168995000 | 1.952%
W912UM19C0007
[7 empty] | 86689 | 1146615000 | 1168995000 | 1.952%
W912UM19C0015
[7 empty] | 81428 | 43171000 | 50468000 | 16.9%
W912UM19C0017
[7 empty] | SMYU073011 | 1227670 | 1227670 | 0%
W912UM20C0001
[7 empty] | 81429 | 54939000 | 55670000 | 1.331%
W912WJ17C0004
[7 empty] | AM00046 | 35970000 | 37442688 | 4.094%
W912WJ19C0011
[7 empty] | 75718 | 20612000 | 26382000 | 27.99%
W912WJ19C0014
[7 empty] | MXRD153006 | 2347000 | 2347000 | 0%
W912WJ21C0009
[7 empty] | DESC20S1 | 1162500000 | 1162500000 | 0%
W9136420B0001
[7 empty] | 390285 | 7400000 | 6945000 | -6.149%
W9136420C0002
[7 empty] | 390285 | 7400000 | 6945000 | -6.149%
W91SMC1922001
[7 empty] | 171510 | 5000000 | 4555000 | -8.9%
W91SMC19C6001
[7 empty] | JLQN049119 | 8184676 | 7901690 | -3.458%
W91ZRS18R00020002
[7 empty] | CEKT139029 | 6707992 | 6353569 | -5.284%
W91ZRS18R50010002
[7 empty] | CEKT149052 | 4979466 | 4990118 | 0.2139%
W91ZRU1622001
[7 empty] | 020143 | 27000000 | 22489000 | -16.71%
WH12DR14D0019
[7 empty] | 32122 | 22375000 | 31400000 | 40.34%
Y18228
[7 empty] | 260222 | 1200000 | 1777000 | 48.08%
Y20003
[7 empty] | 260274 | 3000000 | 2904000 | -3.2%
Y20410
[7 empty] | 260269 | 4141000 | 4055000 | -2.077%
(blank)
34490
90570
91531
95677
95696
M006811090A
M626131005
M626131006
M626131701
M62613604
M67400213
M67400807
M68479102
M68479811
N00206493
N00213211
N00213211A
N00246762
N32443256
N41557735
N41557735A
N476091901
N476091902
N476091907
N476091908
N476091914
N476091917
N476091920
N476091921
N60042117
N61066604
N61159312
N62588312
N628632001
N62863811
N63005955U
N63005964
N63005976
N66691144
N68469760
N83447091
N83447181
[7 empty] | Grand Total | 39282690659.89 | 41154407792 | 4.765%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.